Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Excavator - 36 ton183078 | Corbiere and Sons Contracting908202014-8Excavator - 36 ton183078Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Light Truck - Pick up20600 | Corbiere and Sons Contracting908202014-8Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Light Truck - Pick up20600 | Corbiere and Sons Contracting908202014-8Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Light Truck - Pick up30900 | Corbiere and Sons Contracting908202014-8Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Light Truck - Pick up20600 | Corbiere and Sons Contracting908202014-8Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Foreman121140 | Corbiere and Sons Contracting908202014-8Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Foreman121140 | Corbiere and Sons Contracting908202014-8Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 66 | HR |  |  |  | 0 | 5940 | 772.2 | 6712.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Operator - Principle665940 | Corbiere and Sons Contracting908202014-8Operator - Principle665940Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Labourer - Specialized11825 | Corbiere and Sons Contracting908202014-8Labourer - Specialized11825Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Labourer - Specialized443300 | Corbiere and Sons Contracting908202014-8Labourer - Specialized443300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Labourer - Specialized443300 | Corbiere and Sons Contracting908202014-8Labourer - Specialized443300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8L.O.A.51050 | Corbiere and Sons Contracting908202014-8L.O.A.51050Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520104 | Clearing | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8L.O.A.112310 | Corbiere and Sons Contracting908202014-8L.O.A.112310Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 909 | 202014-9 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 Eastward |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43841 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting909202014-9Feller Buncher368640 | Corbiere and Sons Contracting909202014-9Feller Buncher368640Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 909 | 202014-9 | 53520101 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 Eastward |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43841 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting909202014-9Skidder 274617 | Corbiere and Sons Contracting909202014-9Skidder 274617Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 909 | 202014-9 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 Eastward |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43841 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting909202014-9Light Truck - Pick up401200 | Corbiere and Sons Contracting909202014-9Light Truck - Pick up401200Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 909 | 202014-9 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 Eastward |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43841 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting909202014-9Foreman121140 | Corbiere and Sons Contracting909202014-9Foreman121140Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 909 | 202014-9 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 Eastward |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43841 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting909202014-9Operator - Principle776930 | Corbiere and Sons Contracting909202014-9Operator - Principle776930Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 909 | 202014-9 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 Eastward |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43841 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting909202014-9L.O.A.61260 | Corbiere and Sons Contracting909202014-9L.O.A.61260Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510107 | Access | 0 | Light Truck - Pick up | 30 | 4.4444 | HR | 22.5 | 0 |  |  | 133.3333 | 17.3333 | 150.6666 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Light Truck - Pick up4.4444444133.3333 | Corbiere and Sons Contracting912202015-1Light Truck - Pick up4.4444444133.3333Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 66.6667 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 4.4444 | HR | 22.5 | 0 |  |  | 133.3333 | 17.3333 | 150.6666 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Light Truck - Pick up4.4444444133.3333 | Corbiere and Sons Contracting912202015-1Light Truck - Pick up4.4444444133.3333Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 66.6667 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 4.4444 | HR | 22.5 | 0 |  |  | 133.3333 | 17.3333 | 150.6666 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Light Truck - Pick up4.4444444133.3333 | Corbiere and Sons Contracting912202015-1Light Truck - Pick up4.4444444133.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 66.6667 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 4.4444 | HR | 22.5 | 0 |  |  | 133.3333 | 17.3333 | 150.6666 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Light Truck - Pick up4.4444444133.3333 | Corbiere and Sons Contracting912202015-1Light Truck - Pick up4.4444444133.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 66.6667 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 4.4444 | HR | 22.5 | 0 |  |  | 133.3333 | 17.3333 | 150.6666 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Light Truck - Pick up4.4444444133.3333 | Corbiere and Sons Contracting912202015-1Light Truck - Pick up4.4444444133.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 66.6667 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510107 | Access | 0 | Project Manager | 110 | 1.3333 | HR |  |  | 110 | 0 | 146.6667 | 19.0667 | 165.7334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Manager1.3333333146.6667 | Corbiere and Sons Contracting912202015-1Project Manager1.3333333146.6667Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 73.3333 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510111 | Access | 0 | Project Manager | 110 | 1.3333 | HR |  |  | 110 | 0 | 146.6667 | 19.0667 | 165.7334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Manager1.3333333146.6667 | Corbiere and Sons Contracting912202015-1Project Manager1.3333333146.6667Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 73.3333 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 1.3333 | HR |  |  | 110 | 0 | 146.6667 | 19.0667 | 165.7334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Manager1.3333333146.6667 | Corbiere and Sons Contracting912202015-1Project Manager1.3333333146.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 73.3333 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 1.3333 | HR |  |  | 110 | 0 | 146.6667 | 19.0667 | 165.7334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Manager1.3333333146.6667 | Corbiere and Sons Contracting912202015-1Project Manager1.3333333146.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 73.3333 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.3333 | HR |  |  | 110 | 0 | 146.6667 | 19.0667 | 165.7334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Manager1.3333333146.6667 | Corbiere and Sons Contracting912202015-1Project Manager1.3333333146.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 73.3333 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510107 | Access | 0 | Superintendent | 105 | 1.3333 | HR |  |  | 105 | 0 | 140 | 18.2 | 158.2 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Superintendent1.3333333140 | Corbiere and Sons Contracting912202015-1Superintendent1.3333333140Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510111 | Access | 0 | Superintendent | 105 | 1.3333 | HR |  |  | 105 | 0 | 140 | 18.2 | 158.2 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Superintendent1.3333333140 | Corbiere and Sons Contracting912202015-1Superintendent1.3333333140Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 1.3333 | HR |  |  | 105 | 0 | 140 | 18.2 | 158.2 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Superintendent1.3333333140 | Corbiere and Sons Contracting912202015-1Superintendent1.3333333140Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 1.3333 | HR |  |  | 105 | 0 | 140 | 18.2 | 158.2 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Superintendent1.3333333140 | Corbiere and Sons Contracting912202015-1Superintendent1.3333333140Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 1.3333 | HR |  |  | 105 | 0 | 140 | 18.2 | 158.2 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Superintendent1.3333333140 | Corbiere and Sons Contracting912202015-1Superintendent1.3333333140Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510107 | Access | 0 | Project Coordinator | 80 | 1.3333 | HR |  |  | 80 | 0 | 106.6667 | 13.8667 | 120.5334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Coordinator1.3333333106.6667 | Corbiere and Sons Contracting912202015-1Project Coordinator1.3333333106.6667Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 53.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 1.3333 | HR |  |  | 80 | 0 | 106.6667 | 13.8667 | 120.5334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Coordinator1.3333333106.6667 | Corbiere and Sons Contracting912202015-1Project Coordinator1.3333333106.6667Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 53.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 1.3333 | HR |  |  | 80 | 0 | 106.6667 | 13.8667 | 120.5334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Coordinator1.3333333106.6667 | Corbiere and Sons Contracting912202015-1Project Coordinator1.3333333106.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 53.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 1.3333 | HR |  |  | 80 | 0 | 106.6667 | 13.8667 | 120.5334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Coordinator1.3333333106.6667 | Corbiere and Sons Contracting912202015-1Project Coordinator1.3333333106.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 53.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.3333 | HR |  |  | 80 | 0 | 106.6667 | 13.8667 | 120.5334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Coordinator1.3333333106.6667 | Corbiere and Sons Contracting912202015-1Project Coordinator1.3333333106.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 53.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510107 | Access | 0 | Site Administrator | 50 | 1.1111 | HR |  |  | 50 | 0 | 55.5556 | 7.2222 | 62.7778 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Site Administrator1.111111155.5556 | Corbiere and Sons Contracting912202015-1Site Administrator1.111111155.5556Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 27.7778 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510111 | Access | 0 | Site Administrator | 50 | 1.1111 | HR |  |  | 50 | 0 | 55.5556 | 7.2222 | 62.7778 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Site Administrator1.111111155.5556 | Corbiere and Sons Contracting912202015-1Site Administrator1.111111155.5556Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 27.7778 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520101 | Clearing | 0 | Site Administrator | 50 | 1.1111 | HR |  |  | 50 | 0 | 55.5556 | 7.2222 | 62.7778 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Site Administrator1.111111155.5556 | Corbiere and Sons Contracting912202015-1Site Administrator1.111111155.5556Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 27.7778 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 1.1111 | HR |  |  | 50 | 0 | 55.5556 | 7.2222 | 62.7778 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Site Administrator1.111111155.5556 | Corbiere and Sons Contracting912202015-1Site Administrator1.111111155.5556Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 27.7778 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 1.1111 | HR |  |  | 50 | 0 | 55.5556 | 7.2222 | 62.7778 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Site Administrator1.111111155.5556 | Corbiere and Sons Contracting912202015-1Site Administrator1.111111155.5556Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 27.7778 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510107 | Access | 0 | Project Controls | 70 | 1.3333 | HR |  |  | 70 | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Controls1.333333393.3333 | Corbiere and Sons Contracting912202015-1Project Controls1.333333393.3333Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510111 | Access | 0 | Project Controls | 70 | 1.3333 | HR |  |  | 70 | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Controls1.333333393.3333 | Corbiere and Sons Contracting912202015-1Project Controls1.333333393.3333Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 1.3333 | HR |  |  | 70 | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Controls1.333333393.3333 | Corbiere and Sons Contracting912202015-1Project Controls1.333333393.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 1.3333 | HR |  |  | 70 | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Controls1.333333393.3333 | Corbiere and Sons Contracting912202015-1Project Controls1.333333393.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.3333 | HR |  |  | 70 | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1Project Controls1.333333393.3333 | Corbiere and Sons Contracting912202015-1Project Controls1.333333393.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510107 | Access | 0 | L.O.A. | 210 | 0.55556 | DAY |  |  |  | 0 | 116.6667 | 15.1667 | 131.8334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1L.O.A.0.5555556116.6667 | Corbiere and Sons Contracting912202015-1L.O.A.0.5555556116.6667Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 58.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.55556 | DAY |  |  |  | 0 | 116.6667 | 15.1667 | 131.8334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1L.O.A.0.5555556116.6667 | Corbiere and Sons Contracting912202015-1L.O.A.0.5555556116.6667Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 58.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.55556 | DAY |  |  |  | 0 | 116.6667 | 15.1667 | 131.8334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1L.O.A.0.5555556116.6667 | Corbiere and Sons Contracting912202015-1L.O.A.0.5555556116.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 58.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.55556 | DAY |  |  |  | 0 | 116.6667 | 15.1667 | 131.8334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1L.O.A.0.5555556116.6667 | Corbiere and Sons Contracting912202015-1L.O.A.0.5555556116.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 58.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 912 | 202015-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.55556 | DAY |  |  |  | 0 | 116.6667 | 15.1667 | 131.8334 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting912202015-1L.O.A.0.5555556116.6667 | Corbiere and Sons Contracting912202015-1L.O.A.0.5555556116.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 58.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 921 | 202015-10 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 29 | HR | 180 | 0 |  |  | 6960 | 904.8 | 7864.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A0129 to A130 |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting921202015-10Feller Buncher296960 | Corbiere and Sons Contracting921202015-10Feller Buncher296960Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 921 | 202015-10 | 53520101 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A0129 to A130 |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting921202015-10Skidder 274617 | Corbiere and Sons Contracting921202015-10Skidder 274617Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 921 | 202015-10 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A0129 to A130 |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting921202015-10Light Truck - Pick up401200 | Corbiere and Sons Contracting921202015-10Light Truck - Pick up401200Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 921 | 202015-10 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A0129 to A130 |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting921202015-10Foreman121140 | Corbiere and Sons Contracting921202015-10Foreman121140Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 921 | 202015-10 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A0129 to A130 |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting921202015-10Operator - Principle776930 | Corbiere and Sons Contracting921202015-10Operator - Principle776930Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 921 | 202015-10 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A0129 to A130 |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting921202015-10L.O.A.71470 | Corbiere and Sons Contracting921202015-10L.O.A.71470Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 913 | 202015-2-R1 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Mike cleared the yard with Loader after snow fall; |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting913202015-2-R1Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting913202015-2-R1Loader JD 524 to 624 or equal5495Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 913 | 202015-2-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Mike cleared the yard with Loader after snow fall; |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting913202015-2-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting913202015-2-R1Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 913 | 202015-2-R1 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Mike cleared the yard with Loader after snow fall; |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting913202015-2-R1Operator - Intermdiate11825 | Corbiere and Sons Contracting913202015-2-R1Operator - Intermdiate11825Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 913 | 202015-2-R1 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Mike cleared the yard with Loader after snow fall; |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting913202015-2-R1Operator - Apprentice10600 | Corbiere and Sons Contracting913202015-2-R1Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 913 | 202015-2-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Mike cleared the yard with Loader after snow fall; |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting913202015-2-R1L.O.A.1210 | Corbiere and Sons Contracting913202015-2-R1L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 914 | 202015-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Continuing of Brushing and Raking towards A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting914202015-3Brusher91822.5 | Corbiere and Sons Contracting914202015-3Brusher91822.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 914 | 202015-3 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Continuing of Brushing and Raking towards A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting914202015-3Excavator - 36 ton183078 | Corbiere and Sons Contracting914202015-3Excavator - 36 ton183078Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 914 | 202015-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Continuing of Brushing and Raking towards A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting914202015-3Light Truck - Pick up10300 | Corbiere and Sons Contracting914202015-3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 914 | 202015-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Continuing of Brushing and Raking towards A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting914202015-3Operator - Principle332970 | Corbiere and Sons Contracting914202015-3Operator - Principle332970Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 914 | 202015-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2.9979 | DAY |  |  |  | 0 | 629.55 | 81.8415 | 711.3915 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Continuing of Brushing and Raking towards A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting914202015-3L.O.A.2.997857629.55 | Corbiere and Sons Contracting914202015-3L.O.A.2.997857629.55Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 629.55 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 915 | 202015-4 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Clearing and Prepping of pits after snow removal; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting915202015-4Dozer D6 or equal91215 | Corbiere and Sons Contracting915202015-4Dozer D6 or equal91215Inv#006R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 915 | 202015-4 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Clearing and Prepping of pits after snow removal; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting915202015-4Light Truck - Pick up10300 | Corbiere and Sons Contracting915202015-4Light Truck - Pick up10300Inv#006R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 915 | 202015-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Clearing and Prepping of pits after snow removal; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting915202015-4Operator - Principle11990 | Corbiere and Sons Contracting915202015-4Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 915 | 202015-4 | 53510111 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Clearing and Prepping of pits after snow removal; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting915202015-4Labourer - General11715 | Corbiere and Sons Contracting915202015-4Labourer - General11715Inv#006R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 915 | 202015-4 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Clearing and Prepping of pits after snow removal; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting915202015-4L.O.A.2420 | Corbiere and Sons Contracting915202015-4L.O.A.2420Inv#006R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Dozer - D5 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Dozer - D5 or equal9891 | Corbiere and Sons Contracting918202015-7Dozer - D5 or equal9891Inv#006R01 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Excavator - 30 ton91255.5 | Corbiere and Sons Contracting918202015-7Excavator - 30 ton91255.5Inv#006R01 | [5 empty] | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Excavator - 30 ton91255.5 | Corbiere and Sons Contracting918202015-7Excavator - 30 ton91255.5Inv#006R01 | [5 empty] | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Excavator - 36 ton91539 | Corbiere and Sons Contracting918202015-7Excavator - 36 ton91539Inv#006R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 29 | HR | 94.5 | 0 |  |  | 3654 | 475.02 | 4129.02 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Grader - Cat 12 to 14 or equal293654 | Corbiere and Sons Contracting918202015-7Grader - Cat 12 to 14 or equal293654Inv#006R01 | [5 empty] | 1 | 3654 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Sander Truck111237.5 | Corbiere and Sons Contracting918202015-7Sander Truck111237.5Inv#006R01 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Light Truck - Pick up30900 | Corbiere and Sons Contracting918202015-7Light Truck - Pick up30900Inv#006R01 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Light Truck - Pick up20600 | Corbiere and Sons Contracting918202015-7Light Truck - Pick up20600Inv#006R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting918202015-7Tractor Trailer - 60 Ton101350Inv#006R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Foreman121140 | Corbiere and Sons Contracting918202015-7Foreman121140Inv#006R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Foreman121140 | Corbiere and Sons Contracting918202015-7Foreman121140Inv#006R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Operator - Principle221980 | Corbiere and Sons Contracting918202015-7Operator - Principle221980Inv#006R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Operator - Principle11990 | Corbiere and Sons Contracting918202015-7Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Operator - Principle221980 | Corbiere and Sons Contracting918202015-7Operator - Principle221980Inv#006R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Operator - Principle11990 | Corbiere and Sons Contracting918202015-7Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Operator - Principle | 90 | 48 | HR |  |  |  | 0 | 4320 | 561.6 | 4881.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Operator - Principle484320 | Corbiere and Sons Contracting918202015-7Operator - Principle484320Inv#006R01 | [5 empty] | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Labourer - General | 65 | 27 | HR |  |  |  | 0 | 1755 | 228.15 | 1983.15 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Labourer - General271755 | Corbiere and Sons Contracting918202015-7Labourer - General271755Inv#006R01 | [5 empty] | 1 | 1755 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Labourer - General | 65 | 9 | HR |  |  |  | 0 | 585 | 76.05 | 661.05 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Labourer - General9585 | Corbiere and Sons Contracting918202015-7Labourer - General9585Inv#006R01 | [5 empty] | 1 | 585 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7Labourer - General11715 | Corbiere and Sons Contracting918202015-7Labourer - General11715Inv#006R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 918 | 202015-7 | 53510111 | Access | 0 | L.O.A. | 210 | 17 | DAY |  |  |  | 0 | 3570 | 464.1 | 4034.1 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing of Snow from A080-A082, A091-A092, and down to A082-A084; Labourers Assembled Culverts; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting918202015-7L.O.A.173570 | Corbiere and Sons Contracting918202015-7L.O.A.173570Inv#006R01 | [5 empty] | 1 | 3570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting919202015-8Grinder - 4710 Peterson or equal95011.2Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting919202015-8Grinder - 4710 Peterson or equal95011.2Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Log Loader91377 | Corbiere and Sons Contracting919202015-8Log Loader91377Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Log Loader91377 | Corbiere and Sons Contracting919202015-8Log Loader91377Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Chainsaw and consummables6720 | Corbiere and Sons Contracting919202015-8Chainsaw and consummables6720Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Chainsaw and consummables5600 | Corbiere and Sons Contracting919202015-8Chainsaw and consummables5600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Light Truck - Pick up10300 | Corbiere and Sons Contracting919202015-8Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Light Truck - Pick up10300 | Corbiere and Sons Contracting919202015-8Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Light Truck - Pick up501500 | Corbiere and Sons Contracting919202015-8Light Truck - Pick up501500Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Foreman121140 | Corbiere and Sons Contracting919202015-8Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Foreman121140 | Corbiere and Sons Contracting919202015-8Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Operator - Principle11990 | Corbiere and Sons Contracting919202015-8Operator - Principle11990Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520104 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Operator - Principle11990 | Corbiere and Sons Contracting919202015-8Operator - Principle11990Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 8 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Labourer - Specialized8600 | Corbiere and Sons Contracting919202015-8Labourer - Specialized8600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 38 | HR |  |  |  | 0 | 2850 | 370.5 | 3220.5 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Labourer - Specialized382850 | Corbiere and Sons Contracting919202015-8Labourer - Specialized382850Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8Labourer - Specialized443300 | Corbiere and Sons Contracting919202015-8Labourer - Specialized443300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8L.O.A.1210 | Corbiere and Sons Contracting919202015-8L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 919 | 202015-8 | 53520104 | Clearing | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material from A080 to A082; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting919202015-8L.O.A.122520 | Corbiere and Sons Contracting919202015-8L.O.A.122520Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 920 | 202015-9 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Eastward |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting920202015-9Brusher183645 | Corbiere and Sons Contracting920202015-9Brusher183645Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 920 | 202015-9 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Eastward |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting920202015-9Excavator - 36 ton183078 | Corbiere and Sons Contracting920202015-9Excavator - 36 ton183078Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 920 | 202015-9 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Eastward |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting920202015-9Light Truck - Pick up20600 | Corbiere and Sons Contracting920202015-9Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 920 | 202015-9 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Eastward |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting920202015-9Operator - Principle443960 | Corbiere and Sons Contracting920202015-9Operator - Principle443960Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 920 | 202015-9 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Eastward |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting920202015-9L.O.A.4840 | Corbiere and Sons Contracting920202015-9L.O.A.4840Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 924 | 202016-1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 0 | 0 |  |  | 1500 | 195 | 1695 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting924202016-1Light Truck - Pick up501500 | Corbiere and Sons Contracting924202016-1Light Truck - Pick up501500Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 924 | 202016-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting924202016-1Project Manager121320 | Corbiere and Sons Contracting924202016-1Project Manager121320Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 924 | 202016-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting924202016-1Superintendent121260 | Corbiere and Sons Contracting924202016-1Superintendent121260Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 924 | 202016-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting924202016-1Project Coordinator12960 | Corbiere and Sons Contracting924202016-1Project Coordinator12960Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 924 | 202016-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting924202016-1Safety Advisor121020 | Corbiere and Sons Contracting924202016-1Safety Advisor121020Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 924 | 202016-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 10 | HR |  |  | 0 | 0 | 500 | 65 | 565 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting924202016-1Site Administrator10500 | Corbiere and Sons Contracting924202016-1Site Administrator10500Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 924 | 202016-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting924202016-1Project Controls12840 | Corbiere and Sons Contracting924202016-1Project Controls12840Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 924 | 202016-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting924202016-1L.O.A.61260 | Corbiere and Sons Contracting924202016-1L.O.A.61260Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting933202016-10Grinder - 4710 Peterson or equal95011.2Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting933202016-10Grinder - 4710 Peterson or equal95011.2Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Log Loader91377 | Corbiere and Sons Contracting933202016-10Log Loader91377Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Log Loader91377 | Corbiere and Sons Contracting933202016-10Log Loader91377Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Chainsaw and consummables6720 | Corbiere and Sons Contracting933202016-10Chainsaw and consummables6720Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Light Truck - Pick up10300 | Corbiere and Sons Contracting933202016-10Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Light Truck - Pick up10300 | Corbiere and Sons Contracting933202016-10Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Light Truck - Pick up30900 | Corbiere and Sons Contracting933202016-10Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Foreman121140 | Corbiere and Sons Contracting933202016-10Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Operator - Principle221980 | Corbiere and Sons Contracting933202016-10Operator - Principle221980Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Labourer - Specialized11825 | Corbiere and Sons Contracting933202016-10Labourer - Specialized11825Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10Labourer - Specialized443300 | Corbiere and Sons Contracting933202016-10Labourer - Specialized443300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 933 | 202016-10 | 53520104 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A084 and A081; Handfelling from A084 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting933202016-10L.O.A.81680 | Corbiere and Sons Contracting933202016-10L.O.A.81680Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 934 | 202016-11 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 West |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting934202016-11Brusher183645 | Corbiere and Sons Contracting934202016-11Brusher183645Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 934 | 202016-11 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 West |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting934202016-11Excavator - 36 ton183078 | Corbiere and Sons Contracting934202016-11Excavator - 36 ton183078Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 934 | 202016-11 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 West |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting934202016-11Light Truck - Pick up20600 | Corbiere and Sons Contracting934202016-11Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 934 | 202016-11 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 West |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting934202016-11Operator - Principle443960 | Corbiere and Sons Contracting934202016-11Operator - Principle443960Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 934 | 202016-11 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 West |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting934202016-11L.O.A.4840 | Corbiere and Sons Contracting934202016-11L.O.A.4840Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Feller Buncher368640 | Corbiere and Sons Contracting935202016-12-R1Feller Buncher368640Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Feller Buncher92160 | Corbiere and Sons Contracting935202016-12-R1Feller Buncher92160Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Skidder 274617 | Corbiere and Sons Contracting935202016-12-R1Skidder 274617Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Skidder 91539 | Corbiere and Sons Contracting935202016-12-R1Skidder 91539Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 11 | HR | 101.25 | 0 |  |  | 1485 | 193.05 | 1678.05 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Dozer D6 or equal111485 | Corbiere and Sons Contracting935202016-12-R1Dozer D6 or equal111485Inv#010 | [5 empty] | 1 | 1485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Excavator - 36 ton91539 | Corbiere and Sons Contracting935202016-12-R1Excavator - 36 ton91539Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting935202016-12-R1Excavator Thumb - 30 - 50 ton9121.5Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 11 | HR | 94.5 | 0 |  |  | 1386 | 180.18 | 1566.18 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Grader - Cat 12 to 14 or equal111386 | Corbiere and Sons Contracting935202016-12-R1Grader - Cat 12 to 14 or equal111386Inv#010 | [5 empty] | 1 | 1386 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting935202016-12-R1Light Truck - Pick up10300Inv#010 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Light Truck - Pick up401200 | Corbiere and Sons Contracting935202016-12-R1Light Truck - Pick up401200Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Light Truck - Pick up20600 | Corbiere and Sons Contracting935202016-12-R1Light Truck - Pick up20600Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting935202016-12-R1Light Truck - Pick up10300Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Foreman121140 | Corbiere and Sons Contracting935202016-12-R1Foreman121140Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Foreman6570 | Corbiere and Sons Contracting935202016-12-R1Foreman6570Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53510111 | Access | 0 | Operator - Principle | 90 | 26 | HR |  |  |  | 0 | 2340 | 304.2 | 2644.2 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Operator - Principle262340 | Corbiere and Sons Contracting935202016-12-R1Operator - Principle262340Inv#010 | [5 empty] | 1 | 2340 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 66 | HR |  |  |  | 0 | 5940 | 772.2 | 6712.2 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Operator - Principle665940 | Corbiere and Sons Contracting935202016-12-R1Operator - Principle665940Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Operator - Principle11990 | Corbiere and Sons Contracting935202016-12-R1Operator - Principle11990Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Operator - Principle221980 | Corbiere and Sons Contracting935202016-12-R1Operator - Principle221980Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1Labourer - General11715 | Corbiere and Sons Contracting935202016-12-R1Labourer - General11715Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1L.O.A.2420 | Corbiere and Sons Contracting935202016-12-R1L.O.A.2420Inv#010 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 935 | 202016-12-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-01-10 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing from A128 to A131 |  |  | Fish Hatchery - A128 to B017 | 1 |  |  | 36 | 43900 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting935202016-12-R1L.O.A.91890 | Corbiere and Sons Contracting935202016-12-R1L.O.A.91890Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 925 | 202016-2-R1 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 0 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Mike cleared the yard with Loader after snowfall |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting925202016-2-R1Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting925202016-2-R1Loader JD 524 to 624 or equal5495Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 925 | 202016-2-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Mike cleared the yard with Loader after snowfall |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting925202016-2-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting925202016-2-R1Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 925 | 202016-2-R1 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Mike cleared the yard with Loader after snowfall |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting925202016-2-R1Operator - Apprentice10600 | Corbiere and Sons Contracting925202016-2-R1Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3Brusher91822.5 | Corbiere and Sons Contracting926202016-3Brusher91822.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3Chainsaw and consummables5600 | Corbiere and Sons Contracting926202016-3Chainsaw and consummables5600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3Excavator - 36 ton183078 | Corbiere and Sons Contracting926202016-3Excavator - 36 ton183078Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3Light Truck - Pick up10300 | Corbiere and Sons Contracting926202016-3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3Light Truck - Pick up20600 | Corbiere and Sons Contracting926202016-3Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3Foreman121140 | Corbiere and Sons Contracting926202016-3Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 27 | HR |  |  |  | 0 | 2430 | 315.9 | 2745.9 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3Operator - Principle272430 | Corbiere and Sons Contracting926202016-3Operator - Principle272430Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3Labourer - Specialized443300 | Corbiere and Sons Contracting926202016-3Labourer - Specialized443300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3Labourer - General11715 | Corbiere and Sons Contracting926202016-3Labourer - General11715Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3L.O.A.4840 | Corbiere and Sons Contracting926202016-3L.O.A.4840Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 926 | 202016-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking at A038-A037; Brusher working towards A036; Handfelling from A042-A041 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting926202016-3L.O.A.51050 | Corbiere and Sons Contracting926202016-3L.O.A.51050Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 928 | 202016-5 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 11 | HR | 101.25 | 0 |  |  | 1485 | 193.05 | 1678.05 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads of snow and road maintenance |  |  | Beck Road East - A047 to A054 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting928202016-5Dozer D6 or equal111485 | Corbiere and Sons Contracting928202016-5Dozer D6 or equal111485Inv#006R01 | [5 empty] | 1 | 1485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 928 | 202016-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 13 | HR |  |  |  | 0 | 1170 | 152.1 | 1322.1 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads of snow and road maintenance |  |  | Beck Road East - A047 to A054 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting928202016-5Operator - Principle131170 | Corbiere and Sons Contracting928202016-5Operator - Principle131170Inv#006R01 | [5 empty] | 1 | 1170 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 928 | 202016-5 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads of snow and road maintenance |  |  | Beck Road East - A047 to A054 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting928202016-5L.O.A.1210 | Corbiere and Sons Contracting928202016-5L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 929 | 202016-6 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A072-A073 |  |  | Eldorado - A055 to A079 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting929202016-6Chainsaw and consummables3360 | Corbiere and Sons Contracting929202016-6Chainsaw and consummables3360Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 929 | 202016-6 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A072-A073 |  |  | Eldorado - A055 to A079 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting929202016-6Light Truck - Pick up10300 | Corbiere and Sons Contracting929202016-6Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 929 | 202016-6 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A072-A073 |  |  | Eldorado - A055 to A079 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting929202016-6Labourer - Specialized332475 | Corbiere and Sons Contracting929202016-6Labourer - Specialized332475Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 929 | 202016-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A072-A073 |  |  | Eldorado - A055 to A079 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting929202016-6L.O.A.3630 | Corbiere and Sons Contracting929202016-6L.O.A.3630Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Dozer - D5 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Dozer - D5 or equal9891 | Corbiere and Sons Contracting932202016-9Dozer - D5 or equal9891Inv#006R01 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 32 | HR | 94.5 | 0 |  |  | 4032 | 524.16 | 4556.16 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Grader - Cat 12 to 14 or equal324032 | Corbiere and Sons Contracting932202016-9Grader - Cat 12 to 14 or equal324032Inv#006R01 | [5 empty] | 1 | 4032 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Sander Truck | 112.5 | 12 | HR | 84.38 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Sander Truck121350 | Corbiere and Sons Contracting932202016-9Sander Truck121350Inv#006R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Light Truck - Pick up20600 | Corbiere and Sons Contracting932202016-9Light Truck - Pick up20600Inv#006R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting932202016-9Tractor Trailer - 60 Ton101350Inv#006R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Foreman121140 | Corbiere and Sons Contracting932202016-9Foreman121140Inv#006R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Operator - Principle11990 | Corbiere and Sons Contracting932202016-9Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Operator - Principle | 90 | 13 | HR |  |  |  | 0 | 1170 | 152.1 | 1322.1 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Operator - Principle131170 | Corbiere and Sons Contracting932202016-9Operator - Principle131170Inv#006R01 | [5 empty] | 1 | 1170 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Operator - Principle | 90 | 49 | HR |  |  |  | 0 | 4410 | 573.3 | 4983.3 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Operator - Principle494410 | Corbiere and Sons Contracting932202016-9Operator - Principle494410Inv#006R01 | [5 empty] | 1 | 4410 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Operator - Intermdiate11825 | Corbiere and Sons Contracting932202016-9Operator - Intermdiate11825Inv#006R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9Labourer - General11715 | Corbiere and Sons Contracting932202016-9Labourer - General11715Inv#006R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 932 | 202016-9 | 53510111 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Prepping Road at A081; Snow Removal with D5 from A082-A084; Rd. Building at A092 and Rd. Widening from A082-A084; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting932202016-9L.O.A.91890 | Corbiere and Sons Contracting932202016-9L.O.A.91890Inv#006R01 | [5 empty] | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510107 | Access | 0 | Light Truck - Pick up | 30 | 6.25 | HR | 22.5 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Light Truck - Pick up6.25187.5 | Corbiere and Sons Contracting938202017-1Light Truck - Pick up6.25187.5Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 93.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 6.25 | HR | 22.5 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Light Truck - Pick up6.25187.5 | Corbiere and Sons Contracting938202017-1Light Truck - Pick up6.25187.5Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 93.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 6.25 | HR | 22.5 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Light Truck - Pick up6.25187.5 | Corbiere and Sons Contracting938202017-1Light Truck - Pick up6.25187.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 93.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 6.25 | HR | 22.5 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Light Truck - Pick up6.25187.5 | Corbiere and Sons Contracting938202017-1Light Truck - Pick up6.25187.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 93.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 6.25 | HR | 22.5 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Light Truck - Pick up6.25187.5 | Corbiere and Sons Contracting938202017-1Light Truck - Pick up6.25187.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 93.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510107 | Access | 0 | Project Manager | 110 | 1.5 | HR |  |  | 110 | 0 | 165 | 21.45 | 186.45 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Manager1.5165 | Corbiere and Sons Contracting938202017-1Project Manager1.5165Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 82.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510111 | Access | 0 | Project Manager | 110 | 1.5 | HR |  |  | 110 | 0 | 165 | 21.45 | 186.45 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Manager1.5165 | Corbiere and Sons Contracting938202017-1Project Manager1.5165Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 82.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 1.5 | HR |  |  | 110 | 0 | 165 | 21.45 | 186.45 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Manager1.5165 | Corbiere and Sons Contracting938202017-1Project Manager1.5165Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 82.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 1.5 | HR |  |  | 110 | 0 | 165 | 21.45 | 186.45 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Manager1.5165 | Corbiere and Sons Contracting938202017-1Project Manager1.5165Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 82.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.5 | HR |  |  | 110 | 0 | 165 | 21.45 | 186.45 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Manager1.5165 | Corbiere and Sons Contracting938202017-1Project Manager1.5165Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 82.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510107 | Access | 0 | Superintendent | 105 | 1.5 | HR |  |  | 105 | 0 | 157.5 | 20.475 | 177.975 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Superintendent1.5157.5 | Corbiere and Sons Contracting938202017-1Superintendent1.5157.5Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 78.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510111 | Access | 0 | Superintendent | 105 | 1.5 | HR |  |  | 105 | 0 | 157.5 | 20.475 | 177.975 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Superintendent1.5157.5 | Corbiere and Sons Contracting938202017-1Superintendent1.5157.5Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 78.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 1.5 | HR |  |  | 105 | 0 | 157.5 | 20.475 | 177.975 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Superintendent1.5157.5 | Corbiere and Sons Contracting938202017-1Superintendent1.5157.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 78.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 1.5 | HR |  |  | 105 | 0 | 157.5 | 20.475 | 177.975 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Superintendent1.5157.5 | Corbiere and Sons Contracting938202017-1Superintendent1.5157.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 78.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 1.5 | HR |  |  | 105 | 0 | 157.5 | 20.475 | 177.975 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Superintendent1.5157.5 | Corbiere and Sons Contracting938202017-1Superintendent1.5157.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 78.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510107 | Access | 0 | Project Coordinator | 80 | 1.5 | HR |  |  | 80 | 0 | 120 | 15.6 | 135.6 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Coordinator1.5120 | Corbiere and Sons Contracting938202017-1Project Coordinator1.5120Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 60 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 1.5 | HR |  |  | 80 | 0 | 120 | 15.6 | 135.6 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Coordinator1.5120 | Corbiere and Sons Contracting938202017-1Project Coordinator1.5120Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 60 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 1.5 | HR |  |  | 80 | 0 | 120 | 15.6 | 135.6 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Coordinator1.5120 | Corbiere and Sons Contracting938202017-1Project Coordinator1.5120Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 60 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 1.5 | HR |  |  | 80 | 0 | 120 | 15.6 | 135.6 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Coordinator1.5120 | Corbiere and Sons Contracting938202017-1Project Coordinator1.5120Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 60 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.5 | HR |  |  | 80 | 0 | 120 | 15.6 | 135.6 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Coordinator1.5120 | Corbiere and Sons Contracting938202017-1Project Coordinator1.5120Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 60 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510107 | Access | 0 | Safety Advisor | 85 | 1.5 | HR |  |  | 85 | 0 | 127.5 | 16.575 | 144.075 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Safety Advisor1.5127.5 | Corbiere and Sons Contracting938202017-1Safety Advisor1.5127.5Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 63.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510111 | Access | 0 | Safety Advisor | 85 | 1.5 | HR |  |  | 85 | 0 | 127.5 | 16.575 | 144.075 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Safety Advisor1.5127.5 | Corbiere and Sons Contracting938202017-1Safety Advisor1.5127.5Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 63.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 1.5 | HR |  |  | 85 | 0 | 127.5 | 16.575 | 144.075 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Safety Advisor1.5127.5 | Corbiere and Sons Contracting938202017-1Safety Advisor1.5127.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 63.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 1.5 | HR |  |  | 85 | 0 | 127.5 | 16.575 | 144.075 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Safety Advisor1.5127.5 | Corbiere and Sons Contracting938202017-1Safety Advisor1.5127.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 63.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 1.5 | HR |  |  | 85 | 0 | 127.5 | 16.575 | 144.075 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Safety Advisor1.5127.5 | Corbiere and Sons Contracting938202017-1Safety Advisor1.5127.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 63.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510107 | Access | 0 | Site Administrator | 50 | 1.25 | HR |  |  | 50 | 0 | 62.5 | 8.125 | 70.625 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Site Administrator1.2562.5 | Corbiere and Sons Contracting938202017-1Site Administrator1.2562.5Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 31.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510111 | Access | 0 | Site Administrator | 50 | 1.25 | HR |  |  | 50 | 0 | 62.5 | 8.125 | 70.625 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Site Administrator1.2562.5 | Corbiere and Sons Contracting938202017-1Site Administrator1.2562.5Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 31.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520101 | Clearing | 0 | Site Administrator | 50 | 1.25 | HR |  |  | 50 | 0 | 62.5 | 8.125 | 70.625 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Site Administrator1.2562.5 | Corbiere and Sons Contracting938202017-1Site Administrator1.2562.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 31.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 1.25 | HR |  |  | 50 | 0 | 62.5 | 8.125 | 70.625 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Site Administrator1.2562.5 | Corbiere and Sons Contracting938202017-1Site Administrator1.2562.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 31.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 1.25 | HR |  |  | 50 | 0 | 62.5 | 8.125 | 70.625 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Site Administrator1.2562.5 | Corbiere and Sons Contracting938202017-1Site Administrator1.2562.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 31.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510107 | Access | 0 | Project Controls | 70 | 1.5 | HR |  |  | 70 | 0 | 105 | 13.65 | 118.65 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Controls1.5105 | Corbiere and Sons Contracting938202017-1Project Controls1.5105Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 52.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510111 | Access | 0 | Project Controls | 70 | 1.5 | HR |  |  | 70 | 0 | 105 | 13.65 | 118.65 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Controls1.5105 | Corbiere and Sons Contracting938202017-1Project Controls1.5105Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 52.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 1.5 | HR |  |  | 70 | 0 | 105 | 13.65 | 118.65 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Controls1.5105 | Corbiere and Sons Contracting938202017-1Project Controls1.5105Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 52.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 1.5 | HR |  |  | 70 | 0 | 105 | 13.65 | 118.65 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Controls1.5105 | Corbiere and Sons Contracting938202017-1Project Controls1.5105Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 52.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.5 | HR |  |  | 70 | 0 | 105 | 13.65 | 118.65 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1Project Controls1.5105 | Corbiere and Sons Contracting938202017-1Project Controls1.5105Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 52.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510107 | Access | 0 | L.O.A. | 210 | 0.75 | DAY |  |  |  | 0 | 157.5 | 20.475 | 177.975 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1L.O.A.0.75157.5 | Corbiere and Sons Contracting938202017-1L.O.A.0.75157.5Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 78.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.75 | DAY |  |  |  | 0 | 157.5 | 20.475 | 177.975 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1L.O.A.0.75157.5 | Corbiere and Sons Contracting938202017-1L.O.A.0.75157.5Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 78.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.75 | DAY |  |  |  | 0 | 157.5 | 20.475 | 177.975 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1L.O.A.0.75157.5 | Corbiere and Sons Contracting938202017-1L.O.A.0.75157.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 78.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.75 | DAY |  |  |  | 0 | 157.5 | 20.475 | 177.975 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1L.O.A.0.75157.5 | Corbiere and Sons Contracting938202017-1L.O.A.0.75157.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 78.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 938 | 202017-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.75 | DAY |  |  |  | 0 | 157.5 | 20.475 | 177.975 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | splitted from 53510106 to 53520104, 53520102, 53510104, 53510102, 53510111, 53560101, 53520101, 53510107 - these codes were used on 1/7/2020 | 18 |  | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting938202017-1L.O.A.0.75157.5 | Corbiere and Sons Contracting938202017-1L.O.A.0.75157.5Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 78.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1030 | 202017-2-R1 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintanence |  |  | General Yard Maintanence | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting1030202017-2-R1Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting1030202017-2-R1Loader JD 524 to 624 or equal5495Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1030 | 202017-2-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintanence |  |  | General Yard Maintanence | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting1030202017-2-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting1030202017-2-R1Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1030 | 202017-2-R1 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintanence |  |  | General Yard Maintanence | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting1030202017-2-R1Operator - Apprentice10600 | Corbiere and Sons Contracting1030202017-2-R1Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 939 | 202017-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042-A041; Raking and Brushing from A037 to A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting939202017-3Brusher91822.5 | Corbiere and Sons Contracting939202017-3Brusher91822.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 939 | 202017-3 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042-A041; Raking and Brushing from A037 to A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting939202017-3Chainsaw and consummables5600 | Corbiere and Sons Contracting939202017-3Chainsaw and consummables5600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 939 | 202017-3 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042-A041; Raking and Brushing from A037 to A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting939202017-3Excavator - 36 ton91539 | Corbiere and Sons Contracting939202017-3Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 939 | 202017-3 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042-A041; Raking and Brushing from A037 to A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting939202017-3Light Truck - Pick up20600 | Corbiere and Sons Contracting939202017-3Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 939 | 202017-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042-A041; Raking and Brushing from A037 to A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting939202017-3Foreman121140 | Corbiere and Sons Contracting939202017-3Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 939 | 202017-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 27 | HR |  |  |  | 0 | 2430 | 315.9 | 2745.9 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042-A041; Raking and Brushing from A037 to A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting939202017-3Operator - Principle272430 | Corbiere and Sons Contracting939202017-3Operator - Principle272430Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 939 | 202017-3 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042-A041; Raking and Brushing from A037 to A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting939202017-3Labourer - Specialized443300 | Corbiere and Sons Contracting939202017-3Labourer - Specialized443300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 939 | 202017-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042-A041; Raking and Brushing from A037 to A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting939202017-3L.O.A.3630 | Corbiere and Sons Contracting939202017-3L.O.A.3630Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 939 | 202017-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042-A041; Raking and Brushing from A037 to A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting939202017-3L.O.A.51050 | Corbiere and Sons Contracting939202017-3L.O.A.51050Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 941 | 202017-4 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 5 | HR | 101.25 | 0 |  |  | 675 | 87.75 | 762.75 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Gravelling, Rd. Building and Snow Removal from A37-A036; |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting941202017-4Dozer D6 or equal5675 | Corbiere and Sons Contracting941202017-4Dozer D6 or equal5675Inv#006R01 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 941 | 202017-4 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Gravelling, Rd. Building and Snow Removal from A37-A036; |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting941202017-4Light Truck - Pick up10300 | Corbiere and Sons Contracting941202017-4Light Truck - Pick up10300Inv#006R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 941 | 202017-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 8 | HR |  |  |  | 0 | 720 | 93.6 | 813.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Gravelling, Rd. Building and Snow Removal from A37-A036; |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting941202017-4Operator - Principle8720 | Corbiere and Sons Contracting941202017-4Operator - Principle8720Inv#006R01 | [5 empty] | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 941 | 202017-4 | 53510111 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Gravelling, Rd. Building and Snow Removal from A37-A036; |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting941202017-4Labourer - General11715 | Corbiere and Sons Contracting941202017-4Labourer - General11715Inv#006R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 941 | 202017-4 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Gravelling, Rd. Building and Snow Removal from A37-A036; |  |  |  | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting941202017-4L.O.A.2420 | Corbiere and Sons Contracting941202017-4L.O.A.2420Inv#006R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 943 | 202017-6 | 53510111 | Access | 0 | Dozer - D5 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Gravelling and Rd. Building being from from A086 to A089 and A081-A084; Labourers cleaning tracks and rolling out GEO; Graders and Sander Truck working across all access roads; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting943202017-6Dozer - D5 or equal9891 | Corbiere and Sons Contracting943202017-6Dozer - D5 or equal9891Inv#006R01 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 943 | 202017-6 | 53510111 | Access | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Gravelling and Rd. Building being from from A086 to A089 and A081-A084; Labourers cleaning tracks and rolling out GEO; Graders and Sander Truck working across all access roads; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting943202017-6Excavator - 30 ton91255.5 | Corbiere and Sons Contracting943202017-6Excavator - 30 ton91255.5Inv#006R01 | [5 empty] | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 943 | 202017-6 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Gravelling and Rd. Building being from from A086 to A089 and A081-A084; Labourers cleaning tracks and rolling out GEO; Graders and Sander Truck working across all access roads; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting943202017-6Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting943202017-6Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 | [5 empty] | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 943 | 202017-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 27 | HR | 94.5 | 0 |  |  | 3402 | 442.26 | 3844.26 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Gravelling and Rd. Building being from from A086 to A089 and A081-A084; Labourers cleaning tracks and rolling out GEO; Graders and Sander Truck working across all access roads; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting943202017-6Grader - Cat 12 to 14 or equal273402 | Corbiere and Sons Contracting943202017-6Grader - Cat 12 to 14 or equal273402Inv#006R01 | [5 empty] | 1 | 3402 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 943 | 202017-6 | 53510111 | Access | 0 | Sander Truck | 112.5 | 12 | HR | 84.38 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Gravelling and Rd. Building being from from A086 to A089 and A081-A084; Labourers cleaning tracks and rolling out GEO; Graders and Sander Truck working across all access roads; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting943202017-6Sander Truck121350 | Corbiere and Sons Contracting943202017-6Sander Truck121350Inv#006R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 943 | 202017-6 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Gravelling and Rd. Building being from from A086 to A089 and A081-A084; Labourers cleaning tracks and rolling out GEO; Graders and Sander Truck working across all access roads; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting943202017-6Light Truck - Pick up20600 | Corbiere and Sons Contracting943202017-6Light Truck - Pick up20600Inv#006R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 943 | 202017-6 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Gravelling and Rd. Building being from from A086 to A089 and A081-A084; Labourers cleaning tracks and rolling out GEO; Graders and Sander Truck working across all access roads; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting943202017-6Operator - Principle221980 | Corbiere and Sons Contracting943202017-6Operator - Principle221980Inv#006R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 943 | 202017-6 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Gravelling and Rd. Building being from from A086 to A089 and A081-A084; Labourers cleaning tracks and rolling out GEO; Graders and Sander Truck working across all access roads; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting943202017-6Operator - Principle11990 | Corbiere and Sons Contracting943202017-6Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 943 | 202017-6 | 53510111 | Access | 0 | Operator - Principle | 90 | 35 | HR |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Gravelling and Rd. Building being from from A086 to A089 and A081-A084; Labourers cleaning tracks and rolling out GEO; Graders and Sander Truck working across all access roads; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting943202017-6Operator - Principle353150 | Corbiere and Sons Contracting943202017-6Operator - Principle353150Inv#006R01 | [5 empty] | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 943 | 202017-6 | 53510111 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Gravelling and Rd. Building being from from A086 to A089 and A081-A084; Labourers cleaning tracks and rolling out GEO; Graders and Sander Truck working across all access roads; |  |  |  | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting943202017-6L.O.A.61260 | Corbiere and Sons Contracting943202017-6L.O.A.61260Inv#006R01 | [5 empty] | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting944202017-7Grinder - 4710 Peterson or equal95011.2Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 10 | HR | 417.6 | 0 |  |  | 5568 | 723.84 | 6291.84 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Grinder - 4710 Peterson or equal105568 | Corbiere and Sons Contracting944202017-7Grinder - 4710 Peterson or equal105568Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5568 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Log Loader91377 | Corbiere and Sons Contracting944202017-7Log Loader91377Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 10 | HR | 114.75 | 0 |  |  | 1530 | 198.9 | 1728.9 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Log Loader101530 | Corbiere and Sons Contracting944202017-7Log Loader101530Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1530 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Chainsaw and consummables7840 | Corbiere and Sons Contracting944202017-7Chainsaw and consummables7840Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Chainsaw and consummables3360 | Corbiere and Sons Contracting944202017-7Chainsaw and consummables3360Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Light Truck - Pick up10300 | Corbiere and Sons Contracting944202017-7Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Light Truck - Pick up10300 | Corbiere and Sons Contracting944202017-7Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Light Truck - Pick up30900 | Corbiere and Sons Contracting944202017-7Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Light Truck - Pick up10300 | Corbiere and Sons Contracting944202017-7Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Foreman121140 | Corbiere and Sons Contracting944202017-7Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 23 | HR |  |  |  | 0 | 2070 | 269.1 | 2339.1 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Operator - Principle232070 | Corbiere and Sons Contracting944202017-7Operator - Principle232070Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2070 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Labourer - Specialized11825 | Corbiere and Sons Contracting944202017-7Labourer - Specialized11825Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Labourer - Specialized554125 | Corbiere and Sons Contracting944202017-7Labourer - Specialized554125Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7Labourer - Specialized332475 | Corbiere and Sons Contracting944202017-7Labourer - Specialized332475Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7L.O.A.2420 | Corbiere and Sons Contracting944202017-7L.O.A.2420Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 944 | 202017-7 | 53520104 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A084; Grinding and Equipment Walkout from A081; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting944202017-7L.O.A.102100 | Corbiere and Sons Contracting944202017-7L.O.A.102100Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 945 | 202017-8 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Westward; 1 BR Float moved to A076 once complete. |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting945202017-8Brusher183645 | Corbiere and Sons Contracting945202017-8Brusher183645Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 945 | 202017-8 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Westward; 1 BR Float moved to A076 once complete. |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting945202017-8Excavator - 36 ton183078 | Corbiere and Sons Contracting945202017-8Excavator - 36 ton183078Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 945 | 202017-8 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Westward; 1 BR Float moved to A076 once complete. |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting945202017-8Light Truck - Pick up20600 | Corbiere and Sons Contracting945202017-8Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 945 | 202017-8 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Westward; 1 BR Float moved to A076 once complete. |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting945202017-8Operator - Principle443960 | Corbiere and Sons Contracting945202017-8Operator - Principle443960Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 945 | 202017-8 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Westward; 1 BR Float moved to A076 once complete. |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting945202017-8Labourer - General11715 | Corbiere and Sons Contracting945202017-8Labourer - General11715Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 945 | 202017-8 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing from A122 Westward; 1 BR Float moved to A076 once complete. |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting945202017-8L.O.A.51050 | Corbiere and Sons Contracting945202017-8L.O.A.51050Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Brusher91822.5 | Corbiere and Sons Contracting946202017-9Brusher91822.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Feller Buncher92160 | Corbiere and Sons Contracting946202017-9Feller Buncher92160Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Feller Buncher368640 | Corbiere and Sons Contracting946202017-9Feller Buncher368640Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Skidder 91539 | Corbiere and Sons Contracting946202017-9Skidder 91539Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Skidder 274617 | Corbiere and Sons Contracting946202017-9Skidder 274617Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 8 | HR | 101.25 | 0 |  |  | 1080 | 140.4 | 1220.4 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Dozer D6 or equal81080 | Corbiere and Sons Contracting946202017-9Dozer D6 or equal81080Inv#006R01 | [5 empty] | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Excavator - 30 ton91255.5 | Corbiere and Sons Contracting946202017-9Excavator - 30 ton91255.5Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Excavator - 36 ton5855 | Corbiere and Sons Contracting946202017-9Excavator - 36 ton5855Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Excavator - 36 ton91539 | Corbiere and Sons Contracting946202017-9Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520101 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting946202017-9Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting946202017-9Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting946202017-9Grader - Cat 12 to 14 or equal91134Inv#006R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Light Truck - Pick up10300 | Corbiere and Sons Contracting946202017-9Light Truck - Pick up10300Inv#006R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Light Truck - Pick up30900 | Corbiere and Sons Contracting946202017-9Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Light Truck - Pick up501500 | Corbiere and Sons Contracting946202017-9Light Truck - Pick up501500Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Light Truck - Pick up20600 | Corbiere and Sons Contracting946202017-9Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53510111 | Access | 0 | Foreman | 95 | 1 | HR |  |  |  | 0 | 95 | 12.35 | 107.35 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Foreman195 | Corbiere and Sons Contracting946202017-9Foreman195Inv#006R01 | [5 empty] | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Foreman4380 | Corbiere and Sons Contracting946202017-9Foreman4380Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Foreman | 95 | 11 | HR |  |  |  | 0 | 1045 | 135.85 | 1180.85 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Foreman111045 | Corbiere and Sons Contracting946202017-9Foreman111045Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Foreman | 95 | 2 | HR |  |  |  | 0 | 190 | 24.7 | 214.7 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Foreman2190 | Corbiere and Sons Contracting946202017-9Foreman2190Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Operator - Principle221980 | Corbiere and Sons Contracting946202017-9Operator - Principle221980Inv#006R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Operator - Principle221980 | Corbiere and Sons Contracting946202017-9Operator - Principle221980Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 66 | HR |  |  |  | 0 | 5940 | 772.2 | 6712.2 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Operator - Principle665940 | Corbiere and Sons Contracting946202017-9Operator - Principle665940Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 23 | HR |  |  |  | 0 | 2070 | 269.1 | 2339.1 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Operator - Principle232070 | Corbiere and Sons Contracting946202017-9Operator - Principle232070Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2070 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9Operator - Principle221980 | Corbiere and Sons Contracting946202017-9Operator - Principle221980Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9L.O.A.2420 | Corbiere and Sons Contracting946202017-9L.O.A.2420Inv#006R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9L.O.A.2420 | Corbiere and Sons Contracting946202017-9L.O.A.2420Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 946 | 202017-9 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2020-01-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A128 to A135; Excavators NS0EX-01, NS-EX-02, build road to 40m of B003 - NS-EX-04 raked B004, Feller Buncher NS-FB-01 was floated toA061 and began clearing near A062 - Excavator 250EL NS-BR- 01 was floated to A061 and began brushingnear A062 - Peterbuild Float NS-RT-03 floated NS-FB-01, NS-SK-01 and NS-BR-01 from Cavern Km 5 to Elarado KM 10 Tower A061 - NS-DZ-01 and NS-GR-01 performed winter clearin of Wolf and Cavern Roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43842 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting946202017-9L.O.A.102100 | Corbiere and Sons Contracting946202017-9L.O.A.102100Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 989 | 202018-1 | 53510106 | Access | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  | Approved a secong time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting989202018-1Light Truck - Pick up601800 | Corbiere and Sons Contracting989202018-1Light Truck - Pick up601800INV#30-R02 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 989 | 202018-1 | 53510106 | Access | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  | Approved a secong time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting989202018-1Project Manager121320 | Corbiere and Sons Contracting989202018-1Project Manager121320INV#30-R02 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 989 | 202018-1 | 53510106 | Access | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  | Approved a secong time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting989202018-1Superintendent121260 | Corbiere and Sons Contracting989202018-1Superintendent121260INV#30-R02 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 989 | 202018-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  | Approved a secong time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting989202018-1Project Coordinator12960 | Corbiere and Sons Contracting989202018-1Project Coordinator12960INV#30-R02 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 989 | 202018-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  | Approved a secong time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting989202018-1Project Coordinator12960 | Corbiere and Sons Contracting989202018-1Project Coordinator12960INV#30-R02 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 989 | 202018-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  | Approved a secong time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting989202018-1Safety Advisor121020 | Corbiere and Sons Contracting989202018-1Safety Advisor121020INV#30-R02 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 989 | 202018-1 | 53510106 | Access | 0 | Site Administrator | 50 | 10 | HR |  |  |  | 0 | 500 | 65 | 565 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  | Approved a secong time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting989202018-1Site Administrator10500 | Corbiere and Sons Contracting989202018-1Site Administrator10500INV#30-R02 |  | WF1-Access | WF1-Access |  | 0 | 1 | 500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 989 | 202018-1 | 53510106 | Access | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  | Approved a secong time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting989202018-1Project Controls12840 | Corbiere and Sons Contracting989202018-1Project Controls12840INV#30-R02 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 989 | 202018-1 | 53510106 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  | Approved a secong time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting989202018-1L.O.A.71470 | Corbiere and Sons Contracting989202018-1L.O.A.71470INV#30-R02 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 999 | 202018-11 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B007 to B012; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting999202018-11Feller Buncher368640 | Corbiere and Sons Contracting999202018-11Feller Buncher368640Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 999 | 202018-11 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B007 to B012; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting999202018-11Skidder 274617 | Corbiere and Sons Contracting999202018-11Skidder 274617Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 999 | 202018-11 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B007 to B012; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting999202018-11Light Truck - Pick up501500 | Corbiere and Sons Contracting999202018-11Light Truck - Pick up501500Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 999 | 202018-11 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B007 to B012; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting999202018-11Foreman121140 | Corbiere and Sons Contracting999202018-11Foreman121140Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 999 | 202018-11 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B007 to B012; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting999202018-11Operator - Principle776930 | Corbiere and Sons Contracting999202018-11Operator - Principle776930Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 999 | 202018-11 | 53520102 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B007 to B012; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting999202018-11L.O.A.71470 | Corbiere and Sons Contracting999202018-11L.O.A.71470Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1003 | 202018-15 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 8 | HR | 101.25 | 0 |  |  | 1080 | 140.4 | 1220.4 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Clearing and Rd. Building from A061 to A066; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1003202018-15Dozer D6 or equal81080 | Corbiere and Sons Contracting1003202018-15Dozer D6 or equal81080Inv#006R01 | [5 empty] | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1003 | 202018-15 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Clearing and Rd. Building from A061 to A066; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1003202018-15Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting1003202018-15Grader - Cat 12 to 14 or equal91134Inv#006R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1003 | 202018-15 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Clearing and Rd. Building from A061 to A066; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1003202018-15Light Truck - Pick up10300 | Corbiere and Sons Contracting1003202018-15Light Truck - Pick up10300Inv#006R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1003 | 202018-15 | 53510111 | Access | 0 | Operator - Principle | 90 | 21 | HR |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Clearing and Rd. Building from A061 to A066; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1003202018-15Operator - Principle211890 | Corbiere and Sons Contracting1003202018-15Operator - Principle211890Inv#006R01 | [5 empty] | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1003 | 202018-15 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Clearing and Rd. Building from A061 to A066; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1003202018-15L.O.A.2420 | Corbiere and Sons Contracting1003202018-15L.O.A.2420Inv#006R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 990 | 202018-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Also approved a second time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting990202018-2Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting990202018-2Loader JD 524 to 624 or equal5495INV#30-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 990 | 202018-2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Also approved a second time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting990202018-2Light Truck - Pick up10300 | Corbiere and Sons Contracting990202018-2Light Truck - Pick up10300INV#30-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 990 | 202018-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-13 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Also approved a second time by Dean MacArthur on June 06, 2020. Ryan couldn’t find his signed version. | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting990202018-2Operator - Apprentice10600 | Corbiere and Sons Contracting990202018-2Operator - Apprentice10600INV#30-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 8 | HR | 151.88 | 0 |  |  | 1620 | 210.6 | 1830.6 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Brusher81620 | Corbiere and Sons Contracting991202018-3Brusher81620Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting991202018-3Grinder - 4710 Peterson or equal95011.2Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Log Loader91377 | Corbiere and Sons Contracting991202018-3Log Loader91377Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Chainsaw and consummables5600 | Corbiere and Sons Contracting991202018-3Chainsaw and consummables5600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Excavator - 36 ton91539 | Corbiere and Sons Contracting991202018-3Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting991202018-3Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Light Truck - Pick up10300 | Corbiere and Sons Contracting991202018-3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Light Truck - Pick up10300 | Corbiere and Sons Contracting991202018-3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Light Truck - Pick up20600 | Corbiere and Sons Contracting991202018-3Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Foreman121140 | Corbiere and Sons Contracting991202018-3Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Operator - Principle332970 | Corbiere and Sons Contracting991202018-3Operator - Principle332970Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3Labourer - Specialized443300 | Corbiere and Sons Contracting991202018-3Labourer - Specialized443300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3L.O.A.2420 | Corbiere and Sons Contracting991202018-3L.O.A.2420Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 991 | 202018-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A038; Clearing towards A036; Grinding of Material from A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting991202018-3L.O.A.51050 | Corbiere and Sons Contracting991202018-3L.O.A.51050Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 992 | 202018-4 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Winter Road Maintenance, gravelling and Rd. building all from A036 to A039 and pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting992202018-4Light Truck - Pick up10300 | Corbiere and Sons Contracting992202018-4Light Truck - Pick up10300Inv#006R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 992 | 202018-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 6.5 | HR |  |  |  | 0 | 585 | 76.05 | 661.05 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Winter Road Maintenance, gravelling and Rd. building all from A036 to A039 and pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting992202018-4Operator - Principle6.5585 | Corbiere and Sons Contracting992202018-4Operator - Principle6.5585Inv#006R01 | [5 empty] | 1 | 585 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 992 | 202018-4 | 53510111 | Access | 0 | Labourer - General | 65 | 6.5 | HR |  |  |  | 0 | 422.5 | 54.925 | 477.425 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Winter Road Maintenance, gravelling and Rd. building all from A036 to A039 and pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting992202018-4Labourer - General6.5422.5 | Corbiere and Sons Contracting992202018-4Labourer - General6.5422.5Inv#006R01 | [5 empty] | 1 | 422.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 992 | 202018-4 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Winter Road Maintenance, gravelling and Rd. building all from A036 to A039 and pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting992202018-4L.O.A.2420 | Corbiere and Sons Contracting992202018-4L.O.A.2420Inv#006R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Feller Buncher92160 | Corbiere and Sons Contracting993202018-5Feller Buncher92160Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 7 | HR | 417.6 | 0 |  |  | 3897.6 | 506.688 | 4404.288 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Grinder - 4710 Peterson or equal73897.6 | Corbiere and Sons Contracting993202018-5Grinder - 4710 Peterson or equal73897.6Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3897.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 7 | HR | 114.75 | 0 |  |  | 1071 | 139.23 | 1210.23 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Log Loader71071 | Corbiere and Sons Contracting993202018-5Log Loader71071Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1071 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Skidder 91539 | Corbiere and Sons Contracting993202018-5Skidder 91539Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Excavator - 36 ton91539 | Corbiere and Sons Contracting993202018-5Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting993202018-5Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Light Truck - Pick up20600 | Corbiere and Sons Contracting993202018-5Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Light Truck - Pick up10300 | Corbiere and Sons Contracting993202018-5Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Light Truck - Pick up10300 | Corbiere and Sons Contracting993202018-5Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520101 | Clearing | 0 | Foreman | 95 | 5 | HR |  |  |  | 0 | 475 | 61.75 | 536.75 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Foreman5475 | Corbiere and Sons Contracting993202018-5Foreman5475Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Operator - Principle332970 | Corbiere and Sons Contracting993202018-5Operator - Principle332970Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Operator - Principle11990 | Corbiere and Sons Contracting993202018-5Operator - Principle11990Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520101 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5Labourer - General11715 | Corbiere and Sons Contracting993202018-5Labourer - General11715Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5L.O.A.4840 | Corbiere and Sons Contracting993202018-5L.O.A.4840Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 993 | 202018-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A070 to A071; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting993202018-5L.O.A.2420 | Corbiere and Sons Contracting993202018-5L.O.A.2420Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 994 | 202018-6 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A082 and A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting994202018-6Chainsaw and consummables3360 | Corbiere and Sons Contracting994202018-6Chainsaw and consummables3360Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 994 | 202018-6 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A082 and A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting994202018-6Chainsaw and consummables7840 | Corbiere and Sons Contracting994202018-6Chainsaw and consummables7840Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 994 | 202018-6 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A082 and A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting994202018-6Light Truck - Pick up10300 | Corbiere and Sons Contracting994202018-6Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 994 | 202018-6 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A082 and A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting994202018-6Light Truck - Pick up30900 | Corbiere and Sons Contracting994202018-6Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 994 | 202018-6 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A082 and A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting994202018-6Foreman121140 | Corbiere and Sons Contracting994202018-6Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 994 | 202018-6 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A082 and A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting994202018-6Labourer - Specialized443300 | Corbiere and Sons Contracting994202018-6Labourer - Specialized443300Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 994 | 202018-6 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A082 and A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting994202018-6Labourer - Specialized554125 | Corbiere and Sons Contracting994202018-6Labourer - Specialized554125Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 994 | 202018-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A082 and A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting994202018-6L.O.A.102100 | Corbiere and Sons Contracting994202018-6L.O.A.102100Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53510111 | Access | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8Excavator - 30 ton91255.5 | Corbiere and Sons Contracting996202018-8Excavator - 30 ton91255.5Inv#006R01 | [5 empty] | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting996202018-8Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 | [5 empty] | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 25 | HR | 94.5 | 0 |  |  | 3150 | 409.5 | 3559.5 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8Grader - Cat 12 to 14 or equal253150 | Corbiere and Sons Contracting996202018-8Grader - Cat 12 to 14 or equal253150Inv#006R01 | [5 empty] | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53510111 | Access | 0 | Sander Truck | 112.5 | 12 | HR | 84.38 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8Sander Truck121350 | Corbiere and Sons Contracting996202018-8Sander Truck121350Inv#006R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8Light Truck - Pick up10300 | Corbiere and Sons Contracting996202018-8Light Truck - Pick up10300Inv#006R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting996202018-8Tractor Trailer - 60 Ton101350Inv#006R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8Operator - Principle11990 | Corbiere and Sons Contracting996202018-8Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8Operator - Principle11990 | Corbiere and Sons Contracting996202018-8Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53510111 | Access | 0 | Operator - Principle | 90 | 30 | HR |  |  |  | 0 | 2700 | 351 | 3051 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8Operator - Principle302700 | Corbiere and Sons Contracting996202018-8Operator - Principle302700Inv#006R01 | [5 empty] | 1 | 2700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8Operator - Intermdiate11825 | Corbiere and Sons Contracting996202018-8Operator - Intermdiate11825Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53510111 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8L.O.A.51050 | Corbiere and Sons Contracting996202018-8L.O.A.51050Inv#006R01 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 996 | 202018-8 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing snow from A085-A089; Rd. Building from A081 to A087; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting996202018-8L.O.A.1210 | Corbiere and Sons Contracting996202018-8L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 997 | 202018-9 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 to A126 - 1 Orientation |  |  | Wolf Lake - A118 to A127 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting997202018-9Brusher183645 | Corbiere and Sons Contracting997202018-9Brusher183645Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 997 | 202018-9 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 to A126 - 1 Orientation |  |  | Wolf Lake - A118 to A127 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting997202018-9Excavator - 36 ton183078 | Corbiere and Sons Contracting997202018-9Excavator - 36 ton183078Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 997 | 202018-9 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 to A126 - 1 Orientation |  |  | Wolf Lake - A118 to A127 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting997202018-9Light Truck - Pick up20600 | Corbiere and Sons Contracting997202018-9Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 997 | 202018-9 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 to A126 - 1 Orientation |  |  | Wolf Lake - A118 to A127 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting997202018-9Operator - Principle443960 | Corbiere and Sons Contracting997202018-9Operator - Principle443960Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 997 | 202018-9 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 to A126 - 1 Orientation |  |  | Wolf Lake - A118 to A127 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting997202018-9Labourer - General11715 | Corbiere and Sons Contracting997202018-9Labourer - General11715Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 997 | 202018-9 | 53520102 | Clearing | 0 | Labourer - General | 65 | 5 | HR |  |  |  | 0 | 325 | 42.25 | 367.25 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 to A126 - 1 Orientation |  |  | Wolf Lake - A118 to A127 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting997202018-9Labourer - General5325 | Corbiere and Sons Contracting997202018-9Labourer - General5325Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 997 | 202018-9 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking from A122 to A126 - 1 Orientation |  |  | Wolf Lake - A118 to A127 | 0 |  |  | 37 | 43845 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting997202018-9L.O.A.51050 | Corbiere and Sons Contracting997202018-9L.O.A.51050Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1033 | 202019-1 | 53510106 | Access | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1033202019-1Light Truck - Pick up601800 | Corbiere and Sons Contracting1033202019-1Light Truck - Pick up601800Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1033 | 202019-1 | 53510106 | Access | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1033202019-1Project Manager121320 | Corbiere and Sons Contracting1033202019-1Project Manager121320Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1033 | 202019-1 | 53510106 | Access | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1033202019-1Superintendent121260 | Corbiere and Sons Contracting1033202019-1Superintendent121260Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1033 | 202019-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1033202019-1Project Coordinator12960 | Corbiere and Sons Contracting1033202019-1Project Coordinator12960Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1033 | 202019-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1033202019-1Project Coordinator12960 | Corbiere and Sons Contracting1033202019-1Project Coordinator12960Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1033 | 202019-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1033202019-1Safety Advisor121020 | Corbiere and Sons Contracting1033202019-1Safety Advisor121020Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1033 | 202019-1 | 53510106 | Access | 0 | Site Administrator | 50 | 10 | HR |  |  |  | 0 | 500 | 65 | 565 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1033202019-1Site Administrator10500 | Corbiere and Sons Contracting1033202019-1Site Administrator10500Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1033 | 202019-1 | 53510106 | Access | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1033202019-1Project Controls12840 | Corbiere and Sons Contracting1033202019-1Project Controls12840Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1033 | 202019-1 | 53510106 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project supervision |  |  | Project supervision | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1033202019-1L.O.A.71470 | Corbiere and Sons Contracting1033202019-1L.O.A.71470Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1041 | 202019-10 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Raking from A122 Eastward; |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1041202019-10Brusher183645 | Corbiere and Sons Contracting1041202019-10Brusher183645Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1041 | 202019-10 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Raking from A122 Eastward; |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1041202019-10Excavator - 36 ton91539 | Corbiere and Sons Contracting1041202019-10Excavator - 36 ton91539Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1041 | 202019-10 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Raking from A122 Eastward; |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1041202019-10Light Truck - Pick up10300 | Corbiere and Sons Contracting1041202019-10Light Truck - Pick up10300Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1041 | 202019-10 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Raking from A122 Eastward; |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1041202019-10Operator - Principle332970 | Corbiere and Sons Contracting1041202019-10Operator - Principle332970Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1041 | 202019-10 | 53520102 | Clearing | 0 | Labourer - General | 65 | 4 | HR |  |  |  | 0 | 260 | 33.8 | 293.8 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Raking from A122 Eastward; |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1041202019-10Labourer - General4260 | Corbiere and Sons Contracting1041202019-10Labourer - General4260Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1041 | 202019-10 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Raking from A122 Eastward; |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1041202019-10L.O.A.4840 | Corbiere and Sons Contracting1041202019-10L.O.A.4840Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1042 | 202019-11 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing Snow to start ROW Road at A123 |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1042202019-11Excavator - 36 ton91539 | Corbiere and Sons Contracting1042202019-11Excavator - 36 ton91539Inv#007-R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1042 | 202019-11 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing Snow to start ROW Road at A123 |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1042202019-11Light Truck - Pick up10300 | Corbiere and Sons Contracting1042202019-11Light Truck - Pick up10300Inv#007-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1042 | 202019-11 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing Snow to start ROW Road at A123 |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1042202019-11Operator - Principle11990 | Corbiere and Sons Contracting1042202019-11Operator - Principle11990Inv#007-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1042 | 202019-11 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing Snow to start ROW Road at A123 |  |  | Wolf Lake Road - A118 to A127 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1042202019-11L.O.A.1210 | Corbiere and Sons Contracting1042202019-11L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12Feller Buncher276480 | Corbiere and Sons Contracting1043202019-12Feller Buncher276480Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12Feller Buncher92160 | Corbiere and Sons Contracting1043202019-12Feller Buncher92160Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520101 | Clearing | 0 | Skidder | 171 | 6 | HR | 128.25 | 0 |  |  | 1026 | 133.38 | 1159.38 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12Skidder 61026 | Corbiere and Sons Contracting1043202019-12Skidder 61026Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1026 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520102 | Clearing | 0 | Skidder | 171 | 21 | HR | 128.25 | 0 |  |  | 3591 | 466.83 | 4057.83 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12Skidder 213591 | Corbiere and Sons Contracting1043202019-12Skidder 213591Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3591 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12Excavator - 36 ton91539 | Corbiere and Sons Contracting1043202019-12Excavator - 36 ton91539Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12Excavator - 36 ton91539 | Corbiere and Sons Contracting1043202019-12Excavator - 36 ton91539Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12Light Truck - Pick up20600 | Corbiere and Sons Contracting1043202019-12Light Truck - Pick up20600Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12Light Truck - Pick up30900 | Corbiere and Sons Contracting1043202019-12Light Truck - Pick up30900Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 15 | HR |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12Operator - Principle151350 | Corbiere and Sons Contracting1043202019-12Operator - Principle151350Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 105 | HR |  |  |  | 0 | 9450 | 1228.5 | 10678.5 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12Operator - Principle1059450 | Corbiere and Sons Contracting1043202019-12Operator - Principle1059450Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 9450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12L.O.A.4840 | Corbiere and Sons Contracting1043202019-12L.O.A.4840Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1043 | 202019-12 | 53520102 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing work being performed between A132 and B002; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1043202019-12L.O.A.71470 | Corbiere and Sons Contracting1043202019-12L.O.A.71470Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1034 | 202019-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1034202019-2Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting1034202019-2Loader JD 524 to 624 or equal5495Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1034 | 202019-2 | 53510106 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1034202019-2Light Truck - Pick up10300 | Corbiere and Sons Contracting1034202019-2Light Truck - Pick up10300Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1034 | 202019-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1034202019-2Operator - Apprentice10600 | Corbiere and Sons Contracting1034202019-2Operator - Apprentice10600Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1034 | 202019-2 | 53510106 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1034202019-2L.O.A.1210 | Corbiere and Sons Contracting1034202019-2L.O.A.1210Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1034 | 202019-2 | 53510106 | Access | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1034202019-2Warehouse Supervisor12900 | Corbiere and Sons Contracting1034202019-2Warehouse Supervisor12900Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Brusher91822.5 | Corbiere and Sons Contracting1035202019-3Brusher91822.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting1035202019-3Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Log Loader91377 | Corbiere and Sons Contracting1035202019-3Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Chainsaw and consummables5600 | Corbiere and Sons Contracting1035202019-3Chainsaw and consummables5600Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Light Truck - Pick up10300 | Corbiere and Sons Contracting1035202019-3Light Truck - Pick up10300Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Light Truck - Pick up10300 | Corbiere and Sons Contracting1035202019-3Light Truck - Pick up10300Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Light Truck - Pick up20600 | Corbiere and Sons Contracting1035202019-3Light Truck - Pick up20600Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Foreman121140 | Corbiere and Sons Contracting1035202019-3Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Operator - Principle11990 | Corbiere and Sons Contracting1035202019-3Operator - Principle11990Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Operator - Principle11990 | Corbiere and Sons Contracting1035202019-3Operator - Principle11990Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3Labourer - Specialized443300 | Corbiere and Sons Contracting1035202019-3Labourer - Specialized443300Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3L.O.A.2420 | Corbiere and Sons Contracting1035202019-3L.O.A.2420Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1035 | 202019-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working towards A036; Handfelling from A042-A041; Grind of material at A042; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1035202019-3L.O.A.51050 | Corbiere and Sons Contracting1035202019-3L.O.A.51050Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1036 | 202019-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Road Building, Gravellig and Winter maintenance from A036 to A039 and at the pit; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1036202019-4Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting1036202019-4Loader JD 524 to 624 or equal9891Inv#007-R01 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1036 | 202019-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Road Building, Gravellig and Winter maintenance from A036 to A039 and at the pit; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1036202019-4Operator - Principle11990 | Corbiere and Sons Contracting1036202019-4Operator - Principle11990Inv#007-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1036 | 202019-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 6 | HR |  |  |  | 0 | 540 | 70.2 | 610.2 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Road Building, Gravellig and Winter maintenance from A036 to A039 and at the pit; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1036202019-4Operator - Principle6540 | Corbiere and Sons Contracting1036202019-4Operator - Principle6540Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1036 | 202019-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Road Building, Gravellig and Winter maintenance from A036 to A039 and at the pit; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting1036202019-4L.O.A.1210 | Corbiere and Sons Contracting1036202019-4L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1037 | 202019-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A076; |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1037202019-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting1037202019-5Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1037 | 202019-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A076; |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1037202019-5Log Loader91377 | Corbiere and Sons Contracting1037202019-5Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1037 | 202019-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A076; |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1037202019-5Light Truck - Pick up10300 | Corbiere and Sons Contracting1037202019-5Light Truck - Pick up10300Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1037 | 202019-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A076; |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1037202019-5Operator - Principle11990 | Corbiere and Sons Contracting1037202019-5Operator - Principle11990Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1037 | 202019-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A076; |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1037202019-5L.O.A.1210 | Corbiere and Sons Contracting1037202019-5L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Feller Buncher92160 | Corbiere and Sons Contracting2316202019-6Feller Buncher92160Inv#022 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Skidder 91539 | Corbiere and Sons Contracting2316202019-6Skidder 91539Inv#022 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 4 | HR | 104.63 | 0 |  |  | 558 | 72.54 | 630.54 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Excavator - 30 ton4558 | Corbiere and Sons Contracting2316202019-6Excavator - 30 ton4558Inv#022 |  |  | WF1-Merchantable Clearing |  |  | 1 | 558 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53520101 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 4 | HR | 10.13 | 0 |  |  | 54 | 7.02 | 61.02 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Excavator Thumb - 30 - 50 ton454 | Corbiere and Sons Contracting2316202019-6Excavator Thumb - 30 - 50 ton454Inv#022 |  |  | WF1-Merchantable Clearing |  |  | 1 | 54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting2316202019-6Grader - Cat 12 to 14 or equal91134Inv#022 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Light Truck - Pick up20600 | Corbiere and Sons Contracting2316202019-6Light Truck - Pick up20600Inv#022 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53510107 | Access | 0 | Tractor Trailer - 50 Ton | 130.5 | 10 | HR | 97.88 | 0 |  |  | 1305 | 169.65 | 1474.65 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Tractor Trailer - 50 Ton101305 | Corbiere and Sons Contracting2316202019-6Tractor Trailer - 50 Ton101305Inv#022 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 1305 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53510107 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Foreman2190 | Corbiere and Sons Contracting2316202019-6Foreman2190Inv#022 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53520101 | Clearing | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Foreman5475 | Corbiere and Sons Contracting2316202019-6Foreman5475Inv#022 |  |  | WF1-Merchantable Clearing |  |  | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Operator - Principle11990 | Corbiere and Sons Contracting2316202019-6Operator - Principle11990Inv#022 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 27 | HR |  |  |  | 0 | 2430 | 315.9 | 2745.9 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Operator - Principle272430 | Corbiere and Sons Contracting2316202019-6Operator - Principle272430Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 39 | HR |  |  |  | 0 | 3510 | 456.3 | 3966.3 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Operator - Principle393510 | Corbiere and Sons Contracting2316202019-6Operator - Principle393510Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3510 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53510107 | Access | 0 | Driver - AZ | 70 | 10 | HR |  |  | 105 | 0 | 700 | 91 | 791 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6Driver - AZ10700 | Corbiere and Sons Contracting2316202019-6Driver - AZ10700Inv#022 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53510107 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6L.O.A.1210 | Corbiere and Sons Contracting2316202019-6L.O.A.1210Inv#022 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6L.O.A.1210 | Corbiere and Sons Contracting2316202019-6L.O.A.1210Inv#022 |  | WF1 Mob/Demob |  |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2316 | 202019-6 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-09 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Volvo 380D 38 Ton with Thumb NS-EX-02 built road to A062-NS-EX-01 Link Belt 290 with thumb assisted with roadA061 and assisted buncher in access to stepp slop proimal to A064 - Feller Buncher NS-FB-01 and Skidder NS-SK-01 cut ROW beyond A064.5 - 350EL NS-EX-04 build beyond A062 - Peterbuilt Float NS-RT-03 floated NS-GR-01 and NS-EX-03 from Cavern km 5 to Eldorado KM 11 Tower A061-NS-DZ-01 cleared snow from the ROW rodline beyond A061 - Labourer shovelled snow of Cavern bridge as best as possible - place men working signs and fueled machines | 1 | A-055 to A-084 | Eldorado | 0 | 43931 |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting2316202019-6L.O.A.2420 | Corbiere and Sons Contracting2316202019-6L.O.A.2420Inv#022 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1038 | 202019-7 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A082-A084; Float Truck moving Mulcher; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1038202019-7Chainsaw and consummables3360 | Corbiere and Sons Contracting1038202019-7Chainsaw and consummables3360Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1038 | 202019-7 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A082-A084; Float Truck moving Mulcher; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1038202019-7Chainsaw and consummables6720 | Corbiere and Sons Contracting1038202019-7Chainsaw and consummables6720Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1038 | 202019-7 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A082-A084; Float Truck moving Mulcher; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1038202019-7Light Truck - Pick up10300 | Corbiere and Sons Contracting1038202019-7Light Truck - Pick up10300Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1038 | 202019-7 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A082-A084; Float Truck moving Mulcher; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1038202019-7Light Truck - Pick up30900 | Corbiere and Sons Contracting1038202019-7Light Truck - Pick up30900Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1038 | 202019-7 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A082-A084; Float Truck moving Mulcher; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1038202019-7Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting1038202019-7Tractor Trailer - 60 Ton101350Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1038 | 202019-7 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A082-A084; Float Truck moving Mulcher; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1038202019-7Foreman121140 | Corbiere and Sons Contracting1038202019-7Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1038 | 202019-7 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A082-A084; Float Truck moving Mulcher; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1038202019-7Operator - Intermdiate11825 | Corbiere and Sons Contracting1038202019-7Operator - Intermdiate11825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1038 | 202019-7 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 88 | HR |  |  |  | 0 | 6600 | 858 | 7458 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A082-A084; Float Truck moving Mulcher; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1038202019-7Labourer - Specialized886600 | Corbiere and Sons Contracting1038202019-7Labourer - Specialized886600Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 6600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1038 | 202019-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A082-A084; Float Truck moving Mulcher; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1038202019-7L.O.A.1210 | Corbiere and Sons Contracting1038202019-7L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1038 | 202019-7 | 53520104 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A082-A084; Float Truck moving Mulcher; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1038202019-7L.O.A.91890 | Corbiere and Sons Contracting1038202019-7L.O.A.91890Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Dozer - D5 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Dozer - D5 or equal9891 | Corbiere and Sons Contracting1040202019-9Dozer - D5 or equal9891Inv#007-R01 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Dozer D6 or equal91215 | Corbiere and Sons Contracting1040202019-9Dozer D6 or equal91215Inv#007-R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Dozer D6 or equal91215 | Corbiere and Sons Contracting1040202019-9Dozer D6 or equal91215Inv#007-R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Excavator - 30 ton91255.5 | Corbiere and Sons Contracting1040202019-9Excavator - 30 ton91255.5Inv#007-R01 | [5 empty] | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Excavator - 30 ton | 139.5 | 3 | HR | 104.63 | 0 |  |  | 418.5 | 54.405 | 472.905 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Excavator - 30 ton3418.5 | Corbiere and Sons Contracting1040202019-9Excavator - 30 ton3418.5Inv#007-R01 | [5 empty] | 1 | 418.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Excavator - 36 ton3513 | Corbiere and Sons Contracting1040202019-9Excavator - 36 ton3513Inv#007-R01 | [5 empty] | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting1040202019-9Excavator Thumb - 30 - 50 ton9121.5Inv#007-R01 | [5 empty] | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 27 | HR | 94.5 | 0 |  |  | 3402 | 442.26 | 3844.26 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Grader - Cat 12 to 14 or equal273402 | Corbiere and Sons Contracting1040202019-9Grader - Cat 12 to 14 or equal273402Inv#007-R01 | [5 empty] | 1 | 3402 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Sander Truck | 112.5 | 12 | HR | 84.38 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Sander Truck121350 | Corbiere and Sons Contracting1040202019-9Sander Truck121350Inv#007-R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Light Truck - Pick up10300 | Corbiere and Sons Contracting1040202019-9Light Truck - Pick up10300Inv#007-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Light Truck - Pick up10300 | Corbiere and Sons Contracting1040202019-9Light Truck - Pick up10300Inv#007-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Foreman6570 | Corbiere and Sons Contracting1040202019-9Foreman6570Inv#007-R01 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Operator - Principle | 90 | 46 | HR |  |  |  | 0 | 4140 | 538.2 | 4678.2 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Operator - Principle464140 | Corbiere and Sons Contracting1040202019-9Operator - Principle464140Inv#007-R01 | [5 empty] | 1 | 4140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Operator - Principle | 90 | 7 | HR |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Operator - Principle7630 | Corbiere and Sons Contracting1040202019-9Operator - Principle7630Inv#007-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Operator - Principle | 90 | 5 | HR |  |  |  | 0 | 450 | 58.5 | 508.5 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Operator - Principle5450 | Corbiere and Sons Contracting1040202019-9Operator - Principle5450Inv#007-R01 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Operator - Principle332970 | Corbiere and Sons Contracting1040202019-9Operator - Principle332970Inv#007-R01 | [5 empty] | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9Labourer - General221430 | Corbiere and Sons Contracting1040202019-9Labourer - General221430Inv#007-R01 | [5 empty] | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1040 | 202019-9 | 53510111 | Access | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2020-01-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders opening up access roads; Labourer escorting, replacing signange, cleaning tracks; Snow Removal and Rd. Building from A081 up to A089 then equipment moved down to A075-A071; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting1040202019-9L.O.A.122520 | Corbiere and Sons Contracting1040202019-9L.O.A.122520Inv#007-R01 | [5 empty] | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7607 | 20210101-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2021-01-01 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed Pays Plat entrance for 4 hours - with snow plow and then continued with grader for 2 hours. | 5 | C031-C049 | Pays Plat River | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting760720210101-4Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting760720210101-4Grader - Cat 12 to 14 or equal- After Jan 102253.96Inv#090 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7607 | 20210101-4 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-01 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed Pays Plat entrance for 4 hours - with snow plow and then continued with grader for 2 hours. | 5 | C031-C049 | Pays Plat River | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting760720210101-4Pickup w/ plow4200 | Corbiere and Sons Contracting760720210101-4Pickup w/ plow4200Inv#090 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7607 | 20210101-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-01 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed Pays Plat entrance for 4 hours - with snow plow and then continued with grader for 2 hours. | 5 | C031-C049 | Pays Plat River | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting760720210101-4L.O.A.1210 | Corbiere and Sons Contracting760720210101-4L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7607 | 20210101-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-01 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed Pays Plat entrance for 4 hours - with snow plow and then continued with grader for 2 hours. | 5 | C031-C049 | Pays Plat River | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting760720210101-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting760720210101-4Operator - Principle - After Jan 106450Inv#090 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7611 | 20210102-4 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader graded for 3 hours and then stopped to put chains on for the rest of the day Cole on plow truck in the morning and then Darrel took over working across access road entrances Jordan planning, coordinating and checking out sites for snow removal in WFs 2,3,4,5 | 4 | B194-B210 | Little Gravel River Rd | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting761120210102-4Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting761120210102-4Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#090 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7611 | 20210102-4 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader graded for 3 hours and then stopped to put chains on for the rest of the day Cole on plow truck in the morning and then Darrel took over working across access road entrances Jordan planning, coordinating and checking out sites for snow removal in WFs 2,3,4,5 | 4 | B194-B210 | Little Gravel River Rd | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting761120210102-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting761120210102-4Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7611 | 20210102-4 | 53510411 | Access | 0 | Pickup w/ plow | 50 | 10 | HR | 0 | 0 |  |  | 500 | 65 | 565 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader graded for 3 hours and then stopped to put chains on for the rest of the day Cole on plow truck in the morning and then Darrel took over working across access road entrances Jordan planning, coordinating and checking out sites for snow removal in WFs 2,3,4,5 | 4 | B194-B210 | Little Gravel River Rd | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting761120210102-4Pickup w/ plow10500 | Corbiere and Sons Contracting761120210102-4Pickup w/ plow10500Inv#090 | [5 empty] | 1 | 500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7611 | 20210102-4 | 53510411 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader graded for 3 hours and then stopped to put chains on for the rest of the day Cole on plow truck in the morning and then Darrel took over working across access road entrances Jordan planning, coordinating and checking out sites for snow removal in WFs 2,3,4,5 | 4 | B194-B210 | Little Gravel River Rd | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting761120210102-4Foreman8760 | Corbiere and Sons Contracting761120210102-4Foreman8760Inv#090 | [5 empty] | 1 | 760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7611 | 20210102-4 | 53510411 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader graded for 3 hours and then stopped to put chains on for the rest of the day Cole on plow truck in the morning and then Darrel took over working across access road entrances Jordan planning, coordinating and checking out sites for snow removal in WFs 2,3,4,5 | 4 | B194-B210 | Little Gravel River Rd | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting761120210102-4L.O.A.4840 | Corbiere and Sons Contracting761120210102-4L.O.A.4840Inv#090 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7611 | 20210102-4 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader graded for 3 hours and then stopped to put chains on for the rest of the day Cole on plow truck in the morning and then Darrel took over working across access road entrances Jordan planning, coordinating and checking out sites for snow removal in WFs 2,3,4,5 | 4 | B194-B210 | Little Gravel River Rd | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting761120210102-4Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting761120210102-4Operator - Principle - After Jan 103225Inv#090 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7611 | 20210102-4 | 53510411 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader graded for 3 hours and then stopped to put chains on for the rest of the day Cole on plow truck in the morning and then Darrel took over working across access road entrances Jordan planning, coordinating and checking out sites for snow removal in WFs 2,3,4,5 | 4 | B194-B210 | Little Gravel River Rd | 0 | 43833 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting761120210102-4Operator - Intermdiate - After Jan 1010700 | Corbiere and Sons Contracting761120210102-4Operator - Intermdiate - After Jan 1010700Inv#090 | [5 empty] | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7613 | 20210102-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading along Antler Lake access all day | 5 | C050-C069 | Antler Lake | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting761320210102-6Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting761320210102-6Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#090 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7613 | 20210102-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading along Antler Lake access all day | 5 | C050-C069 | Antler Lake | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting761320210102-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting761320210102-6Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7613 | 20210102-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading along Antler Lake access all day | 5 | C050-C069 | Antler Lake | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting761320210102-6L.O.A.1210 | Corbiere and Sons Contracting761320210102-6L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7613 | 20210102-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading along Antler Lake access all day | 5 | C050-C069 | Antler Lake | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting761320210102-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting761320210102-6Operator - Principle - After Jan 1011.5862.5Inv#090 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7614 | 20210102-7 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Pays Plat Dustin plowing entrance ways all afternoon | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting761420210102-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting761420210102-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#090 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7614 | 20210102-7 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Pays Plat Dustin plowing entrance ways all afternoon | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting761420210102-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting761420210102-7Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7614 | 20210102-7 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 8 | HR | 0 | 0 |  |  | 400 | 52 | 452 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Pays Plat Dustin plowing entrance ways all afternoon | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting761420210102-7Pickup w/ plow8400 | Corbiere and Sons Contracting761420210102-7Pickup w/ plow8400Inv#090 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7614 | 20210102-7 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Pays Plat Dustin plowing entrance ways all afternoon | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting761420210102-7L.O.A.2420 | Corbiere and Sons Contracting761420210102-7L.O.A.2420Inv#090 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7614 | 20210102-7 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Pays Plat Dustin plowing entrance ways all afternoon | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting761420210102-7Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting761420210102-7Operator - Principle - After Jan 1011.5862.5Inv#090 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7614 | 20210102-7 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-01-02 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Pays Plat Dustin plowing entrance ways all afternoon | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting761420210102-7Operator - Intermdiate - After Jan 108560 | Corbiere and Sons Contracting761420210102-7Operator - Intermdiate - After Jan 108560Inv#090 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7677 | 20210103-11 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-01-03 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | GR-02 opened up entrances and turn arounds Labourer escorted and followed grader down the highway and helped locate ditches for narrow entrances | 6 | C186-C195 | Del Lake | 0 | 44202 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting767720210103-11Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting767720210103-11Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#095 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7677 | 20210103-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-03 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | GR-02 opened up entrances and turn arounds Labourer escorted and followed grader down the highway and helped locate ditches for narrow entrances | 6 | C186-C195 | Del Lake | 0 | 44202 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting767720210103-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting767720210103-11Light Truck - Pick up- After Jan 102487.5Inv#095 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7677 | 20210103-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-03 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | GR-02 opened up entrances and turn arounds Labourer escorted and followed grader down the highway and helped locate ditches for narrow entrances | 6 | C186-C195 | Del Lake | 0 | 44202 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting767720210103-11L.O.A.1210 | Corbiere and Sons Contracting767720210103-11L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7677 | 20210103-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-03 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | GR-02 opened up entrances and turn arounds Labourer escorted and followed grader down the highway and helped locate ditches for narrow entrances | 6 | C186-C195 | Del Lake | 0 | 44202 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting767720210103-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting767720210103-11Operator - Principle - After Jan 1011825Inv#095 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7677 | 20210103-11 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-01-03 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | GR-02 opened up entrances and turn arounds Labourer escorted and followed grader down the highway and helped locate ditches for narrow entrances | 6 | C186-C195 | Del Lake | 0 | 44202 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting767720210103-11Labourer - General - After Jan 106360 | Corbiere and Sons Contracting767720210103-11Labourer - General - After Jan 106360Inv#095 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7620 | 20210103-5 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan grading Little Gravel River Rd from East, finished to KM4 and then went into the west side. Dustin plowing entrance ways | 4 | C011-C029 | Nishin Creek Road | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting762020210103-5Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting762020210103-5Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#090 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7620 | 20210103-5 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan grading Little Gravel River Rd from East, finished to KM4 and then went into the west side. Dustin plowing entrance ways | 4 | C011-C029 | Nishin Creek Road | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting762020210103-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting762020210103-5Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7620 | 20210103-5 | 53510411 | Access | 0 | Pickup w/ plow | 50 | 3 | HR | 0 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan grading Little Gravel River Rd from East, finished to KM4 and then went into the west side. Dustin plowing entrance ways | 4 | C011-C029 | Nishin Creek Road | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting762020210103-5Pickup w/ plow3150 | Corbiere and Sons Contracting762020210103-5Pickup w/ plow3150Inv#090 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7620 | 20210103-5 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan grading Little Gravel River Rd from East, finished to KM4 and then went into the west side. Dustin plowing entrance ways | 4 | C011-C029 | Nishin Creek Road | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting762020210103-5L.O.A.1210 | Corbiere and Sons Contracting762020210103-5L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7620 | 20210103-5 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14.5 | HR |  |  | 75 | 0 | 1087.5 | 141.375 | 1228.875 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan grading Little Gravel River Rd from East, finished to KM4 and then went into the west side. Dustin plowing entrance ways | 4 | C011-C029 | Nishin Creek Road | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting762020210103-5Operator - Principle - After Jan 1014.51087.5 | Corbiere and Sons Contracting762020210103-5Operator - Principle - After Jan 1014.51087.5Inv#090 | [5 empty] | 1 | 1087.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7621 | 20210103-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader finished up Pays Plat in the morning and then was floated to Nishin Road in the afternoon. Dustin coordinating and plowing entrance ways. | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762120210103-6Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting762120210103-6Grader - Cat 12 to 14 or equal- After Jan 107888.86Inv#090 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7621 | 20210103-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader finished up Pays Plat in the morning and then was floated to Nishin Road in the afternoon. Dustin coordinating and plowing entrance ways. | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762120210103-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting762120210103-6Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7621 | 20210103-6 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 3 | HR | 0 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader finished up Pays Plat in the morning and then was floated to Nishin Road in the afternoon. Dustin coordinating and plowing entrance ways. | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762120210103-6Pickup w/ plow3150 | Corbiere and Sons Contracting762120210103-6Pickup w/ plow3150Inv#090 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7621 | 20210103-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader finished up Pays Plat in the morning and then was floated to Nishin Road in the afternoon. Dustin coordinating and plowing entrance ways. | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762120210103-6L.O.A.1210 | Corbiere and Sons Contracting762120210103-6L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7621 | 20210103-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader finished up Pays Plat in the morning and then was floated to Nishin Road in the afternoon. Dustin coordinating and plowing entrance ways. | 5 | C031-C049 | Pays Plat River | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762120210103-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting762120210103-6Operator - Principle - After Jan 1011825Inv#090 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7623 | 20210103-8 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on grader working across Cooks Lake Rd all day Rob Couchie on dozer opening up road for snow maintenance and clearing all day Dustin coordinating and plowing entrance ways | 5 | C076-C116 | Cook Lake | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762320210103-8Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting762320210103-8Dozer D6 or equal- After Jan 1010.51380.54Inv#090 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7623 | 20210103-8 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on grader working across Cooks Lake Rd all day Rob Couchie on dozer opening up road for snow maintenance and clearing all day Dustin coordinating and plowing entrance ways | 5 | C076-C116 | Cook Lake | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762320210103-8Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting762320210103-8Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv#090 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7623 | 20210103-8 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on grader working across Cooks Lake Rd all day Rob Couchie on dozer opening up road for snow maintenance and clearing all day Dustin coordinating and plowing entrance ways | 5 | C076-C116 | Cook Lake | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762320210103-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting762320210103-8Light Truck - Pick up- After Jan 102487.5Inv#090 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7623 | 20210103-8 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 3 | HR | 0 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on grader working across Cooks Lake Rd all day Rob Couchie on dozer opening up road for snow maintenance and clearing all day Dustin coordinating and plowing entrance ways | 5 | C076-C116 | Cook Lake | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762320210103-8Pickup w/ plow3150 | Corbiere and Sons Contracting762320210103-8Pickup w/ plow3150Inv#090 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7623 | 20210103-8 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on grader working across Cooks Lake Rd all day Rob Couchie on dozer opening up road for snow maintenance and clearing all day Dustin coordinating and plowing entrance ways | 5 | C076-C116 | Cook Lake | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762320210103-8L.O.A.2420 | Corbiere and Sons Contracting762320210103-8L.O.A.2420Inv#090 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7623 | 20210103-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 26.5 | HR |  |  | 75 | 0 | 1987.5 | 258.375 | 2245.875 | 2021-01-03 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on grader working across Cooks Lake Rd all day Rob Couchie on dozer opening up road for snow maintenance and clearing all day Dustin coordinating and plowing entrance ways | 5 | C076-C116 | Cook Lake | 0 | 44199 |  | 37 | 44202 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting762320210103-8Operator - Principle - After Jan 1026.51987.5 | Corbiere and Sons Contracting762320210103-8Operator - Principle - After Jan 1026.51987.5Inv#090 | [5 empty] | 1 | 1987.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7695 | 20210104-12 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | GR-02 drove to Dead Horse Creek and graded access and turnaround as the float was having trouble turning around (too slippery) | 6 | C203-C209 | Dead Horse Creek | 0 | 44205 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting769520210104-12Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting769520210104-12Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#095 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7695 | 20210104-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | GR-02 drove to Dead Horse Creek and graded access and turnaround as the float was having trouble turning around (too slippery) | 6 | C203-C209 | Dead Horse Creek | 0 | 44205 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting769520210104-12Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting769520210104-12Operator - Principle - After Jan 103225Inv#095 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7908 | 20210104-15 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snowplowed HWY entrance up to float turnaround | 6 | C257-C267 | Hare Lake | 0 | 44215 |  | 36 | 44216 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting790820210104-15Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting790820210104-15Loader JD 524 to 624 or equal5495Inv#095 | [5 empty] | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7908 | 20210104-15 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snowplowed HWY entrance up to float turnaround | 6 | C257-C267 | Hare Lake | 0 | 44215 |  | 36 | 44216 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting790820210104-15L.O.A.1210 | Corbiere and Sons Contracting790820210104-15L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7908 | 20210104-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snowplowed HWY entrance up to float turnaround | 6 | C257-C267 | Hare Lake | 0 | 44215 |  | 36 | 44216 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting790820210104-15Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting790820210104-15Operator - Principle - After Jan 105375Inv#095 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7687 | 20210104-4 | 53510211 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized dozer to Landfill road; waited and then mobed it into Lofty Davies Stacey took over for Dustin on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd John took over for Dwayne W on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd Evan took over for Dwayne H running dozer across Landfill Rd all night clearing snow | 2 | B065-B077 | Red Rock | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting768720210104-4Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting768720210104-4Dozer D6 or equal- After Jan 10121577.76Inv#095 | [5 empty] | 1 | 1577.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7687 | 20210104-4 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized dozer to Landfill road; waited and then mobed it into Lofty Davies Stacey took over for Dustin on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd John took over for Dwayne W on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd Evan took over for Dwayne H running dozer across Landfill Rd all night clearing snow | 2 | B065-B077 | Red Rock | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting768720210104-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting768720210104-4Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7687 | 20210104-4 | 53510211 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized dozer to Landfill road; waited and then mobed it into Lofty Davies Stacey took over for Dustin on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd John took over for Dwayne W on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd Evan took over for Dwayne H running dozer across Landfill Rd all night clearing snow | 2 | B065-B077 | Red Rock | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting768720210104-4Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting768720210104-4Tractor Trailer - 60 Ton- After Jan 108979.12Inv#095 | [5 empty] | 1 | 979.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7687 | 20210104-4 | 53510211 | Access | 0 | Pickup w/ plow | 50 | 28 | HR | 0 | 0 |  |  | 1400 | 182 | 1582 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized dozer to Landfill road; waited and then mobed it into Lofty Davies Stacey took over for Dustin on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd John took over for Dwayne W on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd Evan took over for Dwayne H running dozer across Landfill Rd all night clearing snow | 2 | B065-B077 | Red Rock | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting768720210104-4Pickup w/ plow281400 | Corbiere and Sons Contracting768720210104-4Pickup w/ plow281400Inv#095 | [5 empty] | 1 | 1400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7687 | 20210104-4 | 53510211 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized dozer to Landfill road; waited and then mobed it into Lofty Davies Stacey took over for Dustin on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd John took over for Dwayne W on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd Evan took over for Dwayne H running dozer across Landfill Rd all night clearing snow | 2 | B065-B077 | Red Rock | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting768720210104-4L.O.A.4840 | Corbiere and Sons Contracting768720210104-4L.O.A.4840Inv#095 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7687 | 20210104-4 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized dozer to Landfill road; waited and then mobed it into Lofty Davies Stacey took over for Dustin on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd John took over for Dwayne W on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd Evan took over for Dwayne H running dozer across Landfill Rd all night clearing snow | 2 | B065-B077 | Red Rock | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting768720210104-4Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting768720210104-4Operator - Principle - After Jan 10211575Inv#095 | [5 empty] | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7687 | 20210104-4 | 53510211 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 25 | HR |  |  | 70 | 0 | 1750 | 227.5 | 1977.5 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized dozer to Landfill road; waited and then mobed it into Lofty Davies Stacey took over for Dustin on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd John took over for Dwayne W on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd Evan took over for Dwayne H running dozer across Landfill Rd all night clearing snow | 2 | B065-B077 | Red Rock | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting768720210104-4Operator - Intermdiate - After Jan 10251750 | Corbiere and Sons Contracting768720210104-4Operator - Intermdiate - After Jan 10251750Inv#095 | [5 empty] | 1 | 1750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7687 | 20210104-4 | 53510211 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized dozer to Landfill road; waited and then mobed it into Lofty Davies Stacey took over for Dustin on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd John took over for Dwayne W on pickup w/plow working nightshift clearing Lofty Davies and Landfill Rd Evan took over for Dwayne H running dozer across Landfill Rd all night clearing snow | 2 | B065-B077 | Red Rock | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting768720210104-4Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting768720210104-4Driver - AZ - After Jan 108560Inv#095 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7688 | 20210104-5 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float loaded dozer and brought to Camp Rd 81 - 2 flaggers (Blade & Dawson) needed; (Dwayne H, Dwayne W, Dustin) plowing got done, dozer loaded back up and brought to Landfill Rd. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768820210104-5Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting768820210104-5Dozer D6 or equal- After Jan 104525.92Inv#095 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7688 | 20210104-5 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float loaded dozer and brought to Camp Rd 81 - 2 flaggers (Blade & Dawson) needed; (Dwayne H, Dwayne W, Dustin) plowing got done, dozer loaded back up and brought to Landfill Rd. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768820210104-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting768820210104-5Light Truck - Pick up- After Jan 102487.5Inv#095 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7688 | 20210104-5 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 7 | Dynamic | 91.79 | 0 |  |  | 856.73 | 111.3749 | 968.1049 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float loaded dozer and brought to Camp Rd 81 - 2 flaggers (Blade & Dawson) needed; (Dwayne H, Dwayne W, Dustin) plowing got done, dozer loaded back up and brought to Landfill Rd. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768820210104-5Tractor Trailer - 60 Ton- After Jan 107856.73 | Corbiere and Sons Contracting768820210104-5Tractor Trailer - 60 Ton- After Jan 107856.73Inv#095 | [5 empty] | 1 | 856.73 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7688 | 20210104-5 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 9 | HR | 0 | 0 |  |  | 450 | 58.5 | 508.5 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float loaded dozer and brought to Camp Rd 81 - 2 flaggers (Blade & Dawson) needed; (Dwayne H, Dwayne W, Dustin) plowing got done, dozer loaded back up and brought to Landfill Rd. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768820210104-5Pickup w/ plow9450 | Corbiere and Sons Contracting768820210104-5Pickup w/ plow9450Inv#095 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7688 | 20210104-5 | 53510311 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float loaded dozer and brought to Camp Rd 81 - 2 flaggers (Blade & Dawson) needed; (Dwayne H, Dwayne W, Dustin) plowing got done, dozer loaded back up and brought to Landfill Rd. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768820210104-5L.O.A.61260 | Corbiere and Sons Contracting768820210104-5L.O.A.61260Inv#095 | [5 empty] | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7688 | 20210104-5 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float loaded dozer and brought to Camp Rd 81 - 2 flaggers (Blade & Dawson) needed; (Dwayne H, Dwayne W, Dustin) plowing got done, dozer loaded back up and brought to Landfill Rd. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768820210104-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting768820210104-5Operator - Principle - After Jan 1012900Inv#095 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7688 | 20210104-5 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float loaded dozer and brought to Camp Rd 81 - 2 flaggers (Blade & Dawson) needed; (Dwayne H, Dwayne W, Dustin) plowing got done, dozer loaded back up and brought to Landfill Rd. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768820210104-5Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting768820210104-5Operator - Intermdiate - After Jan 106420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7688 | 20210104-5 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float loaded dozer and brought to Camp Rd 81 - 2 flaggers (Blade & Dawson) needed; (Dwayne H, Dwayne W, Dustin) plowing got done, dozer loaded back up and brought to Landfill Rd. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768820210104-5Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting768820210104-5Driver - AZ - After Jan 107490Inv#095 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7688 | 20210104-5 | 53510311 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float loaded dozer and brought to Camp Rd 81 - 2 flaggers (Blade & Dawson) needed; (Dwayne H, Dwayne W, Dustin) plowing got done, dozer loaded back up and brought to Landfill Rd. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768820210104-5Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting768820210104-5Labourer - General - After Jan 1012720Inv#095 | [5 empty] | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7689 | 20210104-6 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working grader on night shift across Golf Course and Maata's | 3 | B088-B099 | Maata's Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768920210104-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting768920210104-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#095 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7689 | 20210104-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working grader on night shift across Golf Course and Maata's | 3 | B088-B099 | Maata's Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768920210104-6L.O.A.1210 | Corbiere and Sons Contracting768920210104-6L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7689 | 20210104-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working grader on night shift across Golf Course and Maata's | 3 | B088-B099 | Maata's Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting768920210104-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting768920210104-6Operator - Principle - After Jan 1011825Inv#095 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7690 | 20210104-7 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11.5 | Dynamic | 95.24 | 0 |  |  | 1460.27 | 189.8351 | 1650.1051 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all day from C-012 - C-025 Grader demobbed at the end of the day and moved into WF3. | 4 | C011-C029 | Nishin Creek Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting769020210104-7Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27 | Corbiere and Sons Contracting769020210104-7Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27Inv#095 | [5 empty] | 1 | 1460.27 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7690 | 20210104-7 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all day from C-012 - C-025 Grader demobbed at the end of the day and moved into WF3. | 4 | C011-C029 | Nishin Creek Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting769020210104-7Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting769020210104-7Tractor Trailer - 60 Ton- After Jan 104489.56Inv#095 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7690 | 20210104-7 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all day from C-012 - C-025 Grader demobbed at the end of the day and moved into WF3. | 4 | C011-C029 | Nishin Creek Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting769020210104-7L.O.A.1210 | Corbiere and Sons Contracting769020210104-7L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7690 | 20210104-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12.5 | HR |  |  | 75 | 0 | 937.5 | 121.875 | 1059.375 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all day from C-012 - C-025 Grader demobbed at the end of the day and moved into WF3. | 4 | C011-C029 | Nishin Creek Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting769020210104-7Operator - Principle - After Jan 1012.5937.5 | Corbiere and Sons Contracting769020210104-7Operator - Principle - After Jan 1012.5937.5Inv#095 | [5 empty] | 1 | 937.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7690 | 20210104-7 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all day from C-012 - C-025 Grader demobbed at the end of the day and moved into WF3. | 4 | C011-C029 | Nishin Creek Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting769020210104-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting769020210104-7Driver - AZ - After Jan 104280Inv#095 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7692 | 20210104-9 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from laydown and towards C-076 Cooks Lake Rd W Grader working across access roads clearing snow Dustin coordianting and working on plow truck Darrel went to Dorion and mobilized sand truck to Terrace Bay | 5 | C076-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting769220210104-9Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting769220210104-9Dozer D6 or equal- After Jan 10111446.28Inv#095 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7692 | 20210104-9 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from laydown and towards C-076 Cooks Lake Rd W Grader working across access roads clearing snow Dustin coordianting and working on plow truck Darrel went to Dorion and mobilized sand truck to Terrace Bay | 5 | C076-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting769220210104-9Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting769220210104-9Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#095 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7692 | 20210104-9 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 6 | Dynamic | 41.25 | 0 |  |  | 330 | 42.9 | 372.9 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from laydown and towards C-076 Cooks Lake Rd W Grader working across access roads clearing snow Dustin coordianting and working on plow truck Darrel went to Dorion and mobilized sand truck to Terrace Bay | 5 | C076-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting769220210104-9Sander Truck - Hwy- After Jan 106330 | Corbiere and Sons Contracting769220210104-9Sander Truck - Hwy- After Jan 106330Inv#095 | [5 empty] | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7692 | 20210104-9 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from laydown and towards C-076 Cooks Lake Rd W Grader working across access roads clearing snow Dustin coordianting and working on plow truck Darrel went to Dorion and mobilized sand truck to Terrace Bay | 5 | C076-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting769220210104-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting769220210104-9Light Truck - Pick up- After Jan 102487.5Inv#095 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7692 | 20210104-9 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 3 | HR | 0 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from laydown and towards C-076 Cooks Lake Rd W Grader working across access roads clearing snow Dustin coordianting and working on plow truck Darrel went to Dorion and mobilized sand truck to Terrace Bay | 5 | C076-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting769220210104-9Pickup w/ plow3150 | Corbiere and Sons Contracting769220210104-9Pickup w/ plow3150Inv#095 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7692 | 20210104-9 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from laydown and towards C-076 Cooks Lake Rd W Grader working across access roads clearing snow Dustin coordianting and working on plow truck Darrel went to Dorion and mobilized sand truck to Terrace Bay | 5 | C076-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting769220210104-9L.O.A.3630 | Corbiere and Sons Contracting769220210104-9L.O.A.3630Inv#095 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7692 | 20210104-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from laydown and towards C-076 Cooks Lake Rd W Grader working across access roads clearing snow Dustin coordianting and working on plow truck Darrel went to Dorion and mobilized sand truck to Terrace Bay | 5 | C076-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting769220210104-9Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting769220210104-9Operator - Principle - After Jan 10241800Inv#095 | [5 empty] | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7692 | 20210104-9 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-04 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from laydown and towards C-076 Cooks Lake Rd W Grader working across access roads clearing snow Dustin coordianting and working on plow truck Darrel went to Dorion and mobilized sand truck to Terrace Bay | 5 | C076-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting769220210104-9Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting769220210104-9Driver - AZ - After Jan 106420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7705 | 20210105-10 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader to Gravel River Road at the end of the day | 4 | B211-C010 | Gravel River Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting770520210105-10Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting770520210105-10Tractor Trailer - 60 Ton- After Jan 103367.17Inv#095 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7705 | 20210105-10 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader to Gravel River Road at the end of the day | 4 | B211-C010 | Gravel River Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting770520210105-10Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting770520210105-10Driver - AZ - After Jan 103210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7706 | 20210105-11 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 7 |  | 0 | 0 |  |  | 560 | 72.8 | 632.8 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow Truck w/sander working at Camp 81 from 7am-2pm. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770620210105-11Pickup w/ plow and sander7560 | Corbiere and Sons Contracting770620210105-11Pickup w/ plow and sander7560Inv#095 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7706 | 20210105-11 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow Truck w/sander working at Camp 81 from 7am-2pm. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770620210105-11L.O.A.1210 | Corbiere and Sons Contracting770620210105-11L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7706 | 20210105-11 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow Truck w/sander working at Camp 81 from 7am-2pm. | 3 | B145-B149 | Camp Road 81 | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770620210105-11Operator - Intermdiate - After Jan 107490 | Corbiere and Sons Contracting770620210105-11Operator - Intermdiate - After Jan 107490Inv#095 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7710 | 20210105-15 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal from Cooks Lake Rd E all day - Spent 9 hours on the dozer and 3 hours on the grader. | 5 | C093-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting771020210105-15Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting771020210105-15Dozer D6 or equal- After Jan 1091183.32Inv#095 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7710 | 20210105-15 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal from Cooks Lake Rd E all day - Spent 9 hours on the dozer and 3 hours on the grader. | 5 | C093-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting771020210105-15Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting771020210105-15Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#095 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7710 | 20210105-15 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal from Cooks Lake Rd E all day - Spent 9 hours on the dozer and 3 hours on the grader. | 5 | C093-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting771020210105-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting771020210105-15Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7710 | 20210105-15 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal from Cooks Lake Rd E all day - Spent 9 hours on the dozer and 3 hours on the grader. | 5 | C093-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting771020210105-15L.O.A.1210 | Corbiere and Sons Contracting771020210105-15L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7710 | 20210105-15 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal from Cooks Lake Rd E all day - Spent 9 hours on the dozer and 3 hours on the grader. | 5 | C093-C116 | Cook Lake | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting771020210105-15Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting771020210105-15Operator - Principle - After Jan 1013975Inv#095 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7712 | 20210105-17 | 53510211 | Access | 0 | Loader JD 744 to 844 or equal | 162 | 9 | HR | 121.5 | 0 |  |  | 1458 | 189.54 | 1647.54 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader drove from North Shore yard to Lofty Davies Road and started opening to B-063, then directed to go to Golf Course Road and opened up B-085-B-087 then drove back to Lofty Davies Rd. Labourer escorted loader on the highway, helped install chains. | 2 | B054 - B064 | Lofty Davies | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting771220210105-17Loader JD 744 to 844 or equal91458 | Corbiere and Sons Contracting771220210105-17Loader JD 744 to 844 or equal91458Inv#095 | [5 empty] | 1 | 1458 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7712 | 20210105-17 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader drove from North Shore yard to Lofty Davies Road and started opening to B-063, then directed to go to Golf Course Road and opened up B-085-B-087 then drove back to Lofty Davies Rd. Labourer escorted loader on the highway, helped install chains. | 2 | B054 - B064 | Lofty Davies | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting771220210105-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting771220210105-17Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7712 | 20210105-17 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader drove from North Shore yard to Lofty Davies Road and started opening to B-063, then directed to go to Golf Course Road and opened up B-085-B-087 then drove back to Lofty Davies Rd. Labourer escorted loader on the highway, helped install chains. | 2 | B054 - B064 | Lofty Davies | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting771220210105-17Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting771220210105-17Operator - Principle - After Jan 1011825Inv#095 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7712 | 20210105-17 | 53510211 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader drove from North Shore yard to Lofty Davies Road and started opening to B-063, then directed to go to Golf Course Road and opened up B-085-B-087 then drove back to Lofty Davies Rd. Labourer escorted loader on the highway, helped install chains. | 2 | B054 - B064 | Lofty Davies | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting771220210105-17Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting771220210105-17Labourer - General - After Jan 1011660Inv#095 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7930 | 20210105-23 | 53510411 | Access | 0 | 3rd Party Charges | 1 | 967.28 | unit |  |  |  |  | 967.28 | 125.7464 | 1093.0264 | 2021-01-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (4) Loads of Sand for Winter Access Maintenance - Split 50/50 WF4 and WF5 | 4 | B194-B210 | Little Gravel River Rd | 0 | 44217 |  | 36 | 44217 | 202021290 | 4 Loads of Sand for Sanding Roads - Split 50 WF4/50 WF5 |  |  |  | Mike Lecocq | 04 | Corbiere and Sons Contracting793020210105-233rd Party Charges967.28967.28 | Corbiere and Sons Contracting793020210105-233rd Party Charges967.28967.28Inv#109 | [5 empty] | 1 | 967.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7931 | 20210105-24 | 53510511 | Access | 0 | 3rd Party Charges | 1 | 967.28 | unit |  |  |  |  | 967.28 | 125.7464 | 1093.0264 | 2021-01-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (4) Loads of Sand for Winter Access Maintenance - Split 50/50 WF4 and WF5 | 5 | C031-C049 | Pays Plat River | 0 | 44217 |  | 36 | 44217 | 202021290 | 4 Loads of Sand for Sanding Roads - Split 50 WF4/50 WF5 |  |  |  | Mike Lecocq | 05 | Corbiere and Sons Contracting793120210105-243rd Party Charges967.28967.28 | Corbiere and Sons Contracting793120210105-243rd Party Charges967.28967.28Inv#109 | [5 empty] | 1 | 967.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7699 | 20210105-4 | 53510211 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin working plow truck across Lofty Davies all morning. | 2 | B054 - B064 | Lofty Davies | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting769920210105-4Pickup w/ plow4200 | Corbiere and Sons Contracting769920210105-4Pickup w/ plow4200Inv#095 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7699 | 20210105-4 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin working plow truck across Lofty Davies all morning. | 2 | B054 - B064 | Lofty Davies | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting769920210105-4Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting769920210105-4Operator - Principle - After Jan 104300Inv#095 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7700 | 20210105-5 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6T into Jackpine River Road for snow removal; Labourers set up traffic control for unloading dozer Cole came in for night shift to run dozer clearing snow until 5am (machine down 1 hr) | 3 | B159-B160 | Jackpine River Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770020210105-5Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting770020210105-5Dozer D6 or equal- After Jan 1091183.32Inv#095 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7700 | 20210105-5 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6T into Jackpine River Road for snow removal; Labourers set up traffic control for unloading dozer Cole came in for night shift to run dozer clearing snow until 5am (machine down 1 hr) | 3 | B159-B160 | Jackpine River Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770020210105-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting770020210105-5Light Truck - Pick up- After Jan 102487.5Inv#095 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7700 | 20210105-5 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6T into Jackpine River Road for snow removal; Labourers set up traffic control for unloading dozer Cole came in for night shift to run dozer clearing snow until 5am (machine down 1 hr) | 3 | B159-B160 | Jackpine River Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770020210105-5Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting770020210105-5Tractor Trailer - 60 Ton- After Jan 105611.95Inv#095 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7700 | 20210105-5 | 53510311 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6T into Jackpine River Road for snow removal; Labourers set up traffic control for unloading dozer Cole came in for night shift to run dozer clearing snow until 5am (machine down 1 hr) | 3 | B159-B160 | Jackpine River Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770020210105-5L.O.A.4840 | Corbiere and Sons Contracting770020210105-5L.O.A.4840Inv#095 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7700 | 20210105-5 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6T into Jackpine River Road for snow removal; Labourers set up traffic control for unloading dozer Cole came in for night shift to run dozer clearing snow until 5am (machine down 1 hr) | 3 | B159-B160 | Jackpine River Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770020210105-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting770020210105-5Operator - Principle - After Jan 1011825Inv#095 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7700 | 20210105-5 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6T into Jackpine River Road for snow removal; Labourers set up traffic control for unloading dozer Cole came in for night shift to run dozer clearing snow until 5am (machine down 1 hr) | 3 | B159-B160 | Jackpine River Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770020210105-5Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting770020210105-5Driver - AZ - After Jan 105350Inv#095 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7700 | 20210105-5 | 53510311 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6T into Jackpine River Road for snow removal; Labourers set up traffic control for unloading dozer Cole came in for night shift to run dozer clearing snow until 5am (machine down 1 hr) | 3 | B159-B160 | Jackpine River Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770020210105-5Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting770020210105-5Labourer - General - After Jan 1010600Inv#095 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7701 | 20210105-6 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Maata's to Doghead, Grader graded at Doghead | 3 | B100-B109 | Doghead Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770120210105-6Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting770120210105-6Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#095 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7701 | 20210105-6 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Maata's to Doghead, Grader graded at Doghead | 3 | B100-B109 | Doghead Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770120210105-6Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting770120210105-6Tractor Trailer - 60 Ton- After Jan 103367.17Inv#095 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7701 | 20210105-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Maata's to Doghead, Grader graded at Doghead | 3 | B100-B109 | Doghead Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770120210105-6L.O.A.1210 | Corbiere and Sons Contracting770120210105-6L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7701 | 20210105-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Maata's to Doghead, Grader graded at Doghead | 3 | B100-B109 | Doghead Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770120210105-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting770120210105-6Operator - Principle - After Jan 105375Inv#095 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7701 | 20210105-6 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Maata's to Doghead, Grader graded at Doghead | 3 | B100-B109 | Doghead Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770120210105-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting770120210105-6Driver - AZ - After Jan 103210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7702 | 20210105-7 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len started day grading from Golf Course Rd Dustin on plowtruck working across Golf Course road in late morning | 3 | B085-B087 | Golf Course Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770220210105-7Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting770220210105-7Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#095 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7702 | 20210105-7 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len started day grading from Golf Course Rd Dustin on plowtruck working across Golf Course road in late morning | 3 | B085-B087 | Golf Course Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770220210105-7Pickup w/ plow4200 | Corbiere and Sons Contracting770220210105-7Pickup w/ plow4200Inv#095 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7702 | 20210105-7 | 53510311 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len started day grading from Golf Course Rd Dustin on plowtruck working across Golf Course road in late morning | 3 | B085-B087 | Golf Course Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770220210105-7L.O.A.2420 | Corbiere and Sons Contracting770220210105-7L.O.A.2420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7702 | 20210105-7 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len started day grading from Golf Course Rd Dustin on plowtruck working across Golf Course road in late morning | 3 | B085-B087 | Golf Course Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770220210105-7Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting770220210105-7Operator - Principle - After Jan 107525Inv#095 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7702 | 20210105-7 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len started day grading from Golf Course Rd Dustin on plowtruck working across Golf Course road in late morning | 3 | B085-B087 | Golf Course Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770220210105-7Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting770220210105-7Operator - Intermdiate - After Jan 104280Inv#095 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7703 | 20210105-8 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's Rd from 6am-4pm | 3 | B088-B099 | Maata's Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770320210105-8Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting770320210105-8Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#095 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7703 | 20210105-8 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's Rd from 6am-4pm | 3 | B088-B099 | Maata's Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770320210105-8L.O.A.1210 | Corbiere and Sons Contracting770320210105-8L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7703 | 20210105-8 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's Rd from 6am-4pm | 3 | B088-B099 | Maata's Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770320210105-8Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting770320210105-8Operator - Principle - After Jan 1010750Inv#095 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7704 | 20210105-9 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 1 | Dynamic | 95.24 | 0 |  |  | 126.98 | 16.5074 | 143.4874 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Landfill to Fire Hill Grader floated to Fire Hill road and did 1 pass to B-136 Stacey on plow truck w/sander working from 2pm-6pm Dustin on plow truck working on Firehill in afternoon | 3 | B135-B144 | Fire Hill Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770420210105-9Grader - Cat 12 to 14 or equal- After Jan 101126.98 | Corbiere and Sons Contracting770420210105-9Grader - Cat 12 to 14 or equal- After Jan 101126.98Inv#095 | [5 empty] | 1 | 126.98 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7704 | 20210105-9 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Landfill to Fire Hill Grader floated to Fire Hill road and did 1 pass to B-136 Stacey on plow truck w/sander working from 2pm-6pm Dustin on plow truck working on Firehill in afternoon | 3 | B135-B144 | Fire Hill Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770420210105-9Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting770420210105-9Tractor Trailer - 60 Ton- After Jan 103367.17Inv#095 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7704 | 20210105-9 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Landfill to Fire Hill Grader floated to Fire Hill road and did 1 pass to B-136 Stacey on plow truck w/sander working from 2pm-6pm Dustin on plow truck working on Firehill in afternoon | 3 | B135-B144 | Fire Hill Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770420210105-9Pickup w/ plow4200 | Corbiere and Sons Contracting770420210105-9Pickup w/ plow4200Inv#095 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7704 | 20210105-9 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Landfill to Fire Hill Grader floated to Fire Hill road and did 1 pass to B-136 Stacey on plow truck w/sander working from 2pm-6pm Dustin on plow truck working on Firehill in afternoon | 3 | B135-B144 | Fire Hill Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770420210105-9Pickup w/ plow and sander4320 | Corbiere and Sons Contracting770420210105-9Pickup w/ plow and sander4320Inv#095 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7704 | 20210105-9 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Landfill to Fire Hill Grader floated to Fire Hill road and did 1 pass to B-136 Stacey on plow truck w/sander working from 2pm-6pm Dustin on plow truck working on Firehill in afternoon | 3 | B135-B144 | Fire Hill Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770420210105-9Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting770420210105-9Operator - Principle - After Jan 102150Inv#095 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7704 | 20210105-9 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Landfill to Fire Hill Grader floated to Fire Hill road and did 1 pass to B-136 Stacey on plow truck w/sander working from 2pm-6pm Dustin on plow truck working on Firehill in afternoon | 3 | B135-B144 | Fire Hill Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770420210105-9Operator - Intermdiate - After Jan 108560 | Corbiere and Sons Contracting770420210105-9Operator - Intermdiate - After Jan 108560Inv#095 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7704 | 20210105-9 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-05 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Landfill to Fire Hill Grader floated to Fire Hill road and did 1 pass to B-136 Stacey on plow truck w/sander working from 2pm-6pm Dustin on plow truck working on Firehill in afternoon | 3 | B135-B144 | Fire Hill Road | 0 | 44205 |  | 36 | 44206 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting770420210105-9Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting770420210105-9Driver - AZ - After Jan 103210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7732 | 20210106-10 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2.5 | Dynamic | 91.79 | 0 |  |  | 305.975 | 39.7767 | 345.7518 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6T back to Cooks from Cavers once snow removal was completed. | 5 | C076-C116 | Cook Lake | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting773220210106-10Tractor Trailer - 60 Ton- After Jan 102.5305.975 | Corbiere and Sons Contracting773220210106-10Tractor Trailer - 60 Ton- After Jan 102.5305.975Inv#095 | [5 empty] | 1 | 305.975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7732 | 20210106-10 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6T back to Cooks from Cavers once snow removal was completed. | 5 | C076-C116 | Cook Lake | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting773220210106-10Driver - AZ - After Jan 102.5175 | Corbiere and Sons Contracting773220210106-10Driver - AZ - After Jan 102.5175Inv#095 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7726 | 20210106-4 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cooks to Gurney in the morning, Grader clearing snow from B-187 - B-193. | 3 | B187-B193 | Cook-Gurney | 0 | 44206 |  | 37 | 44210 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting772620210106-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting772620210106-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#095 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7726 | 20210106-4 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cooks to Gurney in the morning, Grader clearing snow from B-187 - B-193. | 3 | B187-B193 | Cook-Gurney | 0 | 44206 |  | 37 | 44210 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting772620210106-4Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting772620210106-4Tractor Trailer - 60 Ton- After Jan 103367.17Inv#095 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7726 | 20210106-4 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cooks to Gurney in the morning, Grader clearing snow from B-187 - B-193. | 3 | B187-B193 | Cook-Gurney | 0 | 44206 |  | 37 | 44210 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting772620210106-4L.O.A.1210 | Corbiere and Sons Contracting772620210106-4L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7726 | 20210106-4 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cooks to Gurney in the morning, Grader clearing snow from B-187 - B-193. | 3 | B187-B193 | Cook-Gurney | 0 | 44206 |  | 37 | 44210 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting772620210106-4Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting772620210106-4Operator - Principle - After Jan 1013975Inv#095 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7726 | 20210106-4 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cooks to Gurney in the morning, Grader clearing snow from B-187 - B-193. | 3 | B187-B193 | Cook-Gurney | 0 | 44206 |  | 37 | 44210 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting772620210106-4Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting772620210106-4Driver - AZ - After Jan 103210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7727 | 20210106-5 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len was floated to Maata's and began widening from B-094 - B-099 | 3 | B092-B099 | Maata's Road | 0 | 44206 |  | 37 | 44210 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting772720210106-5Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting772720210106-5Grader - Cat 12 to 14 or equal- After Jan 102253.96Inv#095 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7727 | 20210106-5 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len was floated to Maata's and began widening from B-094 - B-099 | 3 | B092-B099 | Maata's Road | 0 | 44206 |  | 37 | 44210 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting772720210106-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting772720210106-5Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7727 | 20210106-5 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len was floated to Maata's and began widening from B-094 - B-099 | 3 | B092-B099 | Maata's Road | 0 | 44206 |  | 37 | 44210 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting772720210106-5Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting772720210106-5Operator - Principle - After Jan 102150Inv#095 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7728 | 20210106-6 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers doing traffic control for float moving D6 out of Jackpine. | 3 | B159-B160 | Jackpine | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting772820210106-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting772820210106-6Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7728 | 20210106-6 | 53510311 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers doing traffic control for float moving D6 out of Jackpine. | 3 | B159-B160 | Jackpine | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting772820210106-6Labourer - General - After Jan 106360 | Corbiere and Sons Contracting772820210106-6Labourer - General - After Jan 106360Inv#095 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7729 | 20210106-7 | 53510411 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4.5 | Dynamic | 98.61 | 0 |  |  | 591.66 | 76.9158 | 668.5758 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Jackpine to Cavers Dozer clearing snow from C-028 - C-029 | 4 | C028-C029 | Cavers Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting772920210106-7Dozer D6 or equal- After Jan 104.5591.66 | Corbiere and Sons Contracting772920210106-7Dozer D6 or equal- After Jan 104.5591.66Inv#095 | [5 empty] | 1 | 591.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7729 | 20210106-7 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Jackpine to Cavers Dozer clearing snow from C-028 - C-029 | 4 | C028-C029 | Cavers Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting772920210106-7Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting772920210106-7Tractor Trailer - 60 Ton- After Jan 102244.78Inv#095 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7729 | 20210106-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Jackpine to Cavers Dozer clearing snow from C-028 - C-029 | 4 | C028-C029 | Cavers Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting772920210106-7Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting772920210106-7Operator - Principle - After Jan 106.5487.5Inv#095 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7729 | 20210106-7 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Jackpine to Cavers Dozer clearing snow from C-028 - C-029 | 4 | C028-C029 | Cavers Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting772920210106-7Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting772920210106-7Driver - AZ - After Jan 102140Inv#095 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7730 | 20210106-8 | 53510411 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6K from Firehill Road to Nishin - Dozer working part of day clearing snow from C-025 - C-027Grader finished up Gravel River Rd (1pm) - Float moved grader from Gravel River Rd to Maata's RdStacey running plow truck w/sander all day across access raodsDustin running plow truck all day | 4 | C011-C029 | Nishin Creek Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting773020210106-8Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting773020210106-8Dozer D6 or equal- After Jan 104525.92Inv#095 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7730 | 20210106-8 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6.5 | Dynamic | 95.24 | 0 |  |  | 825.37 | 107.2981 | 932.6681 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6K from Firehill Road to Nishin - Dozer working part of day clearing snow from C-025 - C-027Grader finished up Gravel River Rd (1pm) - Float moved grader from Gravel River Rd to Maata's RdStacey running plow truck w/sander all day across access raodsDustin running plow truck all day | 4 | C011-C029 | Nishin Creek Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting773020210106-8Grader - Cat 12 to 14 or equal- After Jan 106.5825.37 | Corbiere and Sons Contracting773020210106-8Grader - Cat 12 to 14 or equal- After Jan 106.5825.37Inv#095 | [5 empty] | 1 | 825.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7730 | 20210106-8 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6K from Firehill Road to Nishin - Dozer working part of day clearing snow from C-025 - C-027Grader finished up Gravel River Rd (1pm) - Float moved grader from Gravel River Rd to Maata's RdStacey running plow truck w/sander all day across access raodsDustin running plow truck all day | 4 | C011-C029 | Nishin Creek Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting773020210106-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting773020210106-8Light Truck - Pick up- After Jan 102487.5Inv#095 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7730 | 20210106-8 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 91.79 | 0 |  |  | 673.145 | 87.5088 | 760.6539 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6K from Firehill Road to Nishin - Dozer working part of day clearing snow from C-025 - C-027Grader finished up Gravel River Rd (1pm) - Float moved grader from Gravel River Rd to Maata's RdStacey running plow truck w/sander all day across access raodsDustin running plow truck all day | 4 | C011-C029 | Nishin Creek Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting773020210106-8Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting773020210106-8Tractor Trailer - 60 Ton- After Jan 105.5673.145Inv#095 | [5 empty] | 1 | 673.145 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7730 | 20210106-8 | 53510411 | Access | 0 | Pickup w/ plow | 50 | 10 | HR | 0 | 0 |  |  | 500 | 65 | 565 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6K from Firehill Road to Nishin - Dozer working part of day clearing snow from C-025 - C-027Grader finished up Gravel River Rd (1pm) - Float moved grader from Gravel River Rd to Maata's RdStacey running plow truck w/sander all day across access raodsDustin running plow truck all day | 4 | C011-C029 | Nishin Creek Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting773020210106-8Pickup w/ plow10500 | Corbiere and Sons Contracting773020210106-8Pickup w/ plow10500Inv#095 | [5 empty] | 1 | 500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7730 | 20210106-8 | 53510411 | Access | 0 | Pickup w/ plow and sander | 80 | 13 |  | 0 | 0 |  |  | 1040 | 135.2 | 1175.2 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6K from Firehill Road to Nishin - Dozer working part of day clearing snow from C-025 - C-027Grader finished up Gravel River Rd (1pm) - Float moved grader from Gravel River Rd to Maata's RdStacey running plow truck w/sander all day across access raodsDustin running plow truck all day | 4 | C011-C029 | Nishin Creek Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting773020210106-8Pickup w/ plow and sander131040 | Corbiere and Sons Contracting773020210106-8Pickup w/ plow and sander131040Inv#095 | [5 empty] | 1 | 1040 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7730 | 20210106-8 | 53510411 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6K from Firehill Road to Nishin - Dozer working part of day clearing snow from C-025 - C-027Grader finished up Gravel River Rd (1pm) - Float moved grader from Gravel River Rd to Maata's RdStacey running plow truck w/sander all day across access raodsDustin running plow truck all day | 4 | C011-C029 | Nishin Creek Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting773020210106-8L.O.A.51050 | Corbiere and Sons Contracting773020210106-8L.O.A.51050Inv#095 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7730 | 20210106-8 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 28.5 | HR |  |  | 75 | 0 | 2137.5 | 277.875 | 2415.375 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6K from Firehill Road to Nishin - Dozer working part of day clearing snow from C-025 - C-027Grader finished up Gravel River Rd (1pm) - Float moved grader from Gravel River Rd to Maata's RdStacey running plow truck w/sander all day across access raodsDustin running plow truck all day | 4 | C011-C029 | Nishin Creek Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting773020210106-8Operator - Principle - After Jan 1028.52137.5 | Corbiere and Sons Contracting773020210106-8Operator - Principle - After Jan 1028.52137.5Inv#095 | [5 empty] | 1 | 2137.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7730 | 20210106-8 | 53510411 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6K from Firehill Road to Nishin - Dozer working part of day clearing snow from C-025 - C-027Grader finished up Gravel River Rd (1pm) - Float moved grader from Gravel River Rd to Maata's RdStacey running plow truck w/sander all day across access raodsDustin running plow truck all day | 4 | C011-C029 | Nishin Creek Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting773020210106-8Operator - Intermdiate - After Jan 1013910 | Corbiere and Sons Contracting773020210106-8Operator - Intermdiate - After Jan 1013910Inv#095 | [5 empty] | 1 | 910 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7730 | 20210106-8 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6K from Firehill Road to Nishin - Dozer working part of day clearing snow from C-025 - C-027Grader finished up Gravel River Rd (1pm) - Float moved grader from Gravel River Rd to Maata's RdStacey running plow truck w/sander all day across access raodsDustin running plow truck all day | 4 | C011-C029 | Nishin Creek Road | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting773020210106-8Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting773020210106-8Driver - AZ - After Jan 105.5385Inv#095 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7731 | 20210106-9 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Pays Plat to AntlerEvan graded from 2pm-11pm | 5 | C050-C069 | Antler Lake | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting773120210106-9Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting773120210106-9Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#095 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7731 | 20210106-9 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Pays Plat to AntlerEvan graded from 2pm-11pm | 5 | C050-C069 | Antler Lake | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting773120210106-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting773120210106-9Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7731 | 20210106-9 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Pays Plat to AntlerEvan graded from 2pm-11pm | 5 | C050-C069 | Antler Lake | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting773120210106-9Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting773120210106-9Tractor Trailer - 60 Ton- After Jan 102244.78Inv#095 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7731 | 20210106-9 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Pays Plat to AntlerEvan graded from 2pm-11pm | 5 | C050-C069 | Antler Lake | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting773120210106-9L.O.A.1210 | Corbiere and Sons Contracting773120210106-9L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7731 | 20210106-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Pays Plat to AntlerEvan graded from 2pm-11pm | 5 | C050-C069 | Antler Lake | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting773120210106-9Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting773120210106-9Operator - Principle - After Jan 109675Inv#095 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7731 | 20210106-9 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-01-06 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Pays Plat to AntlerEvan graded from 2pm-11pm | 5 | C050-C069 | Antler Lake | 0 | 44206 |  | 37 | 44209 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting773120210106-9Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting773120210106-9Driver - AZ - After Jan 102140Inv#095 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7748 | 20210107-10 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer finshed final area from C-107 - C-116 and moved back to laydown. | 5 | C076-C116 | Cook Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting774820210107-10Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting774820210107-10Dozer D6 or equal- After Jan 10101314.8Inv#095 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7748 | 20210107-10 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer finshed final area from C-107 - C-116 and moved back to laydown. | 5 | C076-C116 | Cook Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting774820210107-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting774820210107-10Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7748 | 20210107-10 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer finshed final area from C-107 - C-116 and moved back to laydown. | 5 | C076-C116 | Cook Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting774820210107-10L.O.A.1210 | Corbiere and Sons Contracting774820210107-10L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7748 | 20210107-10 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer finshed final area from C-107 - C-116 and moved back to laydown. | 5 | C076-C116 | Cook Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting774820210107-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting774820210107-10Operator - Principle - After Jan 1011825Inv#095 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7753 | 20210107-15 | 53510511 | Access | 0 | 3rd Party Charges | 1 | 208.8 | unit |  |  |  |  | 208.8 | 27.144 | 235.944 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Norcon Invoices - Screened Winter Sand (Invoice 18289 split 50/50 between WF3/WF5) | 5 | C076-C116 | Cook Lake | 0 | 44207 |  | 37 | 43842 | 18232 | Supply & Load sand into Corbiere truck w/sander |  |  |  | Harold Furlong | 05 | Corbiere and Sons Contracting775320210107-153rd Party Charges208.8208.8 | Corbiere and Sons Contracting775320210107-153rd Party Charges208.8208.8Inv#095 | [5 empty] | 1 | 208.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7753 | 20210107-15 | 53510511 | Access | 0 | 3rd Party Charges | 1 | 1922.61 | unit |  |  |  |  | 1922.61 | 249.9393 | 2172.5493 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Norcon Invoices - Screened Winter Sand (Invoice 18289 split 50/50 between WF3/WF5) | 5 | C076-C116 | Cook Lake | 0 | 44207 |  | 37 | 43842 | 18289 | Screened Winter Sand - 50% WF3 / 50% WF5 |  |  |  | Harold Furlong | 05 | Corbiere and Sons Contracting775320210107-153rd Party Charges1922.611922.61 | Corbiere and Sons Contracting775320210107-153rd Party Charges1922.611922.61Inv#095 | [5 empty] | 1 | 1922.61 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7754 | 20210107-16 | 53510311 | Access | 0 | 3rd Party Charges | 1 | 1922.61 | unit |  |  |  |  | 1922.61 | 249.9393 | 2172.5493 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Norcon Invoices - Screened Winter Sand (Invoice 18289 split 50/50 between WF3/WF5) | 3 | B088-B099 | Maata's Road | 0 | 44207 |  | 37 | 44208 | 18289 | Screened Winter Sand - 50% WF3 / 50% WF5 |  |  |  | Harold Furlong | 03 | Corbiere and Sons Contracting775420210107-163rd Party Charges1922.611922.61 | Corbiere and Sons Contracting775420210107-163rd Party Charges1922.611922.61Inv#095 | [5 empty] | 1 | 1922.61 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7741 | 20210107-4 | 53510211 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working with plow truck with sander across Lofty Davies and Landfill. | 2 | B054 - B064 | Lofty Davies | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting774120210107-4Pickup w/ plow and sander12960 | Corbiere and Sons Contracting774120210107-4Pickup w/ plow and sander12960Inv#095 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7741 | 20210107-4 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working with plow truck with sander across Lofty Davies and Landfill. | 2 | B054 - B064 | Lofty Davies | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting774120210107-4L.O.A.1210 | Corbiere and Sons Contracting774120210107-4L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7741 | 20210107-4 | 53510211 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working with plow truck with sander across Lofty Davies and Landfill. | 2 | B054 - B064 | Lofty Davies | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting774120210107-4Operator - Intermdiate - After Jan 1012840 | Corbiere and Sons Contracting774120210107-4Operator - Intermdiate - After Jan 1012840Inv#095 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7742 | 20210107-5 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader widening areas on Golf Course and Maata's Rd | 3 | B088-B099 | Maata's Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting774220210107-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting774220210107-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#095 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7742 | 20210107-5 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader widening areas on Golf Course and Maata's Rd | 3 | B088-B099 | Maata's Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting774220210107-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting774220210107-5Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7742 | 20210107-5 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader widening areas on Golf Course and Maata's Rd | 3 | B088-B099 | Maata's Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting774220210107-5L.O.A.1210 | Corbiere and Sons Contracting774220210107-5L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7742 | 20210107-5 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader widening areas on Golf Course and Maata's Rd | 3 | B088-B099 | Maata's Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting774220210107-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting774220210107-5Operator - Principle - After Jan 1011825Inv#095 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7743 | 20210107-6 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on plow at Camp Road 81 | 3 | B145-B149 | Camp Road 81 | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting774320210107-6Pickup w/ plow6300 | Corbiere and Sons Contracting774320210107-6Pickup w/ plow6300Inv#095 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7743 | 20210107-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on plow at Camp Road 81 | 3 | B145-B149 | Camp Road 81 | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting774320210107-6L.O.A.1210 | Corbiere and Sons Contracting774320210107-6L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7743 | 20210107-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on plow at Camp Road 81 | 3 | B145-B149 | Camp Road 81 | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting774320210107-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting774320210107-6Operator - Principle - After Jan 106450Inv#095 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7744 | 20210107-7 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 95.24 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Gurney to Cavers and later in the day demobbed grader from Maata's.Grader finished up Gurney and floated to Cavers to work for the rest of the day. | 4 | C028-C029 | Cavers Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting774420210107-7Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting774420210107-7Grader - Cat 12 to 14 or equal- After Jan 108.51079.33Inv#095 | [5 empty] | 1 | 1079.33 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7744 | 20210107-7 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Gurney to Cavers and later in the day demobbed grader from Maata's.Grader finished up Gurney and floated to Cavers to work for the rest of the day. | 4 | C028-C029 | Cavers Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting774420210107-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting774420210107-7Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7744 | 20210107-7 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Gurney to Cavers and later in the day demobbed grader from Maata's.Grader finished up Gurney and floated to Cavers to work for the rest of the day. | 4 | C028-C029 | Cavers Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting774420210107-7Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting774420210107-7Tractor Trailer - 60 Ton- After Jan 106734.34Inv#095 | [5 empty] | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7744 | 20210107-7 | 53510411 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Gurney to Cavers and later in the day demobbed grader from Maata's.Grader finished up Gurney and floated to Cavers to work for the rest of the day. | 4 | C028-C029 | Cavers Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting774420210107-7L.O.A.2420 | Corbiere and Sons Contracting774420210107-7L.O.A.2420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7744 | 20210107-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Gurney to Cavers and later in the day demobbed grader from Maata's.Grader finished up Gurney and floated to Cavers to work for the rest of the day. | 4 | C028-C029 | Cavers Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting774420210107-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting774420210107-7Operator - Principle - After Jan 1012900Inv#095 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7744 | 20210107-7 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Gurney to Cavers and later in the day demobbed grader from Maata's.Grader finished up Gurney and floated to Cavers to work for the rest of the day. | 4 | C028-C029 | Cavers Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting774420210107-7Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting774420210107-7Driver - AZ - After Jan 106420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7747 | 20210107-9 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11.5 | Dynamic | 95.24 | 0 |  |  | 1460.27 | 189.8351 | 1650.1051 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake Road all dayDustin plowing and coordinating activities | 5 | C050-C069 | Antler Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting774720210107-9Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27 | Corbiere and Sons Contracting774720210107-9Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27Inv#095 | [5 empty] | 1 | 1460.27 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7747 | 20210107-9 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake Road all dayDustin plowing and coordinating activities | 5 | C050-C069 | Antler Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting774720210107-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting774720210107-9Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7747 | 20210107-9 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake Road all dayDustin plowing and coordinating activities | 5 | C050-C069 | Antler Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting774720210107-9Pickup w/ plow6300 | Corbiere and Sons Contracting774720210107-9Pickup w/ plow6300Inv#095 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7747 | 20210107-9 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake Road all dayDustin plowing and coordinating activities | 5 | C050-C069 | Antler Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting774720210107-9L.O.A.1210 | Corbiere and Sons Contracting774720210107-9L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7747 | 20210107-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 18.5 | HR |  |  | 75 | 0 | 1387.5 | 180.375 | 1567.875 | 2021-01-07 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake Road all dayDustin plowing and coordinating activities | 5 | C050-C069 | Antler Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting774720210107-9Operator - Principle - After Jan 1018.51387.5 | Corbiere and Sons Contracting774720210107-9Operator - Principle - After Jan 1018.51387.5Inv#095 | [5 empty] | 1 | 1387.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7769 | 20210108-15 | 53510511 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance for access to get mats into C-051-Scratching and sanding of the hills | 5 | C050-C069 | Antler Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776920210108-15Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting776920210108-15Excavator - 36 ton- After Jan 105734.8Inv#095 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7769 | 20210108-15 | 53510511 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance for access to get mats into C-051-Scratching and sanding of the hills | 5 | C050-C069 | Antler Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776920210108-15Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting776920210108-15Rock Truck - 30 Ton- After Jan 105690.25Inv#095 | [5 empty] | 1 | 690.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7769 | 20210108-15 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance for access to get mats into C-051-Scratching and sanding of the hills | 5 | C050-C069 | Antler Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776920210108-15L.O.A.2420 | Corbiere and Sons Contracting776920210108-15L.O.A.2420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7769 | 20210108-15 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance for access to get mats into C-051-Scratching and sanding of the hills | 5 | C050-C069 | Antler Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776920210108-15Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting776920210108-15Operator - Principle - After Jan 105.5412.5Inv#095 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7769 | 20210108-15 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance for access to get mats into C-051-Scratching and sanding of the hills | 5 | C050-C069 | Antler Lake | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776920210108-15Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting776920210108-15Driver - AZ - After Jan 105.5385Inv#095 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7916 | 20210108-19 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed snow from HWY entrance to C-227, float turn around and laydown at C-227 | 6 | C219-C236 | Neys | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting791620210108-19Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting791620210108-19Dozer D6 or equal- After Jan 107920.36Inv#095 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7916 | 20210108-19 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed snow from HWY entrance to C-227, float turn around and laydown at C-227 | 6 | C219-C236 | Neys | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting791620210108-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting791620210108-19Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7916 | 20210108-19 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed snow from HWY entrance to C-227, float turn around and laydown at C-227 | 6 | C219-C236 | Neys | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting791620210108-19L.O.A.1210 | Corbiere and Sons Contracting791620210108-19L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7916 | 20210108-19 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed snow from HWY entrance to C-227, float turn around and laydown at C-227 | 6 | C219-C236 | Neys | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting791620210108-19Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting791620210108-19Operator - Principle - After Jan 107525Inv#095 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7758 | 20210108-4 | 53510211 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on widening Lofty Davies access all day | 2 | B054 - B064 | Lofty Davies | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting775820210108-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting775820210108-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#095 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7758 | 20210108-4 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on widening Lofty Davies access all day | 2 | B054 - B064 | Lofty Davies | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting775820210108-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting775820210108-4Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7758 | 20210108-4 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on widening Lofty Davies access all day | 2 | B054 - B064 | Lofty Davies | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting775820210108-4L.O.A.1210 | Corbiere and Sons Contracting775820210108-4L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7758 | 20210108-4 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on widening Lofty Davies access all day | 2 | B054 - B064 | Lofty Davies | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting775820210108-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting775820210108-4Operator - Principle - After Jan 1011825Inv#095 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7760 | 20210108-6 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Jackfish to Mill Road - 2 flaggers needed for traffic control for the demob from JackfishDozer clearing snow in Mill road all day after float moveDustin running plow truck clearing entrance way and turnaround - planning and coordinating areas to be cleared. | 5 | C117-C124 | Mill Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776020210108-6Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting776020210108-6Dozer D6 or equal- After Jan 106788.88Inv#095 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7760 | 20210108-6 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Jackfish to Mill Road - 2 flaggers needed for traffic control for the demob from JackfishDozer clearing snow in Mill road all day after float moveDustin running plow truck clearing entrance way and turnaround - planning and coordinating areas to be cleared. | 5 | C117-C124 | Mill Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776020210108-6Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting776020210108-6Tractor Trailer - 60 Ton- After Jan 105611.95Inv#095 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7760 | 20210108-6 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Jackfish to Mill Road - 2 flaggers needed for traffic control for the demob from JackfishDozer clearing snow in Mill road all day after float moveDustin running plow truck clearing entrance way and turnaround - planning and coordinating areas to be cleared. | 5 | C117-C124 | Mill Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776020210108-6Pickup w/ plow6300 | Corbiere and Sons Contracting776020210108-6Pickup w/ plow6300Inv#095 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7760 | 20210108-6 | 53510511 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Jackfish to Mill Road - 2 flaggers needed for traffic control for the demob from JackfishDozer clearing snow in Mill road all day after float moveDustin running plow truck clearing entrance way and turnaround - planning and coordinating areas to be cleared. | 5 | C117-C124 | Mill Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776020210108-6L.O.A.4840 | Corbiere and Sons Contracting776020210108-6L.O.A.4840Inv#095 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7760 | 20210108-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Jackfish to Mill Road - 2 flaggers needed for traffic control for the demob from JackfishDozer clearing snow in Mill road all day after float moveDustin running plow truck clearing entrance way and turnaround - planning and coordinating areas to be cleared. | 5 | C117-C124 | Mill Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776020210108-6Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting776020210108-6Operator - Principle - After Jan 10231725Inv#095 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7760 | 20210108-6 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Jackfish to Mill Road - 2 flaggers needed for traffic control for the demob from JackfishDozer clearing snow in Mill road all day after float moveDustin running plow truck clearing entrance way and turnaround - planning and coordinating areas to be cleared. | 5 | C117-C124 | Mill Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776020210108-6Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting776020210108-6Driver - AZ - After Jan 105350Inv#095 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7760 | 20210108-6 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 from Jackfish to Mill Road - 2 flaggers needed for traffic control for the demob from JackfishDozer clearing snow in Mill road all day after float moveDustin running plow truck clearing entrance way and turnaround - planning and coordinating areas to be cleared. | 5 | C117-C124 | Mill Road | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting776020210108-6Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting776020210108-6Labourer - General - After Jan 1010600Inv#095 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8Skidder 5855 | Corbiere and Sons Contracting776220210108-8Skidder 5855Inv#095 | [5 empty] | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting776220210108-8Dozer D6 or equal- After Jan 106788.88Inv#095 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting776220210108-8Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#095 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting776220210108-8Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting776220210108-8Tractor Trailer - 60 Ton- After Jan 105611.95Inv#095 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 17 |  | 0 | 0 |  |  | 1360 | 176.8 | 1536.8 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8Pickup w/ plow and sander171360 | Corbiere and Sons Contracting776220210108-8Pickup w/ plow and sander171360Inv#095 | [5 empty] | 1 | 1360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8Foreman3285 | Corbiere and Sons Contracting776220210108-8Foreman3285Inv#095 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8L.O.A.51050 | Corbiere and Sons Contracting776220210108-8L.O.A.51050Inv#095 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting776220210108-8Operator - Principle - After Jan 10211575Inv#095 | [5 empty] | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 17 | HR |  |  | 70 | 0 | 1190 | 154.7 | 1344.7 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8Operator - Intermdiate - After Jan 10171190 | Corbiere and Sons Contracting776220210108-8Operator - Intermdiate - After Jan 10171190Inv#095 | [5 empty] | 1 | 1190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7762 | 20210108-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-01-08 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler into Lake A and D6T from Santoy Mountain into Lake A for night shift maintenance with matsDarrel on plow truck w/sander from 4am-9am sanding Lake A, Darrel then jumped on skidder and started dragging road from 611 to Structure C-130 - C-137Evan on grader until 3pm and then came back on nightshift and ran dozer dragging mats from 1am-8amStacey started sanding at 4am with Darrel at Lake A and then moved to Santoy Lake and Santoy Mountain to plow and sand | 6 | C129-C151 | Lake A | 0 | 44207 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting776220210108-8Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting776220210108-8Driver - AZ - After Jan 105350Inv#095 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7781 | 20210109-12 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 21.5 | Dynamic | 98.61 | 0 |  |  | 2826.82 | 367.4866 | 3194.3066 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry did maintenance on Lake A with Dozer all day Evan working nightshift dragging mats across Lake A | 6 | C129-C151 | Lake A | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting778120210109-12Dozer D6 or equal- After Jan 1021.52826.82 | Corbiere and Sons Contracting778120210109-12Dozer D6 or equal- After Jan 1021.52826.82Inv#095 | [5 empty] | 1 | 2826.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7781 | 20210109-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry did maintenance on Lake A with Dozer all day Evan working nightshift dragging mats across Lake A | 6 | C129-C151 | Lake A | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting778120210109-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting778120210109-12Light Truck - Pick up- After Jan 102487.5Inv#095 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7781 | 20210109-12 | 53510611 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry did maintenance on Lake A with Dozer all day Evan working nightshift dragging mats across Lake A | 6 | C129-C151 | Lake A | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting778120210109-12Foreman4380 | Corbiere and Sons Contracting778120210109-12Foreman4380Inv#095 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7781 | 20210109-12 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry did maintenance on Lake A with Dozer all day Evan working nightshift dragging mats across Lake A | 6 | C129-C151 | Lake A | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting778120210109-12L.O.A.3630 | Corbiere and Sons Contracting778120210109-12L.O.A.3630Inv#095 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7781 | 20210109-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry did maintenance on Lake A with Dozer all day Evan working nightshift dragging mats across Lake A | 6 | C129-C151 | Lake A | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting778120210109-12Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting778120210109-12Operator - Principle - After Jan 10231725Inv#095 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7835 | 20210109-16 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 and DZ-05 worked on blast location 155346 Middleton Road | 6 | C210-C214 | Middleton Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting783520210109-16Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting783520210109-16Dozer D6 or equal- After Jan 103394.44Inv#095 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7835 | 20210109-16 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 and DZ-05 worked on blast location 155346 Middleton Road | 6 | C210-C214 | Middleton Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting783520210109-16Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting783520210109-16Excavator - 36 ton- After Jan 103440.88Inv#095 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7835 | 20210109-16 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 and DZ-05 worked on blast location 155346 Middleton Road | 6 | C210-C214 | Middleton Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting783520210109-16Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting783520210109-16Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#095 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7835 | 20210109-16 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 and DZ-05 worked on blast location 155346 Middleton Road | 6 | C210-C214 | Middleton Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting783520210109-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting783520210109-16Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7835 | 20210109-16 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 and DZ-05 worked on blast location 155346 Middleton Road | 6 | C210-C214 | Middleton Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting783520210109-16L.O.A.2420 | Corbiere and Sons Contracting783520210109-16L.O.A.2420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7835 | 20210109-16 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 and DZ-05 worked on blast location 155346 Middleton Road | 6 | C210-C214 | Middleton Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting783520210109-16Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting783520210109-16Operator - Principle - After Jan 106450Inv#095 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7773 | 20210109-4 | 53510211 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running grader across Lofty Davies all day widening access roads - Floated to Landfill at the end of the day | 2 | B054 - B064 | Lofty Davies | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting777320210109-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting777320210109-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#095 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7773 | 20210109-4 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running grader across Lofty Davies all day widening access roads - Floated to Landfill at the end of the day | 2 | B054 - B064 | Lofty Davies | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting777320210109-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting777320210109-4Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7773 | 20210109-4 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running grader across Lofty Davies all day widening access roads - Floated to Landfill at the end of the day | 2 | B054 - B064 | Lofty Davies | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting777320210109-4L.O.A.1210 | Corbiere and Sons Contracting777320210109-4L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7773 | 20210109-4 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running grader across Lofty Davies all day widening access roads - Floated to Landfill at the end of the day | 2 | B054 - B064 | Lofty Davies | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting777320210109-4Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting777320210109-4Operator - Principle - After Jan 109675Inv#095 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7774 | 20210109-5 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Lofty Davies into Landfill RdStacey and Dustin plowing and sanding Landfill, Doghead and Valard camp. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting777420210109-5Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting777420210109-5Tractor Trailer - 60 Ton- After Jan 104489.56Inv#095 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7774 | 20210109-5 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 22 |  | 0 | 0 |  |  | 1760 | 228.8 | 1988.8 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Lofty Davies into Landfill RdStacey and Dustin plowing and sanding Landfill, Doghead and Valard camp. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting777420210109-5Pickup w/ plow and sander221760 | Corbiere and Sons Contracting777420210109-5Pickup w/ plow and sander221760Inv#095 | [5 empty] | 1 | 1760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7774 | 20210109-5 | 53510311 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Lofty Davies into Landfill RdStacey and Dustin plowing and sanding Landfill, Doghead and Valard camp. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting777420210109-5L.O.A.3630 | Corbiere and Sons Contracting777420210109-5L.O.A.3630Inv#095 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7774 | 20210109-5 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Lofty Davies into Landfill RdStacey and Dustin plowing and sanding Landfill, Doghead and Valard camp. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting777420210109-5Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting777420210109-5Operator - Principle - After Jan 10141050Inv#095 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7774 | 20210109-5 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Lofty Davies into Landfill RdStacey and Dustin plowing and sanding Landfill, Doghead and Valard camp. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting777420210109-5Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting777420210109-5Operator - Intermdiate - After Jan 1011770Inv#095 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7774 | 20210109-5 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Lofty Davies into Landfill RdStacey and Dustin plowing and sanding Landfill, Doghead and Valard camp. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting777420210109-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting777420210109-5Driver - AZ - After Jan 104280Inv#095 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7775 | 20210109-6 | 53510511 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading dirt and sanding hill on Antler to get access for mat hauling to C-051 | 5 | C050-C069 | Antler Lake | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting777520210109-6Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting777520210109-6Excavator - 36 ton- After Jan 105734.8Inv#095 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7775 | 20210109-6 | 53510511 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading dirt and sanding hill on Antler to get access for mat hauling to C-051 | 5 | C050-C069 | Antler Lake | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting777520210109-6Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting777520210109-6Rock Truck - 30 Ton- After Jan 105690.25Inv#095 | [5 empty] | 1 | 690.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7775 | 20210109-6 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading dirt and sanding hill on Antler to get access for mat hauling to C-051 | 5 | C050-C069 | Antler Lake | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting777520210109-6L.O.A.2420 | Corbiere and Sons Contracting777520210109-6L.O.A.2420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7775 | 20210109-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading dirt and sanding hill on Antler to get access for mat hauling to C-051 | 5 | C050-C069 | Antler Lake | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting777520210109-6Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting777520210109-6Operator - Principle - After Jan 105.5412.5Inv#095 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7775 | 20210109-6 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-01-09 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading dirt and sanding hill on Antler to get access for mat hauling to C-051 | 5 | C050-C069 | Antler Lake | 0 | 44208 |  | 37 | 44208 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting777520210109-6Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting777520210109-6Driver - AZ - After Jan 105.5385Inv#095 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7847 | 20210110-11 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cavers Rd to Blair Lake RdGrader graded access roads all day | 3 | B182-B186 | Blair Lake Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784720210110-11Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting784720210110-11Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#095 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7847 | 20210110-11 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cavers Rd to Blair Lake RdGrader graded access roads all day | 3 | B182-B186 | Blair Lake Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784720210110-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting784720210110-11Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7847 | 20210110-11 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2.5 | Dynamic | 91.79 | 0 |  |  | 305.975 | 39.7767 | 345.7518 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cavers Rd to Blair Lake RdGrader graded access roads all day | 3 | B182-B186 | Blair Lake Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784720210110-11Tractor Trailer - 60 Ton- After Jan 102.5305.975 | Corbiere and Sons Contracting784720210110-11Tractor Trailer - 60 Ton- After Jan 102.5305.975Inv#095 | [5 empty] | 1 | 305.975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7847 | 20210110-11 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cavers Rd to Blair Lake RdGrader graded access roads all day | 3 | B182-B186 | Blair Lake Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784720210110-11L.O.A.1210 | Corbiere and Sons Contracting784720210110-11L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7847 | 20210110-11 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cavers Rd to Blair Lake RdGrader graded access roads all day | 3 | B182-B186 | Blair Lake Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784720210110-11Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting784720210110-11Operator - Principle - After Jan 1012900Inv#095 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7847 | 20210110-11 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Cavers Rd to Blair Lake RdGrader graded access roads all day | 3 | B182-B186 | Blair Lake Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784720210110-11Driver - AZ - After Jan 102.5175 | Corbiere and Sons Contracting784720210110-11Driver - AZ - After Jan 102.5175Inv#095 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7848 | 20210110-12 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Landfill all day and floated to Little Gravel at the end of the dayDustin on pickup w/plow working across various areas clearing snow and coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784820210110-12Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting784820210110-12Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#095 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7848 | 20210110-12 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Landfill all day and floated to Little Gravel at the end of the dayDustin on pickup w/plow working across various areas clearing snow and coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784820210110-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting784820210110-12Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7848 | 20210110-12 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 12 | HR | 0 | 0 |  |  | 600 | 78 | 678 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Landfill all day and floated to Little Gravel at the end of the dayDustin on pickup w/plow working across various areas clearing snow and coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784820210110-12Pickup w/ plow12600 | Corbiere and Sons Contracting784820210110-12Pickup w/ plow12600Inv#095 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7848 | 20210110-12 | 53510311 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Landfill all day and floated to Little Gravel at the end of the dayDustin on pickup w/plow working across various areas clearing snow and coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784820210110-12L.O.A.2420 | Corbiere and Sons Contracting784820210110-12L.O.A.2420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7848 | 20210110-12 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Landfill all day and floated to Little Gravel at the end of the dayDustin on pickup w/plow working across various areas clearing snow and coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784820210110-12Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting784820210110-12Operator - Principle - After Jan 10221650Inv#095 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7849 | 20210110-13 | 53510311 | Access | 0 | Loader JD 744 to 844 or equal | 162 | 6 | HR | 121.5 | 0 |  |  | 972 | 126.36 | 1098.36 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up LD-01 from Lofty Davies, dleivered to Maata's Rd. LD-01 cleared snow banks in Maatas for the ski club then went down Golf Course Rd and cleared trailsFloated back to North Shore yard | 3 | B088-B099 | Maata's Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784920210110-13Loader JD 744 to 844 or equal6972 | Corbiere and Sons Contracting784920210110-13Loader JD 744 to 844 or equal6972Inv#095 | [5 empty] | 1 | 972 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7849 | 20210110-13 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up LD-01 from Lofty Davies, dleivered to Maata's Rd. LD-01 cleared snow banks in Maatas for the ski club then went down Golf Course Rd and cleared trailsFloated back to North Shore yard | 3 | B088-B099 | Maata's Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784920210110-13Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting784920210110-13Tractor Trailer - 60 Ton- After Jan 104489.56Inv#095 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7849 | 20210110-13 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up LD-01 from Lofty Davies, dleivered to Maata's Rd. LD-01 cleared snow banks in Maatas for the ski club then went down Golf Course Rd and cleared trailsFloated back to North Shore yard | 3 | B088-B099 | Maata's Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784920210110-13Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting784920210110-13Operator - Principle - After Jan 106450Inv#095 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7849 | 20210110-13 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up LD-01 from Lofty Davies, dleivered to Maata's Rd. LD-01 cleared snow banks in Maatas for the ski club then went down Golf Course Rd and cleared trailsFloated back to North Shore yard | 3 | B088-B099 | Maata's Road | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting784920210110-13Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting784920210110-13Driver - AZ - After Jan 104280Inv#095 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7840 | 20210110-4 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Landfill Rd to Little Gravel River Rd | 4 | B194-B210 | Little Gravel River Rd | 0 | 44211 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting784020210110-4Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting784020210110-4Tractor Trailer - 60 Ton- After Jan 104489.56Inv#095 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7840 | 20210110-4 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Landfill Rd to Little Gravel River Rd | 4 | B194-B210 | Little Gravel River Rd | 0 | 44211 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting784020210110-4L.O.A.1210 | Corbiere and Sons Contracting784020210110-4L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7840 | 20210110-4 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Landfill Rd to Little Gravel River Rd | 4 | B194-B210 | Little Gravel River Rd | 0 | 44211 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting784020210110-4Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting784020210110-4Operator - Principle - After Jan 102150Inv#095 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7840 | 20210110-4 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Landfill Rd to Little Gravel River Rd | 4 | B194-B210 | Little Gravel River Rd | 0 | 44211 |  | 37 | 44209 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting784020210110-4Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting784020210110-4Driver - AZ - After Jan 104280Inv#095 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7841 | 20210110-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 17 |  | 0 | 0 |  |  | 1360 | 176.8 | 1536.8 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey working across Cooks Lake access all day, John helping in the afternoon | 5 | C076-C116 | Cook Lake | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting784120210110-5Pickup w/ plow and sander171360 | Corbiere and Sons Contracting784120210110-5Pickup w/ plow and sander171360Inv#095 | [5 empty] | 1 | 1360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7841 | 20210110-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey working across Cooks Lake access all day, John helping in the afternoon | 5 | C076-C116 | Cook Lake | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting784120210110-5L.O.A.1210 | Corbiere and Sons Contracting784120210110-5L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7841 | 20210110-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 17 | HR |  |  | 70 | 0 | 1190 | 154.7 | 1344.7 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey working across Cooks Lake access all day, John helping in the afternoon | 5 | C076-C116 | Cook Lake | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting784120210110-5Operator - Intermdiate - After Jan 10171190 | Corbiere and Sons Contracting784120210110-5Operator - Intermdiate - After Jan 10171190Inv#095 | [5 empty] | 1 | 1190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7844 | 20210110-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Santoy Lake and Santoy Mountain hills and access roads for half the day | 6 | C155-C157 | Santoy Mountain | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting784420210110-8Pickup w/ plow and sander6480 | Corbiere and Sons Contracting784420210110-8Pickup w/ plow and sander6480Inv#095 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7844 | 20210110-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Santoy Lake and Santoy Mountain hills and access roads for half the day | 6 | C155-C157 | Santoy Mountain | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting784420210110-8L.O.A.1210 | Corbiere and Sons Contracting784420210110-8L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7844 | 20210110-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Santoy Lake and Santoy Mountain hills and access roads for half the day | 6 | C155-C157 | Santoy Mountain | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting784420210110-8Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting784420210110-8Operator - Intermdiate - After Jan 106420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7845 | 20210110-9 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader dragging tires in Lake A across East and West side all night | 6 | C129-C151 | Lake A | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting784520210110-9Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting784520210110-9Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv#095 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7845 | 20210110-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader dragging tires in Lake A across East and West side all night | 6 | C129-C151 | Lake A | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting784520210110-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting784520210110-9Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7845 | 20210110-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader dragging tires in Lake A across East and West side all night | 6 | C129-C151 | Lake A | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting784520210110-9L.O.A.1210 | Corbiere and Sons Contracting784520210110-9L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7845 | 20210110-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-10 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader dragging tires in Lake A across East and West side all night | 6 | C129-C151 | Lake A | 0 | 44211 |  | 37 | 44214 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting784520210110-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting784520210110-9Operator - Principle - After Jan 1012900Inv#095 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7863 | 20210111-10 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent rest of day widening roads Float moved grader from Camp Road 81 to Fire Hill Road WDustin on plow truck working on Fire Hill areas as well as coordinating and supervising activities | 3 | B135-B144 | Fire Hill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786320210111-10Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting786320210111-10Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#095 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7863 | 20210111-10 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent rest of day widening roads Float moved grader from Camp Road 81 to Fire Hill Road WDustin on plow truck working on Fire Hill areas as well as coordinating and supervising activities | 3 | B135-B144 | Fire Hill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786320210111-10Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting786320210111-10Tractor Trailer - 60 Ton- After Jan 103367.17Inv#095 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7863 | 20210111-10 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent rest of day widening roads Float moved grader from Camp Road 81 to Fire Hill Road WDustin on plow truck working on Fire Hill areas as well as coordinating and supervising activities | 3 | B135-B144 | Fire Hill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786320210111-10Pickup w/ plow6300 | Corbiere and Sons Contracting786320210111-10Pickup w/ plow6300Inv#095 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7863 | 20210111-10 | 53510311 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent rest of day widening roads Float moved grader from Camp Road 81 to Fire Hill Road WDustin on plow truck working on Fire Hill areas as well as coordinating and supervising activities | 3 | B135-B144 | Fire Hill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786320210111-10L.O.A.2420 | Corbiere and Sons Contracting786320210111-10L.O.A.2420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7863 | 20210111-10 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent rest of day widening roads Float moved grader from Camp Road 81 to Fire Hill Road WDustin on plow truck working on Fire Hill areas as well as coordinating and supervising activities | 3 | B135-B144 | Fire Hill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786320210111-10Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting786320210111-10Operator - Principle - After Jan 10181350Inv#095 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7863 | 20210111-10 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent rest of day widening roads Float moved grader from Camp Road 81 to Fire Hill Road WDustin on plow truck working on Fire Hill areas as well as coordinating and supervising activities | 3 | B135-B144 | Fire Hill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786320210111-10Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting786320210111-10Driver - AZ - After Jan 103210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7864 | 20210111-11 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Blair Lake to Camp Road 81 | 3 | B145-B149 | Camp 81 Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786420210111-11Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting786420210111-11Tractor Trailer - 60 Ton- After Jan 103367.17Inv#095 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7864 | 20210111-11 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Blair Lake to Camp Road 81 | 3 | B145-B149 | Camp 81 Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786420210111-11Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting786420210111-11Driver - AZ - After Jan 103210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7865 | 20210111-12 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float went to Little Gravel Rd and moved grader to Fire Hill Creek | 3 | B119-B132 | Fire Hill Creek | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786520210111-12Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting786520210111-12Tractor Trailer - 60 Ton- After Jan 103367.17Inv#095 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7865 | 20210111-12 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float went to Little Gravel Rd and moved grader to Fire Hill Creek | 3 | B119-B132 | Fire Hill Creek | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786520210111-12Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting786520210111-12Driver - AZ - After Jan 103210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7857 | 20210111-4 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader widening out Little Gravel River Rd all the way to B-216 and opening up tower access | 4 | B194-B210 | Little Gravel River Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting785720210111-4Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting785720210111-4Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#095 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7857 | 20210111-4 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader widening out Little Gravel River Rd all the way to B-216 and opening up tower access | 4 | B194-B210 | Little Gravel River Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting785720210111-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting785720210111-4Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7857 | 20210111-4 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader widening out Little Gravel River Rd all the way to B-216 and opening up tower access | 4 | B194-B210 | Little Gravel River Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting785720210111-4L.O.A.1210 | Corbiere and Sons Contracting785720210111-4L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7857 | 20210111-4 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader widening out Little Gravel River Rd all the way to B-216 and opening up tower access | 4 | B194-B210 | Little Gravel River Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting785720210111-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting785720210111-4Operator - Principle - After Jan 1011825Inv#095 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7858 | 20210111-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey working across Antler access half the day | 5 | C050-C069 | Antler Lake | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting785820210111-5Pickup w/ plow and sander6480 | Corbiere and Sons Contracting785820210111-5Pickup w/ plow and sander6480Inv#095 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7858 | 20210111-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey working across Antler access half the day | 5 | C050-C069 | Antler Lake | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting785820210111-5L.O.A.1210 | Corbiere and Sons Contracting785820210111-5L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7858 | 20210111-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey working across Antler access half the day | 5 | C050-C069 | Antler Lake | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting785820210111-5Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting785820210111-5Operator - Intermdiate - After Jan 106420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7862 | 20210111-9 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader spent half the day at Gurney and floated to Fire Hill Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786220210111-9Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting786220210111-9Grader - Cat 12 to 14 or equal- After Jan 105.5698.39Inv#095 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7862 | 20210111-9 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader spent half the day at Gurney and floated to Fire Hill Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786220210111-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting786220210111-9Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7862 | 20210111-9 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader spent half the day at Gurney and floated to Fire Hill Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786220210111-9L.O.A.1210 | Corbiere and Sons Contracting786220210111-9L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7862 | 20210111-9 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2021-01-11 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader spent half the day at Gurney and floated to Fire Hill Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting786220210111-9Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting786220210111-9Operator - Principle - After Jan 106.5487.5Inv#095 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7924 | 20210112-21 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed AU1 road out from C243 to Hwy 17, and float turn around. | 6 | C237-C243 | Culvert Creek | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting792420210112-21Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting792420210112-21Dozer D6 or equal- After Jan 104525.92Inv#095 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7924 | 20210112-21 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed AU1 road out from C243 to Hwy 17, and float turn around. | 6 | C237-C243 | Culvert Creek | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting792420210112-21Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting792420210112-21Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7924 | 20210112-21 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed AU1 road out from C243 to Hwy 17, and float turn around. | 6 | C237-C243 | Culvert Creek | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting792420210112-21L.O.A.1210 | Corbiere and Sons Contracting792420210112-21L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7924 | 20210112-21 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed AU1 road out from C243 to Hwy 17, and float turn around. | 6 | C237-C243 | Culvert Creek | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting792420210112-21Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting792420210112-21Operator - Principle - After Jan 104300Inv#095 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7926 | 20210112-23 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walked excavator out from C-270 to assist lost CP Rail pickup | 6 | C257-C267 | Hare Lake | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting792620210112-23Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting792620210112-23Excavator - 36 ton- After Jan 102293.92Inv#095 | [5 empty] | 1 | 293.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7926 | 20210112-23 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walked excavator out from C-270 to assist lost CP Rail pickup | 6 | C257-C267 | Hare Lake | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting792620210112-23Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting792620210112-23Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#095 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7926 | 20210112-23 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walked excavator out from C-270 to assist lost CP Rail pickup | 6 | C257-C267 | Hare Lake | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting792620210112-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting792620210112-23Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7926 | 20210112-23 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walked excavator out from C-270 to assist lost CP Rail pickup | 6 | C257-C267 | Hare Lake | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting792620210112-23L.O.A.1210 | Corbiere and Sons Contracting792620210112-23L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7926 | 20210112-23 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walked excavator out from C-270 to assist lost CP Rail pickup | 6 | C257-C267 | Hare Lake | 0 | 44215 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting792620210112-23Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting792620210112-23Operator - Principle - After Jan 102150Inv#095 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7873 | 20210112-4 | 53510211 | Access | 0 | Pickup w/ plow and sander | 80 | 14 |  | 0 | 0 |  |  | 1120 | 145.6 | 1265.6 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey and Dustin worked on sanding area in Lofty Davies | 2 | B054 - B064 | Lofty Davies | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting787320210112-4Pickup w/ plow and sander141120 | Corbiere and Sons Contracting787320210112-4Pickup w/ plow and sander141120Inv#095 | [5 empty] | 1 | 1120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7873 | 20210112-4 | 53510211 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey and Dustin worked on sanding area in Lofty Davies | 2 | B054 - B064 | Lofty Davies | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting787320210112-4L.O.A.2420 | Corbiere and Sons Contracting787320210112-4L.O.A.2420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7873 | 20210112-4 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey and Dustin worked on sanding area in Lofty Davies | 2 | B054 - B064 | Lofty Davies | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting787320210112-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting787320210112-4Operator - Principle - After Jan 1012900Inv#095 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7873 | 20210112-4 | 53510211 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey and Dustin worked on sanding area in Lofty Davies | 2 | B054 - B064 | Lofty Davies | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting787320210112-4Operator - Intermdiate - After Jan 108560 | Corbiere and Sons Contracting787320210112-4Operator - Intermdiate - After Jan 108560Inv#095 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7876 | 20210112-7 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading at Fire Hill Creek E and widened access from B-124 - B-133 | 3 | B124-B132 | Fire Hill Creek East | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting787620210112-7Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting787620210112-7Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#095 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7876 | 20210112-7 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading at Fire Hill Creek E and widened access from B-124 - B-133 | 3 | B124-B132 | Fire Hill Creek East | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting787620210112-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting787620210112-7Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7876 | 20210112-7 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading at Fire Hill Creek E and widened access from B-124 - B-133 | 3 | B124-B132 | Fire Hill Creek East | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting787620210112-7L.O.A.1210 | Corbiere and Sons Contracting787620210112-7L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7876 | 20210112-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4.5 | HR |  |  | 75 | 0 | 337.5 | 43.875 | 381.375 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading at Fire Hill Creek E and widened access from B-124 - B-133 | 3 | B124-B132 | Fire Hill Creek East | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting787620210112-7Operator - Principle - After Jan 104.5337.5 | Corbiere and Sons Contracting787620210112-7Operator - Principle - After Jan 104.5337.5Inv#095 | [5 empty] | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7877 | 20210112-8 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Fire Hill Road West to Mill RoadGrader were floated here and began widening access all day | 5 | C117-C124 | Mill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting787720210112-8Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting787720210112-8Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#095 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7877 | 20210112-8 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Fire Hill Road West to Mill RoadGrader were floated here and began widening access all day | 5 | C117-C124 | Mill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting787720210112-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting787720210112-8Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7877 | 20210112-8 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Fire Hill Road West to Mill RoadGrader were floated here and began widening access all day | 5 | C117-C124 | Mill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting787720210112-8Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting787720210112-8Tractor Trailer - 60 Ton- After Jan 105611.95Inv#095 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7877 | 20210112-8 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Fire Hill Road West to Mill RoadGrader were floated here and began widening access all day | 5 | C117-C124 | Mill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting787720210112-8L.O.A.2420 | Corbiere and Sons Contracting787720210112-8L.O.A.2420Inv#095 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7877 | 20210112-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Fire Hill Road West to Mill RoadGrader were floated here and began widening access all day | 5 | C117-C124 | Mill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting787720210112-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting787720210112-8Operator - Principle - After Jan 1011.5862.5Inv#095 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7877 | 20210112-8 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-01-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Fire Hill Road West to Mill RoadGrader were floated here and began widening access all day | 5 | C117-C124 | Mill Road | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting787720210112-8Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting787720210112-8Driver - AZ - After Jan 105350Inv#095 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7901 | 20210113-13 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 did some road re-hab on Lake A Road E | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting790120210113-13Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting790120210113-13Excavator - 36 ton- After Jan 104587.84Inv#095 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7901 | 20210113-13 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 did some road re-hab on Lake A Road E | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting790120210113-13Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting790120210113-13Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#095 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7901 | 20210113-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 did some road re-hab on Lake A Road E | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting790120210113-13Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting790120210113-13Operator - Principle - After Jan 104300Inv#095 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7894 | 20210113-6 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Mill Road to Antler Lake Rd | 5 | C050-C069 | Antler Lake | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting789420210113-6Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting789420210113-6Tractor Trailer - 60 Ton- After Jan 103367.17Inv#095 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7894 | 20210113-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Mill Road to Antler Lake Rd | 5 | C050-C069 | Antler Lake | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting789420210113-6L.O.A.1210 | Corbiere and Sons Contracting789420210113-6L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7894 | 20210113-6 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Mill Road to Antler Lake Rd | 5 | C050-C069 | Antler Lake | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting789420210113-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting789420210113-6Driver - AZ - After Jan 103210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7896 | 20210113-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 95.24 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader scratching east side of Lake A Stacey on plow with sander working across Lake A, Dustin with plow helping in the morning. Dawson demobbed skidder | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting789620210113-8Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting789620210113-8Grader - Cat 12 to 14 or equal- After Jan 108.51079.33Inv#095 | [5 empty] | 1 | 1079.33 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7896 | 20210113-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader scratching east side of Lake A Stacey on plow with sander working across Lake A, Dustin with plow helping in the morning. Dawson demobbed skidder | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting789620210113-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting789620210113-8Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7896 | 20210113-8 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader scratching east side of Lake A Stacey on plow with sander working across Lake A, Dustin with plow helping in the morning. Dawson demobbed skidder | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting789620210113-8Pickup w/ plow4200 | Corbiere and Sons Contracting789620210113-8Pickup w/ plow4200Inv#095 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7896 | 20210113-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 9 |  | 0 | 0 |  |  | 720 | 93.6 | 813.6 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader scratching east side of Lake A Stacey on plow with sander working across Lake A, Dustin with plow helping in the morning. Dawson demobbed skidder | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting789620210113-8Pickup w/ plow and sander9720 | Corbiere and Sons Contracting789620210113-8Pickup w/ plow and sander9720Inv#095 | [5 empty] | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7896 | 20210113-8 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader scratching east side of Lake A Stacey on plow with sander working across Lake A, Dustin with plow helping in the morning. Dawson demobbed skidder | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting789620210113-8L.O.A.3630 | Corbiere and Sons Contracting789620210113-8L.O.A.3630Inv#095 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7896 | 20210113-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader scratching east side of Lake A Stacey on plow with sander working across Lake A, Dustin with plow helping in the morning. Dawson demobbed skidder | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting789620210113-8Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting789620210113-8Operator - Principle - After Jan 1013975Inv#095 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7896 | 20210113-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 9 | HR |  |  | 70 | 0 | 630 | 81.9 | 711.9 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader scratching east side of Lake A Stacey on plow with sander working across Lake A, Dustin with plow helping in the morning. Dawson demobbed skidder | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting789620210113-8Operator - Intermdiate - After Jan 109630 | Corbiere and Sons Contracting789620210113-8Operator - Intermdiate - After Jan 109630Inv#095 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7896 | 20210113-8 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2021-01-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader scratching east side of Lake A Stacey on plow with sander working across Lake A, Dustin with plow helping in the morning. Dawson demobbed skidder | 6 | C129-C151 | Lake A | 0 | 44213 |  | 37 | 44216 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting789620210113-8Labourer - General - After Jan 102120 | Corbiere and Sons Contracting789620210113-8Labourer - General - After Jan 102120Inv#095 | [5 empty] | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7944 | 20210114-11 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent day from C-146 moving and fixing road | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting794420210114-11Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting794420210114-11Excavator - 36 ton- After Jan 1010.51543.08Inv#104 | [5 empty] | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7944 | 20210114-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent day from C-146 moving and fixing road | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting794420210114-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting794420210114-11Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7944 | 20210114-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent day from C-146 moving and fixing road | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting794420210114-11L.O.A.1210 | Corbiere and Sons Contracting794420210114-11L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7944 | 20210114-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent day from C-146 moving and fixing road | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting794420210114-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting794420210114-11Operator - Principle - After Jan 1011825Inv#104 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7997 | 20210114-16 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repair at Lake A Road East. | 6 | C129-C151 | Lake A | 0 | 44219 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting799720210114-16Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting799720210114-16Excavator - 36 ton- After Jan 101146.96Inv#104 | [5 empty] | 1 | 146.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7997 | 20210114-16 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repair at Lake A Road East. | 6 | C129-C151 | Lake A | 0 | 44219 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting799720210114-16Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting799720210114-16Excavator Thumb - 30 - 50 ton- After Jan 10112.21Inv#104 | [5 empty] | 1 | 12.21 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7997 | 20210114-16 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repair at Lake A Road East. | 6 | C129-C151 | Lake A | 0 | 44219 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting799720210114-16Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting799720210114-16Operator - Principle - After Jan 10175Inv#104 | [5 empty] | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7940 | 20210114-7 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Fire Hill Road E to Landfill in preparation for snowfall | 3 | B078-B084 | Landfill Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting794020210114-7Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting794020210114-7Tractor Trailer - 60 Ton- After Jan 102244.78Inv#104 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7940 | 20210114-7 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Fire Hill Road E to Landfill in preparation for snowfall | 3 | B078-B084 | Landfill Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting794020210114-7Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting794020210114-7Driver - AZ - After Jan 102140Inv#104 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7942 | 20210114-9 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler Lake Rd to Nishin CreekGrader started working on access roads and scratching in C-016 area. | 4 | C011-C029 | Nishin Creek Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting794220210114-9Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting794220210114-9Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#104 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7942 | 20210114-9 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler Lake Rd to Nishin CreekGrader started working on access roads and scratching in C-016 area. | 4 | C011-C029 | Nishin Creek Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting794220210114-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting794220210114-9Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7942 | 20210114-9 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler Lake Rd to Nishin CreekGrader started working on access roads and scratching in C-016 area. | 4 | C011-C029 | Nishin Creek Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting794220210114-9Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting794220210114-9Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7942 | 20210114-9 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler Lake Rd to Nishin CreekGrader started working on access roads and scratching in C-016 area. | 4 | C011-C029 | Nishin Creek Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting794220210114-9L.O.A.1210 | Corbiere and Sons Contracting794220210114-9L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7942 | 20210114-9 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler Lake Rd to Nishin CreekGrader started working on access roads and scratching in C-016 area. | 4 | C011-C029 | Nishin Creek Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting794220210114-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting794220210114-9Operator - Principle - After Jan 1011825Inv#104 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7942 | 20210114-9 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-14 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Antler Lake Rd to Nishin CreekGrader started working on access roads and scratching in C-016 area. | 4 | C011-C029 | Nishin Creek Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting794220210114-9Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting794220210114-9Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8028 | 20210115-13 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2.5 | Dynamic | 110.22 | 0 |  |  | 367.4 | 47.762 | 415.162 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 did some road repair at Lake A Rd E | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting802820210115-13Excavator - 36 ton- After Jan 102.5367.4 | Corbiere and Sons Contracting802820210115-13Excavator - 36 ton- After Jan 102.5367.4Inv#104 | [5 empty] | 1 | 367.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8028 | 20210115-13 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2.5 | HR | 9.16 | 0 |  |  | 30.525 | 3.9682 | 34.4933 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 did some road repair at Lake A Rd E | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting802820210115-13Excavator Thumb - 30 - 50 ton- After Jan 102.530.525 | Corbiere and Sons Contracting802820210115-13Excavator Thumb - 30 - 50 ton- After Jan 102.530.525Inv#104 | [5 empty] | 1 | 30.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8028 | 20210115-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2.5 | HR |  |  | 75 | 0 | 187.5 | 24.375 | 211.875 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 did some road repair at Lake A Rd E | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting802820210115-13Operator - Principle - After Jan 102.5187.5 | Corbiere and Sons Contracting802820210115-13Operator - Principle - After Jan 102.5187.5Inv#104 | [5 empty] | 1 | 187.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8029 | 20210115-14 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 1 | Dynamic | 98.61 | 0 |  |  | 131.48 | 17.0924 | 148.5724 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 opened AU1 road | 6 | C215-C218 | Little Pie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting802920210115-14Dozer D6 or equal- After Jan 101131.48 | Corbiere and Sons Contracting802920210115-14Dozer D6 or equal- After Jan 101131.48Inv#104 | [5 empty] | 1 | 131.48 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8029 | 20210115-14 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 opened AU1 road | 6 | C215-C218 | Little Pie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting802920210115-14Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting802920210115-14Operator - Principle - After Jan 10175Inv#104 | [5 empty] | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7955 | 20210115-7 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len and Grader working across Lake A access roadsJosh moving road from C-146 structure and widen corners + Fill in voids from C-147 - C-148Cole supervising and coordinating | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting795520210115-7Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting795520210115-7Excavator - 36 ton- After Jan 1010.51543.08Inv#104 | [5 empty] | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7955 | 20210115-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 95.24 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len and Grader working across Lake A access roadsJosh moving road from C-146 structure and widen corners + Fill in voids from C-147 - C-148Cole supervising and coordinating | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting795520210115-7Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting795520210115-7Grader - Cat 12 to 14 or equal- After Jan 108.51079.33Inv#104 | [5 empty] | 1 | 1079.33 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7955 | 20210115-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len and Grader working across Lake A access roadsJosh moving road from C-146 structure and widen corners + Fill in voids from C-147 - C-148Cole supervising and coordinating | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting795520210115-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting795520210115-7Light Truck - Pick up- After Jan 102487.5Inv#104 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7955 | 20210115-7 | 53510611 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len and Grader working across Lake A access roadsJosh moving road from C-146 structure and widen corners + Fill in voids from C-147 - C-148Cole supervising and coordinating | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting795520210115-7Foreman6570 | Corbiere and Sons Contracting795520210115-7Foreman6570Inv#104 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7955 | 20210115-7 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len and Grader working across Lake A access roadsJosh moving road from C-146 structure and widen corners + Fill in voids from C-147 - C-148Cole supervising and coordinating | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting795520210115-7L.O.A.3630 | Corbiere and Sons Contracting795520210115-7L.O.A.3630Inv#104 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7955 | 20210115-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2021-01-15 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len and Grader working across Lake A access roadsJosh moving road from C-146 structure and widen corners + Fill in voids from C-147 - C-148Cole supervising and coordinating | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting795520210115-7Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting795520210115-7Operator - Principle - After Jan 10201500Inv#104 | [5 empty] | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8036 | 20210116-14 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 1 | Dynamic | 98.61 | 0 |  |  | 131.48 | 17.0924 | 148.5724 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 opened up a turnaround and parking space at Little Pic River Bridge AU1 road. | 6 | C215-C218 | Little Pie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting803620210116-14Dozer D6 or equal- After Jan 101131.48 | Corbiere and Sons Contracting803620210116-14Dozer D6 or equal- After Jan 101131.48Inv#104 | [5 empty] | 1 | 131.48 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8036 | 20210116-14 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 opened up a turnaround and parking space at Little Pic River Bridge AU1 road. | 6 | C215-C218 | Little Pie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting803620210116-14Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting803620210116-14Operator - Principle - After Jan 10175Inv#104 | [5 empty] | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7964 | 20210116-6 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin went out to Fire Hill to sand hill until called in to quarantine | 3 | B135-B144 | Fire Hill Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting796420210116-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting796420210116-6Pickup w/ plow and sander4320Inv#104 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7964 | 20210116-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin went out to Fire Hill to sand hill until called in to quarantine | 3 | B135-B144 | Fire Hill Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting796420210116-6L.O.A.1210 | Corbiere and Sons Contracting796420210116-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7964 | 20210116-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin went out to Fire Hill to sand hill until called in to quarantine | 3 | B135-B144 | Fire Hill Road | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting796420210116-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting796420210116-6Operator - Principle - After Jan 104300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7966 | 20210116-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Lake A, John on sand truck sanding Lake A for part of the day. | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting796620210116-8Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting796620210116-8Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#104 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7966 | 20210116-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Lake A, John on sand truck sanding Lake A for part of the day. | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting796620210116-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting796620210116-8Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7966 | 20210116-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Lake A, John on sand truck sanding Lake A for part of the day. | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting796620210116-8Pickup w/ plow and sander6480 | Corbiere and Sons Contracting796620210116-8Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7966 | 20210116-8 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Lake A, John on sand truck sanding Lake A for part of the day. | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting796620210116-8L.O.A.2420 | Corbiere and Sons Contracting796620210116-8L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7966 | 20210116-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Lake A, John on sand truck sanding Lake A for part of the day. | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting796620210116-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting796620210116-8Operator - Principle - After Jan 1011825Inv#104 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7966 | 20210116-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-16 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len on grader working across Lake A, John on sand truck sanding Lake A for part of the day. | 6 | C129-C151 | Lake A | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting796620210116-8Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting796620210116-8Operator - Intermdiate - After Jan 106420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7979 | 20210117-11 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-17 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated in by Jeff in preparation for next snow fall. | 5 | C076-C116 | Cook Lake | 0 | 44218 |  | 37 | 43854 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting797920210117-11Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting797920210117-11Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7979 | 20210117-11 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-17 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated in by Jeff in preparation for next snow fall. | 5 | C076-C116 | Cook Lake | 0 | 44218 |  | 37 | 43854 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting797920210117-11L.O.A.1210 | Corbiere and Sons Contracting797920210117-11L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7979 | 20210117-11 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-17 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated in by Jeff in preparation for next snow fall. | 5 | C076-C116 | Cook Lake | 0 | 44218 |  | 37 | 43854 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting797920210117-11Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting797920210117-11Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7977 | 20210117-9 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-01-17 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked all day on grader across Santoy Lake Rd after being floated in by Jeff from Prairie River | 6 | C158 - C170 | Santoy Mountain | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting797720210117-9Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting797720210117-9Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#104 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7977 | 20210117-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-17 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked all day on grader across Santoy Lake Rd after being floated in by Jeff from Prairie River | 6 | C158 - C170 | Santoy Mountain | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting797720210117-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting797720210117-9Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7977 | 20210117-9 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-17 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked all day on grader across Santoy Lake Rd after being floated in by Jeff from Prairie River | 6 | C158 - C170 | Santoy Mountain | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting797720210117-9Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting797720210117-9Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7977 | 20210117-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-17 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked all day on grader across Santoy Lake Rd after being floated in by Jeff from Prairie River | 6 | C158 - C170 | Santoy Mountain | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting797720210117-9L.O.A.1210 | Corbiere and Sons Contracting797720210117-9L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7977 | 20210117-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-17 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked all day on grader across Santoy Lake Rd after being floated in by Jeff from Prairie River | 6 | C158 - C170 | Santoy Mountain | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting797720210117-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting797720210117-9Operator - Principle - After Jan 1011825Inv#104 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7977 | 20210117-9 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-17 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked all day on grader across Santoy Lake Rd after being floated in by Jeff from Prairie River | 6 | C158 - C170 | Santoy Mountain | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting797720210117-9Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting797720210117-9Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7994 | 20210119-7 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 7 |  | 0 | 0 |  |  | 560 | 72.8 | 632.8 | 2021-01-19 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey sanding hills on Doghead all the way to laydown. | 3 | B100-B109 | Doghead | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting799420210119-7Pickup w/ plow and sander7560 | Corbiere and Sons Contracting799420210119-7Pickup w/ plow and sander7560Inv#104 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7994 | 20210119-7 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-19 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey sanding hills on Doghead all the way to laydown. | 3 | B100-B109 | Doghead | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting799420210119-7L.O.A.1210 | Corbiere and Sons Contracting799420210119-7L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7994 | 20210119-7 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-01-19 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey sanding hills on Doghead all the way to laydown. | 3 | B100-B109 | Doghead | 0 | 44218 |  | 37 | 44220 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting799420210119-7Operator - Intermdiate - After Jan 107490 | Corbiere and Sons Contracting799420210119-7Operator - Intermdiate - After Jan 107490Inv#104 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8149 | 20210120-7 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer work on road for crane width | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814920210120-7Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting814920210120-7Excavator - 36 ton- After Jan 10142057.44Inv#104 | [5 empty] | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8149 | 20210120-7 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer work on road for crane width | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814920210120-7Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting814920210120-7Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#104 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8149 | 20210120-7 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer work on road for crane width | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814920210120-7Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting814920210120-7Excavator Hammer - 30 - 50 ton- After Jan 1012760.56Inv#104 | [5 empty] | 1 | 760.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8149 | 20210120-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer work on road for crane width | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814920210120-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting814920210120-7Light Truck - Pick up- After Jan 102487.5Inv#104 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8149 | 20210120-7 | 53510611 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer work on road for crane width | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814920210120-7Foreman4380 | Corbiere and Sons Contracting814920210120-7Foreman4380Inv#104 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8149 | 20210120-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer work on road for crane width | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814920210120-7L.O.A.2420 | Corbiere and Sons Contracting814920210120-7L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8149 | 20210120-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer work on road for crane width | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814920210120-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting814920210120-7Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8151 | 20210120-9 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work done to Peninsula. | 6 | C268-C279 | Peninsula Road | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815120210120-9Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting815120210120-9Excavator - 30 ton- After Jan 104553.8Inv#104 | [5 empty] | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8151 | 20210120-9 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work done to Peninsula. | 6 | C268-C279 | Peninsula Road | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815120210120-9Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting815120210120-9Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#104 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8151 | 20210120-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work done to Peninsula. | 6 | C268-C279 | Peninsula Road | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815120210120-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting815120210120-9Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8151 | 20210120-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work done to Peninsula. | 6 | C268-C279 | Peninsula Road | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815120210120-9L.O.A.1210 | Corbiere and Sons Contracting815120210120-9L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8151 | 20210120-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-20 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work done to Peninsula. | 6 | C268-C279 | Peninsula Road | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815120210120-9Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting815120210120-9Operator - Principle - After Jan 104300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8060 | 20210121-10 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow clearing snow on Little Pic | 6 | C215-C218 | Little Pie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806020210121-10Pickup w/ plow4200 | Corbiere and Sons Contracting806020210121-10Pickup w/ plow4200Inv#104 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8060 | 20210121-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow clearing snow on Little Pic | 6 | C215-C218 | Little Pie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806020210121-10L.O.A.1210 | Corbiere and Sons Contracting806020210121-10L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8060 | 20210121-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow clearing snow on Little Pic | 6 | C215-C218 | Little Pie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806020210121-10Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting806020210121-10Operator - Intermdiate - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8061 | 20210121-11 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow clearing snow on Ripple Lake | 6 | C196-C202 | Ripple Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806120210121-11Pickup w/ plow4200 | Corbiere and Sons Contracting806120210121-11Pickup w/ plow4200Inv#104 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8061 | 20210121-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow clearing snow on Ripple Lake | 6 | C196-C202 | Ripple Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806120210121-11Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting806120210121-11Operator - Intermdiate - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8062 | 20210121-12 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow clearing snow on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806220210121-12Pickup w/ plow4200 | Corbiere and Sons Contracting806220210121-12Pickup w/ plow4200Inv#104 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8062 | 20210121-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow clearing snow on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806220210121-12Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting806220210121-12Operator - Intermdiate - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8063 | 20210121-13 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader cleared Neys in the morning, Dozer spent 5 hrs opening up Neys Rd | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806320210121-13Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting806320210121-13Dozer D6 or equal- After Jan 105657.4Inv#104 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8063 | 20210121-13 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader cleared Neys in the morning, Dozer spent 5 hrs opening up Neys Rd | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806320210121-13Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting806320210121-13Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#104 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8063 | 20210121-13 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader cleared Neys in the morning, Dozer spent 5 hrs opening up Neys Rd | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806320210121-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting806320210121-13Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8063 | 20210121-13 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader cleared Neys in the morning, Dozer spent 5 hrs opening up Neys Rd | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806320210121-13L.O.A.2420 | Corbiere and Sons Contracting806320210121-13L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8063 | 20210121-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12.5 | HR |  |  | 75 | 0 | 937.5 | 121.875 | 1059.375 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader cleared Neys in the morning, Dozer spent 5 hrs opening up Neys Rd | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806320210121-13Operator - Principle - After Jan 1012.5937.5 | Corbiere and Sons Contracting806320210121-13Operator - Principle - After Jan 1012.5937.5Inv#104 | [5 empty] | 1 | 937.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8064 | 20210121-14 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader got floated to Lake A for the rest of the day | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806420210121-14Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting806420210121-14Grader - Cat 12 to 14 or equal- After Jan 105.5698.39Inv#104 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8064 | 20210121-14 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader got floated to Lake A for the rest of the day | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806420210121-14Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting806420210121-14Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8064 | 20210121-14 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader got floated to Lake A for the rest of the day | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806420210121-14L.O.A.1210 | Corbiere and Sons Contracting806420210121-14L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8064 | 20210121-14 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader got floated to Lake A for the rest of the day | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806420210121-14Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting806420210121-14Operator - Principle - After Jan 107525Inv#104 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8064 | 20210121-14 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader got floated to Lake A for the rest of the day | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806420210121-14Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting806420210121-14Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8065 | 20210121-15 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer did snow removal at Hare Lake in the morning for 3 hours | 6 | C257-C267 | Hare Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806520210121-15Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting806520210121-15Dozer D6 or equal- After Jan 103394.44Inv#104 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8065 | 20210121-15 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer did snow removal at Hare Lake in the morning for 3 hours | 6 | C257-C267 | Hare Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806520210121-15L.O.A.1210 | Corbiere and Sons Contracting806520210121-15L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8065 | 20210121-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer did snow removal at Hare Lake in the morning for 3 hours | 6 | C257-C267 | Hare Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting806520210121-15Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting806520210121-15Operator - Principle - After Jan 103225Inv#104 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8153 | 20210121-18 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared snow from HWY to float turn around | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815320210121-18Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting815320210121-18Dozer D6 or equal- After Jan 102262.96Inv#104 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8153 | 20210121-18 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared snow from HWY to float turn around | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815320210121-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting815320210121-18Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8153 | 20210121-18 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared snow from HWY to float turn around | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815320210121-18L.O.A.1210 | Corbiere and Sons Contracting815320210121-18L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8153 | 20210121-18 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared snow from HWY to float turn around | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815320210121-18Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting815320210121-18Operator - Principle - After Jan 102150Inv#104 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8154 | 20210121-19 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815420210121-19Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting815420210121-19Excavator - 36 ton- After Jan 106881.76Inv#104 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8154 | 20210121-19 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815420210121-19Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting815420210121-19Excavator - 36 ton- After Jan 106881.76Inv#104 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8154 | 20210121-19 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815420210121-19Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting815420210121-19Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#104 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8154 | 20210121-19 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815420210121-19Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting815420210121-19Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#104 | [5 empty] | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8154 | 20210121-19 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815420210121-19Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting815420210121-19Light Truck - Pick up- After Jan 102487.5Inv#104 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8154 | 20210121-19 | 53510611 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815420210121-19Foreman4380 | Corbiere and Sons Contracting815420210121-19Foreman4380Inv#104 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8154 | 20210121-19 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815420210121-19L.O.A.1210 | Corbiere and Sons Contracting815420210121-19L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8154 | 20210121-19 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting815420210121-19Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting815420210121-19Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8056 | 20210121-6 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader on Landfill for the morning. | 3 | B078-B084 | Red Rock No 7 | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting805620210121-6Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting805620210121-6Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#104 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8056 | 20210121-6 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader on Landfill for the morning. | 3 | B078-B084 | Red Rock No 7 | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting805620210121-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting805620210121-6Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8056 | 20210121-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader on Landfill for the morning. | 3 | B078-B084 | Red Rock No 7 | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting805620210121-6L.O.A.1210 | Corbiere and Sons Contracting805620210121-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8056 | 20210121-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4.5 | HR |  |  | 75 | 0 | 337.5 | 43.875 | 381.375 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader on Landfill for the morning. | 3 | B078-B084 | Red Rock No 7 | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting805620210121-6Operator - Principle - After Jan 104.5337.5 | Corbiere and Sons Contracting805620210121-6Operator - Principle - After Jan 104.5337.5Inv#104 | [5 empty] | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8057 | 20210121-7 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 12 | HR | 0 | 0 |  |  | 600 | 78 | 678 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey on pickup with plow working across Firehill and Camp Road 81 | 3 | B45-B149 | Camp 81 Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting805720210121-7Pickup w/ plow12600 | Corbiere and Sons Contracting805720210121-7Pickup w/ plow12600Inv#104 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8057 | 20210121-7 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey on pickup with plow working across Firehill and Camp Road 81 | 3 | B45-B149 | Camp 81 Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting805720210121-7L.O.A.1210 | Corbiere and Sons Contracting805720210121-7L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8057 | 20210121-7 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey on pickup with plow working across Firehill and Camp Road 81 | 3 | B45-B149 | Camp 81 Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting805720210121-7Operator - Intermdiate - After Jan 1012840 | Corbiere and Sons Contracting805720210121-7Operator - Intermdiate - After Jan 1012840Inv#104 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8058 | 20210121-8 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12 | Dynamic | 95.24 | 0 |  |  | 1523.76 | 198.0888 | 1721.8488 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary working on grader across Cooks access all day (4am start) - Grader floated to Antler at the end of the dayDustin on pickup w/plow at Cooks/Mill/Antler | 5 | C076-C116 | Cook Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting805820210121-8Grader - Cat 12 to 14 or equal- After Jan 10121523.76 | Corbiere and Sons Contracting805820210121-8Grader - Cat 12 to 14 or equal- After Jan 10121523.76Inv#104 | [5 empty] | 1 | 1523.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8058 | 20210121-8 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary working on grader across Cooks access all day (4am start) - Grader floated to Antler at the end of the dayDustin on pickup w/plow at Cooks/Mill/Antler | 5 | C076-C116 | Cook Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting805820210121-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting805820210121-8Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8058 | 20210121-8 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary working on grader across Cooks access all day (4am start) - Grader floated to Antler at the end of the dayDustin on pickup w/plow at Cooks/Mill/Antler | 5 | C076-C116 | Cook Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting805820210121-8Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting805820210121-8Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8058 | 20210121-8 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 12 | HR | 0 | 0 |  |  | 600 | 78 | 678 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary working on grader across Cooks access all day (4am start) - Grader floated to Antler at the end of the dayDustin on pickup w/plow at Cooks/Mill/Antler | 5 | C076-C116 | Cook Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting805820210121-8Pickup w/ plow12600 | Corbiere and Sons Contracting805820210121-8Pickup w/ plow12600Inv#104 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8058 | 20210121-8 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary working on grader across Cooks access all day (4am start) - Grader floated to Antler at the end of the dayDustin on pickup w/plow at Cooks/Mill/Antler | 5 | C076-C116 | Cook Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting805820210121-8L.O.A.3630 | Corbiere and Sons Contracting805820210121-8L.O.A.3630Inv#104 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8058 | 20210121-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24.5 | HR |  |  | 75 | 0 | 1837.5 | 238.875 | 2076.375 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary working on grader across Cooks access all day (4am start) - Grader floated to Antler at the end of the dayDustin on pickup w/plow at Cooks/Mill/Antler | 5 | C076-C116 | Cook Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting805820210121-8Operator - Principle - After Jan 1024.51837.5 | Corbiere and Sons Contracting805820210121-8Operator - Principle - After Jan 1024.51837.5Inv#104 | [5 empty] | 1 | 1837.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8058 | 20210121-8 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary working on grader across Cooks access all day (4am start) - Grader floated to Antler at the end of the dayDustin on pickup w/plow at Cooks/Mill/Antler | 5 | C076-C116 | Cook Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting805820210121-8Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting805820210121-8Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8059 | 20210121-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal on Peninsula | 6 | C268-C279 | Peninsula Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting805920210121-9Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting805920210121-9Dozer D6 or equal- After Jan 105657.4Inv#104 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8059 | 20210121-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal on Peninsula | 6 | C268-C279 | Peninsula Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting805920210121-9L.O.A.1210 | Corbiere and Sons Contracting805920210121-9L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8059 | 20210121-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-01-21 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal on Peninsula | 6 | C268-C279 | Peninsula Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting805920210121-9Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting805920210121-9Operator - Principle - After Jan 105375Inv#104 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8077 | 20210122-10 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow working across Ripple Lake | 6 | C196-C202 | Ripple Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807720210122-10Pickup w/ plow5250 | Corbiere and Sons Contracting807720210122-10Pickup w/ plow5250Inv#104 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8077 | 20210122-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow working across Ripple Lake | 6 | C196-C202 | Ripple Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807720210122-10Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting807720210122-10Operator - Intermdiate - After Jan 105350Inv#104 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8078 | 20210122-11 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake APickup w/plow and sander working across Lake A | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807820210122-11Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting807820210122-11Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#104 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8078 | 20210122-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake APickup w/plow and sander working across Lake A | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807820210122-11Pickup w/ plow and sander3240 | Corbiere and Sons Contracting807820210122-11Pickup w/ plow and sander3240Inv#104 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8078 | 20210122-11 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake APickup w/plow and sander working across Lake A | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807820210122-11L.O.A.2420 | Corbiere and Sons Contracting807820210122-11L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8078 | 20210122-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake APickup w/plow and sander working across Lake A | 6 | C129-C151 | Lake A | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807820210122-11Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting807820210122-11Operator - Principle - After Jan 10151125Inv#104 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8079 | 20210122-12 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from Lake A to Prairie River - Cole took over a Prarie and finished off the last few towers. | 6 | C171-C185 | Prairie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807920210122-12Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting807920210122-12Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#104 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8079 | 20210122-12 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from Lake A to Prairie River - Cole took over a Prarie and finished off the last few towers. | 6 | C171-C185 | Prairie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807920210122-12Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting807920210122-12Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8079 | 20210122-12 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from Lake A to Prairie River - Cole took over a Prarie and finished off the last few towers. | 6 | C171-C185 | Prairie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807920210122-12L.O.A.2420 | Corbiere and Sons Contracting807920210122-12L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8079 | 20210122-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from Lake A to Prairie River - Cole took over a Prarie and finished off the last few towers. | 6 | C171-C185 | Prairie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807920210122-12Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting807920210122-12Operator - Principle - After Jan 104300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8079 | 20210122-12 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from Lake A to Prairie River - Cole took over a Prarie and finished off the last few towers. | 6 | C171-C185 | Prairie River | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting807920210122-12Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting807920210122-12Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8080 | 20210122-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working across Santoy | 6 | C158-C170 | Santoy Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808020210122-13Pickup w/ plow and sander3240 | Corbiere and Sons Contracting808020210122-13Pickup w/ plow and sander3240Inv#104 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8080 | 20210122-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working across Santoy | 6 | C158-C170 | Santoy Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808020210122-13Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting808020210122-13Operator - Principle - After Jan 103225Inv#104 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8084 | 20210122-17 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared snow on the way to WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44229 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808420210122-17Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting808420210122-17Dozer D6 or equal- After Jan 102262.96Inv#104 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8084 | 20210122-17 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared snow on the way to WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44229 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808420210122-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting808420210122-17Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8084 | 20210122-17 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared snow on the way to WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44229 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808420210122-17Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting808420210122-17Operator - Principle - After Jan 102150Inv#104 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8085 | 20210122-18 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808520210122-18Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting808520210122-18Excavator - 36 ton- After Jan 10121763.52Inv#104 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8085 | 20210122-18 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808520210122-18Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting808520210122-18Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#104 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8085 | 20210122-18 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808520210122-18Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting808520210122-18Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#104 | [5 empty] | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8085 | 20210122-18 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808520210122-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting808520210122-18Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8085 | 20210122-18 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808520210122-18Foreman2190 | Corbiere and Sons Contracting808520210122-18Foreman2190Inv#104 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8085 | 20210122-18 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808520210122-18L.O.A.1210 | Corbiere and Sons Contracting808520210122-18L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8085 | 20210122-18 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes | 6 | C219-C236 | Neys | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808520210122-18Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting808520210122-18Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8089 | 20210122-22 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 cleared Del Lake Rd of snow | 6 | C186-C195 | Del Lake | 0 | 44229 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808920210122-22Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting808920210122-22Dozer D6 or equal- After Jan 105657.4Inv#104 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8089 | 20210122-22 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 cleared Del Lake Rd of snow | 6 | C186-C195 | Del Lake | 0 | 44229 |  | 37 | 44237 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting808920210122-22Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting808920210122-22Operator - Principle - After Jan 105375Inv#104 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8073 | 20210122-6 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow truck working across Doghead | 3 | B100-B109 | Doghead Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting807320210122-6Pickup w/ plow6300 | Corbiere and Sons Contracting807320210122-6Pickup w/ plow6300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8073 | 20210122-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow truck working across Doghead | 3 | B100-B109 | Doghead Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting807320210122-6L.O.A.1210 | Corbiere and Sons Contracting807320210122-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8073 | 20210122-6 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow truck working across Doghead | 3 | B100-B109 | Doghead Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting807320210122-6Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting807320210122-6Operator - Intermdiate - After Jan 106420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8074 | 20210122-7 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader plowing Nishin all morning | 4 | C011-C029 | Nishin creek Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting807420210122-7Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting807420210122-7Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#104 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8074 | 20210122-7 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader plowing Nishin all morning | 4 | C011-C029 | Nishin creek Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting807420210122-7L.O.A.1210 | Corbiere and Sons Contracting807420210122-7L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8074 | 20210122-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader plowing Nishin all morning | 4 | C011-C029 | Nishin creek Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting807420210122-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting807420210122-7Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8075 | 20210122-8 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader plowing Gravel Rd in afternoon, Dustin helping out with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting807520210122-8Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting807520210122-8Grader - Cat 12 to 14 or equal- After Jan 105.5698.39Inv#104 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8075 | 20210122-8 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader plowing Gravel Rd in afternoon, Dustin helping out with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting807520210122-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting807520210122-8Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8075 | 20210122-8 | 53510411 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 |  |  |  | 300 | 39 | 339 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader plowing Gravel Rd in afternoon, Dustin helping out with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting807520210122-8Pickup w/ plow6300 | Corbiere and Sons Contracting807520210122-8Pickup w/ plow6300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8075 | 20210122-8 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader plowing Gravel Rd in afternoon, Dustin helping out with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting807520210122-8L.O.A.1210 | Corbiere and Sons Contracting807520210122-8L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8075 | 20210122-8 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader plowing Gravel Rd in afternoon, Dustin helping out with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting807520210122-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting807520210122-8Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8076 | 20210122-9 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12.5 | Dynamic | 95.24 | 0 |  |  | 1587.25 | 206.3425 | 1793.5925 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary and Grader working across access roads | 5 | C050-C069 | Antler Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting807620210122-9Grader - Cat 12 to 14 or equal- After Jan 1012.51587.25 | Corbiere and Sons Contracting807620210122-9Grader - Cat 12 to 14 or equal- After Jan 1012.51587.25Inv#104 | [5 empty] | 1 | 1587.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8076 | 20210122-9 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary and Grader working across access roads | 5 | C050-C069 | Antler Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting807620210122-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting807620210122-9Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8076 | 20210122-9 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary and Grader working across access roads | 5 | C050-C069 | Antler Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting807620210122-9L.O.A.1210 | Corbiere and Sons Contracting807620210122-9L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8076 | 20210122-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-01-22 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary and Grader working across access roads | 5 | C050-C069 | Antler Lake | 0 | 44222 |  | 37 | 44237 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting807620210122-9Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting807620210122-9Operator - Principle - After Jan 1013975Inv#104 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8101 | 20210123-10 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore came here to run grader to open up areas from C-036 to C-048Jeff moved grader from Prairie River to Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting810120210123-10Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting810120210123-10Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#104 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8101 | 20210123-10 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore came here to run grader to open up areas from C-036 to C-048Jeff moved grader from Prairie River to Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting810120210123-10Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting810120210123-10Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8101 | 20210123-10 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore came here to run grader to open up areas from C-036 to C-048Jeff moved grader from Prairie River to Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting810120210123-10L.O.A.1210 | Corbiere and Sons Contracting810120210123-10L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8101 | 20210123-10 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore came here to run grader to open up areas from C-036 to C-048Jeff moved grader from Prairie River to Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting810120210123-10Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting810120210123-10Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8101 | 20210123-10 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore came here to run grader to open up areas from C-036 to C-048Jeff moved grader from Prairie River to Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting810120210123-10Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting810120210123-10Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8102 | 20210123-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S worked on plow truck with sander across Lake A from 10am - 6pm | 6 | C129-C151 | Lake A | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810220210123-11Pickup w/ plow and sander8640 | Corbiere and Sons Contracting810220210123-11Pickup w/ plow and sander8640Inv#104 | [5 empty] | 1 | 640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8102 | 20210123-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S worked on plow truck with sander across Lake A from 10am - 6pm | 6 | C129-C151 | Lake A | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810220210123-11L.O.A.1210 | Corbiere and Sons Contracting810220210123-11L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8102 | 20210123-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S worked on plow truck with sander across Lake A from 10am - 6pm | 6 | C129-C151 | Lake A | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810220210123-11Operator - Intermdiate - After Jan 108560 | Corbiere and Sons Contracting810220210123-11Operator - Intermdiate - After Jan 108560Inv#104 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8103 | 20210123-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working across Ripple Lake | 6 | C196-C202 | Ripple Lake | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810320210123-12Pickup w/ plow and sander4320 | Corbiere and Sons Contracting810320210123-12Pickup w/ plow and sander4320Inv#104 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8103 | 20210123-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working across Ripple Lake | 6 | C196-C202 | Ripple Lake | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810320210123-12Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting810320210123-12Operator - Principle - After Jan 104300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8105 | 20210123-14 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes. Near C-237 | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810520210123-14Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting810520210123-14Excavator - 36 ton- After Jan 10121763.52Inv#104 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8105 | 20210123-14 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes. Near C-237 | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810520210123-14Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting810520210123-14Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#104 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8105 | 20210123-14 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes. Near C-237 | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810520210123-14Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting810520210123-14Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#104 | [5 empty] | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8105 | 20210123-14 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes. Near C-237 | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810520210123-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting810520210123-14Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8105 | 20210123-14 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes. Near C-237 | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810520210123-14Foreman2190 | Corbiere and Sons Contracting810520210123-14Foreman2190Inv#104 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8105 | 20210123-14 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes. Near C-237 | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810520210123-14L.O.A.1210 | Corbiere and Sons Contracting810520210123-14L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8105 | 20210123-14 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on road for cranes. Near C-237 | 6 | C219-C236 | Neys | 0 | 44222 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting810520210123-14Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting810520210123-14Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8097 | 20210123-6 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore ran grader in Landfill all morningJeff moved grader from Landfill to Gurney | 3 | B078-B084 | Red Rock No 7 | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting809720210123-6Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting809720210123-6Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#104 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8097 | 20210123-6 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore ran grader in Landfill all morningJeff moved grader from Landfill to Gurney | 3 | B078-B084 | Red Rock No 7 | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting809720210123-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting809720210123-6Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8097 | 20210123-6 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore ran grader in Landfill all morningJeff moved grader from Landfill to Gurney | 3 | B078-B084 | Red Rock No 7 | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting809720210123-6Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting809720210123-6Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8097 | 20210123-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore ran grader in Landfill all morningJeff moved grader from Landfill to Gurney | 3 | B078-B084 | Red Rock No 7 | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting809720210123-6L.O.A.1210 | Corbiere and Sons Contracting809720210123-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8097 | 20210123-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore ran grader in Landfill all morningJeff moved grader from Landfill to Gurney | 3 | B078-B084 | Red Rock No 7 | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting809720210123-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting809720210123-6Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8097 | 20210123-6 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roger from North Shore ran grader in Landfill all morningJeff moved grader from Landfill to Gurney | 3 | B078-B084 | Red Rock No 7 | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting809720210123-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting809720210123-6Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8098 | 20210123-7 | 53510411 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin and Pickup w/plow and sander worked across Little Gravel River Road and plowed truck turnaround at Gravel River Road. | 4 | B194-B210 | Little Gravel River Road | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting809820210123-7Pickup w/ plow and sander8640 | Corbiere and Sons Contracting809820210123-7Pickup w/ plow and sander8640Inv#104 | [5 empty] | 1 | 640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8098 | 20210123-7 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin and Pickup w/plow and sander worked across Little Gravel River Road and plowed truck turnaround at Gravel River Road. | 4 | B194-B210 | Little Gravel River Road | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting809820210123-7L.O.A.1210 | Corbiere and Sons Contracting809820210123-7L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8098 | 20210123-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin and Pickup w/plow and sander worked across Little Gravel River Road and plowed truck turnaround at Gravel River Road. | 4 | B194-B210 | Little Gravel River Road | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting809820210123-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting809820210123-7Operator - Principle - After Jan 108600Inv#104 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8099 | 20210123-8 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4.5 | Dynamic | 95.24 | 0 |  |  | 571.41 | 74.2833 | 645.6933 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler in the morning and floated to Cooks Lake for the rest of the day. | 5 | C050-C069 | Antler Lake | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting809920210123-8Grader - Cat 12 to 14 or equal- After Jan 104.5571.41 | Corbiere and Sons Contracting809920210123-8Grader - Cat 12 to 14 or equal- After Jan 104.5571.41Inv#104 | [5 empty] | 1 | 571.41 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8099 | 20210123-8 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2.5 | Dynamic | 91.79 | 0 |  |  | 305.975 | 39.7767 | 345.7518 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler in the morning and floated to Cooks Lake for the rest of the day. | 5 | C050-C069 | Antler Lake | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting809920210123-8Tractor Trailer - 60 Ton- After Jan 102.5305.975 | Corbiere and Sons Contracting809920210123-8Tractor Trailer - 60 Ton- After Jan 102.5305.975Inv#104 | [5 empty] | 1 | 305.975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8099 | 20210123-8 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler in the morning and floated to Cooks Lake for the rest of the day. | 5 | C050-C069 | Antler Lake | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting809920210123-8L.O.A.1210 | Corbiere and Sons Contracting809920210123-8L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8099 | 20210123-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler in the morning and floated to Cooks Lake for the rest of the day. | 5 | C050-C069 | Antler Lake | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting809920210123-8Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting809920210123-8Operator - Principle - After Jan 107525Inv#104 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8099 | 20210123-8 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler in the morning and floated to Cooks Lake for the rest of the day. | 5 | C050-C069 | Antler Lake | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting809920210123-8Driver - AZ - After Jan 102.5175 | Corbiere and Sons Contracting809920210123-8Driver - AZ - After Jan 102.5175Inv#104 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8100 | 20210123-9 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Cooks Lake access all afternoon | 5 | C076-C116 | Cook Lake | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting810020210123-9Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting810020210123-9Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#104 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8100 | 20210123-9 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Cooks Lake access all afternoon | 5 | C076-C116 | Cook Lake | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting810020210123-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting810020210123-9Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8100 | 20210123-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-23 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Cooks Lake access all afternoon | 5 | C076-C116 | Cook Lake | 0 | 44222 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting810020210123-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting810020210123-9Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8119 | 20210124-10 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand Laforest working all day in Pays Plat River Road E on Grader | 5 | C031-C049 | Pays Plat River | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811920210124-10Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting811920210124-10Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#104 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8119 | 20210124-10 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand Laforest working all day in Pays Plat River Road E on Grader | 5 | C031-C049 | Pays Plat River | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811920210124-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting811920210124-10Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8119 | 20210124-10 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand Laforest working all day in Pays Plat River Road E on Grader | 5 | C031-C049 | Pays Plat River | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811920210124-10L.O.A.1210 | Corbiere and Sons Contracting811920210124-10L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8119 | 20210124-10 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand Laforest working all day in Pays Plat River Road E on Grader | 5 | C031-C049 | Pays Plat River | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811920210124-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting811920210124-10Operator - Principle - After Jan 1011825Inv#104 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8120 | 20210124-11 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on grader across Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812020210124-11Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting812020210124-11Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#104 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8120 | 20210124-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on grader across Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812020210124-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting812020210124-11Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8120 | 20210124-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on grader across Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812020210124-11L.O.A.1210 | Corbiere and Sons Contracting812020210124-11L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8120 | 20210124-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on grader across Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812020210124-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting812020210124-11Operator - Principle - After Jan 1011825Inv#104 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8121 | 20210124-12 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S worked on plow truck with plow and sander across Lake A until 3pm; Dustin on pickup w/ plow on Lake A until 3pm and then went to Mill Rd.Leslie worked on 350X4 repairing road on Lake A at KM6 and KM7 for 5 hours. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812120210124-12Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting812120210124-12Excavator - 36 ton- After Jan 105734.8Inv#104 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8121 | 20210124-12 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 8 | HR | 0 | 0 |  |  | 400 | 52 | 452 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S worked on plow truck with plow and sander across Lake A until 3pm; Dustin on pickup w/ plow on Lake A until 3pm and then went to Mill Rd.Leslie worked on 350X4 repairing road on Lake A at KM6 and KM7 for 5 hours. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812120210124-12Pickup w/ plow8400 | Corbiere and Sons Contracting812120210124-12Pickup w/ plow8400Inv#104 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8121 | 20210124-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S worked on plow truck with plow and sander across Lake A until 3pm; Dustin on pickup w/ plow on Lake A until 3pm and then went to Mill Rd.Leslie worked on 350X4 repairing road on Lake A at KM6 and KM7 for 5 hours. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812120210124-12Pickup w/ plow and sander8640 | Corbiere and Sons Contracting812120210124-12Pickup w/ plow and sander8640Inv#104 | [5 empty] | 1 | 640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8121 | 20210124-12 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S worked on plow truck with plow and sander across Lake A until 3pm; Dustin on pickup w/ plow on Lake A until 3pm and then went to Mill Rd.Leslie worked on 350X4 repairing road on Lake A at KM6 and KM7 for 5 hours. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812120210124-12L.O.A.3630 | Corbiere and Sons Contracting812120210124-12L.O.A.3630Inv#104 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8121 | 20210124-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S worked on plow truck with plow and sander across Lake A until 3pm; Dustin on pickup w/ plow on Lake A until 3pm and then went to Mill Rd.Leslie worked on 350X4 repairing road on Lake A at KM6 and KM7 for 5 hours. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812120210124-12Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting812120210124-12Operator - Principle - After Jan 1013975Inv#104 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8121 | 20210124-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S worked on plow truck with plow and sander across Lake A until 3pm; Dustin on pickup w/ plow on Lake A until 3pm and then went to Mill Rd.Leslie worked on 350X4 repairing road on Lake A at KM6 and KM7 for 5 hours. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812120210124-12Operator - Intermdiate - After Jan 108560 | Corbiere and Sons Contracting812120210124-12Operator - Intermdiate - After Jan 108560Inv#104 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8122 | 20210124-13 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Pays Plat to Lake A at the end of the day. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812220210124-13Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting812220210124-13Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8122 | 20210124-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Pays Plat to Lake A at the end of the day. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812220210124-13L.O.A.1210 | Corbiere and Sons Contracting812220210124-13L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8122 | 20210124-13 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from Pays Plat to Lake A at the end of the day. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting812220210124-13Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting812220210124-13Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8124 | 20210124-15 | 53510411 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 cleared Cavers Rd for snow from highway to C-029. | 4 | C028-C029 | Cavers Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting812420210124-15Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting812420210124-15Dozer D6 or equal- After Jan 104525.92Inv#104 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8124 | 20210124-15 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 cleared Cavers Rd for snow from highway to C-029. | 4 | C028-C029 | Cavers Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting812420210124-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting812420210124-15Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8124 | 20210124-15 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 cleared Cavers Rd for snow from highway to C-029. | 4 | C028-C029 | Cavers Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting812420210124-15Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting812420210124-15Operator - Principle - After Jan 104300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8183 | 20210124-18 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-239 - C-241 | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818320210124-18Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting818320210124-18Excavator - 36 ton- After Jan 10121763.52Inv#104 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8183 | 20210124-18 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-239 - C-241 | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818320210124-18Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting818320210124-18Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#104 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8183 | 20210124-18 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-239 - C-241 | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818320210124-18Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting818320210124-18Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#104 | [5 empty] | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8183 | 20210124-18 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-239 - C-241 | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818320210124-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting818320210124-18Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8183 | 20210124-18 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-239 - C-241 | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818320210124-18Foreman2190 | Corbiere and Sons Contracting818320210124-18Foreman2190Inv#104 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8183 | 20210124-18 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-239 - C-241 | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818320210124-18L.O.A.1210 | Corbiere and Sons Contracting818320210124-18L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8183 | 20210124-18 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-239 - C-241 | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818320210124-18Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting818320210124-18Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8115 | 20210124-6 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel from North Shore working on Grader all day across Gurney East | 3 | B191-B193 | Gurney East | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting811520210124-6Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting811520210124-6Grader - Cat 12 to 14 or equal- After Jan 105.5698.39Inv#104 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8115 | 20210124-6 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel from North Shore working on Grader all day across Gurney East | 3 | B191-B193 | Gurney East | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting811520210124-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting811520210124-6Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8115 | 20210124-6 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel from North Shore working on Grader all day across Gurney East | 3 | B191-B193 | Gurney East | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting811520210124-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting811520210124-6Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8116 | 20210124-7 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel North Shore working on Grader all day across Little Gravel River Rd | 4 | B194-B210 | Little Gravel River Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting811620210124-7Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting811620210124-7Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#104 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8116 | 20210124-7 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel North Shore working on Grader all day across Little Gravel River Rd | 4 | B194-B210 | Little Gravel River Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting811620210124-7L.O.A.1210 | Corbiere and Sons Contracting811620210124-7L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8116 | 20210124-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel North Shore working on Grader all day across Little Gravel River Rd | 4 | B194-B210 | Little Gravel River Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting811620210124-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting811620210124-7Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8117 | 20210124-8 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12 | Dynamic | 95.24 | 0 |  |  | 1523.76 | 198.0888 | 1721.8488 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all day at Cooks Lake Rd E all the way into Tower 216 | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811720210124-8Grader - Cat 12 to 14 or equal- After Jan 10121523.76 | Corbiere and Sons Contracting811720210124-8Grader - Cat 12 to 14 or equal- After Jan 10121523.76Inv#104 | [5 empty] | 1 | 1523.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8117 | 20210124-8 | 53510511 | Access | 0 | Light Truck - 1 to 3 Ton- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all day at Cooks Lake Rd E all the way into Tower 216 | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811720210124-8Light Truck - 1 to 3 Ton- After Jan 101243.75 | Corbiere and Sons Contracting811720210124-8Light Truck - 1 to 3 Ton- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8117 | 20210124-8 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all day at Cooks Lake Rd E all the way into Tower 216 | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811720210124-8L.O.A.1210 | Corbiere and Sons Contracting811720210124-8L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8117 | 20210124-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all day at Cooks Lake Rd E all the way into Tower 216 | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811720210124-8Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting811720210124-8Operator - Principle - After Jan 1013975Inv#104 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8118 | 20210124-9 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John working on plow w/sander for 3 hoursDustin working across Mill for 4 hours | 5 | C117-C124 | Mill Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811820210124-9Pickup w/ plow4200 | Corbiere and Sons Contracting811820210124-9Pickup w/ plow4200Inv#104 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8118 | 20210124-9 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John working on plow w/sander for 3 hoursDustin working across Mill for 4 hours | 5 | C117-C124 | Mill Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811820210124-9Pickup w/ plow and sander3240 | Corbiere and Sons Contracting811820210124-9Pickup w/ plow and sander3240Inv#104 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8118 | 20210124-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John working on plow w/sander for 3 hoursDustin working across Mill for 4 hours | 5 | C117-C124 | Mill Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811820210124-9Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting811820210124-9Operator - Principle - After Jan 104300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8118 | 20210124-9 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-24 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John working on plow w/sander for 3 hoursDustin working across Mill for 4 hours | 5 | C117-C124 | Mill Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting811820210124-9Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting811820210124-9Operator - Intermdiate - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8138 | 20210125-11 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit worked on grader across Mill road for morning until it broke downJohn S working on Mill Road for half day | 5 | C117-C120 | Mill Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813820210125-11Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting813820210125-11Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#104 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8138 | 20210125-11 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit worked on grader across Mill road for morning until it broke downJohn S working on Mill Road for half day | 5 | C117-C120 | Mill Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813820210125-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting813820210125-11Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8138 | 20210125-11 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit worked on grader across Mill road for morning until it broke downJohn S working on Mill Road for half day | 5 | C117-C120 | Mill Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813820210125-11Pickup w/ plow and sander6480 | Corbiere and Sons Contracting813820210125-11Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8138 | 20210125-11 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit worked on grader across Mill road for morning until it broke downJohn S working on Mill Road for half day | 5 | C117-C120 | Mill Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813820210125-11L.O.A.2420 | Corbiere and Sons Contracting813820210125-11L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8138 | 20210125-11 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit worked on grader across Mill road for morning until it broke downJohn S working on Mill Road for half day | 5 | C117-C120 | Mill Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813820210125-11Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting813820210125-11Operator - Principle - After Jan 105375Inv#104 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8138 | 20210125-11 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit worked on grader across Mill road for morning until it broke downJohn S working on Mill Road for half day | 5 | C117-C120 | Mill Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813820210125-11Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting813820210125-11Operator - Intermdiate - After Jan 106420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8139 | 20210125-12 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan spent most of the day grader Lake A and then was floated to Prarie by Paul to start there. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting813920210125-12Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting813920210125-12Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv#104 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8139 | 20210125-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan spent most of the day grader Lake A and then was floated to Prarie by Paul to start there. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting813920210125-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting813920210125-12Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8139 | 20210125-12 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan spent most of the day grader Lake A and then was floated to Prarie by Paul to start there. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting813920210125-12Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting813920210125-12Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8139 | 20210125-12 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan spent most of the day grader Lake A and then was floated to Prarie by Paul to start there. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting813920210125-12L.O.A.2420 | Corbiere and Sons Contracting813920210125-12L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8139 | 20210125-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan spent most of the day grader Lake A and then was floated to Prarie by Paul to start there. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting813920210125-12Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting813920210125-12Operator - Principle - After Jan 10141050Inv#104 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8139 | 20210125-12 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan spent most of the day grader Lake A and then was floated to Prarie by Paul to start there. | 6 | C129-C151 | Lake A | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting813920210125-12Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting813920210125-12Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8140 | 20210125-13 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin spent day on pickup w/plow going to Del Lake | 6 | C129-C151 | Del Lake Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814020210125-13Pickup w/ plow4200 | Corbiere and Sons Contracting814020210125-13Pickup w/ plow4200Inv#104 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8140 | 20210125-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin spent day on pickup w/plow going to Del Lake | 6 | C129-C151 | Del Lake Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814020210125-13L.O.A.1210 | Corbiere and Sons Contracting814020210125-13L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8140 | 20210125-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin spent day on pickup w/plow going to Del Lake | 6 | C129-C151 | Del Lake Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814020210125-13Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting814020210125-13Operator - Principle - After Jan 104300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8141 | 20210125-14 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin spent day on pickup w/plow at Ripple | 6 | C198-C202 | Ripple Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814120210125-14Pickup w/ plow4200 | Corbiere and Sons Contracting814120210125-14Pickup w/ plow4200Inv#104 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8141 | 20210125-14 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin spent day on pickup w/plow at Ripple | 6 | C198-C202 | Ripple Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814120210125-14Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting814120210125-14Operator - Principle - After Jan 104300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8142 | 20210125-15 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin spent day on pickup w/plow at Hare Lake | 6 | C257-C267 | Hare Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814220210125-15Pickup w/ plow4200 | Corbiere and Sons Contracting814220210125-15Pickup w/ plow4200Inv#104 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8142 | 20210125-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin spent day on pickup w/plow at Hare Lake | 6 | C257-C267 | Hare Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting814220210125-15Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting814220210125-15Operator - Principle - After Jan 104300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8187 | 20210125-18 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-241 - Hwy entrance. | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818720210125-18Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting818720210125-18Excavator - 36 ton- After Jan 10121763.52Inv#104 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8187 | 20210125-18 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-241 - Hwy entrance. | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818720210125-18Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting818720210125-18Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#104 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8187 | 20210125-18 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-241 - Hwy entrance. | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818720210125-18Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting818720210125-18Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#104 | [5 empty] | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8187 | 20210125-18 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-241 - Hwy entrance. | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818720210125-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting818720210125-18Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8187 | 20210125-18 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-241 - Hwy entrance. | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818720210125-18Foreman2190 | Corbiere and Sons Contracting818720210125-18Foreman2190Inv#104 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8187 | 20210125-18 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-241 - Hwy entrance. | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818720210125-18L.O.A.1210 | Corbiere and Sons Contracting818720210125-18L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8187 | 20210125-18 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on road for cranes from C-241 - Hwy entrance. | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818720210125-18Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting818720210125-18Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8189 | 20210125-20 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed snow from float turn around to WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818920210125-20Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting818920210125-20Dozer D6 or equal- After Jan 106788.88Inv#104 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8189 | 20210125-20 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed snow from float turn around to WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818920210125-20Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting818920210125-20Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8189 | 20210125-20 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed snow from float turn around to WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818920210125-20L.O.A.1210 | Corbiere and Sons Contracting818920210125-20L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8189 | 20210125-20 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed snow from float turn around to WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44230 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818920210125-20Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting818920210125-20Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8323 | 20210125-22 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-01-25 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie spent all day fixing road from C-150 to C-145 on 350X4 | 6 | C129-C151 | Lake A | 0 | 44237 |  | 36 | 44242 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting832320210125-22Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting832320210125-22Excavator - 36 ton- After Jan 10101469.6Inv#109 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8323 | 20210125-22 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-25 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie spent all day fixing road from C-150 to C-145 on 350X4 | 6 | C129-C151 | Lake A | 0 | 44237 |  | 36 | 44242 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting832320210125-22Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting832320210125-22Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8323 | 20210125-22 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-25 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie spent all day fixing road from C-150 to C-145 on 350X4 | 6 | C129-C151 | Lake A | 0 | 44237 |  | 36 | 44242 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting832320210125-22L.O.A.1210 | Corbiere and Sons Contracting832320210125-22L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8323 | 20210125-22 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-25 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie spent all day fixing road from C-150 to C-145 on 350X4 | 6 | C129-C151 | Lake A | 0 | 44237 |  | 36 | 44242 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting832320210125-22Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting832320210125-22Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8324 | 20210125-23 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-01-25 |  |  |  |  | 1 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | EX-08 walked into Del Lake and cleared around towers C-186- C-188 | 6 | C186-C195 | Del Lake | 0 | 44237 | [9 empty] | 06 | Corbiere and Sons Contracting832420210125-23Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting832420210125-23Excavator - 30 ton- After Jan 1081107.6 | [5 empty] | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8324 | 20210125-23 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-01-25 |  |  |  |  | 1 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | EX-08 walked into Del Lake and cleared around towers C-186- C-188 | 6 | C186-C195 | Del Lake | 0 | 44237 | [9 empty] | 06 | Corbiere and Sons Contracting832420210125-23Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting832420210125-23Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8324 | 20210125-23 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-25 |  |  |  |  | 1 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | EX-08 walked into Del Lake and cleared around towers C-186- C-188 | 6 | C186-C195 | Del Lake | 0 | 44237 | [9 empty] | 06 | Corbiere and Sons Contracting832420210125-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting832420210125-23Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8324 | 20210125-23 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-25 |  |  |  |  | 1 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | EX-08 walked into Del Lake and cleared around towers C-186- C-188 | 6 | C186-C195 | Del Lake | 0 | 44237 | [9 empty] | 06 | Corbiere and Sons Contracting832420210125-23L.O.A.1210 | Corbiere and Sons Contracting832420210125-23L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8324 | 20210125-23 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-01-25 |  |  |  |  | 1 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | EX-08 walked into Del Lake and cleared around towers C-186- C-188 | 6 | C186-C195 | Del Lake | 0 | 44237 | [9 empty] | 06 | Corbiere and Sons Contracting832420210125-23Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting832420210125-23Operator - Principle - After Jan 1010750 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8133 | 20210125-6 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel working on Gurney East | 3 | B191-B193 | Gurney East | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting813320210125-6Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting813320210125-6Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#104 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8133 | 20210125-6 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel working on Gurney East | 3 | B191-B193 | Gurney East | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting813320210125-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting813320210125-6Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8133 | 20210125-6 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel working on Gurney East | 3 | B191-B193 | Gurney East | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting813320210125-6L.O.A.1210 | Corbiere and Sons Contracting813320210125-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8133 | 20210125-6 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel working on Gurney East | 3 | B191-B193 | Gurney East | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting813320210125-6Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting813320210125-6Operator - Principle - After Jan 103225Inv#104 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8134 | 20210125-7 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel North Shore working on Grader across Little Gravel River RdRichard Pine new grader operator did orientation in the morning | 4 | B194-B210 | Little Gravel River Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting813420210125-7Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting813420210125-7Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#104 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8134 | 20210125-7 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel North Shore working on Grader across Little Gravel River RdRichard Pine new grader operator did orientation in the morning | 4 | B194-B210 | Little Gravel River Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting813420210125-7L.O.A.1210 | Corbiere and Sons Contracting813420210125-7L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8134 | 20210125-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel North Shore working on Grader across Little Gravel River RdRichard Pine new grader operator did orientation in the morning | 4 | B194-B210 | Little Gravel River Road | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting813420210125-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting813420210125-7Operator - Principle - After Jan 108600Inv#104 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8135 | 20210125-8 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader from Little Gravel to AntlerJohn S. with pickup w/plow and sander working across Antler. | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813520210125-8Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting813520210125-8Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#104 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8135 | 20210125-8 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader from Little Gravel to AntlerJohn S. with pickup w/plow and sander working across Antler. | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813520210125-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting813520210125-8Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8135 | 20210125-8 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader from Little Gravel to AntlerJohn S. with pickup w/plow and sander working across Antler. | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813520210125-8Pickup w/ plow and sander6480 | Corbiere and Sons Contracting813520210125-8Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8135 | 20210125-8 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader from Little Gravel to AntlerJohn S. with pickup w/plow and sander working across Antler. | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813520210125-8L.O.A.3630 | Corbiere and Sons Contracting813520210125-8L.O.A.3630Inv#104 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8135 | 20210125-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader from Little Gravel to AntlerJohn S. with pickup w/plow and sander working across Antler. | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813520210125-8Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting813520210125-8Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8135 | 20210125-8 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader from Little Gravel to AntlerJohn S. with pickup w/plow and sander working across Antler. | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813520210125-8Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting813520210125-8Operator - Intermdiate - After Jan 106420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8135 | 20210125-8 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader from Little Gravel to AntlerJohn S. with pickup w/plow and sander working across Antler. | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813520210125-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting813520210125-8Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8136 | 20210125-9 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 13.5 | Dynamic | 95.24 | 0 |  |  | 1714.23 | 222.8499 | 1937.0799 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent all day trying to keep up with snowfall on Cooks Road East and West. | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813620210125-9Grader - Cat 12 to 14 or equal- After Jan 1013.51714.23 | Corbiere and Sons Contracting813620210125-9Grader - Cat 12 to 14 or equal- After Jan 1013.51714.23Inv#104 | [5 empty] | 1 | 1714.23 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8136 | 20210125-9 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent all day trying to keep up with snowfall on Cooks Road East and West. | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813620210125-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting813620210125-9Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8136 | 20210125-9 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent all day trying to keep up with snowfall on Cooks Road East and West. | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813620210125-9L.O.A.1210 | Corbiere and Sons Contracting813620210125-9L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8136 | 20210125-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-01-25 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent all day trying to keep up with snowfall on Cooks Road East and West. | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting813620210125-9Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting813620210125-9Operator - Principle - After Jan 10141050Inv#104 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8165 | 20210126-11 | 53510211 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from North Shore yard to Stewart Lake to open road ahead of grinding operation | 2 | B030 - B044 | Stewart Lake | 0 | 44229 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting816520210126-11Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting816520210126-11Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8165 | 20210126-11 | 53510211 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 |  | 210 | 27.3 | 237.3 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from North Shore yard to Stewart Lake to open road ahead of grinding operation | 2 | B030 - B044 | Stewart Lake | 0 | 44229 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting816520210126-11Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting816520210126-11Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8199 | 20210126-15 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on culvert creek, cleaned snow in float turn around, floated hammer machine to Little Red Sucker, finished the day hammering on the way into Little Red Sucker. | 6 | C237-C243 | Culvert Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting819920210126-15Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting819920210126-15Excavator - 36 ton- After Jan 10121763.52Inv#104 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8199 | 20210126-15 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on culvert creek, cleaned snow in float turn around, floated hammer machine to Little Red Sucker, finished the day hammering on the way into Little Red Sucker. | 6 | C237-C243 | Culvert Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting819920210126-15Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting819920210126-15Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#104 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8199 | 20210126-15 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on culvert creek, cleaned snow in float turn around, floated hammer machine to Little Red Sucker, finished the day hammering on the way into Little Red Sucker. | 6 | C237-C243 | Culvert Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting819920210126-15Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting819920210126-15Excavator Hammer - 30 - 50 ton- After Jan 107443.66Inv#104 | [5 empty] | 1 | 443.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8199 | 20210126-15 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on culvert creek, cleaned snow in float turn around, floated hammer machine to Little Red Sucker, finished the day hammering on the way into Little Red Sucker. | 6 | C237-C243 | Culvert Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting819920210126-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting819920210126-15Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8199 | 20210126-15 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on culvert creek, cleaned snow in float turn around, floated hammer machine to Little Red Sucker, finished the day hammering on the way into Little Red Sucker. | 6 | C237-C243 | Culvert Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting819920210126-15Foreman2190 | Corbiere and Sons Contracting819920210126-15Foreman2190Inv#104 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8199 | 20210126-15 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on culvert creek, cleaned snow in float turn around, floated hammer machine to Little Red Sucker, finished the day hammering on the way into Little Red Sucker. | 6 | C237-C243 | Culvert Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting819920210126-15L.O.A.1210 | Corbiere and Sons Contracting819920210126-15L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8199 | 20210126-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on culvert creek, cleaned snow in float turn around, floated hammer machine to Little Red Sucker, finished the day hammering on the way into Little Red Sucker. | 6 | C237-C243 | Culvert Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting819920210126-15Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting819920210126-15Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8158 | 20210126-4 | 53510411 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow truck worked across Nishin and Gravel River Rd | 4 | B211-C010 | Gravel River Road | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting815820210126-4Pickup w/ plow11550 | Corbiere and Sons Contracting815820210126-4Pickup w/ plow11550Inv#104 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8158 | 20210126-4 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow truck worked across Nishin and Gravel River Rd | 4 | B211-C010 | Gravel River Road | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting815820210126-4L.O.A.1210 | Corbiere and Sons Contracting815820210126-4L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8158 | 20210126-4 | 53510411 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow truck worked across Nishin and Gravel River Rd | 4 | B211-C010 | Gravel River Road | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting815820210126-4Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting815820210126-4Operator - Intermdiate - After Jan 1011770Inv#104 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8159 | 20210126-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard spent full day on greader across Anter access roadsDustin on pickup w/plow and sander out for half day | 5 | C050-C069 | Antler Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting815920210126-5Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting815920210126-5Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#104 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8159 | 20210126-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard spent full day on greader across Anter access roadsDustin on pickup w/plow and sander out for half day | 5 | C050-C069 | Antler Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting815920210126-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting815920210126-5Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8159 | 20210126-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard spent full day on greader across Anter access roadsDustin on pickup w/plow and sander out for half day | 5 | C050-C069 | Antler Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting815920210126-5Pickup w/ plow and sander6480 | Corbiere and Sons Contracting815920210126-5Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8159 | 20210126-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard spent full day on greader across Anter access roadsDustin on pickup w/plow and sander out for half day | 5 | C050-C069 | Antler Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting815920210126-5L.O.A.2420 | Corbiere and Sons Contracting815920210126-5L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8159 | 20210126-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard spent full day on greader across Anter access roadsDustin on pickup w/plow and sander out for half day | 5 | C050-C069 | Antler Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting815920210126-5Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting815920210126-5Operator - Principle - After Jan 10171275Inv#104 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8160 | 20210126-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12 | Dynamic | 95.24 | 0 |  |  | 1523.76 | 198.0888 | 1721.8488 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Cooks Lake access roads again; still needs to clear C-096 and C-097 | 5 | C076-C116 | Cook Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting816020210126-6Grader - Cat 12 to 14 or equal- After Jan 10121523.76 | Corbiere and Sons Contracting816020210126-6Grader - Cat 12 to 14 or equal- After Jan 10121523.76Inv#104 | [5 empty] | 1 | 1523.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8160 | 20210126-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Cooks Lake access roads again; still needs to clear C-096 and C-097 | 5 | C076-C116 | Cook Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting816020210126-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting816020210126-6Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8160 | 20210126-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Cooks Lake access roads again; still needs to clear C-096 and C-097 | 5 | C076-C116 | Cook Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting816020210126-6L.O.A.1210 | Corbiere and Sons Contracting816020210126-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8160 | 20210126-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12.5 | HR |  |  | 75 | 0 | 937.5 | 121.875 | 1059.375 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Cooks Lake access roads again; still needs to clear C-096 and C-097 | 5 | C076-C116 | Cook Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting816020210126-6Operator - Principle - After Jan 1012.5937.5 | Corbiere and Sons Contracting816020210126-6Operator - Principle - After Jan 1012.5937.5Inv#104 | [5 empty] | 1 | 937.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8162 | 20210126-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan finished grading Del West and Prarie and then moved to Culvert Creek | 6 | C186-C195 | Del Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting816220210126-8Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting816220210126-8Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#104 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8162 | 20210126-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan finished grading Del West and Prarie and then moved to Culvert Creek | 6 | C186-C195 | Del Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting816220210126-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting816220210126-8Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8162 | 20210126-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan finished grading Del West and Prarie and then moved to Culvert Creek | 6 | C186-C195 | Del Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting816220210126-8L.O.A.1210 | Corbiere and Sons Contracting816220210126-8L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8162 | 20210126-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan finished grading Del West and Prarie and then moved to Culvert Creek | 6 | C186-C195 | Del Lake | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting816220210126-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting816220210126-8Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8163 | 20210126-9 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated grader from Del Lake to Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting816320210126-9Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting816320210126-9Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8163 | 20210126-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated grader from Del Lake to Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting816320210126-9L.O.A.1210 | Corbiere and Sons Contracting816320210126-9L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8163 | 20210126-9 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-26 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated grader from Del Lake to Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44229 |  | 50 | 44230 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting816320210126-9Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting816320210126-9Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8177 | 20210127-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin organized, supervised and plowed/sanded Mink | 6 | C244-C247 | Mink Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817720210127-10Pickup w/ plow and sander6480 | Corbiere and Sons Contracting817720210127-10Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8177 | 20210127-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin organized, supervised and plowed/sanded Mink | 6 | C244-C247 | Mink Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817720210127-10Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting817720210127-10Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8178 | 20210127-11 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry spent 2 hours to C-233 clearing snow with dozer | 6 | C219-C236 | Neys | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817820210127-11Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting817820210127-11Dozer D6 or equal- After Jan 102262.96Inv#104 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8178 | 20210127-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry spent 2 hours to C-233 clearing snow with dozer | 6 | C219-C236 | Neys | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817820210127-11L.O.A.1210 | Corbiere and Sons Contracting817820210127-11L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8178 | 20210127-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry spent 2 hours to C-233 clearing snow with dozer | 6 | C219-C236 | Neys | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817820210127-11Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting817820210127-11Operator - Principle - After Jan 102150Inv#104 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8180 | 20210127-13 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 98.61 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Regrading road from C-258 | 6 | C257-C267 | Hare Lake | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818020210127-13Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting818020210127-13Dozer D6 or equal- After Jan 105.5723.14Inv#104 | [5 empty] | 1 | 723.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8180 | 20210127-13 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Regrading road from C-258 | 6 | C257-C267 | Hare Lake | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818020210127-13Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting818020210127-13Excavator - 30 ton- After Jan 105.5761.475Inv#104 | [5 empty] | 1 | 761.475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8180 | 20210127-13 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Regrading road from C-258 | 6 | C257-C267 | Hare Lake | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818020210127-13Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting818020210127-13Excavator Thumb - 30 - 50 ton- After Jan 105.567.155Inv#104 | [5 empty] | 1 | 67.155 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8180 | 20210127-13 | 53510611 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5.5 | Dynamic | 103.54 | 0 |  |  | 759.275 | 98.7057 | 857.9807 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Regrading road from C-258 | 6 | C257-C267 | Hare Lake | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818020210127-13Rock Truck - 30 Ton- After Jan 105.5759.275 | Corbiere and Sons Contracting818020210127-13Rock Truck - 30 Ton- After Jan 105.5759.275Inv#104 | [5 empty] | 1 | 759.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8180 | 20210127-13 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Regrading road from C-258 | 6 | C257-C267 | Hare Lake | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818020210127-13L.O.A.3630 | Corbiere and Sons Contracting818020210127-13L.O.A.3630Inv#104 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8180 | 20210127-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Regrading road from C-258 | 6 | C257-C267 | Hare Lake | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818020210127-13Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting818020210127-13Operator - Principle - After Jan 1011825Inv#104 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8180 | 20210127-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Regrading road from C-258 | 6 | C257-C267 | Hare Lake | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting818020210127-13Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting818020210127-13Operator - Intermdiate - After Jan 105.5385Inv#104 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8203 | 20210127-18 | 53510211 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 6 | Dynamic | 60.7 | 0 |  |  | 485.58 | 63.1254 | 548.7054 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 and DZ-02 opened up B-036 - B-040 | 2 | B030 - B044 | Stewart Lake | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting820320210127-18Dozer - D5 or equal- After Jan 106485.58 | Corbiere and Sons Contracting820320210127-18Dozer - D5 or equal- After Jan 106485.58Inv#104 | [5 empty] | 1 | 485.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8203 | 20210127-18 | 53510211 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 and DZ-02 opened up B-036 - B-040 | 2 | B030 - B044 | Stewart Lake | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting820320210127-18Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting820320210127-18Dozer D6 or equal- After Jan 107920.36Inv#104 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8203 | 20210127-18 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 and DZ-02 opened up B-036 - B-040 | 2 | B030 - B044 | Stewart Lake | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting820320210127-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting820320210127-18Light Truck - Pick up- After Jan 102487.5Inv#104 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8203 | 20210127-18 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 and DZ-02 opened up B-036 - B-040 | 2 | B030 - B044 | Stewart Lake | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting820320210127-18Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting820320210127-18Operator - Principle - After Jan 10141050Inv#104 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8205 | 20210127-20 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820520210127-20Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting820520210127-20Excavator - 36 ton- After Jan 10121763.52Inv#104 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8205 | 20210127-20 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820520210127-20Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting820520210127-20Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#104 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8205 | 20210127-20 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820520210127-20Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting820520210127-20Excavator Hammer - 30 - 50 ton- After Jan 107443.66Inv#104 | [5 empty] | 1 | 443.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8205 | 20210127-20 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820520210127-20Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting820520210127-20Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8205 | 20210127-20 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820520210127-20Foreman2190 | Corbiere and Sons Contracting820520210127-20Foreman2190Inv#104 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8205 | 20210127-20 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820520210127-20L.O.A.1210 | Corbiere and Sons Contracting820520210127-20L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8205 | 20210127-20 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820520210127-20Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting820520210127-20Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8171 | 20210127-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Little Red Sucker CreekEvan ran grader all day at Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817120210127-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting817120210127-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#104 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8171 | 20210127-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Little Red Sucker CreekEvan ran grader all day at Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817120210127-4Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting817120210127-4Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8171 | 20210127-4 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Little Red Sucker CreekEvan ran grader all day at Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817120210127-4L.O.A.2420 | Corbiere and Sons Contracting817120210127-4L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8171 | 20210127-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Little Red Sucker CreekEvan ran grader all day at Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817120210127-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting817120210127-4Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8171 | 20210127-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Little Red Sucker CreekEvan ran grader all day at Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817120210127-4Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting817120210127-4Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8172 | 20210127-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7.5 | Dynamic | 95.24 | 0 |  |  | 952.35 | 123.8055 | 1076.1555 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine ran grader at Culvert Creek until 3pm | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817220210127-5Grader - Cat 12 to 14 or equal- After Jan 107.5952.35 | Corbiere and Sons Contracting817220210127-5Grader - Cat 12 to 14 or equal- After Jan 107.5952.35Inv#104 | [5 empty] | 1 | 952.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8172 | 20210127-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine ran grader at Culvert Creek until 3pm | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817220210127-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting817220210127-5Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8172 | 20210127-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine ran grader at Culvert Creek until 3pm | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817220210127-5L.O.A.1210 | Corbiere and Sons Contracting817220210127-5L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8172 | 20210127-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine ran grader at Culvert Creek until 3pm | 6 | C237-C243 | Culvert Creek | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817220210127-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting817220210127-5Operator - Principle - After Jan 108600Inv#104 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8173 | 20210127-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander truck cleared entrance and sanded Little Pic, 217-218. | 6 | C215-C218 | Little Pie River | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817320210127-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting817320210127-6Pickup w/ plow and sander4320Inv#104 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8173 | 20210127-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander truck cleared entrance and sanded Little Pic, 217-218. | 6 | C215-C218 | Little Pie River | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817320210127-6L.O.A.1210 | Corbiere and Sons Contracting817320210127-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8173 | 20210127-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander truck cleared entrance and sanded Little Pic, 217-218. | 6 | C215-C218 | Little Pie River | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817320210127-6Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting817320210127-6Operator - Intermdiate - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8174 | 20210127-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander truck cleared entrance and sanded Jackfish | 6 | C152-C154 | Jackfish Lake | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817420210127-7Pickup w/ plow and sander4320 | Corbiere and Sons Contracting817420210127-7Pickup w/ plow and sander4320Inv#104 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8174 | 20210127-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander truck cleared entrance and sanded Jackfish | 6 | C152-C154 | Jackfish Lake | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817420210127-7Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting817420210127-7Operator - Intermdiate - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8175 | 20210127-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander truck cleared entrance and sanded Lake A | 6 | C129-C151 | Lake A | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817520210127-8Pickup w/ plow and sander3240 | Corbiere and Sons Contracting817520210127-8Pickup w/ plow and sander3240Inv#104 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8175 | 20210127-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander truck cleared entrance and sanded Lake A | 6 | C129-C151 | Lake A | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817520210127-8Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting817520210127-8Operator - Intermdiate - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8176 | 20210127-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin organized, supervised and plowed/sanded Santoy Mountain. | 6 | C155-C157 | Santoy Mountain | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817620210127-9Pickup w/ plow and sander6480 | Corbiere and Sons Contracting817620210127-9Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8176 | 20210127-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin organized, supervised and plowed/sanded Santoy Mountain. | 6 | C155-C157 | Santoy Mountain | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817620210127-9L.O.A.1210 | Corbiere and Sons Contracting817620210127-9L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8176 | 20210127-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-27 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin organized, supervised and plowed/sanded Santoy Mountain. | 6 | C155-C157 | Santoy Mountain | 0 | 44230 |  | 50 | 44231 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting817620210127-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting817620210127-9Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8259 | 20210128-10 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul floated Len's Grader from Little Red Sucker to Santoy Mountain and then Len worked there for rest of the day. | 6 | C155-C157 | Santoy Mountain | 0 | 44232 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting825920210128-10Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting825920210128-10Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#104 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8259 | 20210128-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul floated Len's Grader from Little Red Sucker to Santoy Mountain and then Len worked there for rest of the day. | 6 | C155-C157 | Santoy Mountain | 0 | 44232 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting825920210128-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting825920210128-10Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8259 | 20210128-10 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul floated Len's Grader from Little Red Sucker to Santoy Mountain and then Len worked there for rest of the day. | 6 | C155-C157 | Santoy Mountain | 0 | 44232 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting825920210128-10Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting825920210128-10Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8259 | 20210128-10 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul floated Len's Grader from Little Red Sucker to Santoy Mountain and then Len worked there for rest of the day. | 6 | C155-C157 | Santoy Mountain | 0 | 44232 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting825920210128-10L.O.A.2420 | Corbiere and Sons Contracting825920210128-10L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8259 | 20210128-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul floated Len's Grader from Little Red Sucker to Santoy Mountain and then Len worked there for rest of the day. | 6 | C155-C157 | Santoy Mountain | 0 | 44232 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting825920210128-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting825920210128-10Operator - Principle - After Jan 1011825Inv#104 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8259 | 20210128-10 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul floated Len's Grader from Little Red Sucker to Santoy Mountain and then Len worked there for rest of the day. | 6 | C155-C157 | Santoy Mountain | 0 | 44232 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting825920210128-10Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting825920210128-10Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8261 | 20210128-12 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Chris and Jesse cleared snow on Hare Lake from C-266 - C-267 | 6 | C257-C267 | Hare Lake | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826120210128-12Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting826120210128-12Dozer D6 or equal- After Jan 105657.4Inv#104 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8261 | 20210128-12 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Chris and Jesse cleared snow on Hare Lake from C-266 - C-267 | 6 | C257-C267 | Hare Lake | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826120210128-12Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting826120210128-12Excavator - 30 ton- After Jan 105692.25Inv#104 | [5 empty] | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8261 | 20210128-12 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Chris and Jesse cleared snow on Hare Lake from C-266 - C-267 | 6 | C257-C267 | Hare Lake | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826120210128-12Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting826120210128-12Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#104 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8261 | 20210128-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Chris and Jesse cleared snow on Hare Lake from C-266 - C-267 | 6 | C257-C267 | Hare Lake | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826120210128-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting826120210128-12Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8261 | 20210128-12 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Chris and Jesse cleared snow on Hare Lake from C-266 - C-267 | 6 | C257-C267 | Hare Lake | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826120210128-12L.O.A.2420 | Corbiere and Sons Contracting826120210128-12L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8261 | 20210128-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Chris and Jesse cleared snow on Hare Lake from C-266 - C-267 | 6 | C257-C267 | Hare Lake | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826120210128-12Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting826120210128-12Operator - Principle - After Jan 1010750Inv#104 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8207 | 20210128-6 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820720210128-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting820720210128-6Excavator - 36 ton- After Jan 10121763.52Inv#104 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8207 | 20210128-6 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820720210128-6Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting820720210128-6Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#104 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8207 | 20210128-6 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820720210128-6Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting820720210128-6Excavator Hammer - 30 - 50 ton- After Jan 108507.04Inv#104 | [5 empty] | 1 | 507.04 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8207 | 20210128-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820720210128-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting820720210128-6Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8207 | 20210128-6 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820720210128-6Foreman2190 | Corbiere and Sons Contracting820720210128-6Foreman2190Inv#104 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8207 | 20210128-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820720210128-6L.O.A.1210 | Corbiere and Sons Contracting820720210128-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8207 | 20210128-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting820720210128-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting820720210128-6Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8257 | 20210128-8 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Cooks Lake to Jackpine - 2 flaggers neededGary's grader was floated to Jackpine, cleared B-159-B160 | 3 | B159-B161 | Jackpine | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825720210128-8Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting825720210128-8Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#104 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8257 | 20210128-8 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Cooks Lake to Jackpine - 2 flaggers neededGary's grader was floated to Jackpine, cleared B-159-B160 | 3 | B159-B161 | Jackpine | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825720210128-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting825720210128-8Light Truck - Pick up- After Jan 102487.5Inv#104 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8257 | 20210128-8 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Cooks Lake to Jackpine - 2 flaggers neededGary's grader was floated to Jackpine, cleared B-159-B160 | 3 | B159-B161 | Jackpine | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825720210128-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting825720210128-8Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8257 | 20210128-8 | 53510311 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Cooks Lake to Jackpine - 2 flaggers neededGary's grader was floated to Jackpine, cleared B-159-B160 | 3 | B159-B161 | Jackpine | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825720210128-8L.O.A.4840 | Corbiere and Sons Contracting825720210128-8L.O.A.4840Inv#104 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8257 | 20210128-8 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Cooks Lake to Jackpine - 2 flaggers neededGary's grader was floated to Jackpine, cleared B-159-B160 | 3 | B159-B161 | Jackpine | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825720210128-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting825720210128-8Operator - Principle - After Jan 108600Inv#104 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8257 | 20210128-8 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Cooks Lake to Jackpine - 2 flaggers neededGary's grader was floated to Jackpine, cleared B-159-B160 | 3 | B159-B161 | Jackpine | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825720210128-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting825720210128-8Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8257 | 20210128-8 | 53510311 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Cooks Lake to Jackpine - 2 flaggers neededGary's grader was floated to Jackpine, cleared B-159-B160 | 3 | B159-B161 | Jackpine | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825720210128-8Labourer - General - After Jan 108480 | Corbiere and Sons Contracting825720210128-8Labourer - General - After Jan 108480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8258 | 20210128-9 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Jackpine to Doghead - 2 flaggers requiredGarys grader was floated to Doghead to continueJohn S. worked on pickup w/ plow and sander across DogheadDustin working on plow truck and coordinating activities | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825820210128-9Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting825820210128-9Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#104 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8258 | 20210128-9 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Jackpine to Doghead - 2 flaggers requiredGarys grader was floated to Doghead to continueJohn S. worked on pickup w/ plow and sander across DogheadDustin working on plow truck and coordinating activities | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825820210128-9Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting825820210128-9Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8258 | 20210128-9 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 12 | HR | 0 | 0 |  |  | 600 | 78 | 678 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Jackpine to Doghead - 2 flaggers requiredGarys grader was floated to Doghead to continueJohn S. worked on pickup w/ plow and sander across DogheadDustin working on plow truck and coordinating activities | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825820210128-9Pickup w/ plow12600 | Corbiere and Sons Contracting825820210128-9Pickup w/ plow12600Inv#104 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8258 | 20210128-9 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Jackpine to Doghead - 2 flaggers requiredGarys grader was floated to Doghead to continueJohn S. worked on pickup w/ plow and sander across DogheadDustin working on plow truck and coordinating activities | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825820210128-9Pickup w/ plow and sander11880 | Corbiere and Sons Contracting825820210128-9Pickup w/ plow and sander11880Inv#104 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8258 | 20210128-9 | 53510311 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Jackpine to Doghead - 2 flaggers requiredGarys grader was floated to Doghead to continueJohn S. worked on pickup w/ plow and sander across DogheadDustin working on plow truck and coordinating activities | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825820210128-9L.O.A.2420 | Corbiere and Sons Contracting825820210128-9L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8258 | 20210128-9 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Jackpine to Doghead - 2 flaggers requiredGarys grader was floated to Doghead to continueJohn S. worked on pickup w/ plow and sander across DogheadDustin working on plow truck and coordinating activities | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825820210128-9Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting825820210128-9Operator - Principle - After Jan 10171275Inv#104 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8258 | 20210128-9 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Jackpine to Doghead - 2 flaggers requiredGarys grader was floated to Doghead to continueJohn S. worked on pickup w/ plow and sander across DogheadDustin working on plow truck and coordinating activities | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825820210128-9Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting825820210128-9Operator - Intermdiate - After Jan 1011770Inv#104 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8258 | 20210128-9 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Jackpine to Doghead - 2 flaggers requiredGarys grader was floated to Doghead to continueJohn S. worked on pickup w/ plow and sander across DogheadDustin working on plow truck and coordinating activities | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825820210128-9Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting825820210128-9Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8258 | 20210128-9 | 53510311 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-01-28 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Grader from Jackpine to Doghead - 2 flaggers requiredGarys grader was floated to Doghead to continueJohn S. worked on pickup w/ plow and sander across DogheadDustin working on plow truck and coordinating activities | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting825820210128-9Labourer - General - After Jan 108480 | Corbiere and Sons Contracting825820210128-9Labourer - General - After Jan 108480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8263 | 20210129-10 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Culvert Creek to Mink Creek ; Ben and Jayden fallged for move to MinkEvan worked on grader across MinkDustin plowing access entrances and coordinator/planning | 6 | C244-C247 | Mink Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826320210129-10Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting826320210129-10Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#104 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8263 | 20210129-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Culvert Creek to Mink Creek ; Ben and Jayden fallged for move to MinkEvan worked on grader across MinkDustin plowing access entrances and coordinator/planning | 6 | C244-C247 | Mink Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826320210129-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting826320210129-10Light Truck - Pick up- After Jan 102487.5Inv#104 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8263 | 20210129-10 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Culvert Creek to Mink Creek ; Ben and Jayden fallged for move to MinkEvan worked on grader across MinkDustin plowing access entrances and coordinator/planning | 6 | C244-C247 | Mink Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826320210129-10Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting826320210129-10Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8263 | 20210129-10 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Culvert Creek to Mink Creek ; Ben and Jayden fallged for move to MinkEvan worked on grader across MinkDustin plowing access entrances and coordinator/planning | 6 | C244-C247 | Mink Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826320210129-10Pickup w/ plow4200 | Corbiere and Sons Contracting826320210129-10Pickup w/ plow4200Inv#104 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8263 | 20210129-10 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Culvert Creek to Mink Creek ; Ben and Jayden fallged for move to MinkEvan worked on grader across MinkDustin plowing access entrances and coordinator/planning | 6 | C244-C247 | Mink Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826320210129-10L.O.A.4840 | Corbiere and Sons Contracting826320210129-10L.O.A.4840Inv#104 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8263 | 20210129-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Culvert Creek to Mink Creek ; Ben and Jayden fallged for move to MinkEvan worked on grader across MinkDustin plowing access entrances and coordinator/planning | 6 | C244-C247 | Mink Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826320210129-10Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting826320210129-10Operator - Principle - After Jan 1010750Inv#104 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8263 | 20210129-10 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Culvert Creek to Mink Creek ; Ben and Jayden fallged for move to MinkEvan worked on grader across MinkDustin plowing access entrances and coordinator/planning | 6 | C244-C247 | Mink Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826320210129-10Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting826320210129-10Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8263 | 20210129-10 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Culvert Creek to Mink Creek ; Ben and Jayden fallged for move to MinkEvan worked on grader across MinkDustin plowing access entrances and coordinator/planning | 6 | C244-C247 | Mink Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826320210129-10Labourer - General - After Jan 106360 | Corbiere and Sons Contracting826320210129-10Labourer - General - After Jan 106360Inv#104 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8264 | 20210129-11 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated grader from Santoy Mountain to Lake A; Len floated to Lake A at the end of the dayJohn worked on pickup w/plow and sader across Lake ADustin plowing access entrances and coordinator/planning | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826420210129-11Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting826420210129-11Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8264 | 20210129-11 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated grader from Santoy Mountain to Lake A; Len floated to Lake A at the end of the dayJohn worked on pickup w/plow and sader across Lake ADustin plowing access entrances and coordinator/planning | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826420210129-11Pickup w/ plow4200 | Corbiere and Sons Contracting826420210129-11Pickup w/ plow4200Inv#104 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8264 | 20210129-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated grader from Santoy Mountain to Lake A; Len floated to Lake A at the end of the dayJohn worked on pickup w/plow and sader across Lake ADustin plowing access entrances and coordinator/planning | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826420210129-11Pickup w/ plow and sander6480 | Corbiere and Sons Contracting826420210129-11Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8264 | 20210129-11 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated grader from Santoy Mountain to Lake A; Len floated to Lake A at the end of the dayJohn worked on pickup w/plow and sader across Lake ADustin plowing access entrances and coordinator/planning | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826420210129-11L.O.A.2420 | Corbiere and Sons Contracting826420210129-11L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8264 | 20210129-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated grader from Santoy Mountain to Lake A; Len floated to Lake A at the end of the dayJohn worked on pickup w/plow and sader across Lake ADustin plowing access entrances and coordinator/planning | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826420210129-11Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting826420210129-11Operator - Principle - After Jan 106450Inv#104 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8264 | 20210129-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated grader from Santoy Mountain to Lake A; Len floated to Lake A at the end of the dayJohn worked on pickup w/plow and sader across Lake ADustin plowing access entrances and coordinator/planning | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826420210129-11Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting826420210129-11Operator - Intermdiate - After Jan 106420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8264 | 20210129-11 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated grader from Santoy Mountain to Lake A; Len floated to Lake A at the end of the dayJohn worked on pickup w/plow and sader across Lake ADustin plowing access entrances and coordinator/planning | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826420210129-11Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting826420210129-11Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8265 | 20210129-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John worked on pickup w/plow and sander across Hare Lake. | 6 | C257-C267 | Hare Lake | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826520210129-12Pickup w/ plow and sander6480 | Corbiere and Sons Contracting826520210129-12Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8265 | 20210129-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John worked on pickup w/plow and sander across Hare Lake. | 6 | C257-C267 | Hare Lake | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826520210129-12Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting826520210129-12Operator - Intermdiate - After Jan 106420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8266 | 20210129-13 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked across Santoy Mountain all day and was floated at the end. | 6 | C155-C157 | Santoy Mountain | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826620210129-13Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting826620210129-13Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#104 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8266 | 20210129-13 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked across Santoy Mountain all day and was floated at the end. | 6 | C155-C157 | Santoy Mountain | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826620210129-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting826620210129-13Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8266 | 20210129-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked across Santoy Mountain all day and was floated at the end. | 6 | C155-C157 | Santoy Mountain | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826620210129-13L.O.A.1210 | Corbiere and Sons Contracting826620210129-13L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8266 | 20210129-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked across Santoy Mountain all day and was floated at the end. | 6 | C155-C157 | Santoy Mountain | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826620210129-13Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting826620210129-13Operator - Principle - After Jan 109675Inv#104 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8267 | 20210129-14 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader across Culvert CreekDustin plowing access entrances and coordinator/planning | 6 | C237-C243 | Culvert Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826720210129-14Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting826720210129-14Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#104 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8267 | 20210129-14 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader across Culvert CreekDustin plowing access entrances and coordinator/planning | 6 | C237-C243 | Culvert Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826720210129-14Pickup w/ plow4200 | Corbiere and Sons Contracting826720210129-14Pickup w/ plow4200Inv#104 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8267 | 20210129-14 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader across Culvert CreekDustin plowing access entrances and coordinator/planning | 6 | C237-C243 | Culvert Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting826720210129-14Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting826720210129-14Operator - Principle - After Jan 1010750Inv#104 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8428 | 20210129-17 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1847.78 | unit |  |  |  |  | 1847.78 | 240.2114 | 2087.9914 | 2021-01-29 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Sand provided for WF6 | 6 | C257-C267 | Hare lake | 0 | 44246 |  | 36 | 44246 | 18320 | Winter Control Sand |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting842820210129-173rd Party Charges1847.781847.78 | Corbiere and Sons Contracting842820210129-173rd Party Charges1847.781847.78Inv#109 | [5 empty] | 1 | 1847.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8210 | 20210129-6 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting821020210129-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting821020210129-6Excavator - 36 ton- After Jan 10121763.52Inv#104 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8210 | 20210129-6 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting821020210129-6Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting821020210129-6Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#104 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8210 | 20210129-6 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting821020210129-6Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting821020210129-6Excavator Hammer - 30 - 50 ton- After Jan 107443.66Inv#104 | [5 empty] | 1 | 443.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8210 | 20210129-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting821020210129-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting821020210129-6Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8210 | 20210129-6 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting821020210129-6Foreman2190 | Corbiere and Sons Contracting821020210129-6Foreman2190Inv#104 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8210 | 20210129-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting821020210129-6L.O.A.1210 | Corbiere and Sons Contracting821020210129-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8210 | 20210129-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44232 |  | 50 | 44232 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting821020210129-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting821020210129-6Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8262 | 20210129-9 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader only ran for 5 hours at Doghead, broke down twice during the day. | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting826220210129-9Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting826220210129-9Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#104 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8262 | 20210129-9 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader only ran for 5 hours at Doghead, broke down twice during the day. | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting826220210129-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting826220210129-9Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8262 | 20210129-9 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader only ran for 5 hours at Doghead, broke down twice during the day. | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting826220210129-9L.O.A.1210 | Corbiere and Sons Contracting826220210129-9L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8262 | 20210129-9 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-01-29 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader only ran for 5 hours at Doghead, broke down twice during the day. | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting826220210129-9Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting826220210129-9Operator - Principle - After Jan 105375Inv#104 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8278 | 20210130-10 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked across Lake A for the day - Grader broke down for 3 hours midday. | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting827820210130-10Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting827820210130-10Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#104 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8278 | 20210130-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked across Lake A for the day - Grader broke down for 3 hours midday. | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting827820210130-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting827820210130-10Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8278 | 20210130-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked across Lake A for the day - Grader broke down for 3 hours midday. | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting827820210130-10L.O.A.1210 | Corbiere and Sons Contracting827820210130-10L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8278 | 20210130-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked across Lake A for the day - Grader broke down for 3 hours midday. | 6 | C129-C151 | Lake A | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting827820210130-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting827820210130-10Operator - Principle - After Jan 1011825Inv#104 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8281 | 20210130-13 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828120210130-13Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting828120210130-13Excavator - 36 ton- After Jan 10121763.52Inv#104 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8281 | 20210130-13 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828120210130-13Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting828120210130-13Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#104 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8281 | 20210130-13 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828120210130-13Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting828120210130-13Excavator Hammer - 30 - 50 ton- After Jan 107443.66Inv#104 | [5 empty] | 1 | 443.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8281 | 20210130-13 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828120210130-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting828120210130-13Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8281 | 20210130-13 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828120210130-13Foreman2190 | Corbiere and Sons Contracting828120210130-13Foreman2190Inv#104 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8281 | 20210130-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828120210130-13L.O.A.1210 | Corbiere and Sons Contracting828120210130-13L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8281 | 20210130-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828120210130-13Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting828120210130-13Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8273 | 20210130-5 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Blair Lake RdEvan on grader at Blair Lake all dayDustin on Pickup w/plow opening up entrance way to Blair | 3 | B182-B186 | Blair Lake Road | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827320210130-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting827320210130-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#104 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8273 | 20210130-5 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Blair Lake RdEvan on grader at Blair Lake all dayDustin on Pickup w/plow opening up entrance way to Blair | 3 | B182-B186 | Blair Lake Road | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827320210130-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting827320210130-5Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8273 | 20210130-5 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Blair Lake RdEvan on grader at Blair Lake all dayDustin on Pickup w/plow opening up entrance way to Blair | 3 | B182-B186 | Blair Lake Road | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827320210130-5Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting827320210130-5Tractor Trailer - 60 Ton- After Jan 105611.95Inv#104 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8273 | 20210130-5 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Blair Lake RdEvan on grader at Blair Lake all dayDustin on Pickup w/plow opening up entrance way to Blair | 3 | B182-B186 | Blair Lake Road | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827320210130-5Pickup w/ plow6300 | Corbiere and Sons Contracting827320210130-5Pickup w/ plow6300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8273 | 20210130-5 | 53510311 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Blair Lake RdEvan on grader at Blair Lake all dayDustin on Pickup w/plow opening up entrance way to Blair | 3 | B182-B186 | Blair Lake Road | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827320210130-5L.O.A.3630 | Corbiere and Sons Contracting827320210130-5L.O.A.3630Inv#104 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8273 | 20210130-5 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Blair Lake RdEvan on grader at Blair Lake all dayDustin on Pickup w/plow opening up entrance way to Blair | 3 | B182-B186 | Blair Lake Road | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827320210130-5Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting827320210130-5Operator - Principle - After Jan 10181350Inv#104 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8273 | 20210130-5 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Blair Lake RdEvan on grader at Blair Lake all dayDustin on Pickup w/plow opening up entrance way to Blair | 3 | B182-B186 | Blair Lake Road | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827320210130-5Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting827320210130-5Driver - AZ - After Jan 105350Inv#104 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8274 | 20210130-6 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John sanded areas across work front 3, Doghead and Maatas | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827420210130-6Pickup w/ plow and sander6480 | Corbiere and Sons Contracting827420210130-6Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8274 | 20210130-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John sanded areas across work front 3, Doghead and Maatas | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827420210130-6L.O.A.1210 | Corbiere and Sons Contracting827420210130-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8274 | 20210130-6 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John sanded areas across work front 3, Doghead and Maatas | 3 | B100-B109 | Doghead | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827420210130-6Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting827420210130-6Operator - Intermdiate - After Jan 106420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8275 | 20210130-7 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John sanded areas across work front 3, Doghead and Maatas | 3 | B088-B099 | Maata's Road | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827520210130-7Pickup w/ plow and sander5400 | Corbiere and Sons Contracting827520210130-7Pickup w/ plow and sander5400Inv#104 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8275 | 20210130-7 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John sanded areas across work front 3, Doghead and Maatas | 3 | B088-B099 | Maata's Road | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827520210130-7L.O.A.1210 | Corbiere and Sons Contracting827520210130-7L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8275 | 20210130-7 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John sanded areas across work front 3, Doghead and Maatas | 3 | B088-B099 | Maata's Road | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting827520210130-7Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting827520210130-7Operator - Intermdiate - After Jan 105350Inv#104 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8276 | 20210130-8 | 53510211 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Squash Valley Rd, Gary worked in this area; Dustin opened up entrances. | 2 | B045 - B053 | Squaw Valley | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827620210130-8Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting827620210130-8Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#104 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8276 | 20210130-8 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Squash Valley Rd, Gary worked in this area; Dustin opened up entrances. | 2 | B045 - B053 | Squaw Valley | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827620210130-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting827620210130-8Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8276 | 20210130-8 | 53510211 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Squash Valley Rd, Gary worked in this area; Dustin opened up entrances. | 2 | B045 - B053 | Squaw Valley | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827620210130-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting827620210130-8Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8276 | 20210130-8 | 53510211 | Access | 0 | Pickup w/ plow | 50 | 3 | HR | 0 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Squash Valley Rd, Gary worked in this area; Dustin opened up entrances. | 2 | B045 - B053 | Squaw Valley | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827620210130-8Pickup w/ plow3150 | Corbiere and Sons Contracting827620210130-8Pickup w/ plow3150Inv#104 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8276 | 20210130-8 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Squash Valley Rd, Gary worked in this area; Dustin opened up entrances. | 2 | B045 - B053 | Squaw Valley | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827620210130-8L.O.A.1210 | Corbiere and Sons Contracting827620210130-8L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8276 | 20210130-8 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Squash Valley Rd, Gary worked in this area; Dustin opened up entrances. | 2 | B045 - B053 | Squaw Valley | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827620210130-8Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting827620210130-8Operator - Principle - After Jan 109675Inv#104 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8276 | 20210130-8 | 53510211 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Squash Valley Rd, Gary worked in this area; Dustin opened up entrances. | 2 | B045 - B053 | Squaw Valley | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827620210130-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting827620210130-8Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8277 | 20210130-9 | 53510211 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Lofty Davies, Gary worked in this area; Dustin opened up entrances. | 2 | B054 - B064 | Lofty Davies | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827720210130-9Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting827720210130-9Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#104 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8277 | 20210130-9 | 53510211 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Lofty Davies, Gary worked in this area; Dustin opened up entrances. | 2 | B054 - B064 | Lofty Davies | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827720210130-9Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting827720210130-9Tractor Trailer - 60 Ton- After Jan 103367.17Inv#104 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8277 | 20210130-9 | 53510211 | Access | 0 | Pickup w/ plow | 50 | 3 | HR | 0 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Lofty Davies, Gary worked in this area; Dustin opened up entrances. | 2 | B054 - B064 | Lofty Davies | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827720210130-9Pickup w/ plow3150 | Corbiere and Sons Contracting827720210130-9Pickup w/ plow3150Inv#104 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8277 | 20210130-9 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Lofty Davies, Gary worked in this area; Dustin opened up entrances. | 2 | B054 - B064 | Lofty Davies | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827720210130-9Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting827720210130-9Operator - Principle - After Jan 109675Inv#104 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8277 | 20210130-9 | 53510211 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-30 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Lofty Davies, Gary worked in this area; Dustin opened up entrances. | 2 | B054 - B064 | Lofty Davies | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting827720210130-9Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting827720210130-9Driver - AZ - After Jan 103210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8296 | 20210131-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John, Dan spent day capping the road at C-239 - C-231 as pickups were unable to access the area due to snow fills loosening up. | 6 | C237-C243 | Culvert Creek | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829620210131-10Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting829620210131-10Dozer D6 or equal- After Jan 1010.51380.54Inv#104 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8296 | 20210131-10 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John, Dan spent day capping the road at C-239 - C-231 as pickups were unable to access the area due to snow fills loosening up. | 6 | C237-C243 | Culvert Creek | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829620210131-10Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting829620210131-10Excavator - 30 ton- After Jan 1010.51453.725Inv#104 | [5 empty] | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8296 | 20210131-10 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John, Dan spent day capping the road at C-239 - C-231 as pickups were unable to access the area due to snow fills loosening up. | 6 | C237-C243 | Culvert Creek | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829620210131-10Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting829620210131-10Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#104 | [5 empty] | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8296 | 20210131-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John, Dan spent day capping the road at C-239 - C-231 as pickups were unable to access the area due to snow fills loosening up. | 6 | C237-C243 | Culvert Creek | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829620210131-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting829620210131-10Light Truck - Pick up- After Jan 102487.5Inv#104 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8296 | 20210131-10 | 53510611 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John, Dan spent day capping the road at C-239 - C-231 as pickups were unable to access the area due to snow fills loosening up. | 6 | C237-C243 | Culvert Creek | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829620210131-10Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting829620210131-10Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#104 | [5 empty] | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8296 | 20210131-10 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John, Dan spent day capping the road at C-239 - C-231 as pickups were unable to access the area due to snow fills loosening up. | 6 | C237-C243 | Culvert Creek | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829620210131-10L.O.A.3630 | Corbiere and Sons Contracting829620210131-10L.O.A.3630Inv#104 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8296 | 20210131-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John, Dan spent day capping the road at C-239 - C-231 as pickups were unable to access the area due to snow fills loosening up. | 6 | C237-C243 | Culvert Creek | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829620210131-10Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting829620210131-10Operator - Principle - After Jan 10221650Inv#104 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8296 | 20210131-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John, Dan spent day capping the road at C-239 - C-231 as pickups were unable to access the area due to snow fills loosening up. | 6 | C237-C243 | Culvert Creek | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829620210131-10Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting829620210131-10Operator - Intermdiate - After Jan 1011770Inv#104 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8321 | 20210131-12 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11.5 | Dynamic | 95.24 | 0 |  |  | 1460.27 | 189.8351 | 1650.1051 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard pine and grader working in Landfill for snow removal to Tower B-084 and working to highway. | 3 | B078-B084 | Red Rock No. 7 | 0 | 44228 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832120210131-12Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27 | Corbiere and Sons Contracting832120210131-12Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27Inv#104 | [5 empty] | 1 | 1460.27 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8321 | 20210131-12 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard pine and grader working in Landfill for snow removal to Tower B-084 and working to highway. | 3 | B078-B084 | Red Rock No. 7 | 0 | 44228 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832120210131-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting832120210131-12Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8321 | 20210131-12 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard pine and grader working in Landfill for snow removal to Tower B-084 and working to highway. | 3 | B078-B084 | Red Rock No. 7 | 0 | 44228 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832120210131-12L.O.A.1210 | Corbiere and Sons Contracting832120210131-12L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8321 | 20210131-12 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard pine and grader working in Landfill for snow removal to Tower B-084 and working to highway. | 3 | B078-B084 | Red Rock No. 7 | 0 | 44228 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832120210131-12Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting832120210131-12Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8287 | 20210131-5 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. Float EXC-22 and EXC-21 to Hare Lake road to begin work in that area. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828720210131-5Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting828720210131-5Excavator - 36 ton- After Jan 10121763.52Inv#104 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8287 | 20210131-5 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. Float EXC-22 and EXC-21 to Hare Lake road to begin work in that area. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828720210131-5Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting828720210131-5Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#104 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8287 | 20210131-5 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. Float EXC-22 and EXC-21 to Hare Lake road to begin work in that area. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828720210131-5Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting828720210131-5Excavator Hammer - 30 - 50 ton- After Jan 108507.04Inv#104 | [5 empty] | 1 | 507.04 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8287 | 20210131-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. Float EXC-22 and EXC-21 to Hare Lake road to begin work in that area. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828720210131-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting828720210131-5Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8287 | 20210131-5 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. Float EXC-22 and EXC-21 to Hare Lake road to begin work in that area. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828720210131-5Foreman2190 | Corbiere and Sons Contracting828720210131-5Foreman2190Inv#104 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8287 | 20210131-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. Float EXC-22 and EXC-21 to Hare Lake road to begin work in that area. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828720210131-5L.O.A.1210 | Corbiere and Sons Contracting828720210131-5L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8287 | 20210131-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Little Red Sucker. Float EXC-22 and EXC-21 to Hare Lake road to begin work in that area. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44233 |  | 50 | 44233 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting828720210131-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting828720210131-5Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8294 | 20210131-8 | 53510211 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11.5 | Dynamic | 95.24 | 0 |  |  | 1460.27 | 189.8351 | 1650.1051 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader across Lofty Davies widening and removnig snow all dayDustin working on pickup/plow, planning and coordinating snow removal in WF2-WF6. | 2 | B054 - B064 | Lofty Davies | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting829420210131-8Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27 | Corbiere and Sons Contracting829420210131-8Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27Inv#104 | [5 empty] | 1 | 1460.27 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8294 | 20210131-8 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader across Lofty Davies widening and removnig snow all dayDustin working on pickup/plow, planning and coordinating snow removal in WF2-WF6. | 2 | B054 - B064 | Lofty Davies | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting829420210131-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting829420210131-8Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8294 | 20210131-8 | 53510211 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader across Lofty Davies widening and removnig snow all dayDustin working on pickup/plow, planning and coordinating snow removal in WF2-WF6. | 2 | B054 - B064 | Lofty Davies | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting829420210131-8Pickup w/ plow6300 | Corbiere and Sons Contracting829420210131-8Pickup w/ plow6300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8294 | 20210131-8 | 53510211 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader across Lofty Davies widening and removnig snow all dayDustin working on pickup/plow, planning and coordinating snow removal in WF2-WF6. | 2 | B054 - B064 | Lofty Davies | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting829420210131-8L.O.A.2420 | Corbiere and Sons Contracting829420210131-8L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8294 | 20210131-8 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader across Lofty Davies widening and removnig snow all dayDustin working on pickup/plow, planning and coordinating snow removal in WF2-WF6. | 2 | B054 - B064 | Lofty Davies | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting829420210131-8Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting829420210131-8Operator - Principle - After Jan 10181350Inv#104 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8295 | 20210131-9 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader across Lake A access roads all day - scratching hills and widening Dustin working on pickup/plow, planning and coordinating snow removal in WF2-WF6. | 6 | C129-C151 | Lake A | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829520210131-9Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting829520210131-9Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#104 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8295 | 20210131-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader across Lake A access roads all day - scratching hills and widening Dustin working on pickup/plow, planning and coordinating snow removal in WF2-WF6. | 6 | C129-C151 | Lake A | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829520210131-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting829520210131-9Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8295 | 20210131-9 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader across Lake A access roads all day - scratching hills and widening Dustin working on pickup/plow, planning and coordinating snow removal in WF2-WF6. | 6 | C129-C151 | Lake A | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829520210131-9Pickup w/ plow6300 | Corbiere and Sons Contracting829520210131-9Pickup w/ plow6300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8295 | 20210131-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader across Lake A access roads all day - scratching hills and widening Dustin working on pickup/plow, planning and coordinating snow removal in WF2-WF6. | 6 | C129-C151 | Lake A | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829520210131-9L.O.A.1210 | Corbiere and Sons Contracting829520210131-9L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8295 | 20210131-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2021-01-31 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader across Lake A access roads all day - scratching hills and widening Dustin working on pickup/plow, planning and coordinating snow removal in WF2-WF6. | 6 | C129-C151 | Lake A | 0 | 44234 |  | 50 | 44234 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting829520210131-9Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting829520210131-9Operator - Principle - After Jan 10171275Inv#104 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8298 | 20210201- | 53510211 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7.5 | Dynamic | 95.24 | 0 |  |  | 952.35 | 123.8055 | 1076.1555 | 2021-02-01 |  |  |  |  | 1 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | Spent the morning finishing off Lofty Davies. | 2 | B054 - B064 | Lofty Davies | 0 | 44235 | [9 empty] | 02 | Corbiere and Sons Contracting829820210201-Grader - Cat 12 to 14 or equal- After Jan 107.5952.35 | Corbiere and Sons Contracting829820210201-Grader - Cat 12 to 14 or equal- After Jan 107.5952.35 | [5 empty] | 1 | 952.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8298 | 20210201- | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-01 |  |  |  |  | 1 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | Spent the morning finishing off Lofty Davies. | 2 | B054 - B064 | Lofty Davies | 0 | 44235 | [9 empty] | 02 | Corbiere and Sons Contracting829820210201-L.O.A.1210 | Corbiere and Sons Contracting829820210201-L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8298 | 20210201- | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-02-01 |  |  |  |  | 1 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | Spent the morning finishing off Lofty Davies. | 2 | B054 - B064 | Lofty Davies | 0 | 44235 | [9 empty] | 02 | Corbiere and Sons Contracting829820210201-Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting829820210201-Operator - Principle - After Jan 108600 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8395 | 20210201-12 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-02-01 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Hare Lake Rd | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839520210201-12Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting839520210201-12Excavator - 36 ton- After Jan 10121763.52Inv#109 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8395 | 20210201-12 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-02-01 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Hare Lake Rd | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839520210201-12Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting839520210201-12Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#109 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8395 | 20210201-12 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-02-01 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Hare Lake Rd | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839520210201-12Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting839520210201-12Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#109 | [5 empty] | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8395 | 20210201-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-01 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Hare Lake Rd | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839520210201-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting839520210201-12Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8395 | 20210201-12 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-02-01 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Hare Lake Rd | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839520210201-12Foreman2190 | Corbiere and Sons Contracting839520210201-12Foreman2190Inv#109 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8395 | 20210201-12 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-01 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Hare Lake Rd | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839520210201-12L.O.A.1210 | Corbiere and Sons Contracting839520210201-12L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8395 | 20210201-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-01 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer/Excavator work on Hare Lake Rd | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839520210201-12Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting839520210201-12Operator - Principle - After Jan 1012900Inv#109 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8322 | 20210201-5 | 53510211 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7.5 | Dynamic | 95.24 | 0 |  |  | 952.35 | 123.8055 | 1076.1555 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent the morning finishing off Lofty Davies. | 2 | B054 - B064 | Lofty Davies | 0 | 44237 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting832220210201-5Grader - Cat 12 to 14 or equal- After Jan 107.5952.35 | Corbiere and Sons Contracting832220210201-5Grader - Cat 12 to 14 or equal- After Jan 107.5952.35Inv#104 | [5 empty] | 1 | 952.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8322 | 20210201-5 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent the morning finishing off Lofty Davies. | 2 | B054 - B064 | Lofty Davies | 0 | 44237 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting832220210201-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting832220210201-5Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8322 | 20210201-5 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent the morning finishing off Lofty Davies. | 2 | B054 - B064 | Lofty Davies | 0 | 44237 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting832220210201-5L.O.A.1210 | Corbiere and Sons Contracting832220210201-5L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8322 | 20210201-5 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent the morning finishing off Lofty Davies. | 2 | B054 - B064 | Lofty Davies | 0 | 44237 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting832220210201-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting832220210201-5Operator - Principle - After Jan 108600Inv#104 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8299 | 20210201-6 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7.5 | Dynamic | 95.24 | 0 |  |  | 952.35 | 123.8055 | 1076.1555 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine spent morning finishing up Landfill Road. | 3 | B078-B084 | Red Rock No. 7 | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting829920210201-6Grader - Cat 12 to 14 or equal- After Jan 107.5952.35 | Corbiere and Sons Contracting829920210201-6Grader - Cat 12 to 14 or equal- After Jan 107.5952.35Inv#104 | [5 empty] | 1 | 952.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8299 | 20210201-6 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine spent morning finishing up Landfill Road. | 3 | B078-B084 | Red Rock No. 7 | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting829920210201-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting829920210201-6Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8299 | 20210201-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine spent morning finishing up Landfill Road. | 3 | B078-B084 | Red Rock No. 7 | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting829920210201-6L.O.A.1210 | Corbiere and Sons Contracting829920210201-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8299 | 20210201-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine spent morning finishing up Landfill Road. | 3 | B078-B084 | Red Rock No. 7 | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting829920210201-6Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting829920210201-6Operator - Principle - After Jan 108600Inv#104 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8300 | 20210201-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7.5 | Dynamic | 95.24 | 0 |  |  | 952.35 | 123.8055 | 1076.1555 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on scratching Lake A until 3pmDustin working with sander truck at Lake A | 6 | C129-C151 | Lake A | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830020210201-7Grader - Cat 12 to 14 or equal- After Jan 107.5952.35 | Corbiere and Sons Contracting830020210201-7Grader - Cat 12 to 14 or equal- After Jan 107.5952.35Inv#104 | [5 empty] | 1 | 952.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8300 | 20210201-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on scratching Lake A until 3pmDustin working with sander truck at Lake A | 6 | C129-C151 | Lake A | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830020210201-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting830020210201-7Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8300 | 20210201-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on scratching Lake A until 3pmDustin working with sander truck at Lake A | 6 | C129-C151 | Lake A | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830020210201-7Pickup w/ plow and sander6480 | Corbiere and Sons Contracting830020210201-7Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8300 | 20210201-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on scratching Lake A until 3pmDustin working with sander truck at Lake A | 6 | C129-C151 | Lake A | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830020210201-7L.O.A.2420 | Corbiere and Sons Contracting830020210201-7L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8300 | 20210201-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on scratching Lake A until 3pmDustin working with sander truck at Lake A | 6 | C129-C151 | Lake A | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830020210201-7Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting830020210201-7Operator - Principle - After Jan 10141050Inv#104 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8301 | 20210201-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John and Dan spent 4 hours finishing capping of roads from C-230 - C-234 | 6 | C219-C236 | Neys | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830120210201-8Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting830120210201-8Dozer D6 or equal- After Jan 104525.92Inv#104 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8301 | 20210201-8 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John and Dan spent 4 hours finishing capping of roads from C-230 - C-234 | 6 | C219-C236 | Neys | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830120210201-8Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting830120210201-8Excavator - 30 ton- After Jan 104553.8Inv#104 | [5 empty] | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8301 | 20210201-8 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John and Dan spent 4 hours finishing capping of roads from C-230 - C-234 | 6 | C219-C236 | Neys | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830120210201-8Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting830120210201-8Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#104 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8301 | 20210201-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John and Dan spent 4 hours finishing capping of roads from C-230 - C-234 | 6 | C219-C236 | Neys | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830120210201-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting830120210201-8Light Truck - Pick up- After Jan 102487.5Inv#104 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8301 | 20210201-8 | 53510611 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John and Dan spent 4 hours finishing capping of roads from C-230 - C-234 | 6 | C219-C236 | Neys | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830120210201-8Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting830120210201-8Rock Truck - 30 Ton- After Jan 104552.2Inv#104 | [5 empty] | 1 | 552.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8301 | 20210201-8 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John and Dan spent 4 hours finishing capping of roads from C-230 - C-234 | 6 | C219-C236 | Neys | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830120210201-8L.O.A.3630 | Corbiere and Sons Contracting830120210201-8L.O.A.3630Inv#104 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8301 | 20210201-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-01 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry, John and Dan spent 4 hours finishing capping of roads from C-230 - C-234 | 6 | C219-C236 | Neys | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting830120210201-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting830120210201-8Operator - Principle - After Jan 1012900Inv#104 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8397 | 20210202-11 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-02-02 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Hare Lake. | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839720210202-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting839720210202-11Excavator - 36 ton- After Jan 10121763.52Inv#109 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8397 | 20210202-11 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-02-02 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Hare Lake. | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839720210202-11Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting839720210202-11Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#109 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8397 | 20210202-11 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-02-02 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Hare Lake. | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839720210202-11Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting839720210202-11Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#109 | [5 empty] | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8397 | 20210202-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-02 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Hare Lake. | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839720210202-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting839720210202-11Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8397 | 20210202-11 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-02-02 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Hare Lake. | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839720210202-11Foreman2190 | Corbiere and Sons Contracting839720210202-11Foreman2190Inv#109 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8397 | 20210202-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-02 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Hare Lake. | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839720210202-11L.O.A.1210 | Corbiere and Sons Contracting839720210202-11L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8397 | 20210202-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-02 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer / Excavator work on Hare Lake. | 6 | C257-C267 | Hare Lake Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting839720210202-11Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting839720210202-11Operator - Principle - After Jan 1012900Inv#109 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8315 | 20210202-4 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lofty Davies to Ruby LakeLen running grader at Ruby Lake Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B110-B118 | Ruby Lake | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831520210202-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting831520210202-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#104 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8315 | 20210202-4 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lofty Davies to Ruby LakeLen running grader at Ruby Lake Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B110-B118 | Ruby Lake | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831520210202-4Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting831520210202-4Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8315 | 20210202-4 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 |  |  |  | 300 | 39 | 339 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lofty Davies to Ruby LakeLen running grader at Ruby Lake Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B110-B118 | Ruby Lake | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831520210202-4Pickup w/ plow6300 | Corbiere and Sons Contracting831520210202-4Pickup w/ plow6300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8315 | 20210202-4 | 53510311 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lofty Davies to Ruby LakeLen running grader at Ruby Lake Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B110-B118 | Ruby Lake | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831520210202-4L.O.A.2420 | Corbiere and Sons Contracting831520210202-4L.O.A.2420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8315 | 20210202-4 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 18.5 | HR |  |  | 75 | 0 | 1387.5 | 180.375 | 1567.875 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lofty Davies to Ruby LakeLen running grader at Ruby Lake Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B110-B118 | Ruby Lake | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831520210202-4Operator - Principle - After Jan 1018.51387.5 | Corbiere and Sons Contracting831520210202-4Operator - Principle - After Jan 1018.51387.5Inv#104 | [5 empty] | 1 | 1387.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8315 | 20210202-4 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lofty Davies to Ruby LakeLen running grader at Ruby Lake Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B110-B118 | Ruby Lake | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831520210202-4Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting831520210202-4Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8316 | 20210202-5 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and Float moved grader from Landfill to Fire Hill - 2 flaggers neededRichard Pine running grader at Firehill Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B135-B144 | Fire Hill | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831620210202-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting831620210202-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#104 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8316 | 20210202-5 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and Float moved grader from Landfill to Fire Hill - 2 flaggers neededRichard Pine running grader at Firehill Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B135-B144 | Fire Hill | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831620210202-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting831620210202-5Light Truck - Pick up- After Jan 101243.75Inv#104 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8316 | 20210202-5 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and Float moved grader from Landfill to Fire Hill - 2 flaggers neededRichard Pine running grader at Firehill Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B135-B144 | Fire Hill | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831620210202-5Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting831620210202-5Tractor Trailer - 60 Ton- After Jan 104489.56Inv#104 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8316 | 20210202-5 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and Float moved grader from Landfill to Fire Hill - 2 flaggers neededRichard Pine running grader at Firehill Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B135-B144 | Fire Hill | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831620210202-5Pickup w/ plow6300 | Corbiere and Sons Contracting831620210202-5Pickup w/ plow6300Inv#104 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8316 | 20210202-5 | 53510311 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and Float moved grader from Landfill to Fire Hill - 2 flaggers neededRichard Pine running grader at Firehill Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B135-B144 | Fire Hill | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831620210202-5L.O.A.51050 | Corbiere and Sons Contracting831620210202-5L.O.A.51050Inv#104 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8316 | 20210202-5 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 18.5 | HR |  |  | 75 | 0 | 1387.5 | 180.375 | 1567.875 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and Float moved grader from Landfill to Fire Hill - 2 flaggers neededRichard Pine running grader at Firehill Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B135-B144 | Fire Hill | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831620210202-5Operator - Principle - After Jan 1018.51387.5 | Corbiere and Sons Contracting831620210202-5Operator - Principle - After Jan 1018.51387.5Inv#104 | [5 empty] | 1 | 1387.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8316 | 20210202-5 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and Float moved grader from Landfill to Fire Hill - 2 flaggers neededRichard Pine running grader at Firehill Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B135-B144 | Fire Hill | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831620210202-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting831620210202-5Driver - AZ - After Jan 104280Inv#104 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8316 | 20210202-5 | 53510311 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and Float moved grader from Landfill to Fire Hill - 2 flaggers neededRichard Pine running grader at Firehill Road all dayDustin working on pickup w/plow and coordinating activities | 3 | B135-B144 | Fire Hill | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831620210202-5Labourer - General - After Jan 108480 | Corbiere and Sons Contracting831620210202-5Labourer - General - After Jan 108480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8317 | 20210202-6 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 7 |  | 0 | 0 |  |  | 560 | 72.8 | 632.8 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dawson plowed at Golf Course Rd for first half of day. | 3 | B085-B087 | Golf Course Road | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831720210202-6Pickup w/ plow and sander7560 | Corbiere and Sons Contracting831720210202-6Pickup w/ plow and sander7560Inv#104 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8317 | 20210202-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dawson plowed at Golf Course Rd for first half of day. | 3 | B085-B087 | Golf Course Road | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831720210202-6L.O.A.1210 | Corbiere and Sons Contracting831720210202-6L.O.A.1210Inv#104 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8317 | 20210202-6 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dawson plowed at Golf Course Rd for first half of day. | 3 | B085-B087 | Golf Course Road | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting831720210202-6Operator - Intermdiate - After Jan 107490 | Corbiere and Sons Contracting831720210202-6Operator - Intermdiate - After Jan 107490Inv#104 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8318 | 20210202-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dawson on pickup w/plow worked across Lake A and Santoy | 6 | C129-C151 | Lake A | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting831820210202-7Pickup w/ plow and sander6480 | Corbiere and Sons Contracting831820210202-7Pickup w/ plow and sander6480Inv#104 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8318 | 20210202-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-02-02 | 0 | Inv#104 | 44238 | 142 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dawson on pickup w/plow worked across Lake A and Santoy | 6 | C129-C151 | Lake A | 0 | 44235 |  | 50 | 44237 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting831820210202-7Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting831820210202-7Operator - Intermdiate - After Jan 106420Inv#104 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8328 | 20210203-4 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11.5 | Dynamic | 95.24 | 0 |  |  | 1460.27 | 189.8351 | 1650.1051 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard worked on grader across Maata's Rd | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832820210203-4Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27 | Corbiere and Sons Contracting832820210203-4Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27Inv#109 | [5 empty] | 1 | 1460.27 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8328 | 20210203-4 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard worked on grader across Maata's Rd | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832820210203-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting832820210203-4Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8328 | 20210203-4 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard worked on grader across Maata's Rd | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832820210203-4L.O.A.1210 | Corbiere and Sons Contracting832820210203-4L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8328 | 20210203-4 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard worked on grader across Maata's Rd | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832820210203-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting832820210203-4Operator - Principle - After Jan 1012900Inv#109 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8329 | 20210203-5 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4.5 | Dynamic | 95.24 | 0 |  |  | 571.41 | 74.2833 | 645.6933 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len spent part of day widening Ruby and then moved to Antler to run grader there. | 3 | B110-B118 | Ruby Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832920210203-5Grader - Cat 12 to 14 or equal- After Jan 104.5571.41 | Corbiere and Sons Contracting832920210203-5Grader - Cat 12 to 14 or equal- After Jan 104.5571.41Inv#109 | [5 empty] | 1 | 571.41 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8329 | 20210203-5 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len spent part of day widening Ruby and then moved to Antler to run grader there. | 3 | B110-B118 | Ruby Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832920210203-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting832920210203-5Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8329 | 20210203-5 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len spent part of day widening Ruby and then moved to Antler to run grader there. | 3 | B110-B118 | Ruby Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting832920210203-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting832920210203-5Operator - Principle - After Jan 105375Inv#109 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8330 | 20210203-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6.5 | Dynamic | 95.24 | 0 |  |  | 825.37 | 107.2981 | 932.6681 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Antler Lake Rd; Len Greg ran grader all afternoon; Dustin Corbiere plowed entrance. | 5 | C050-C069 | Antler Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting833020210203-6Grader - Cat 12 to 14 or equal- After Jan 106.5825.37 | Corbiere and Sons Contracting833020210203-6Grader - Cat 12 to 14 or equal- After Jan 106.5825.37Inv#109 | [5 empty] | 1 | 825.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8330 | 20210203-6 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Antler Lake Rd; Len Greg ran grader all afternoon; Dustin Corbiere plowed entrance. | 5 | C050-C069 | Antler Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting833020210203-6Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting833020210203-6Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8330 | 20210203-6 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Antler Lake Rd; Len Greg ran grader all afternoon; Dustin Corbiere plowed entrance. | 5 | C050-C069 | Antler Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting833020210203-6Pickup w/ plow4200 | Corbiere and Sons Contracting833020210203-6Pickup w/ plow4200Inv#109 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8330 | 20210203-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Antler Lake Rd; Len Greg ran grader all afternoon; Dustin Corbiere plowed entrance. | 5 | C050-C069 | Antler Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting833020210203-6L.O.A.1210 | Corbiere and Sons Contracting833020210203-6L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8330 | 20210203-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Antler Lake Rd; Len Greg ran grader all afternoon; Dustin Corbiere plowed entrance. | 5 | C050-C069 | Antler Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting833020210203-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting833020210203-6Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8330 | 20210203-6 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Antler Lake Rd; Len Greg ran grader all afternoon; Dustin Corbiere plowed entrance. | 5 | C050-C069 | Antler Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting833020210203-6Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting833020210203-6Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8331 | 20210203-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Lake A; Ron Dowding ran gader for night shift. Dustin sanded Lake A and planned and coordinated areas to be cleared | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting833120210203-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting833120210203-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#109 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8331 | 20210203-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Lake A; Ron Dowding ran gader for night shift. Dustin sanded Lake A and planned and coordinated areas to be cleared | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting833120210203-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting833120210203-7Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8331 | 20210203-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Lake A; Ron Dowding ran gader for night shift. Dustin sanded Lake A and planned and coordinated areas to be cleared | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting833120210203-7Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting833120210203-7Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8331 | 20210203-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Lake A; Ron Dowding ran gader for night shift. Dustin sanded Lake A and planned and coordinated areas to be cleared | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting833120210203-7Pickup w/ plow and sander8640 | Corbiere and Sons Contracting833120210203-7Pickup w/ plow and sander8640Inv#109 | [5 empty] | 1 | 640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8331 | 20210203-7 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Lake A; Ron Dowding ran gader for night shift. Dustin sanded Lake A and planned and coordinated areas to be cleared | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting833120210203-7L.O.A.3630 | Corbiere and Sons Contracting833120210203-7L.O.A.3630Inv#109 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8331 | 20210203-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 19 | HR |  |  | 75 | 0 | 1425 | 185.25 | 1610.25 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Lake A; Ron Dowding ran gader for night shift. Dustin sanded Lake A and planned and coordinated areas to be cleared | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting833120210203-7Operator - Principle - After Jan 10191425 | Corbiere and Sons Contracting833120210203-7Operator - Principle - After Jan 10191425Inv#109 | [5 empty] | 1 | 1425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8331 | 20210203-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-03 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Paul and float moved grader into Lake A; Ron Dowding ran gader for night shift. Dustin sanded Lake A and planned and coordinated areas to be cleared | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting833120210203-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting833120210203-7Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8342 | 20210204-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin in pickup truck with plow and sander working across Lake A | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting834220210204-10Pickup w/ plow and sander6480 | Corbiere and Sons Contracting834220210204-10Pickup w/ plow and sander6480Inv#109 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8342 | 20210204-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin in pickup truck with plow and sander working across Lake A | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting834220210204-10L.O.A.1210 | Corbiere and Sons Contracting834220210204-10L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8342 | 20210204-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin in pickup truck with plow and sander working across Lake A | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting834220210204-10Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting834220210204-10Operator - Principle - After Jan 106450Inv#109 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8336 | 20210204-4 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11.5 | Dynamic | 95.24 | 0 |  |  | 1460.27 | 189.8351 | 1650.1051 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader in Maata's Road all dayDawson Campbell worked on plow truck with sander ipening up road way entrances for 8 hours. | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting833620210204-4Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27 | Corbiere and Sons Contracting833620210204-4Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27Inv#109 | [5 empty] | 1 | 1460.27 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8336 | 20210204-4 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader in Maata's Road all dayDawson Campbell worked on plow truck with sander ipening up road way entrances for 8 hours. | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting833620210204-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting833620210204-4Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8336 | 20210204-4 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader in Maata's Road all dayDawson Campbell worked on plow truck with sander ipening up road way entrances for 8 hours. | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting833620210204-4Pickup w/ plow and sander8640 | Corbiere and Sons Contracting833620210204-4Pickup w/ plow and sander8640Inv#109 | [5 empty] | 1 | 640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8336 | 20210204-4 | 53510311 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader in Maata's Road all dayDawson Campbell worked on plow truck with sander ipening up road way entrances for 8 hours. | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting833620210204-4L.O.A.2420 | Corbiere and Sons Contracting833620210204-4L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8336 | 20210204-4 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader in Maata's Road all dayDawson Campbell worked on plow truck with sander ipening up road way entrances for 8 hours. | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting833620210204-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting833620210204-4Operator - Principle - After Jan 1012900Inv#109 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8336 | 20210204-4 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader in Maata's Road all dayDawson Campbell worked on plow truck with sander ipening up road way entrances for 8 hours. | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting833620210204-4Operator - Intermdiate - After Jan 108560 | Corbiere and Sons Contracting833620210204-4Operator - Intermdiate - After Jan 108560Inv#109 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8337 | 20210204-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 21 | Dynamic | 95.24 | 0 |  |  | 2666.58 | 346.6554 | 3013.2354 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding worked across Antler Lake all night on the graderLen Gregory ran grader during the day | 5 | C050-C069 | Antler Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting833720210204-5Grader - Cat 12 to 14 or equal- After Jan 10212666.58 | Corbiere and Sons Contracting833720210204-5Grader - Cat 12 to 14 or equal- After Jan 10212666.58Inv#109 | [5 empty] | 1 | 2666.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8337 | 20210204-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding worked across Antler Lake all night on the graderLen Gregory ran grader during the day | 5 | C050-C069 | Antler Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting833720210204-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting833720210204-5Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8337 | 20210204-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding worked across Antler Lake all night on the graderLen Gregory ran grader during the day | 5 | C050-C069 | Antler Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting833720210204-5L.O.A.2420 | Corbiere and Sons Contracting833720210204-5L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8337 | 20210204-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding worked across Antler Lake all night on the graderLen Gregory ran grader during the day | 5 | C050-C069 | Antler Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting833720210204-5Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting833720210204-5Operator - Principle - After Jan 10221650Inv#109 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8339 | 20210204-7 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn in pickup w/plow clearing Jackfish | 6 | C152-C154 | Jackfish Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting833920210204-7Pickup w/ plow6300 | Corbiere and Sons Contracting833920210204-7Pickup w/ plow6300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8339 | 20210204-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn in pickup w/plow clearing Jackfish | 6 | C152-C154 | Jackfish Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting833920210204-7L.O.A.1210 | Corbiere and Sons Contracting833920210204-7L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8339 | 20210204-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn in pickup w/plow clearing Jackfish | 6 | C152-C154 | Jackfish Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting833920210204-7Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting833920210204-7Operator - Intermdiate - After Jan 106420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8340 | 20210204-8 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn in pickup w/plow clearing Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting834020210204-8Pickup w/ plow5250 | Corbiere and Sons Contracting834020210204-8Pickup w/ plow5250Inv#109 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8340 | 20210204-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn in pickup w/plow clearing Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting834020210204-8Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting834020210204-8Operator - Intermdiate - After Jan 105350Inv#109 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8341 | 20210204-9 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin in pickup truck with plow and sander working across Mill Rd | 5 | C158-C170 | Mill Road | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting834120210204-9Pickup w/ plow and sander6480 | Corbiere and Sons Contracting834120210204-9Pickup w/ plow and sander6480Inv#109 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8341 | 20210204-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-04 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin in pickup truck with plow and sander working across Mill Rd | 5 | C158-C170 | Mill Road | 0 | 44236 |  | 50 | 44243 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting834120210204-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting834120210204-9Operator - Principle - After Jan 106450Inv#109 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8354 | 20210205-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn plowed Jackfish | 6 | C152-C154 | Jackfish Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835420210205-10Pickup w/ plow and sander4320 | Corbiere and Sons Contracting835420210205-10Pickup w/ plow and sander4320Inv#109 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8354 | 20210205-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn plowed Jackfish | 6 | C152-C154 | Jackfish Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835420210205-10L.O.A.1210 | Corbiere and Sons Contracting835420210205-10L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8354 | 20210205-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn plowed Jackfish | 6 | C152-C154 | Jackfish Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835420210205-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting835420210205-10Operator - Principle - After Jan 104300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8355 | 20210205-11 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim plowed snow on Peninsula with dozer | 6 | C268-C279 | Peninsula Rd | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835520210205-11Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting835520210205-11Dozer D6 or equal- After Jan 105657.4Inv#109 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8355 | 20210205-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim plowed snow on Peninsula with dozer | 6 | C268-C279 | Peninsula Rd | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835520210205-11L.O.A.1210 | Corbiere and Sons Contracting835520210205-11L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8355 | 20210205-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim plowed snow on Peninsula with dozer | 6 | C268-C279 | Peninsula Rd | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835520210205-11Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting835520210205-11Operator - Principle - After Jan 105375Inv#109 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8356 | 20210205-12 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removed snow all day on Neys and Culvert Creek with dozer. | 6 | C219-C236 | Neys | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835620210205-12Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting835620210205-12Dozer D6 or equal- After Jan 10101314.8Inv#109 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8356 | 20210205-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removed snow all day on Neys and Culvert Creek with dozer. | 6 | C219-C236 | Neys | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835620210205-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting835620210205-12Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8356 | 20210205-12 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removed snow all day on Neys and Culvert Creek with dozer. | 6 | C219-C236 | Neys | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835620210205-12L.O.A.1210 | Corbiere and Sons Contracting835620210205-12L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8356 | 20210205-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removed snow all day on Neys and Culvert Creek with dozer. | 6 | C219-C236 | Neys | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835620210205-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting835620210205-12Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8357 | 20210205-13 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Nick removed snow on Hare for half day and Dwayne did the rest of the day. | 6 | C257-C267 | Hare Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835720210205-13Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting835720210205-13Dozer D6 or equal- After Jan 10101314.8Inv#109 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8357 | 20210205-13 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Nick removed snow on Hare for half day and Dwayne did the rest of the day. | 6 | C257-C267 | Hare Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835720210205-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting835720210205-13Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8357 | 20210205-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Nick removed snow on Hare for half day and Dwayne did the rest of the day. | 6 | C257-C267 | Hare Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835720210205-13L.O.A.1210 | Corbiere and Sons Contracting835720210205-13L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8357 | 20210205-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Nick removed snow on Hare for half day and Dwayne did the rest of the day. | 6 | C257-C267 | Hare Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835720210205-13Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting835720210205-13Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8349 | 20210205-5 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11.5 | Dynamic | 95.24 | 0 |  |  | 1460.27 | 189.8351 | 1650.1051 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued all day trying to clear snow and widen, kept blowing and driftingGerrit worked on pickup w/plow and sander opening up entrance ways and clearing as much as he could | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting834920210205-5Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27 | Corbiere and Sons Contracting834920210205-5Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27Inv#109 | [5 empty] | 1 | 1460.27 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8349 | 20210205-5 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued all day trying to clear snow and widen, kept blowing and driftingGerrit worked on pickup w/plow and sander opening up entrance ways and clearing as much as he could | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting834920210205-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting834920210205-5Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8349 | 20210205-5 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued all day trying to clear snow and widen, kept blowing and driftingGerrit worked on pickup w/plow and sander opening up entrance ways and clearing as much as he could | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting834920210205-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting834920210205-5Pickup w/ plow and sander12960Inv#109 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8349 | 20210205-5 | 53510311 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued all day trying to clear snow and widen, kept blowing and driftingGerrit worked on pickup w/plow and sander opening up entrance ways and clearing as much as he could | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting834920210205-5L.O.A.2420 | Corbiere and Sons Contracting834920210205-5L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8349 | 20210205-5 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued all day trying to clear snow and widen, kept blowing and driftingGerrit worked on pickup w/plow and sander opening up entrance ways and clearing as much as he could | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting834920210205-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting834920210205-5Operator - Principle - After Jan 1012900Inv#109 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8349 | 20210205-5 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued all day trying to clear snow and widen, kept blowing and driftingGerrit worked on pickup w/plow and sander opening up entrance ways and clearing as much as he could | 3 | B088-B099 | Maata's | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting834920210205-5Operator - Intermdiate - After Jan 1012840 | Corbiere and Sons Contracting834920210205-5Operator - Intermdiate - After Jan 1012840Inv#109 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8350 | 20210205-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11.5 | Dynamic | 95.24 | 0 |  |  | 1460.27 | 189.8351 | 1650.1051 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader at Antler for morning; Richard took over at 12 and finished at 7pm | 5 | C070 - C075 | Antler Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting835020210205-6Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27 | Corbiere and Sons Contracting835020210205-6Grader - Cat 12 to 14 or equal- After Jan 1011.51460.27Inv#109 | [5 empty] | 1 | 1460.27 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8350 | 20210205-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader at Antler for morning; Richard took over at 12 and finished at 7pm | 5 | C070 - C075 | Antler Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting835020210205-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting835020210205-6Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8350 | 20210205-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader at Antler for morning; Richard took over at 12 and finished at 7pm | 5 | C070 - C075 | Antler Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting835020210205-6L.O.A.1210 | Corbiere and Sons Contracting835020210205-6L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8350 | 20210205-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader at Antler for morning; Richard took over at 12 and finished at 7pm | 5 | C070 - C075 | Antler Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting835020210205-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting835020210205-6Operator - Principle - After Jan 1012900Inv#109 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8352 | 20210205-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 15 | Dynamic | 95.24 | 0 |  |  | 1904.7 | 247.611 | 2152.311 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len ran grader in Lake A for afternoon; Ron ran grader in Lake A all night Shawn organizing crews, plowed Lake A | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835220210205-8Grader - Cat 12 to 14 or equal- After Jan 10151904.7 | Corbiere and Sons Contracting835220210205-8Grader - Cat 12 to 14 or equal- After Jan 10151904.7Inv#109 | [5 empty] | 1 | 1904.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8352 | 20210205-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len ran grader in Lake A for afternoon; Ron ran grader in Lake A all night Shawn organizing crews, plowed Lake A | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835220210205-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting835220210205-8Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8352 | 20210205-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len ran grader in Lake A for afternoon; Ron ran grader in Lake A all night Shawn organizing crews, plowed Lake A | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835220210205-8Pickup w/ plow and sander4320 | Corbiere and Sons Contracting835220210205-8Pickup w/ plow and sander4320Inv#109 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8352 | 20210205-8 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len ran grader in Lake A for afternoon; Ron ran grader in Lake A all night Shawn organizing crews, plowed Lake A | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835220210205-8L.O.A.2420 | Corbiere and Sons Contracting835220210205-8L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8352 | 20210205-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len ran grader in Lake A for afternoon; Ron ran grader in Lake A all night Shawn organizing crews, plowed Lake A | 6 | C129-C151 | Lake A | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835220210205-8Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting835220210205-8Operator - Principle - After Jan 10211575Inv#109 | [5 empty] | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8353 | 20210205-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn plowed Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835320210205-9Pickup w/ plow and sander4320 | Corbiere and Sons Contracting835320210205-9Pickup w/ plow and sander4320Inv#109 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8353 | 20210205-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-02-05 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn plowed Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44236 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting835320210205-9Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting835320210205-9Operator - Principle - After Jan 104300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8368 | 20210206-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Chris spent 3 hours clearing snow with dozer towards the tracks | 6 | C257-C267 | Hare Lake | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836820210206-10Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting836820210206-10Dozer D6 or equal- After Jan 103394.44Inv#109 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8368 | 20210206-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Chris spent 3 hours clearing snow with dozer towards the tracks | 6 | C257-C267 | Hare Lake | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836820210206-10L.O.A.1210 | Corbiere and Sons Contracting836820210206-10L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8368 | 20210206-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Chris spent 3 hours clearing snow with dozer towards the tracks | 6 | C257-C267 | Hare Lake | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836820210206-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting836820210206-10Operator - Principle - After Jan 104300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8362 | 20210206-4 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 19.5 | Dynamic | 95.24 | 0 |  |  | 2476.11 | 321.8943 | 2798.0043 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader back to Landfill as 911 snow removal needed to be done.Gary worked in Landfill all day after grader was floated; Ron worked nightshift on graderShawn worked on plow truck opening up entrances across various areas in WF3 as well as coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting836220210206-4Grader - Cat 12 to 14 or equal- After Jan 1019.52476.11 | Corbiere and Sons Contracting836220210206-4Grader - Cat 12 to 14 or equal- After Jan 1019.52476.11Inv#109 | [5 empty] | 1 | 2476.11 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8362 | 20210206-4 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader back to Landfill as 911 snow removal needed to be done.Gary worked in Landfill all day after grader was floated; Ron worked nightshift on graderShawn worked on plow truck opening up entrances across various areas in WF3 as well as coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting836220210206-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting836220210206-4Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8362 | 20210206-4 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader back to Landfill as 911 snow removal needed to be done.Gary worked in Landfill all day after grader was floated; Ron worked nightshift on graderShawn worked on plow truck opening up entrances across various areas in WF3 as well as coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting836220210206-4Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting836220210206-4Tractor Trailer - 60 Ton- After Jan 105611.95Inv#109 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8362 | 20210206-4 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader back to Landfill as 911 snow removal needed to be done.Gary worked in Landfill all day after grader was floated; Ron worked nightshift on graderShawn worked on plow truck opening up entrances across various areas in WF3 as well as coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting836220210206-4Pickup w/ plow and sander12960 | Corbiere and Sons Contracting836220210206-4Pickup w/ plow and sander12960Inv#109 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8362 | 20210206-4 | 53510311 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader back to Landfill as 911 snow removal needed to be done.Gary worked in Landfill all day after grader was floated; Ron worked nightshift on graderShawn worked on plow truck opening up entrances across various areas in WF3 as well as coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting836220210206-4L.O.A.4840 | Corbiere and Sons Contracting836220210206-4L.O.A.4840Inv#109 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8362 | 20210206-4 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 35.5 | HR |  |  | 75 | 0 | 2662.5 | 346.125 | 3008.625 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader back to Landfill as 911 snow removal needed to be done.Gary worked in Landfill all day after grader was floated; Ron worked nightshift on graderShawn worked on plow truck opening up entrances across various areas in WF3 as well as coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting836220210206-4Operator - Principle - After Jan 1035.52662.5 | Corbiere and Sons Contracting836220210206-4Operator - Principle - After Jan 1035.52662.5Inv#109 | [5 empty] | 1 | 2662.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8362 | 20210206-4 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader back to Landfill as 911 snow removal needed to be done.Gary worked in Landfill all day after grader was floated; Ron worked nightshift on graderShawn worked on plow truck opening up entrances across various areas in WF3 as well as coordinating. | 3 | B078-B084 | Landfill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting836220210206-4Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting836220210206-4Driver - AZ - After Jan 105350Inv#109 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8363 | 20210206-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Antler to CooksRichard worked on grader in Cooks all day after it was floated. | 5 | C076-C116 | Cook Lake | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting836320210206-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting836320210206-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#109 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8363 | 20210206-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Antler to CooksRichard worked on grader in Cooks all day after it was floated. | 5 | C076-C116 | Cook Lake | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting836320210206-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting836320210206-5Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8363 | 20210206-5 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Antler to CooksRichard worked on grader in Cooks all day after it was floated. | 5 | C076-C116 | Cook Lake | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting836320210206-5Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting836320210206-5Tractor Trailer - 60 Ton- After Jan 103367.17Inv#109 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8363 | 20210206-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Antler to CooksRichard worked on grader in Cooks all day after it was floated. | 5 | C076-C116 | Cook Lake | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting836320210206-5L.O.A.2420 | Corbiere and Sons Contracting836320210206-5L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8363 | 20210206-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Antler to CooksRichard worked on grader in Cooks all day after it was floated. | 5 | C076-C116 | Cook Lake | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting836320210206-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting836320210206-5Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8363 | 20210206-5 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Antler to CooksRichard worked on grader in Cooks all day after it was floated. | 5 | C076-C116 | Cook Lake | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting836320210206-5Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting836320210206-5Driver - AZ - After Jan 103210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8364 | 20210206-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 95.24 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit and grader worked across Mill Rd. | 5 | C117-C124 | Mill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting836420210206-6Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting836420210206-6Grader - Cat 12 to 14 or equal- After Jan 108.51079.33Inv#109 | [5 empty] | 1 | 1079.33 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8364 | 20210206-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit and grader worked across Mill Rd. | 5 | C117-C124 | Mill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting836420210206-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting836420210206-6Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8364 | 20210206-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit and grader worked across Mill Rd. | 5 | C117-C124 | Mill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting836420210206-6L.O.A.1210 | Corbiere and Sons Contracting836420210206-6L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8364 | 20210206-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit and grader worked across Mill Rd. | 5 | C117-C124 | Mill Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting836420210206-6Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting836420210206-6Operator - Principle - After Jan 109675Inv#109 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8365 | 20210206-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lake A to Prarie River Len's Grader was floated to Prarie River, broke down 2 hours later. | 6 | C171-C185 | Prairie River | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836520210206-7Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting836520210206-7Grader - Cat 12 to 14 or equal- After Jan 102253.96Inv#109 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8365 | 20210206-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lake A to Prarie River Len's Grader was floated to Prarie River, broke down 2 hours later. | 6 | C171-C185 | Prairie River | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836520210206-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting836520210206-7Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8365 | 20210206-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lake A to Prarie River Len's Grader was floated to Prarie River, broke down 2 hours later. | 6 | C171-C185 | Prairie River | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836520210206-7Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting836520210206-7Tractor Trailer - 60 Ton- After Jan 103367.17Inv#109 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8365 | 20210206-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lake A to Prarie River Len's Grader was floated to Prarie River, broke down 2 hours later. | 6 | C171-C185 | Prairie River | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836520210206-7L.O.A.1210 | Corbiere and Sons Contracting836520210206-7L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8365 | 20210206-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lake A to Prarie River Len's Grader was floated to Prarie River, broke down 2 hours later. | 6 | C171-C185 | Prairie River | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836520210206-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting836520210206-7Operator - Principle - After Jan 106450Inv#109 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8365 | 20210206-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Lake A to Prarie River Len's Grader was floated to Prarie River, broke down 2 hours later. | 6 | C171-C185 | Prairie River | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836520210206-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting836520210206-7Driver - AZ - After Jan 103210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8366 | 20210206-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on pickup w/plow and sander across various areas in WF6 opening up as many entrances as he couldTim and Dozer did snow removal across all pads and roads in PeninsulaRob Couchie removed snow from C-270 Nick removing snow from C-269 | 6 | C268-C279 | Peninsula Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836620210206-8Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting836620210206-8Dozer D6 or equal- After Jan 10101314.8Inv#109 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8366 | 20210206-8 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6.5 | Dynamic | 103.84 | 0 |  |  | 899.925 | 116.9903 | 1016.9153 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on pickup w/plow and sander across various areas in WF6 opening up as many entrances as he couldTim and Dozer did snow removal across all pads and roads in PeninsulaRob Couchie removed snow from C-270 Nick removing snow from C-269 | 6 | C268-C279 | Peninsula Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836620210206-8Excavator - 30 ton- After Jan 106.5899.925 | Corbiere and Sons Contracting836620210206-8Excavator - 30 ton- After Jan 106.5899.925Inv#109 | [5 empty] | 1 | 899.925 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8366 | 20210206-8 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6.5 | Dynamic | 110.22 | 0 |  |  | 955.24 | 124.1812 | 1079.4212 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on pickup w/plow and sander across various areas in WF6 opening up as many entrances as he couldTim and Dozer did snow removal across all pads and roads in PeninsulaRob Couchie removed snow from C-270 Nick removing snow from C-269 | 6 | C268-C279 | Peninsula Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836620210206-8Excavator - 36 ton- After Jan 106.5955.24 | Corbiere and Sons Contracting836620210206-8Excavator - 36 ton- After Jan 106.5955.24Inv#109 | [5 empty] | 1 | 955.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8366 | 20210206-8 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6.5 | HR | 9.16 | 0 |  |  | 79.365 | 10.3174 | 89.6825 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on pickup w/plow and sander across various areas in WF6 opening up as many entrances as he couldTim and Dozer did snow removal across all pads and roads in PeninsulaRob Couchie removed snow from C-270 Nick removing snow from C-269 | 6 | C268-C279 | Peninsula Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836620210206-8Excavator Thumb - 30 - 50 ton- After Jan 106.579.365 | Corbiere and Sons Contracting836620210206-8Excavator Thumb - 30 - 50 ton- After Jan 106.579.365Inv#109 | [5 empty] | 1 | 79.365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8366 | 20210206-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on pickup w/plow and sander across various areas in WF6 opening up as many entrances as he couldTim and Dozer did snow removal across all pads and roads in PeninsulaRob Couchie removed snow from C-270 Nick removing snow from C-269 | 6 | C268-C279 | Peninsula Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836620210206-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting836620210206-8Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8366 | 20210206-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12.5 |  | 0 | 0 |  |  | 1000 | 130 | 1130 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on pickup w/plow and sander across various areas in WF6 opening up as many entrances as he couldTim and Dozer did snow removal across all pads and roads in PeninsulaRob Couchie removed snow from C-270 Nick removing snow from C-269 | 6 | C268-C279 | Peninsula Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836620210206-8Pickup w/ plow and sander12.51000 | Corbiere and Sons Contracting836620210206-8Pickup w/ plow and sander12.51000Inv#109 | [5 empty] | 1 | 1000 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8366 | 20210206-8 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on pickup w/plow and sander across various areas in WF6 opening up as many entrances as he couldTim and Dozer did snow removal across all pads and roads in PeninsulaRob Couchie removed snow from C-270 Nick removing snow from C-269 | 6 | C268-C279 | Peninsula Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836620210206-8L.O.A.3630 | Corbiere and Sons Contracting836620210206-8L.O.A.3630Inv#109 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8366 | 20210206-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 75 | 0 | 1875 | 243.75 | 2118.75 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on pickup w/plow and sander across various areas in WF6 opening up as many entrances as he couldTim and Dozer did snow removal across all pads and roads in PeninsulaRob Couchie removed snow from C-270 Nick removing snow from C-269 | 6 | C268-C279 | Peninsula Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836620210206-8Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting836620210206-8Operator - Principle - After Jan 10251875Inv#109 | [5 empty] | 1 | 1875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8366 | 20210206-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 12.5 | HR |  |  | 70 | 0 | 875 | 113.75 | 988.75 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on pickup w/plow and sander across various areas in WF6 opening up as many entrances as he couldTim and Dozer did snow removal across all pads and roads in PeninsulaRob Couchie removed snow from C-270 Nick removing snow from C-269 | 6 | C268-C279 | Peninsula Road | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836620210206-8Operator - Intermdiate - After Jan 1012.5875 | Corbiere and Sons Contracting836620210206-8Operator - Intermdiate - After Jan 1012.5875Inv#109 | [5 empty] | 1 | 875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8367 | 20210206-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing snow with dozer from Neys to Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836720210206-9Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting836720210206-9Dozer D6 or equal- After Jan 10101314.8Inv#109 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8367 | 20210206-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing snow with dozer from Neys to Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836720210206-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting836720210206-9Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8367 | 20210206-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing snow with dozer from Neys to Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836720210206-9L.O.A.1210 | Corbiere and Sons Contracting836720210206-9L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8367 | 20210206-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-06 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing snow with dozer from Neys to Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44238 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting836720210206-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting836720210206-9Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8380 | 20210207-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim clearing off snow in Peninsula for assembly crews | 6 | C268-C279 | Peninsula Road | 0 | 44242 |  | 50 | 44245 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting838020210207-10Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting838020210207-10Dozer D6 or equal- After Jan 1010.51380.54Inv#109 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8380 | 20210207-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim clearing off snow in Peninsula for assembly crews | 6 | C268-C279 | Peninsula Road | 0 | 44242 |  | 50 | 44245 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting838020210207-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting838020210207-10Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8380 | 20210207-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim clearing off snow in Peninsula for assembly crews | 6 | C268-C279 | Peninsula Road | 0 | 44242 |  | 50 | 44245 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting838020210207-10L.O.A.1210 | Corbiere and Sons Contracting838020210207-10L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8380 | 20210207-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim clearing off snow in Peninsula for assembly crews | 6 | C268-C279 | Peninsula Road | 0 | 44242 |  | 50 | 44245 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting838020210207-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting838020210207-10Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8374 | 20210207-4 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 17 | Dynamic | 95.24 | 0 |  |  | 2158.66 | 280.6258 | 2439.2858 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Landfill back to Maata's to do widening Gary ran grader in Landfill and Maata's during the day, Evan ran grader for 1/2 the night. Shawn Panamick worked with plow truck, doing entrances and roadways as much as he could, plus coordinating and float moves. | 3 | B088-B099 | Maata's Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting837420210207-4Grader - Cat 12 to 14 or equal- After Jan 10172158.66 | Corbiere and Sons Contracting837420210207-4Grader - Cat 12 to 14 or equal- After Jan 10172158.66Inv#109 | [5 empty] | 1 | 2158.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8374 | 20210207-4 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Landfill back to Maata's to do widening Gary ran grader in Landfill and Maata's during the day, Evan ran grader for 1/2 the night. Shawn Panamick worked with plow truck, doing entrances and roadways as much as he could, plus coordinating and float moves. | 3 | B088-B099 | Maata's Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting837420210207-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting837420210207-4Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8374 | 20210207-4 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Landfill back to Maata's to do widening Gary ran grader in Landfill and Maata's during the day, Evan ran grader for 1/2 the night. Shawn Panamick worked with plow truck, doing entrances and roadways as much as he could, plus coordinating and float moves. | 3 | B088-B099 | Maata's Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting837420210207-4Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting837420210207-4Tractor Trailer - 60 Ton- After Jan 105611.95Inv#109 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8374 | 20210207-4 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 12 | HR | 0 | 0 |  |  | 600 | 78 | 678 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Landfill back to Maata's to do widening Gary ran grader in Landfill and Maata's during the day, Evan ran grader for 1/2 the night. Shawn Panamick worked with plow truck, doing entrances and roadways as much as he could, plus coordinating and float moves. | 3 | B088-B099 | Maata's Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting837420210207-4Pickup w/ plow12600 | Corbiere and Sons Contracting837420210207-4Pickup w/ plow12600Inv#109 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8374 | 20210207-4 | 53510311 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Landfill back to Maata's to do widening Gary ran grader in Landfill and Maata's during the day, Evan ran grader for 1/2 the night. Shawn Panamick worked with plow truck, doing entrances and roadways as much as he could, plus coordinating and float moves. | 3 | B088-B099 | Maata's Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting837420210207-4L.O.A.4840 | Corbiere and Sons Contracting837420210207-4L.O.A.4840Inv#109 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8374 | 20210207-4 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 29.5 | HR |  |  | 75 | 0 | 2212.5 | 287.625 | 2500.125 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Landfill back to Maata's to do widening Gary ran grader in Landfill and Maata's during the day, Evan ran grader for 1/2 the night. Shawn Panamick worked with plow truck, doing entrances and roadways as much as he could, plus coordinating and float moves. | 3 | B088-B099 | Maata's Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting837420210207-4Operator - Principle - After Jan 1029.52212.5 | Corbiere and Sons Contracting837420210207-4Operator - Principle - After Jan 1029.52212.5Inv#109 | [5 empty] | 1 | 2212.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8374 | 20210207-4 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Landfill back to Maata's to do widening Gary ran grader in Landfill and Maata's during the day, Evan ran grader for 1/2 the night. Shawn Panamick worked with plow truck, doing entrances and roadways as much as he could, plus coordinating and float moves. | 3 | B088-B099 | Maata's Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting837420210207-4Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting837420210207-4Driver - AZ - After Jan 105350Inv#109 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8375 | 20210207-5 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan opened up Gurney, Gravel and Pays Plat East with the plow truck | 3 | B211-C010 | Gravel River Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting837520210207-5Pickup w/ plow6300 | Corbiere and Sons Contracting837520210207-5Pickup w/ plow6300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8375 | 20210207-5 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan opened up Gurney, Gravel and Pays Plat East with the plow truck | 3 | B211-C010 | Gravel River Road | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting837520210207-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting837520210207-5Operator - Principle - After Jan 106450Inv#109 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8376 | 20210207-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Mink Creek, labourers did flagging for float movesRichard ran grader in Mink | 6 | C244-C247 | Mink Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837620210207-6Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting837620210207-6Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#109 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8376 | 20210207-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Mink Creek, labourers did flagging for float movesRichard ran grader in Mink | 6 | C244-C247 | Mink Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837620210207-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting837620210207-6Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8376 | 20210207-6 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Mink Creek, labourers did flagging for float movesRichard ran grader in Mink | 6 | C244-C247 | Mink Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837620210207-6Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting837620210207-6Tractor Trailer - 60 Ton- After Jan 103367.17Inv#109 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8376 | 20210207-6 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Mink Creek, labourers did flagging for float movesRichard ran grader in Mink | 6 | C244-C247 | Mink Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837620210207-6L.O.A.4840 | Corbiere and Sons Contracting837620210207-6L.O.A.4840Inv#109 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8376 | 20210207-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Mink Creek, labourers did flagging for float movesRichard ran grader in Mink | 6 | C244-C247 | Mink Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837620210207-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting837620210207-6Operator - Principle - After Jan 104300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8376 | 20210207-6 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Mink Creek, labourers did flagging for float movesRichard ran grader in Mink | 6 | C244-C247 | Mink Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837620210207-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting837620210207-6Driver - AZ - After Jan 103210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8376 | 20210207-6 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Mink Creek, labourers did flagging for float movesRichard ran grader in Mink | 6 | C244-C247 | Mink Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837620210207-6Labourer - General - After Jan 104240 | Corbiere and Sons Contracting837620210207-6Labourer - General - After Jan 104240Inv#109 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8377 | 20210207-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Deadhorse, labourers did flagging for float movesRichard ran grader in Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837720210207-7Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting837720210207-7Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#109 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8377 | 20210207-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Deadhorse, labourers did flagging for float movesRichard ran grader in Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837720210207-7Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting837720210207-7Tractor Trailer - 60 Ton- After Jan 103367.17Inv#109 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8377 | 20210207-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Deadhorse, labourers did flagging for float movesRichard ran grader in Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837720210207-7Pickup w/ plow and sander6480 | Corbiere and Sons Contracting837720210207-7Pickup w/ plow and sander6480Inv#109 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8377 | 20210207-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Deadhorse, labourers did flagging for float movesRichard ran grader in Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837720210207-7Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting837720210207-7Operator - Principle - After Jan 1010750Inv#109 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8377 | 20210207-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Deadhorse, labourers did flagging for float movesRichard ran grader in Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837720210207-7Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting837720210207-7Operator - Intermdiate - After Jan 106420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8377 | 20210207-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Deadhorse, labourers did flagging for float movesRichard ran grader in Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837720210207-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting837720210207-7Driver - AZ - After Jan 103210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8377 | 20210207-7 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Deadhorse, labourers did flagging for float movesRichard ran grader in Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837720210207-7Labourer - General - After Jan 104240 | Corbiere and Sons Contracting837720210207-7Labourer - General - After Jan 104240Inv#109 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8378 | 20210207-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Ripple, labourers did flagging for float movesRichard ran grader in Ripple | 6 | C203-C209 | Ripple Lake | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837820210207-8Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting837820210207-8Grader - Cat 12 to 14 or equal- After Jan 102253.96Inv#109 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8378 | 20210207-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Ripple, labourers did flagging for float movesRichard ran grader in Ripple | 6 | C203-C209 | Ripple Lake | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837820210207-8Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting837820210207-8Tractor Trailer - 60 Ton- After Jan 102244.78Inv#109 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8378 | 20210207-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Ripple, labourers did flagging for float movesRichard ran grader in Ripple | 6 | C203-C209 | Ripple Lake | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837820210207-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting837820210207-8Operator - Principle - After Jan 104300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8378 | 20210207-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Ripple, labourers did flagging for float movesRichard ran grader in Ripple | 6 | C203-C209 | Ripple Lake | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837820210207-8Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting837820210207-8Driver - AZ - After Jan 102140Inv#109 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8378 | 20210207-8 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved grader into Ripple, labourers did flagging for float movesRichard ran grader in Ripple | 6 | C203-C209 | Ripple Lake | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837820210207-8Labourer - General - After Jan 104240 | Corbiere and Sons Contracting837820210207-8Labourer - General - After Jan 104240Inv#109 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8379 | 20210207-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding finished off Dead Horse at night and then went to Prairie River to clear snow with dozerTerry Boucher worked on dozer plowing snow during the day | 6 | C171-C185 | Priarie River | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837920210207-9Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting837920210207-9Dozer D6 or equal- After Jan 10121577.76Inv#109 | [5 empty] | 1 | 1577.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8379 | 20210207-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding finished off Dead Horse at night and then went to Prairie River to clear snow with dozerTerry Boucher worked on dozer plowing snow during the day | 6 | C171-C185 | Priarie River | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837920210207-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting837920210207-9Light Truck - Pick up- After Jan 103731.25Inv#109 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8379 | 20210207-9 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding finished off Dead Horse at night and then went to Prairie River to clear snow with dozerTerry Boucher worked on dozer plowing snow during the day | 6 | C171-C185 | Priarie River | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837920210207-9Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting837920210207-9Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8379 | 20210207-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding finished off Dead Horse at night and then went to Prairie River to clear snow with dozerTerry Boucher worked on dozer plowing snow during the day | 6 | C171-C185 | Priarie River | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837920210207-9Pickup w/ plow and sander6480 | Corbiere and Sons Contracting837920210207-9Pickup w/ plow and sander6480Inv#109 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8379 | 20210207-9 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding finished off Dead Horse at night and then went to Prairie River to clear snow with dozerTerry Boucher worked on dozer plowing snow during the day | 6 | C171-C185 | Priarie River | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837920210207-9L.O.A.3630 | Corbiere and Sons Contracting837920210207-9L.O.A.3630Inv#109 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8379 | 20210207-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding finished off Dead Horse at night and then went to Prairie River to clear snow with dozerTerry Boucher worked on dozer plowing snow during the day | 6 | C171-C185 | Priarie River | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837920210207-9Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting837920210207-9Operator - Principle - After Jan 10171275Inv#109 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8379 | 20210207-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding finished off Dead Horse at night and then went to Prairie River to clear snow with dozerTerry Boucher worked on dozer plowing snow during the day | 6 | C171-C185 | Priarie River | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837920210207-9Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting837920210207-9Operator - Intermdiate - After Jan 106420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8379 | 20210207-9 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-07 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron Dowding finished off Dead Horse at night and then went to Prairie River to clear snow with dozerTerry Boucher worked on dozer plowing snow during the day | 6 | C171-C185 | Priarie River | 0 | 44242 |  | 50 | 44244 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting837920210207-9Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting837920210207-9Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8511 | 20210208-10 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 20 | Dynamic | 98.61 | 0 |  |  | 2629.6 | 341.848 | 2971.448 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry ran Dozer in Pays Plat all day / Ron ran dozer in Pays Plat all night | 5 | C031-C049 | Pays Plat River | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting851120210208-10Dozer D6 or equal- After Jan 10202629.6 | Corbiere and Sons Contracting851120210208-10Dozer D6 or equal- After Jan 10202629.6Inv#109 | [5 empty] | 1 | 2629.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8511 | 20210208-10 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry ran Dozer in Pays Plat all day / Ron ran dozer in Pays Plat all night | 5 | C031-C049 | Pays Plat River | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting851120210208-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting851120210208-10Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8511 | 20210208-10 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry ran Dozer in Pays Plat all day / Ron ran dozer in Pays Plat all night | 5 | C031-C049 | Pays Plat River | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting851120210208-10L.O.A.2420 | Corbiere and Sons Contracting851120210208-10L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8511 | 20210208-10 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry ran Dozer in Pays Plat all day / Ron ran dozer in Pays Plat all night | 5 | C031-C049 | Pays Plat River | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting851120210208-10Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting851120210208-10Operator - Principle - After Jan 10221650Inv#109 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8512 | 20210208-11 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard finished touch ups in Dead Horse and was then floated | 6 | C203-C209 | Dead Horse Creek | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851220210208-11Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting851220210208-11Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#109 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8512 | 20210208-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard finished touch ups in Dead Horse and was then floated | 6 | C203-C209 | Dead Horse Creek | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851220210208-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting851220210208-11Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8512 | 20210208-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard finished touch ups in Dead Horse and was then floated | 6 | C203-C209 | Dead Horse Creek | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851220210208-11L.O.A.1210 | Corbiere and Sons Contracting851220210208-11L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8512 | 20210208-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard finished touch ups in Dead Horse and was then floated | 6 | C203-C209 | Dead Horse Creek | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851220210208-11Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting851220210208-11Operator - Principle - After Jan 103225Inv#109 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8513 | 20210208-12 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard was floated by Doug to Santoy Mountain / Evan ran grader all night in Santoy Mountain and Lake | 6 | C155-C157 | Santoy Mountain | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851320210208-12Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting851320210208-12Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv#109 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8513 | 20210208-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard was floated by Doug to Santoy Mountain / Evan ran grader all night in Santoy Mountain and Lake | 6 | C155-C157 | Santoy Mountain | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851320210208-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting851320210208-12Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8513 | 20210208-12 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard was floated by Doug to Santoy Mountain / Evan ran grader all night in Santoy Mountain and Lake | 6 | C155-C157 | Santoy Mountain | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851320210208-12Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting851320210208-12Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8513 | 20210208-12 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard was floated by Doug to Santoy Mountain / Evan ran grader all night in Santoy Mountain and Lake | 6 | C155-C157 | Santoy Mountain | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851320210208-12L.O.A.2420 | Corbiere and Sons Contracting851320210208-12L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8513 | 20210208-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14.5 | HR |  |  | 75 | 0 | 1087.5 | 141.375 | 1228.875 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard was floated by Doug to Santoy Mountain / Evan ran grader all night in Santoy Mountain and Lake | 6 | C155-C157 | Santoy Mountain | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851320210208-12Operator - Principle - After Jan 1014.51087.5 | Corbiere and Sons Contracting851320210208-12Operator - Principle - After Jan 1014.51087.5Inv#109 | [5 empty] | 1 | 1087.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8513 | 20210208-12 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard was floated by Doug to Santoy Mountain / Evan ran grader all night in Santoy Mountain and Lake | 6 | C155-C157 | Santoy Mountain | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851320210208-12Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting851320210208-12Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8514 | 20210208-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on plow truck with sander at Lake A and other areas. | 6 | C129-C151 | Lake A | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851420210208-13Pickup w/ plow and sander11880 | Corbiere and Sons Contracting851420210208-13Pickup w/ plow and sander11880Inv#109 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8514 | 20210208-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on plow truck with sander at Lake A and other areas. | 6 | C129-C151 | Lake A | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851420210208-13L.O.A.1210 | Corbiere and Sons Contracting851420210208-13L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8514 | 20210208-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on plow truck with sander at Lake A and other areas. | 6 | C129-C151 | Lake A | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting851420210208-13Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting851420210208-13Operator - Intermdiate - After Jan 1011770Inv#109 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8507 | 20210208-6 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Maata's to Jackpine - 2 flaggers requiredGary ran grader in Jackpine after float move | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850720210208-6Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting850720210208-6Grader - Cat 12 to 14 or equal- After Jan 107888.86Inv#109 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8507 | 20210208-6 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Maata's to Jackpine - 2 flaggers requiredGary ran grader in Jackpine after float move | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850720210208-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting850720210208-6Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8507 | 20210208-6 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Maata's to Jackpine - 2 flaggers requiredGary ran grader in Jackpine after float move | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850720210208-6Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting850720210208-6Tractor Trailer - 60 Ton- After Jan 106734.34Inv#109 | [5 empty] | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8507 | 20210208-6 | 53510311 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Maata's to Jackpine - 2 flaggers requiredGary ran grader in Jackpine after float move | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850720210208-6L.O.A.4840 | Corbiere and Sons Contracting850720210208-6L.O.A.4840Inv#109 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8507 | 20210208-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Maata's to Jackpine - 2 flaggers requiredGary ran grader in Jackpine after float move | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850720210208-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting850720210208-6Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8507 | 20210208-6 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Maata's to Jackpine - 2 flaggers requiredGary ran grader in Jackpine after float move | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850720210208-6Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting850720210208-6Driver - AZ - After Jan 106420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8507 | 20210208-6 | 53510311 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader from Maata's to Jackpine - 2 flaggers requiredGary ran grader in Jackpine after float move | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850720210208-6Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting850720210208-6Labourer - General - After Jan 1010600Inv#109 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8508 | 20210208-7 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 2 | HR | 0 | 0 |  |  | 100 | 13 | 113 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn Panamick checked out Maata's Rd | 3 | B088-B099 | Maata's Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850820210208-7Pickup w/ plow2100 | Corbiere and Sons Contracting850820210208-7Pickup w/ plow2100Inv#109 | [5 empty] | 1 | 100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8508 | 20210208-7 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn Panamick checked out Maata's Rd | 3 | B088-B099 | Maata's Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850820210208-7Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting850820210208-7Operator - Principle - After Jan 102150Inv#109 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8509 | 20210208-8 | 53510311 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn Panamick plowed entrance to Gurney | 3 | B187-B193 | Gurney Lake Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850920210208-8Pickup w/ plow4200 | Corbiere and Sons Contracting850920210208-8Pickup w/ plow4200Inv#109 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8509 | 20210208-8 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn Panamick plowed entrance to Gurney | 3 | B187-B193 | Gurney Lake Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting850920210208-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting850920210208-8Operator - Principle - After Jan 104300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8510 | 20210208-9 | 53510411 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed Nishin Road to the Y for Double Star | 4 | C011-C029 | Nishin Creek Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting851020210208-9Pickup w/ plow6300 | Corbiere and Sons Contracting851020210208-9Pickup w/ plow6300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8510 | 20210208-9 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed Nishin Road to the Y for Double Star | 4 | C011-C029 | Nishin Creek Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting851020210208-9L.O.A.1210 | Corbiere and Sons Contracting851020210208-9L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8510 | 20210208-9 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-08 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed Nishin Road to the Y for Double Star | 4 | C011-C029 | Nishin Creek Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting851020210208-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting851020210208-9Operator - Principle - After Jan 106450Inv#109 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8520 | 20210209-10 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader into Gravel River Rd, Richard got as far as C-004 with grader. Shawn helping with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting852020210209-10Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting852020210209-10Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#109 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8520 | 20210209-10 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader into Gravel River Rd, Richard got as far as C-004 with grader. Shawn helping with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting852020210209-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting852020210209-10Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8520 | 20210209-10 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader into Gravel River Rd, Richard got as far as C-004 with grader. Shawn helping with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting852020210209-10Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting852020210209-10Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8520 | 20210209-10 | 53510411 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader into Gravel River Rd, Richard got as far as C-004 with grader. Shawn helping with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting852020210209-10Pickup w/ plow4200 | Corbiere and Sons Contracting852020210209-10Pickup w/ plow4200Inv#109 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8520 | 20210209-10 | 53510411 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader into Gravel River Rd, Richard got as far as C-004 with grader. Shawn helping with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting852020210209-10L.O.A.2420 | Corbiere and Sons Contracting852020210209-10L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8520 | 20210209-10 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15.5 | HR |  |  | 75 | 0 | 1162.5 | 151.125 | 1313.625 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader into Gravel River Rd, Richard got as far as C-004 with grader. Shawn helping with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting852020210209-10Operator - Principle - After Jan 1015.51162.5 | Corbiere and Sons Contracting852020210209-10Operator - Principle - After Jan 1015.51162.5Inv#109 | [5 empty] | 1 | 1162.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8520 | 20210209-10 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader into Gravel River Rd, Richard got as far as C-004 with grader. Shawn helping with plow truck | 4 | B211-C010 | Gravel River Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting852020210209-10Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting852020210209-10Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8521 | 20210209-11 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and pickup w/plow opened up Neys and Culvert Creek | 6 | C219-C236 | Neys | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting852120210209-11Pickup w/ plow4200 | Corbiere and Sons Contracting852120210209-11Pickup w/ plow4200Inv#109 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8521 | 20210209-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and pickup w/plow opened up Neys and Culvert Creek | 6 | C219-C236 | Neys | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting852120210209-11Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting852120210209-11Operator - Principle - After Jan 104300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8522 | 20210209-12 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and pickup w/plow opened up Neys and Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting852220210209-12Pickup w/ plow4200 | Corbiere and Sons Contracting852220210209-12Pickup w/ plow4200Inv#109 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8522 | 20210209-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and pickup w/plow opened up Neys and Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting852220210209-12Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting852220210209-12Operator - Principle - After Jan 104300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8393 | 20210209-6 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on road into C-195, walked excavator into first fork road. | 6 | C186-C195 | Del Lake | 0 | 44242 |  | 36 | 44244 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting839320210209-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting839320210209-6Excavator - 36 ton- After Jan 10121763.52Inv#109 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8393 | 20210209-6 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on road into C-195, walked excavator into first fork road. | 6 | C186-C195 | Del Lake | 0 | 44242 |  | 36 | 44244 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting839320210209-6Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting839320210209-6Excavator Thumb - 30 - 50 ton- After Jan 10112.21Inv#109 | [5 empty] | 1 | 12.21 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8393 | 20210209-6 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on road into C-195, walked excavator into first fork road. | 6 | C186-C195 | Del Lake | 0 | 44242 |  | 36 | 44244 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting839320210209-6Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting839320210209-6Excavator Hammer - 30 - 50 ton- After Jan 1011697.18Inv#109 | [5 empty] | 1 | 697.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8393 | 20210209-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on road into C-195, walked excavator into first fork road. | 6 | C186-C195 | Del Lake | 0 | 44242 |  | 36 | 44244 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting839320210209-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting839320210209-6Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8393 | 20210209-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on road into C-195, walked excavator into first fork road. | 6 | C186-C195 | Del Lake | 0 | 44242 |  | 36 | 44244 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting839320210209-6L.O.A.1210 | Corbiere and Sons Contracting839320210209-6L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8393 | 20210209-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on road into C-195, walked excavator into first fork road. | 6 | C186-C195 | Del Lake | 0 | 44242 |  | 36 | 44244 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting839320210209-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting839320210209-6Operator - Principle - After Jan 1012900Inv#109 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8517 | 20210209-7 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 19 | Dynamic | 98.61 | 0 |  |  | 2498.12 | 324.7556 | 2822.8756 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved DZ from Pays Plat to Deadhead to clear tower B-100Terry worked on dozer after being floated / Ron worked all night | 3 | B100-B109 | Doghead Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851720210209-7Dozer D6 or equal- After Jan 10192498.12 | Corbiere and Sons Contracting851720210209-7Dozer D6 or equal- After Jan 10192498.12Inv#109 | [5 empty] | 1 | 2498.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8517 | 20210209-7 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved DZ from Pays Plat to Deadhead to clear tower B-100Terry worked on dozer after being floated / Ron worked all night | 3 | B100-B109 | Doghead Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851720210209-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting851720210209-7Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8517 | 20210209-7 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved DZ from Pays Plat to Deadhead to clear tower B-100Terry worked on dozer after being floated / Ron worked all night | 3 | B100-B109 | Doghead Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851720210209-7Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting851720210209-7Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8517 | 20210209-7 | 53510311 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved DZ from Pays Plat to Deadhead to clear tower B-100Terry worked on dozer after being floated / Ron worked all night | 3 | B100-B109 | Doghead Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851720210209-7L.O.A.3630 | Corbiere and Sons Contracting851720210209-7L.O.A.3630Inv#109 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8517 | 20210209-7 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved DZ from Pays Plat to Deadhead to clear tower B-100Terry worked on dozer after being floated / Ron worked all night | 3 | B100-B109 | Doghead Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851720210209-7Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting851720210209-7Operator - Principle - After Jan 10231725Inv#109 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8517 | 20210209-7 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved DZ from Pays Plat to Deadhead to clear tower B-100Terry worked on dozer after being floated / Ron worked all night | 3 | B100-B109 | Doghead Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851720210209-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting851720210209-7Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8518 | 20210209-8 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Jackpine to Gurney Evan worked across accesses all night | 3 | B187-B193 | Gurney Lake Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851820210209-8Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting851820210209-8Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#109 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8518 | 20210209-8 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Jackpine to Gurney Evan worked across accesses all night | 3 | B187-B193 | Gurney Lake Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851820210209-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting851820210209-8Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8518 | 20210209-8 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Jackpine to Gurney Evan worked across accesses all night | 3 | B187-B193 | Gurney Lake Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851820210209-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting851820210209-8Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8518 | 20210209-8 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Jackpine to Gurney Evan worked across accesses all night | 3 | B187-B193 | Gurney Lake Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851820210209-8L.O.A.1210 | Corbiere and Sons Contracting851820210209-8L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8518 | 20210209-8 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Jackpine to Gurney Evan worked across accesses all night | 3 | B187-B193 | Gurney Lake Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851820210209-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting851820210209-8Operator - Principle - After Jan 1011.5862.5Inv#109 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8518 | 20210209-8 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff floated Grader from Jackpine to Gurney Evan worked across accesses all night | 3 | B187-B193 | Gurney Lake Road | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851820210209-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting851820210209-8Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8519 | 20210209-9 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader in Jackpine | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851920210209-9Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting851920210209-9Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#109 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8519 | 20210209-9 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader in Jackpine | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851920210209-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting851920210209-9Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8519 | 20210209-9 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader in Jackpine | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851920210209-9L.O.A.1210 | Corbiere and Sons Contracting851920210209-9L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8519 | 20210209-9 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-09 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader in Jackpine | 3 | B159-B160 | Jackpine | 0 | 44249 |  | 50 | 44249 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting851920210209-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting851920210209-9Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8413 | 20210210-10 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved grader from Gurney to Pays Plat River Rd E; Len worked on graderDarrel went around helping with plow truck and sanding areas as needed. | 5 | C036-C049 | Pays Plat River | 0 | 44237 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841320210210-10Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting841320210210-10Grader - Cat 12 to 14 or equal- After Jan 107888.86Inv#109 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8413 | 20210210-10 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved grader from Gurney to Pays Plat River Rd E; Len worked on graderDarrel went around helping with plow truck and sanding areas as needed. | 5 | C036-C049 | Pays Plat River | 0 | 44237 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841320210210-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting841320210210-10Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8413 | 20210210-10 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved grader from Gurney to Pays Plat River Rd E; Len worked on graderDarrel went around helping with plow truck and sanding areas as needed. | 5 | C036-C049 | Pays Plat River | 0 | 44237 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841320210210-10Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting841320210210-10Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8413 | 20210210-10 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved grader from Gurney to Pays Plat River Rd E; Len worked on graderDarrel went around helping with plow truck and sanding areas as needed. | 5 | C036-C049 | Pays Plat River | 0 | 44237 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841320210210-10Pickup w/ plow and sander11880 | Corbiere and Sons Contracting841320210210-10Pickup w/ plow and sander11880Inv#109 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8413 | 20210210-10 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved grader from Gurney to Pays Plat River Rd E; Len worked on graderDarrel went around helping with plow truck and sanding areas as needed. | 5 | C036-C049 | Pays Plat River | 0 | 44237 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841320210210-10L.O.A.3630 | Corbiere and Sons Contracting841320210210-10L.O.A.3630Inv#109 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8413 | 20210210-10 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved grader from Gurney to Pays Plat River Rd E; Len worked on graderDarrel went around helping with plow truck and sanding areas as needed. | 5 | C036-C049 | Pays Plat River | 0 | 44237 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841320210210-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting841320210210-10Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8413 | 20210210-10 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved grader from Gurney to Pays Plat River Rd E; Len worked on graderDarrel went around helping with plow truck and sanding areas as needed. | 5 | C036-C049 | Pays Plat River | 0 | 44237 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841320210210-10Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting841320210210-10Operator - Intermdiate - After Jan 1011770Inv#109 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8413 | 20210210-10 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff moved grader from Gurney to Pays Plat River Rd E; Len worked on graderDarrel went around helping with plow truck and sanding areas as needed. | 5 | C036-C049 | Pays Plat River | 0 | 44237 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841320210210-10Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting841320210210-10Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8414 | 20210210-11 | 53510511 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse did orientation and drove loader to C-124 to clear access tower. | 5 | C117-C124 | Mill Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841420210210-11Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting841420210210-11Loader JD 524 to 624 or equal9891Inv#109 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8414 | 20210210-11 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse did orientation and drove loader to C-124 to clear access tower. | 5 | C117-C124 | Mill Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841420210210-11L.O.A.1210 | Corbiere and Sons Contracting841420210210-11L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8414 | 20210210-11 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 9 | HR |  |  | 70 | 0 | 630 | 81.9 | 711.9 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse did orientation and drove loader to C-124 to clear access tower. | 5 | C117-C124 | Mill Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting841420210210-11Operator - Intermdiate - After Jan 109630 | Corbiere and Sons Contracting841420210210-11Operator - Intermdiate - After Jan 109630Inv#109 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8415 | 20210210-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug went in and sanded Hare Lake Rd | 6 | C257-C267 | Hare Lake | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting841520210210-12Pickup w/ plow and sander5400 | Corbiere and Sons Contracting841520210210-12Pickup w/ plow and sander5400Inv#109 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8415 | 20210210-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug went in and sanded Hare Lake Rd | 6 | C257-C267 | Hare Lake | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting841520210210-12Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting841520210210-12Operator - Intermdiate - After Jan 105350Inv#109 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8454 | 20210210-15 | 53510211 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 opened up B-051-B-053 Plow truck opened up turnaround at Valley Road | 2 | B045 - B053 | Squaw Valley | 0 | 44245 |  | 37 | 44247 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting845420210210-15Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting845420210210-15Dozer D6 or equal- After Jan 106788.88Inv#109 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8454 | 20210210-15 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 opened up B-051-B-053 Plow truck opened up turnaround at Valley Road | 2 | B045 - B053 | Squaw Valley | 0 | 44245 |  | 37 | 44247 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting845420210210-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting845420210210-15Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8454 | 20210210-15 | 53510211 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 opened up B-051-B-053 Plow truck opened up turnaround at Valley Road | 2 | B045 - B053 | Squaw Valley | 0 | 44245 |  | 37 | 44247 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting845420210210-15Pickup w/ plow5250 | Corbiere and Sons Contracting845420210210-15Pickup w/ plow5250Inv#109 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8454 | 20210210-15 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 opened up B-051-B-053 Plow truck opened up turnaround at Valley Road | 2 | B045 - B053 | Squaw Valley | 0 | 44245 |  | 37 | 44247 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting845420210210-15Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting845420210210-15Operator - Principle - After Jan 108600Inv#109 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8454 | 20210210-15 | 53510211 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5.5 | HR |  |  | 60 | 0 | 330 | 42.9 | 372.9 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 opened up B-051-B-053 Plow truck opened up turnaround at Valley Road | 2 | B045 - B053 | Squaw Valley | 0 | 44245 |  | 37 | 44247 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting845420210210-15Labourer - General - After Jan 105.5330 | Corbiere and Sons Contracting845420210210-15Labourer - General - After Jan 105.5330Inv#109 | [5 empty] | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8455 | 20210210-16 | 53510211 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow truck opened up turnaround for the float at Stewart Lake Rd | 2 | B030 - B044 | Stewart Lake | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting845520210210-16Pickup w/ plow5250 | Corbiere and Sons Contracting845520210210-16Pickup w/ plow5250Inv#109 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8455 | 20210210-16 | 53510211 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5.5 | HR |  |  | 60 | 0 | 330 | 42.9 | 372.9 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow truck opened up turnaround for the float at Stewart Lake Rd | 2 | B030 - B044 | Stewart Lake | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting845520210210-16Labourer - General - After Jan 105.5330 | Corbiere and Sons Contracting845520210210-16Labourer - General - After Jan 105.5330Inv#109 | [5 empty] | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8409 | 20210210-6 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting840920210210-6Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting840920210210-6Excavator - 36 ton- After Jan 10142057.44Inv#109 | [5 empty] | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8409 | 20210210-6 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting840920210210-6Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting840920210210-6Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#109 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8409 | 20210210-6 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting840920210210-6Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting840920210210-6Excavator Hammer - 30 - 50 ton- After Jan 108507.04Inv#109 | [5 empty] | 1 | 507.04 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8409 | 20210210-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting840920210210-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting840920210210-6Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8409 | 20210210-6 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting840920210210-6L.O.A.2420 | Corbiere and Sons Contracting840920210210-6L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8409 | 20210210-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting840920210210-6Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting840920210210-6Operator - Principle - After Jan 10141050Inv#109 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8411 | 20210210-8 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug on pickup w/plow and sander working across Dog head all morningTerry on dozer in Doghead all day clearing to B-100. | 3 | B100-B109 | Doghead Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting841120210210-8Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting841120210210-8Dozer D6 or equal- After Jan 10101314.8Inv#109 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8411 | 20210210-8 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug on pickup w/plow and sander working across Dog head all morningTerry on dozer in Doghead all day clearing to B-100. | 3 | B100-B109 | Doghead Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting841120210210-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting841120210210-8Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8411 | 20210210-8 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug on pickup w/plow and sander working across Dog head all morningTerry on dozer in Doghead all day clearing to B-100. | 3 | B100-B109 | Doghead Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting841120210210-8Pickup w/ plow and sander6480 | Corbiere and Sons Contracting841120210210-8Pickup w/ plow and sander6480Inv#109 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8411 | 20210210-8 | 53510311 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug on pickup w/plow and sander working across Dog head all morningTerry on dozer in Doghead all day clearing to B-100. | 3 | B100-B109 | Doghead Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting841120210210-8L.O.A.2420 | Corbiere and Sons Contracting841120210210-8L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8411 | 20210210-8 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug on pickup w/plow and sander working across Dog head all morningTerry on dozer in Doghead all day clearing to B-100. | 3 | B100-B109 | Doghead Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting841120210210-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting841120210210-8Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8411 | 20210210-8 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug on pickup w/plow and sander working across Dog head all morningTerry on dozer in Doghead all day clearing to B-100. | 3 | B100-B109 | Doghead Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting841120210210-8Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting841120210210-8Operator - Intermdiate - After Jan 106420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8412 | 20210210-9 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 18.5 | Dynamic | 95.24 | 0 |  |  | 2349.13 | 305.3869 | 2654.5169 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard ran grader in Gravel River road for Daylight; Evan ray grader for Night shiftShawn Panamick working on plow truck clearing entrances and coordinating/planning activities. | 4 | B211-C010 | Gravel River Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting841220210210-9Grader - Cat 12 to 14 or equal- After Jan 1018.52349.13 | Corbiere and Sons Contracting841220210210-9Grader - Cat 12 to 14 or equal- After Jan 1018.52349.13Inv#109 | [5 empty] | 1 | 2349.13 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8412 | 20210210-9 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard ran grader in Gravel River road for Daylight; Evan ray grader for Night shiftShawn Panamick working on plow truck clearing entrances and coordinating/planning activities. | 4 | B211-C010 | Gravel River Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting841220210210-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting841220210210-9Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8412 | 20210210-9 | 53510411 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard ran grader in Gravel River road for Daylight; Evan ray grader for Night shiftShawn Panamick working on plow truck clearing entrances and coordinating/planning activities. | 4 | B211-C010 | Gravel River Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting841220210210-9Pickup w/ plow11550 | Corbiere and Sons Contracting841220210210-9Pickup w/ plow11550Inv#109 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8412 | 20210210-9 | 53510411 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard ran grader in Gravel River road for Daylight; Evan ray grader for Night shiftShawn Panamick working on plow truck clearing entrances and coordinating/planning activities. | 4 | B211-C010 | Gravel River Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting841220210210-9L.O.A.3630 | Corbiere and Sons Contracting841220210210-9L.O.A.3630Inv#109 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8412 | 20210210-9 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 31.5 | HR |  |  | 75 | 0 | 2362.5 | 307.125 | 2669.625 | 2021-02-10 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard ran grader in Gravel River road for Daylight; Evan ray grader for Night shiftShawn Panamick working on plow truck clearing entrances and coordinating/planning activities. | 4 | B211-C010 | Gravel River Road | 0 | 44244 |  | 37 | 44245 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting841220210210-9Operator - Principle - After Jan 1031.52362.5 | Corbiere and Sons Contracting841220210210-9Operator - Principle - After Jan 1031.52362.5Inv#109 | [5 empty] | 1 | 2362.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8458 | 20210211-11 | 53510311 | Access | 0 | Loader JD 744 to 844 or equal | 162 | 3 | HR | 121.5 | 0 |  |  | 486 | 63.18 | 549.18 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | LD-01 opened up B-092 tower and around skid steerFloat moved LD-01 to Maata's Road and back to North Shore yard. | 3 | B088-B099 | Maata's Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting845820210211-11Loader JD 744 to 844 or equal3486 | Corbiere and Sons Contracting845820210211-11Loader JD 744 to 844 or equal3486Inv#109 | [5 empty] | 1 | 486 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8458 | 20210211-11 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | LD-01 opened up B-092 tower and around skid steerFloat moved LD-01 to Maata's Road and back to North Shore yard. | 3 | B088-B099 | Maata's Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting845820210211-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting845820210211-11Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8458 | 20210211-11 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | LD-01 opened up B-092 tower and around skid steerFloat moved LD-01 to Maata's Road and back to North Shore yard. | 3 | B088-B099 | Maata's Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting845820210211-11Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting845820210211-11Tractor Trailer - 60 Ton- After Jan 103367.17Inv#109 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8458 | 20210211-11 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | LD-01 opened up B-092 tower and around skid steerFloat moved LD-01 to Maata's Road and back to North Shore yard. | 3 | B088-B099 | Maata's Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting845820210211-11Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting845820210211-11Operator - Principle - After Jan 105375Inv#109 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8458 | 20210211-11 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | LD-01 opened up B-092 tower and around skid steerFloat moved LD-01 to Maata's Road and back to North Shore yard. | 3 | B088-B099 | Maata's Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting845820210211-11Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting845820210211-11Driver - AZ - After Jan 103210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8459 | 20210211-12 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 to Fire Hill Rd EDZ-01 opened up the road from B-136 - B-144 and made a turnaround further in to shorten the walk for the grinding crew. | 3 | B136-B144 | Fire Hill Road East | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting845920210211-12Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting845920210211-12Dozer D6 or equal- After Jan 107920.36Inv#109 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8459 | 20210211-12 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 to Fire Hill Rd EDZ-01 opened up the road from B-136 - B-144 and made a turnaround further in to shorten the walk for the grinding crew. | 3 | B136-B144 | Fire Hill Road East | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting845920210211-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting845920210211-12Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8459 | 20210211-12 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 to Fire Hill Rd EDZ-01 opened up the road from B-136 - B-144 and made a turnaround further in to shorten the walk for the grinding crew. | 3 | B136-B144 | Fire Hill Road East | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting845920210211-12Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting845920210211-12Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8459 | 20210211-12 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 to Fire Hill Rd EDZ-01 opened up the road from B-136 - B-144 and made a turnaround further in to shorten the walk for the grinding crew. | 3 | B136-B144 | Fire Hill Road East | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting845920210211-12Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting845920210211-12Operator - Principle - After Jan 109675Inv#109 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8459 | 20210211-12 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 to Fire Hill Rd EDZ-01 opened up the road from B-136 - B-144 and made a turnaround further in to shorten the walk for the grinding crew. | 3 | B136-B144 | Fire Hill Road East | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting845920210211-12Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting845920210211-12Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8421 | 20210211-4 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting842120210211-4Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting842120210211-4Excavator - 36 ton- After Jan 10142057.44Inv#109 | [5 empty] | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8421 | 20210211-4 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting842120210211-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting842120210211-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#109 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8421 | 20210211-4 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting842120210211-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting842120210211-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#109 | [5 empty] | 1 | 570.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8421 | 20210211-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting842120210211-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting842120210211-4Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8421 | 20210211-4 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting842120210211-4L.O.A.2420 | Corbiere and Sons Contracting842120210211-4L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8421 | 20210211-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake, second operator assisted in moving equipment and pick up ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting842120210211-4Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting842120210211-4Operator - Principle - After Jan 10141050Inv#109 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8423 | 20210211-6 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer moved into Landfill to do widening - Terry ran it until 7pm; Ron took overRichard on Pikcup w/plow and sander across Landfill | 3 | B078-B084 | Landfill Road | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting842320210211-6Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting842320210211-6Dozer D6 or equal- After Jan 105657.4Inv#109 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8423 | 20210211-6 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer moved into Landfill to do widening - Terry ran it until 7pm; Ron took overRichard on Pikcup w/plow and sander across Landfill | 3 | B078-B084 | Landfill Road | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting842320210211-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting842320210211-6Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8423 | 20210211-6 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer moved into Landfill to do widening - Terry ran it until 7pm; Ron took overRichard on Pikcup w/plow and sander across Landfill | 3 | B078-B084 | Landfill Road | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting842320210211-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting842320210211-6Pickup w/ plow and sander11880Inv#109 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8423 | 20210211-6 | 53510311 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer moved into Landfill to do widening - Terry ran it until 7pm; Ron took overRichard on Pikcup w/plow and sander across Landfill | 3 | B078-B084 | Landfill Road | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting842320210211-6L.O.A.3630 | Corbiere and Sons Contracting842320210211-6L.O.A.3630Inv#109 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8423 | 20210211-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer moved into Landfill to do widening - Terry ran it until 7pm; Ron took overRichard on Pikcup w/plow and sander across Landfill | 3 | B078-B084 | Landfill Road | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting842320210211-6Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting842320210211-6Operator - Principle - After Jan 1010750Inv#109 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8423 | 20210211-6 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer moved into Landfill to do widening - Terry ran it until 7pm; Ron took overRichard on Pikcup w/plow and sander across Landfill | 3 | B078-B084 | Landfill Road | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting842320210211-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting842320210211-6Operator - Intermdiate - After Jan 1011770Inv#109 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8424 | 20210211-7 | 53510511 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 8 | HR | 74.25 | 0 |  |  | 792 | 102.96 | 894.96 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel drove loader to clear Mill Rd | 5 | C117-C124 | Mill Road | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting842420210211-7Loader JD 524 to 624 or equal8792 | Corbiere and Sons Contracting842420210211-7Loader JD 524 to 624 or equal8792Inv#109 | [5 empty] | 1 | 792 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8424 | 20210211-7 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel drove loader to clear Mill Rd | 5 | C117-C124 | Mill Road | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting842420210211-7L.O.A.1210 | Corbiere and Sons Contracting842420210211-7L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8424 | 20210211-7 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel drove loader to clear Mill Rd | 5 | C117-C124 | Mill Road | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting842420210211-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting842420210211-7Operator - Principle - After Jan 108600Inv#109 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8425 | 20210211-8 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 12 | HR | 0 | 0 |  |  | 600 | 78 | 678 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went to clear Antler Lake to C-056 for DSD. | 5 | C050-C069 | Antler Lake | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting842520210211-8Pickup w/ plow12600 | Corbiere and Sons Contracting842520210211-8Pickup w/ plow12600Inv#109 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8425 | 20210211-8 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went to clear Antler Lake to C-056 for DSD. | 5 | C050-C069 | Antler Lake | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting842520210211-8L.O.A.1210 | Corbiere and Sons Contracting842520210211-8L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8425 | 20210211-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-11 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went to clear Antler Lake to C-056 for DSD. | 5 | C050-C069 | Antler Lake | 0 | 44244 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting842520210211-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting842520210211-8Operator - Principle - After Jan 1012900Inv#109 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8460 | 20210212-13 | 53510411 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Fire Hill Road E to Little Gravel River Rd DZ-01 opened up road C-202 - C-215 | 4 | B194-B210 | Little Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846020210212-13Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting846020210212-13Dozer D6 or equal- After Jan 1081051.84Inv#109 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8460 | 20210212-13 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Fire Hill Road E to Little Gravel River Rd DZ-01 opened up road C-202 - C-215 | 4 | B194-B210 | Little Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846020210212-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting846020210212-13Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8460 | 20210212-13 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Fire Hill Road E to Little Gravel River Rd DZ-01 opened up road C-202 - C-215 | 4 | B194-B210 | Little Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846020210212-13Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting846020210212-13Tractor Trailer - 60 Ton- After Jan 102244.78Inv#109 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8460 | 20210212-13 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Fire Hill Road E to Little Gravel River Rd DZ-01 opened up road C-202 - C-215 | 4 | B194-B210 | Little Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846020210212-13Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting846020210212-13Operator - Principle - After Jan 1010750Inv#109 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8460 | 20210212-13 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Fire Hill Road E to Little Gravel River Rd DZ-01 opened up road C-202 - C-215 | 4 | B194-B210 | Little Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846020210212-13Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting846020210212-13Driver - AZ - After Jan 102140Inv#109 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8617 | 20210212-16 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-02-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lkae road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861720210212-16Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting861720210212-16Excavator - 36 ton- After Jan 1081175.68Inv#114 | [5 empty] | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8617 | 20210212-16 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 |  |  |  | 881.76 | 114.6288 | 996.3888 | 2021-02-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lkae road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861720210212-16Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting861720210212-16Excavator - 36 ton- After Jan 106881.76Inv#114 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8617 | 20210212-16 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-02-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lkae road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861720210212-16Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting861720210212-16Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#114 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8617 | 20210212-16 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-02-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lkae road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861720210212-16Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting861720210212-16Excavator Hammer - 30 - 50 ton- After Jan 108507.04Inv#114 | [5 empty] | 1 | 507.04 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8617 | 20210212-16 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lkae road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861720210212-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting861720210212-16Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8617 | 20210212-16 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lkae road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861720210212-16L.O.A.2420 | Corbiere and Sons Contracting861720210212-16L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8617 | 20210212-16 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lkae road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861720210212-16Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting861720210212-16Operator - Principle - After Jan 10141050Inv#114 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8432 | 20210212-4 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 95.24 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine ran grader from 1pm - 10pm | 4 | B211-C010 | Gravel River Road | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting843220210212-4Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting843220210212-4Grader - Cat 12 to 14 or equal- After Jan 108.51079.33Inv#109 | [5 empty] | 1 | 1079.33 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8432 | 20210212-4 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine ran grader from 1pm - 10pm | 4 | B211-C010 | Gravel River Road | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting843220210212-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting843220210212-4Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8432 | 20210212-4 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine ran grader from 1pm - 10pm | 4 | B211-C010 | Gravel River Road | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting843220210212-4L.O.A.1210 | Corbiere and Sons Contracting843220210212-4L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8432 | 20210212-4 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine ran grader from 1pm - 10pm | 4 | B211-C010 | Gravel River Road | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting843220210212-4Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting843220210212-4Operator - Principle - After Jan 109675Inv#109 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8433 | 20210212-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Pays Plat, Terry worked rest of day | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843320210212-5Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting843320210212-5Dozer D6 or equal- After Jan 1081051.84Inv#109 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8433 | 20210212-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Pays Plat, Terry worked rest of day | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843320210212-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting843320210212-5Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8433 | 20210212-5 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Pays Plat, Terry worked rest of day | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843320210212-5Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting843320210212-5Tractor Trailer - 60 Ton- After Jan 105611.95Inv#109 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8433 | 20210212-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Pays Plat, Terry worked rest of day | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843320210212-5L.O.A.2420 | Corbiere and Sons Contracting843320210212-5L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8433 | 20210212-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Pays Plat, Terry worked rest of day | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843320210212-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting843320210212-5Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8433 | 20210212-5 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Pays Plat, Terry worked rest of day | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843320210212-5Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting843320210212-5Driver - AZ - After Jan 105350Inv#109 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8434 | 20210212-6 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran dozer in Cooks on night shift; Shawn P cleared porta potty on Cooks and helped plan/coordinate areas | 5 | C076-C116 | Cook Lake | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843420210212-6Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting843420210212-6Dozer D6 or equal- After Jan 10101314.8Inv#109 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8434 | 20210212-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran dozer in Cooks on night shift; Shawn P cleared porta potty on Cooks and helped plan/coordinate areas | 5 | C076-C116 | Cook Lake | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843420210212-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting843420210212-6Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8434 | 20210212-6 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 12 | HR | 0 | 0 |  |  | 600 | 78 | 678 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran dozer in Cooks on night shift; Shawn P cleared porta potty on Cooks and helped plan/coordinate areas | 5 | C076-C116 | Cook Lake | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843420210212-6Pickup w/ plow12600 | Corbiere and Sons Contracting843420210212-6Pickup w/ plow12600Inv#109 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8434 | 20210212-6 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran dozer in Cooks on night shift; Shawn P cleared porta potty on Cooks and helped plan/coordinate areas | 5 | C076-C116 | Cook Lake | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843420210212-6L.O.A.2420 | Corbiere and Sons Contracting843420210212-6L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8434 | 20210212-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran dozer in Cooks on night shift; Shawn P cleared porta potty on Cooks and helped plan/coordinate areas | 5 | C076-C116 | Cook Lake | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting843420210212-6Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting843420210212-6Operator - Principle - After Jan 10231725Inv#109 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8435 | 20210212-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on PU with plow and sander across Lake A, Santoy Mountain and Prarie River Rd | 6 | C129-C151 | Lake A | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting843520210212-7Pickup w/ plow and sander4320 | Corbiere and Sons Contracting843520210212-7Pickup w/ plow and sander4320Inv#109 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8435 | 20210212-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on PU with plow and sander across Lake A, Santoy Mountain and Prarie River Rd | 6 | C129-C151 | Lake A | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting843520210212-7L.O.A.1210 | Corbiere and Sons Contracting843520210212-7L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8435 | 20210212-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on PU with plow and sander across Lake A, Santoy Mountain and Prarie River Rd | 6 | C129-C151 | Lake A | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting843520210212-7Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting843520210212-7Operator - Intermdiate - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8436 | 20210212-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on PU with plow and sander across Lake A, Santoy Mountain and Prarie River Rd | 6 | C155-C157 | Santoy Mountain | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting843620210212-8Pickup w/ plow and sander4320 | Corbiere and Sons Contracting843620210212-8Pickup w/ plow and sander4320Inv#109 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8436 | 20210212-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on PU with plow and sander across Lake A, Santoy Mountain and Prarie River Rd | 6 | C155-C157 | Santoy Mountain | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting843620210212-8Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting843620210212-8Operator - Intermdiate - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8437 | 20210212-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3.5 |  | 0 | 0 |  |  | 280 | 36.4 | 316.4 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on PU with plow and sander across Lake A, Santoy Mountain and Prarie River Rd | 6 | C171-C185 | Prairie River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting843720210212-9Pickup w/ plow and sander3.5280 | Corbiere and Sons Contracting843720210212-9Pickup w/ plow and sander3.5280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8437 | 20210212-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3.5 | HR |  |  | 70 | 0 | 245 | 31.85 | 276.85 | 2021-02-12 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on PU with plow and sander across Lake A, Santoy Mountain and Prarie River Rd | 6 | C171-C185 | Prairie River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting843720210212-9Operator - Intermdiate - After Jan 103.5245 | Corbiere and Sons Contracting843720210212-9Operator - Intermdiate - After Jan 103.5245Inv#109 | [5 empty] | 1 | 245 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8462 | 20210213-14 | 53510411 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Little Gravel to Gravel RvierDZ-01 opened up road C-002-C-014 | 4 | B211-C010 | Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846220210213-14Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting846220210213-14Dozer D6 or equal- After Jan 107920.36Inv#109 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8462 | 20210213-14 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Little Gravel to Gravel RvierDZ-01 opened up road C-002-C-014 | 4 | B211-C010 | Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846220210213-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting846220210213-14Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8462 | 20210213-14 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Little Gravel to Gravel RvierDZ-01 opened up road C-002-C-014 | 4 | B211-C010 | Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846220210213-14Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting846220210213-14Tractor Trailer - 60 Ton- After Jan 105611.95Inv#109 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8462 | 20210213-14 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Little Gravel to Gravel RvierDZ-01 opened up road C-002-C-014 | 4 | B211-C010 | Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846220210213-14Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting846220210213-14Operator - Principle - After Jan 1010750Inv#109 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8462 | 20210213-14 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Little Gravel to Gravel RvierDZ-01 opened up road C-002-C-014 | 4 | B211-C010 | Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846220210213-14Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting846220210213-14Driver - AZ - After Jan 105350Inv#109 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8618 | 20210213-15 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2021-02-13 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861820210213-15Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting861820210213-15Excavator - 36 ton- After Jan 10142057.44Inv#114 | [5 empty] | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8618 | 20210213-15 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-02-13 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861820210213-15Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting861820210213-15Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#114 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8618 | 20210213-15 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-02-13 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861820210213-15Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting861820210213-15Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#114 | [5 empty] | 1 | 570.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8618 | 20210213-15 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-13 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861820210213-15Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting861820210213-15Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8618 | 20210213-15 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-13 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861820210213-15L.O.A.2420 | Corbiere and Sons Contracting861820210213-15L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8618 | 20210213-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-13 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861820210213-15Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting861820210213-15Operator - Principle - After Jan 10141050Inv#114 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8444 | 20210213-3 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Gravel River Rd | 4 | B211-C010 | Gravel River Road | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting844420210213-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting844420210213-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#109 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8444 | 20210213-3 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Gravel River Rd | 4 | B211-C010 | Gravel River Road | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting844420210213-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting844420210213-3Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8444 | 20210213-3 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Gravel River Rd | 4 | B211-C010 | Gravel River Road | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting844420210213-3L.O.A.1210 | Corbiere and Sons Contracting844420210213-3L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8444 | 20210213-3 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Gravel River Rd | 4 | B211-C010 | Gravel River Road | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting844420210213-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting844420210213-3Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8445 | 20210213-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continuing on dozer at Pays PlatDarrel spent day on pickup with plow and sander opening up skidoo trails | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting844520210213-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting844520210213-4Dozer D6 or equal- After Jan 10101314.8Inv#109 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8445 | 20210213-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continuing on dozer at Pays PlatDarrel spent day on pickup with plow and sander opening up skidoo trails | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting844520210213-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting844520210213-4Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8445 | 20210213-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continuing on dozer at Pays PlatDarrel spent day on pickup with plow and sander opening up skidoo trails | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting844520210213-4Pickup w/ plow and sander11880 | Corbiere and Sons Contracting844520210213-4Pickup w/ plow and sander11880Inv#109 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8445 | 20210213-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continuing on dozer at Pays PlatDarrel spent day on pickup with plow and sander opening up skidoo trails | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting844520210213-4L.O.A.2420 | Corbiere and Sons Contracting844520210213-4L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8445 | 20210213-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continuing on dozer at Pays PlatDarrel spent day on pickup with plow and sander opening up skidoo trails | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting844520210213-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting844520210213-4Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8445 | 20210213-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continuing on dozer at Pays PlatDarrel spent day on pickup with plow and sander opening up skidoo trails | 5 | C031-C049 | Pays Plat River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting844520210213-4Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting844520210213-4Operator - Intermdiate - After Jan 1011770Inv#109 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8446 | 20210213-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8.5 | Dynamic | 98.61 | 0 |  |  | 1117.58 | 145.2854 | 1262.8654 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Dozer in Prarie River trying to open up area from C-171-C173; Evan came in for 4 hours at night to try but couldn't get up hillLeff moved dozer from Cooks to Prarie | 6 | C171-C185 | Prairie River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844620210213-5Dozer D6 or equal- After Jan 108.51117.58 | Corbiere and Sons Contracting844620210213-5Dozer D6 or equal- After Jan 108.51117.58Inv#109 | [5 empty] | 1 | 1117.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8446 | 20210213-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Dozer in Prarie River trying to open up area from C-171-C173; Evan came in for 4 hours at night to try but couldn't get up hillLeff moved dozer from Cooks to Prarie | 6 | C171-C185 | Prairie River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844620210213-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting844620210213-5Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8446 | 20210213-5 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Dozer in Prarie River trying to open up area from C-171-C173; Evan came in for 4 hours at night to try but couldn't get up hillLeff moved dozer from Cooks to Prarie | 6 | C171-C185 | Prairie River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844620210213-5Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting844620210213-5Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8446 | 20210213-5 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Dozer in Prarie River trying to open up area from C-171-C173; Evan came in for 4 hours at night to try but couldn't get up hillLeff moved dozer from Cooks to Prarie | 6 | C171-C185 | Prairie River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844620210213-5L.O.A.3630 | Corbiere and Sons Contracting844620210213-5L.O.A.3630Inv#109 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8446 | 20210213-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Dozer in Prarie River trying to open up area from C-171-C173; Evan came in for 4 hours at night to try but couldn't get up hillLeff moved dozer from Cooks to Prarie | 6 | C171-C185 | Prairie River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844620210213-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting844620210213-5Operator - Principle - After Jan 1011.5862.5Inv#109 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8446 | 20210213-5 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Dozer in Prarie River trying to open up area from C-171-C173; Evan came in for 4 hours at night to try but couldn't get up hillLeff moved dozer from Cooks to Prarie | 6 | C171-C185 | Prairie River | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844620210213-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting844620210213-5Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8447 | 20210213-6 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn plowed snow drifts on Neys and Santoy Lake and coordinatated activities | 6 | C219-C236 | Neys | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844720210213-6Pickup w/ plow6300 | Corbiere and Sons Contracting844720210213-6Pickup w/ plow6300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8447 | 20210213-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn plowed snow drifts on Neys and Santoy Lake and coordinatated activities | 6 | C219-C236 | Neys | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844720210213-6L.O.A.1210 | Corbiere and Sons Contracting844720210213-6L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8447 | 20210213-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn plowed snow drifts on Neys and Santoy Lake and coordinatated activities | 6 | C219-C236 | Neys | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844720210213-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting844720210213-6Operator - Principle - After Jan 106450Inv#109 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8448 | 20210213-7 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn plowed snow drifts on Neys and Santoy Lake and coordinatated activities | 6 | C158-C170 | Santoy Mountain | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844820210213-7Pickup w/ plow6300 | Corbiere and Sons Contracting844820210213-7Pickup w/ plow6300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8448 | 20210213-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-13 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn plowed snow drifts on Neys and Santoy Lake and coordinatated activities | 6 | C158-C170 | Santoy Mountain | 0 | 44245 |  | 37 | 44246 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting844820210213-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting844820210213-7Operator - Principle - After Jan 106450Inv#109 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8472 | 20210214-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn took plow truck with sander in afternoon to go to Culvert Creek before highway got shut down. | 6 | C237-C243 | Culvert Creek | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting847220210214-10Pickup w/ plow and sander5400 | Corbiere and Sons Contracting847220210214-10Pickup w/ plow and sander5400Inv#109 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8472 | 20210214-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn took plow truck with sander in afternoon to go to Culvert Creek before highway got shut down. | 6 | C237-C243 | Culvert Creek | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting847220210214-10Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting847220210214-10Operator - Principle - After Jan 105375Inv#109 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8619 | 20210214-12 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2021-02-14 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861920210214-12Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting861920210214-12Excavator - 36 ton- After Jan 10142057.44Inv#114 | [5 empty] | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8619 | 20210214-12 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-02-14 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861920210214-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting861920210214-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#114 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8619 | 20210214-12 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-02-14 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861920210214-12Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting861920210214-12Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#114 | [5 empty] | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8619 | 20210214-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-14 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861920210214-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting861920210214-12Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8619 | 20210214-12 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-14 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861920210214-12L.O.A.2420 | Corbiere and Sons Contracting861920210214-12L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8619 | 20210214-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-14 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861920210214-12Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting861920210214-12Operator - Principle - After Jan 10141050Inv#114 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8465 | 20210214-3 | 53510411 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and pickup w/plow went to Gravel River to widen entrance for float. | 4 | B211-C010 | Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846520210214-3Pickup w/ plow6300 | Corbiere and Sons Contracting846520210214-3Pickup w/ plow6300Inv#109 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8465 | 20210214-3 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and pickup w/plow went to Gravel River to widen entrance for float. | 4 | B211-C010 | Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846520210214-3L.O.A.1210 | Corbiere and Sons Contracting846520210214-3L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8465 | 20210214-3 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and pickup w/plow went to Gravel River to widen entrance for float. | 4 | B211-C010 | Gravel River Road | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting846520210214-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting846520210214-3Operator - Principle - After Jan 106450Inv#109 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8466 | 20210214-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 17 | Dynamic | 98.61 | 0 |  |  | 2235.16 | 290.5708 | 2525.7308 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on dozer in Pays Plat, Evan completed on night shift | 5 | C031-C049 | Pays Plat River | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting846620210214-4Dozer D6 or equal- After Jan 10172235.16 | Corbiere and Sons Contracting846620210214-4Dozer D6 or equal- After Jan 10172235.16Inv#109 | [5 empty] | 1 | 2235.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8466 | 20210214-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on dozer in Pays Plat, Evan completed on night shift | 5 | C031-C049 | Pays Plat River | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting846620210214-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting846620210214-4Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8466 | 20210214-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on dozer in Pays Plat, Evan completed on night shift | 5 | C031-C049 | Pays Plat River | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting846620210214-4L.O.A.2420 | Corbiere and Sons Contracting846620210214-4L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8466 | 20210214-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on dozer in Pays Plat, Evan completed on night shift | 5 | C031-C049 | Pays Plat River | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting846620210214-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting846620210214-4Operator - Principle - After Jan 10221650Inv#109 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8470 | 20210214-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and pickup w/plow and sander went to Mink Creek to sand entrance and hills. | 6 | C219-C236 | Mink Creek | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting847020210214-8Pickup w/ plow and sander6480 | Corbiere and Sons Contracting847020210214-8Pickup w/ plow and sander6480Inv#109 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8470 | 20210214-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and pickup w/plow and sander went to Mink Creek to sand entrance and hills. | 6 | C219-C236 | Mink Creek | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting847020210214-8L.O.A.1210 | Corbiere and Sons Contracting847020210214-8L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8470 | 20210214-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and pickup w/plow and sander went to Mink Creek to sand entrance and hills. | 6 | C219-C236 | Mink Creek | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting847020210214-8Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting847020210214-8Operator - Intermdiate - After Jan 106420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8471 | 20210214-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on dozer spent day clearing snow trying to get to tower C-171 | 6 | C171-C185 | Prairie River | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting847120210214-9Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting847120210214-9Dozer D6 or equal- After Jan 10101314.8Inv#109 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8471 | 20210214-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on dozer spent day clearing snow trying to get to tower C-171 | 6 | C171-C185 | Prairie River | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting847120210214-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting847120210214-9Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8471 | 20210214-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on dozer spent day clearing snow trying to get to tower C-171 | 6 | C171-C185 | Prairie River | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting847120210214-9L.O.A.1210 | Corbiere and Sons Contracting847120210214-9L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8471 | 20210214-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-14 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on dozer spent day clearing snow trying to get to tower C-171 | 6 | C171-C185 | Prairie River | 0 | 44246 |  | 37 | 44247 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting847120210214-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting847120210214-9Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8620 | 20210215-11 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2021-02-15 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862020210215-11Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting862020210215-11Excavator - 36 ton- After Jan 10142057.44Inv#114 | [5 empty] | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8620 | 20210215-11 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-02-15 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862020210215-11Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting862020210215-11Excavator Thumb - 30 - 50 ton- After Jan 10785.47Inv#114 | [5 empty] | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8620 | 20210215-11 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2021-02-15 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862020210215-11Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting862020210215-11Excavator Hammer - 30 - 50 ton- After Jan 107443.66Inv#114 | [5 empty] | 1 | 443.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8620 | 20210215-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-15 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862020210215-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting862020210215-11Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8620 | 20210215-11 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-15 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862020210215-11L.O.A.2420 | Corbiere and Sons Contracting862020210215-11L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8620 | 20210215-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-15 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862020210215-11Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting862020210215-11Operator - Principle - After Jan 10141050Inv#114 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8526 | 20210215-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7.5 | Dynamic | 98.61 | 0 |  |  | 986.1 | 128.193 | 1114.293 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved dozer from Pays Plat to Cooks Lake to continue snow removalTerry worked on dozer in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting852620210215-3Dozer D6 or equal- After Jan 107.5986.1 | Corbiere and Sons Contracting852620210215-3Dozer D6 or equal- After Jan 107.5986.1Inv#109 | [5 empty] | 1 | 986.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8526 | 20210215-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved dozer from Pays Plat to Cooks Lake to continue snow removalTerry worked on dozer in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting852620210215-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting852620210215-3Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8526 | 20210215-3 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2.5 | Dynamic | 91.79 | 0 |  |  | 305.975 | 39.7767 | 345.7518 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved dozer from Pays Plat to Cooks Lake to continue snow removalTerry worked on dozer in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting852620210215-3Tractor Trailer - 60 Ton- After Jan 102.5305.975 | Corbiere and Sons Contracting852620210215-3Tractor Trailer - 60 Ton- After Jan 102.5305.975Inv#109 | [5 empty] | 1 | 305.975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8526 | 20210215-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved dozer from Pays Plat to Cooks Lake to continue snow removalTerry worked on dozer in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting852620210215-3L.O.A.1210 | Corbiere and Sons Contracting852620210215-3L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8526 | 20210215-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved dozer from Pays Plat to Cooks Lake to continue snow removalTerry worked on dozer in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting852620210215-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting852620210215-3Operator - Principle - After Jan 1011825Inv#109 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8526 | 20210215-3 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved dozer from Pays Plat to Cooks Lake to continue snow removalTerry worked on dozer in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting852620210215-3Driver - AZ - After Jan 102.5175 | Corbiere and Sons Contracting852620210215-3Driver - AZ - After Jan 102.5175Inv#109 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8527 | 20210215-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Mink Creek - 2 flaggers requiredRon spent 7 hours on grader in Mink opening up access during the day | 6 | C219-C236 | Mink Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852720210215-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting852720210215-4Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#109 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8527 | 20210215-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Mink Creek - 2 flaggers requiredRon spent 7 hours on grader in Mink opening up access during the day | 6 | C219-C236 | Mink Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852720210215-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting852720210215-4Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8527 | 20210215-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Mink Creek - 2 flaggers requiredRon spent 7 hours on grader in Mink opening up access during the day | 6 | C219-C236 | Mink Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852720210215-4Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting852720210215-4Tractor Trailer - 60 Ton- After Jan 104489.56Inv#109 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8527 | 20210215-4 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Mink Creek - 2 flaggers requiredRon spent 7 hours on grader in Mink opening up access during the day | 6 | C219-C236 | Mink Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852720210215-4L.O.A.4840 | Corbiere and Sons Contracting852720210215-4L.O.A.4840Inv#109 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8527 | 20210215-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Mink Creek - 2 flaggers requiredRon spent 7 hours on grader in Mink opening up access during the day | 6 | C219-C236 | Mink Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852720210215-4Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting852720210215-4Operator - Principle - After Jan 107525Inv#109 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8527 | 20210215-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Mink Creek - 2 flaggers requiredRon spent 7 hours on grader in Mink opening up access during the day | 6 | C219-C236 | Mink Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852720210215-4Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting852720210215-4Driver - AZ - After Jan 104280Inv#109 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8527 | 20210215-4 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved grader into Mink Creek - 2 flaggers requiredRon spent 7 hours on grader in Mink opening up access during the day | 6 | C219-C236 | Mink Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852720210215-4Labourer - General - After Jan 108480 | Corbiere and Sons Contracting852720210215-4Labourer - General - After Jan 108480Inv#109 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8528 | 20210215-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Leslie's 350X4 from Lake A to Prairie River to do road repairsTim spent day on dozer doing road maintenance from C-171 | 6 | C171-C185 | Prairie River | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852820210215-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting852820210215-5Dozer D6 or equal- After Jan 10101314.8Inv#109 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8528 | 20210215-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Leslie's 350X4 from Lake A to Prairie River to do road repairsTim spent day on dozer doing road maintenance from C-171 | 6 | C171-C185 | Prairie River | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852820210215-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting852820210215-5Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8528 | 20210215-5 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Leslie's 350X4 from Lake A to Prairie River to do road repairsTim spent day on dozer doing road maintenance from C-171 | 6 | C171-C185 | Prairie River | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852820210215-5Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting852820210215-5Tractor Trailer - 60 Ton- After Jan 103367.17Inv#109 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8528 | 20210215-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Leslie's 350X4 from Lake A to Prairie River to do road repairsTim spent day on dozer doing road maintenance from C-171 | 6 | C171-C185 | Prairie River | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852820210215-5L.O.A.1210 | Corbiere and Sons Contracting852820210215-5L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8528 | 20210215-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Leslie's 350X4 from Lake A to Prairie River to do road repairsTim spent day on dozer doing road maintenance from C-171 | 6 | C171-C185 | Prairie River | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852820210215-5Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting852820210215-5Operator - Principle - After Jan 10151125Inv#109 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8528 | 20210215-5 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float moved Leslie's 350X4 from Lake A to Prairie River to do road repairsTim spent day on dozer doing road maintenance from C-171 | 6 | C171-C185 | Prairie River | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852820210215-5Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting852820210215-5Driver - AZ - After Jan 103210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8529 | 20210215-6 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie spent morning mobing out and scratching hill at C-135 for crane access - was floated to Prarie after | 6 | C129-C151 | Lake A | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852920210215-6Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting852920210215-6Excavator - 30 ton- After Jan 105692.25Inv#109 | [5 empty] | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8529 | 20210215-6 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie spent morning mobing out and scratching hill at C-135 for crane access - was floated to Prarie after | 6 | C129-C151 | Lake A | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852920210215-6Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting852920210215-6Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#109 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8529 | 20210215-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie spent morning mobing out and scratching hill at C-135 for crane access - was floated to Prarie after | 6 | C129-C151 | Lake A | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852920210215-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting852920210215-6Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8529 | 20210215-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie spent morning mobing out and scratching hill at C-135 for crane access - was floated to Prarie after | 6 | C129-C151 | Lake A | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852920210215-6L.O.A.1210 | Corbiere and Sons Contracting852920210215-6L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8529 | 20210215-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie spent morning mobing out and scratching hill at C-135 for crane access - was floated to Prarie after | 6 | C129-C151 | Lake A | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting852920210215-6Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting852920210215-6Operator - Principle - After Jan 109675Inv#109 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8530 | 20210215-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked on grader overnight and cleared Culvert Creek and Neys | 6 | C237-C243 | Culvert Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853020210215-7Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting853020210215-7Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#109 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8530 | 20210215-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked on grader overnight and cleared Culvert Creek and Neys | 6 | C237-C243 | Culvert Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853020210215-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting853020210215-7Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8530 | 20210215-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked on grader overnight and cleared Culvert Creek and Neys | 6 | C237-C243 | Culvert Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853020210215-7L.O.A.1210 | Corbiere and Sons Contracting853020210215-7L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8530 | 20210215-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked on grader overnight and cleared Culvert Creek and Neys | 6 | C237-C243 | Culvert Creek | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853020210215-7Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting853020210215-7Operator - Principle - After Jan 105.5412.5Inv#109 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8531 | 20210215-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked on grader overnight and cleared Culvert Creek and Neys | 6 | C219-C236 | Neys | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853120210215-8Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting853120210215-8Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#109 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8531 | 20210215-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked on grader overnight and cleared Culvert Creek and Neys | 6 | C219-C236 | Neys | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853120210215-8Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting853120210215-8Operator - Principle - After Jan 105.5412.5Inv#109 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8532 | 20210215-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out and sanded Hare Lake access | 6 | C257-C267 | Hare Lake Road | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853220210215-9Pickup w/ plow and sander8640 | Corbiere and Sons Contracting853220210215-9Pickup w/ plow and sander8640Inv#109 | [5 empty] | 1 | 640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8532 | 20210215-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out and sanded Hare Lake access | 6 | C257-C267 | Hare Lake Road | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853220210215-9L.O.A.1210 | Corbiere and Sons Contracting853220210215-9L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8532 | 20210215-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-02-15 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out and sanded Hare Lake access | 6 | C257-C267 | Hare Lake Road | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853220210215-9Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting853220210215-9Operator - Principle - After Jan 108600Inv#109 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8801 | 20210216-10 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1897.16 | unit |  |  |  |  | 1897.16 | 246.6308 | 2143.7908 | 2021-02-16 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sand delivered for Winter Access Maintenance | 6 |  | Terrace Bay Yard | 0 | 44265 |  | 36 | 44268 | 18332 | Sand delivered for access roads |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting880120210216-103rd Party Charges1897.161897.16 | Corbiere and Sons Contracting880120210216-103rd Party Charges1897.161897.16Inv#114 | [5 empty] | 1 | 1897.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8537 | 20210216-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 20 | Dynamic | 98.61 | 0 |  |  | 2629.6 | 341.848 | 2971.448 | 2021-02-16 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on Cooks, Evan took over on night shift Shawn Panamick on pickup w/plow coordinating snow removal, verifying areas. | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting853720210216-4Dozer D6 or equal- After Jan 10202629.6 | Corbiere and Sons Contracting853720210216-4Dozer D6 or equal- After Jan 10202629.6Inv#109 | [5 empty] | 1 | 2629.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8537 | 20210216-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-16 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on Cooks, Evan took over on night shift Shawn Panamick on pickup w/plow coordinating snow removal, verifying areas. | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting853720210216-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting853720210216-4Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8537 | 20210216-4 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 8 | HR | 0 | 0 |  |  | 400 | 52 | 452 | 2021-02-16 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on Cooks, Evan took over on night shift Shawn Panamick on pickup w/plow coordinating snow removal, verifying areas. | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting853720210216-4Pickup w/ plow8400 | Corbiere and Sons Contracting853720210216-4Pickup w/ plow8400Inv#109 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8537 | 20210216-4 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-16 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on Cooks, Evan took over on night shift Shawn Panamick on pickup w/plow coordinating snow removal, verifying areas. | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting853720210216-4L.O.A.3630 | Corbiere and Sons Contracting853720210216-4L.O.A.3630Inv#109 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8537 | 20210216-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30 | HR |  |  | 75 | 0 | 2250 | 292.5 | 2542.5 | 2021-02-16 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on Cooks, Evan took over on night shift Shawn Panamick on pickup w/plow coordinating snow removal, verifying areas. | 5 | C076-C116 | Cook Lake | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting853720210216-4Operator - Principle - After Jan 10302250 | Corbiere and Sons Contracting853720210216-4Operator - Principle - After Jan 10302250Inv#109 | [5 empty] | 1 | 2250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8539 | 20210216-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 13 |  | 0 | 0 |  |  | 1040 | 135.2 | 1175.2 | 2021-02-16 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day on pickup w/plow and sander working across various areas in WF6 | 6 | C129-C151 | Lake A | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853920210216-6Pickup w/ plow and sander131040 | Corbiere and Sons Contracting853920210216-6Pickup w/ plow and sander131040Inv#109 | [5 empty] | 1 | 1040 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8539 | 20210216-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-16 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day on pickup w/plow and sander working across various areas in WF6 | 6 | C129-C151 | Lake A | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853920210216-6L.O.A.1210 | Corbiere and Sons Contracting853920210216-6L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8539 | 20210216-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-02-16 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day on pickup w/plow and sander working across various areas in WF6 | 6 | C129-C151 | Lake A | 0 | 44249 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting853920210216-6Operator - Intermdiate - After Jan 1013910 | Corbiere and Sons Contracting853920210216-6Operator - Intermdiate - After Jan 1013910Inv#109 | [5 empty] | 1 | 910 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8621 | 20210216-9 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2021-02-16 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake Road | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862120210216-9Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting862120210216-9Excavator - 36 ton- After Jan 10142057.44Inv#114 | [5 empty] | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8621 | 20210216-9 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-02-16 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake Road | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862120210216-9Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting862120210216-9Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#114 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8621 | 20210216-9 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-02-16 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake Road | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862120210216-9Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting862120210216-9Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#114 | [5 empty] | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8621 | 20210216-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-16 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake Road | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862120210216-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting862120210216-9Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8621 | 20210216-9 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-16 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake Road | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862120210216-9L.O.A.2420 | Corbiere and Sons Contracting862120210216-9L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8621 | 20210216-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-16 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake Rd, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake Road | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862120210216-9Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting862120210216-9Operator - Principle - After Jan 10141050Inv#114 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8622 | 20210217-10 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 13 | Dynamic | 110.22 | 0 |  |  | 1910.48 | 248.3624 | 2158.8424 | 2021-02-17 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862220210217-10Excavator - 36 ton- After Jan 10131910.48 | Corbiere and Sons Contracting862220210217-10Excavator - 36 ton- After Jan 10131910.48Inv#114 | [5 empty] | 1 | 1910.48 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8622 | 20210217-10 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-02-17 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862220210217-10Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting862220210217-10Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#114 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8622 | 20210217-10 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-02-17 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862220210217-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting862220210217-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18Inv#114 | [5 empty] | 1 | 697.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8622 | 20210217-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-17 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862220210217-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting862220210217-10Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8622 | 20210217-10 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-17 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862220210217-10L.O.A.2420 | Corbiere and Sons Contracting862220210217-10L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8622 | 20210217-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-02-17 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862220210217-10Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting862220210217-10Operator - Principle - After Jan 1013975Inv#114 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8543 | 20210217-3 | 53510311 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 13 | Dynamic | 64.79 | 0 |  |  | 1122.94 | 145.9822 | 1268.9222 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel took sander truck to Landfill (5am start) to sand for stringers all day | 3 | B078-B084 | Landfill | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting854320210217-3Sander Truck - Forestry- After Jan 10131122.94 | Corbiere and Sons Contracting854320210217-3Sander Truck - Forestry- After Jan 10131122.94Inv#109 | [5 empty] | 1 | 1122.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8543 | 20210217-3 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel took sander truck to Landfill (5am start) to sand for stringers all day | 3 | B078-B084 | Landfill | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting854320210217-3L.O.A.1210 | Corbiere and Sons Contracting854320210217-3L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8543 | 20210217-3 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel took sander truck to Landfill (5am start) to sand for stringers all day | 3 | B078-B084 | Landfill | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting854320210217-3Operator - Intermdiate - After Jan 1013910 | Corbiere and Sons Contracting854320210217-3Operator - Intermdiate - After Jan 1013910Inv#109 | [5 empty] | 1 | 910 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8544 | 20210217-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 20 | Dynamic | 98.61 | 0 |  |  | 2629.6 | 341.848 | 2971.448 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on Cooks, Evan took over on night shift | 5 | C076-C116 | Cook Lake | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting854420210217-4Dozer D6 or equal- After Jan 10202629.6 | Corbiere and Sons Contracting854420210217-4Dozer D6 or equal- After Jan 10202629.6Inv#109 | [5 empty] | 1 | 2629.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8544 | 20210217-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on Cooks, Evan took over on night shift | 5 | C076-C116 | Cook Lake | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting854420210217-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting854420210217-4Light Truck - Pick up- After Jan 102487.5Inv#109 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8544 | 20210217-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on Cooks, Evan took over on night shift | 5 | C076-C116 | Cook Lake | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting854420210217-4L.O.A.2420 | Corbiere and Sons Contracting854420210217-4L.O.A.2420Inv#109 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8544 | 20210217-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued on Cooks, Evan took over on night shift | 5 | C076-C116 | Cook Lake | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting854420210217-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting854420210217-4Operator - Principle - After Jan 10221650Inv#109 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8545 | 20210217-5 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn sanded Lake A, Scott widening corners. | 6 | C129-C151 | Lake A | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting854520210217-5Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting854520210217-5Excavator - 30 ton- After Jan 102276.9Inv#109 | [5 empty] | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8545 | 20210217-5 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn sanded Lake A, Scott widening corners. | 6 | C129-C151 | Lake A | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting854520210217-5Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting854520210217-5Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#109 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8545 | 20210217-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn sanded Lake A, Scott widening corners. | 6 | C129-C151 | Lake A | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting854520210217-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting854520210217-5Light Truck - Pick up- After Jan 101243.75Inv#109 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8545 | 20210217-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn sanded Lake A, Scott widening corners. | 6 | C129-C151 | Lake A | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting854520210217-5Pickup w/ plow and sander6480 | Corbiere and Sons Contracting854520210217-5Pickup w/ plow and sander6480Inv#109 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8545 | 20210217-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn sanded Lake A, Scott widening corners. | 6 | C129-C151 | Lake A | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting854520210217-5L.O.A.1210 | Corbiere and Sons Contracting854520210217-5L.O.A.1210Inv#109 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8545 | 20210217-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn sanded Lake A, Scott widening corners. | 6 | C129-C151 | Lake A | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting854520210217-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting854520210217-5Operator - Principle - After Jan 108600Inv#109 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8546 | 20210217-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn sanded Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting854620210217-6Pickup w/ plow and sander6480 | Corbiere and Sons Contracting854620210217-6Pickup w/ plow and sander6480Inv#109 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8546 | 20210217-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-17 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn sanded Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44250 |  | 37 | 44250 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting854620210217-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting854620210217-6Operator - Principle - After Jan 106450Inv#109 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8625 | 20210218-10 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44259 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862520210218-10Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting862520210218-10Excavator - 36 ton- After Jan 10142057.44Inv#114 | [5 empty] | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8625 | 20210218-10 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44259 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862520210218-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting862520210218-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47Inv#114 | [5 empty] | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8625 | 20210218-10 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44259 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862520210218-10Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting862520210218-10Excavator Hammer - 30 - 50 ton- After Jan 107443.66Inv#114 | [5 empty] | 1 | 443.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8625 | 20210218-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44259 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862520210218-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting862520210218-10Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8625 | 20210218-10 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44259 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862520210218-10L.O.A.2420 | Corbiere and Sons Contracting862520210218-10L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8625 | 20210218-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 6 | C186-C195 | Del Lake West | 0 | 44254 |  | 37 | 44259 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862520210218-10Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting862520210218-10Operator - Principle - After Jan 10141050Inv#114 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8591 | 20210218-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on plow truck with sander across Santoy Mountain, Santoy Lake and Hare. | 6 | C155-C157 | Santoy Mountain | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859120210218-3Pickup w/ plow and sander4320 | Corbiere and Sons Contracting859120210218-3Pickup w/ plow and sander4320Inv#114 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8591 | 20210218-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on plow truck with sander across Santoy Mountain, Santoy Lake and Hare. | 6 | C155-C157 | Santoy Mountain | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859120210218-3L.O.A.1210 | Corbiere and Sons Contracting859120210218-3L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8591 | 20210218-3 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on plow truck with sander across Santoy Mountain, Santoy Lake and Hare. | 6 | C155-C157 | Santoy Mountain | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859120210218-3Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting859120210218-3Operator - Intermdiate - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8592 | 20210218-4 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on plow truck with sander across Santoy Mountain, Santoy Lake and Hare. | 6 | C158-C170 | Santoy Lake | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859220210218-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting859220210218-4Pickup w/ plow and sander4320Inv#114 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8592 | 20210218-4 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on plow truck with sander across Santoy Mountain, Santoy Lake and Hare. | 6 | C158-C170 | Santoy Lake | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859220210218-4Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting859220210218-4Operator - Intermdiate - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8593 | 20210218-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on plow truck with sander across Santoy Mountain, Santoy Lake and Hare. | 6 | C257-C267 | Hare Lake | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859320210218-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting859320210218-5Pickup w/ plow and sander3240Inv#114 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8593 | 20210218-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel worked on plow truck with sander across Santoy Mountain, Santoy Lake and Hare. | 6 | C257-C267 | Hare Lake | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859320210218-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting859320210218-5Operator - Intermdiate - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8624 | 20210218-9 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went to Antler to cleanout skidoo trail at KM2. | 5 | C050-C069 | Antler Lake Rd | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting862420210218-9Pickup w/ plow6300 | Corbiere and Sons Contracting862420210218-9Pickup w/ plow6300Inv#114 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8624 | 20210218-9 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went to Antler to cleanout skidoo trail at KM2. | 5 | C050-C069 | Antler Lake Rd | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting862420210218-9L.O.A.1210 | Corbiere and Sons Contracting862420210218-9L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8624 | 20210218-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-18 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went to Antler to cleanout skidoo trail at KM2. | 5 | C050-C069 | Antler Lake Rd | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting862420210218-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting862420210218-9Operator - Principle - After Jan 106450Inv#114 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8626 | 20210219-12 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 0 |  |  | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862620210219-12Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting862620210219-12Excavator - 36 ton- After Jan 10142057.44Inv#114 | [5 empty] | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8626 | 20210219-12 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 0 |  |  | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862620210219-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting862620210219-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#114 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8626 | 20210219-12 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 0 |  |  | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862620210219-12Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting862620210219-12Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#114 | [5 empty] | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8626 | 20210219-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 0 |  |  | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862620210219-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting862620210219-12Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8626 | 20210219-12 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 0 |  |  | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862620210219-12L.O.A.2420 | Corbiere and Sons Contracting862620210219-12L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8626 | 20210219-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer spots on Del Lake road, second operator assisted in moving equipment and pickup ahead, as well as assisted excavating. | 0 |  |  | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862620210219-12Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting862620210219-12Operator - Principle - After Jan 10141050Inv#114 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8599 | 20210219-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and floated moved grader into Culvert CreekShawn went out with pickup/sander and did Hare, Culvert, NeysLen came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C237-C243 | Culvert Creek | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859920210219-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting859920210219-3Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#114 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8599 | 20210219-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and floated moved grader into Culvert CreekShawn went out with pickup/sander and did Hare, Culvert, NeysLen came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C237-C243 | Culvert Creek | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859920210219-3Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting859920210219-3Tractor Trailer - 60 Ton- After Jan 105611.95Inv#114 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8599 | 20210219-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and floated moved grader into Culvert CreekShawn went out with pickup/sander and did Hare, Culvert, NeysLen came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C237-C243 | Culvert Creek | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859920210219-3Pickup w/ plow and sander4320 | Corbiere and Sons Contracting859920210219-3Pickup w/ plow and sander4320Inv#114 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8599 | 20210219-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and floated moved grader into Culvert CreekShawn went out with pickup/sander and did Hare, Culvert, NeysLen came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C237-C243 | Culvert Creek | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859920210219-3L.O.A.2420 | Corbiere and Sons Contracting859920210219-3L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8599 | 20210219-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and floated moved grader into Culvert CreekShawn went out with pickup/sander and did Hare, Culvert, NeysLen came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C237-C243 | Culvert Creek | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859920210219-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting859920210219-3Operator - Principle - After Jan 109675Inv#114 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8599 | 20210219-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and floated moved grader into Culvert CreekShawn went out with pickup/sander and did Hare, Culvert, NeysLen came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C237-C243 | Culvert Creek | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting859920210219-3Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting859920210219-3Driver - AZ - After Jan 105350Inv#114 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8600 | 20210219-4 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Operators moved Switchback hill on Hare Lake Rd | 6 | C257-C267 | Hare Lake | 0 | 44251 |  | 37 | 44249 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860020210219-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting860020210219-4Dozer D6 or equal- After Jan 10101314.8Inv#114 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8600 | 20210219-4 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Operators moved Switchback hill on Hare Lake Rd | 6 | C257-C267 | Hare Lake | 0 | 44251 |  | 37 | 44249 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860020210219-4Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting860020210219-4Excavator - 30 ton- After Jan 10101384.5Inv#114 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8600 | 20210219-4 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Operators moved Switchback hill on Hare Lake Rd | 6 | C257-C267 | Hare Lake | 0 | 44251 |  | 37 | 44249 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860020210219-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting860020210219-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#114 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8600 | 20210219-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Operators moved Switchback hill on Hare Lake Rd | 6 | C257-C267 | Hare Lake | 0 | 44251 |  | 37 | 44249 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860020210219-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting860020210219-4Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8600 | 20210219-4 | 53510611 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Operators moved Switchback hill on Hare Lake Rd | 6 | C257-C267 | Hare Lake | 0 | 44251 |  | 37 | 44249 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860020210219-4Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting860020210219-4Rock Truck - 30 Ton- After Jan 10101380.5Inv#114 | [5 empty] | 1 | 1380.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8600 | 20210219-4 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Operators moved Switchback hill on Hare Lake Rd | 6 | C257-C267 | Hare Lake | 0 | 44251 |  | 37 | 44249 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860020210219-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting860020210219-4Pickup w/ plow and sander4320Inv#114 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8600 | 20210219-4 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Operators moved Switchback hill on Hare Lake Rd | 6 | C257-C267 | Hare Lake | 0 | 44251 |  | 37 | 44249 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860020210219-4L.O.A.3630 | Corbiere and Sons Contracting860020210219-4L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8600 | 20210219-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 37 | HR |  |  | 75 | 0 | 2775 | 360.75 | 3135.75 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Operators moved Switchback hill on Hare Lake Rd | 6 | C257-C267 | Hare Lake | 0 | 44251 |  | 37 | 44249 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860020210219-4Operator - Principle - After Jan 10372775 | Corbiere and Sons Contracting860020210219-4Operator - Principle - After Jan 10372775Inv#114 | [5 empty] | 1 | 2775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8601 | 20210219-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Doug floated linkbelt and dozer into Neys to do road maintenance; Darrel ran dozer clearing snow after it was floated and worked late; Rick mobed in 350 after it was floated. Len came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860120210219-5Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting860120210219-5Dozer D6 or equal- After Jan 1091183.32Inv#114 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8601 | 20210219-5 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Doug floated linkbelt and dozer into Neys to do road maintenance; Darrel ran dozer clearing snow after it was floated and worked late; Rick mobed in 350 after it was floated. Len came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860120210219-5Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting860120210219-5Excavator - 36 ton- After Jan 102293.92Inv#114 | [5 empty] | 1 | 293.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8601 | 20210219-5 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Doug floated linkbelt and dozer into Neys to do road maintenance; Darrel ran dozer clearing snow after it was floated and worked late; Rick mobed in 350 after it was floated. Len came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860120210219-5Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting860120210219-5Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#114 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8601 | 20210219-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Doug floated linkbelt and dozer into Neys to do road maintenance; Darrel ran dozer clearing snow after it was floated and worked late; Rick mobed in 350 after it was floated. Len came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860120210219-5Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting860120210219-5Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#114 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8601 | 20210219-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Doug floated linkbelt and dozer into Neys to do road maintenance; Darrel ran dozer clearing snow after it was floated and worked late; Rick mobed in 350 after it was floated. Len came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860120210219-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting860120210219-5Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8601 | 20210219-5 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Doug floated linkbelt and dozer into Neys to do road maintenance; Darrel ran dozer clearing snow after it was floated and worked late; Rick mobed in 350 after it was floated. Len came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860120210219-5Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting860120210219-5Tractor Trailer - 60 Ton- After Jan 106734.34Inv#114 | [5 empty] | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8601 | 20210219-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Doug floated linkbelt and dozer into Neys to do road maintenance; Darrel ran dozer clearing snow after it was floated and worked late; Rick mobed in 350 after it was floated. Len came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860120210219-5Pickup w/ plow and sander4320 | Corbiere and Sons Contracting860120210219-5Pickup w/ plow and sander4320Inv#114 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8601 | 20210219-5 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Doug floated linkbelt and dozer into Neys to do road maintenance; Darrel ran dozer clearing snow after it was floated and worked late; Rick mobed in 350 after it was floated. Len came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860120210219-5L.O.A.3630 | Corbiere and Sons Contracting860120210219-5L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8601 | 20210219-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 75 | 0 | 1875 | 243.75 | 2118.75 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Doug floated linkbelt and dozer into Neys to do road maintenance; Darrel ran dozer clearing snow after it was floated and worked late; Rick mobed in 350 after it was floated. Len came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860120210219-5Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting860120210219-5Operator - Principle - After Jan 10251875Inv#114 | [5 empty] | 1 | 1875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8601 | 20210219-5 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn went out with pickup/sander and did Hare, Culvert, Neys. Doug floated linkbelt and dozer into Neys to do road maintenance; Darrel ran dozer clearing snow after it was floated and worked late; Rick mobed in 350 after it was floated. Len came in for 10am and ran grader at Culverts and Neys until 8 pm | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860120210219-5Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting860120210219-5Driver - AZ - After Jan 106420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8602 | 20210219-6 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan on pickup with plow at Lake A, Santoy, and Del. | 6 | C129-C151 | Lake A | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860220210219-6Pickup w/ plow4200 | Corbiere and Sons Contracting860220210219-6Pickup w/ plow4200Inv#114 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8602 | 20210219-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan on pickup with plow at Lake A, Santoy, and Del. | 6 | C129-C151 | Lake A | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860220210219-6L.O.A.1210 | Corbiere and Sons Contracting860220210219-6L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8602 | 20210219-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan on pickup with plow at Lake A, Santoy, and Del. | 6 | C129-C151 | Lake A | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860220210219-6Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting860220210219-6Operator - Intermdiate - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8603 | 20210219-7 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan on pickup with plow at Lake A, Santoy, and Del. | 6 | C158-C170 | Santoy Lake | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860320210219-7Pickup w/ plow4200 | Corbiere and Sons Contracting860320210219-7Pickup w/ plow4200Inv#114 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8603 | 20210219-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan on pickup with plow at Lake A, Santoy, and Del. | 6 | C158-C170 | Santoy Lake | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860320210219-7Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting860320210219-7Operator - Intermdiate - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8604 | 20210219-8 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 3 | HR | 0 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan on pickup with plow at Lake A, Santoy, and Del. | 6 | C186-C195 | Del Lake | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860420210219-8Pickup w/ plow3150 | Corbiere and Sons Contracting860420210219-8Pickup w/ plow3150Inv#114 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8604 | 20210219-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan on pickup with plow at Lake A, Santoy, and Del. | 6 | C186-C195 | Del Lake | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860420210219-8Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting860420210219-8Operator - Intermdiate - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8605 | 20210219-9 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie spent day working in hammering acess road until machine went down - 2pm | 6 | C171-C185 | Prairie River | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860520210219-9Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting860520210219-9Excavator - 30 ton- After Jan 107969.15Inv#114 | [5 empty] | 1 | 969.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8605 | 20210219-9 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie spent day working in hammering acess road until machine went down - 2pm | 6 | C171-C185 | Prairie River | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860520210219-9Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting860520210219-9Excavator Hammer - 30 - 50 ton- After Jan 107443.66Inv#114 | [5 empty] | 1 | 443.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8605 | 20210219-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie spent day working in hammering acess road until machine went down - 2pm | 6 | C171-C185 | Prairie River | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860520210219-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting860520210219-9Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8605 | 20210219-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie spent day working in hammering acess road until machine went down - 2pm | 6 | C171-C185 | Prairie River | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860520210219-9L.O.A.1210 | Corbiere and Sons Contracting860520210219-9L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8605 | 20210219-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-02-19 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie spent day working in hammering acess road until machine went down - 2pm | 6 | C171-C185 | Prairie River | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting860520210219-9Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting860520210219-9Operator - Principle - After Jan 107525Inv#114 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8629 | 20210220-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day clearing snow from Neys East and Culvert Creek on dozer. | 6 | C237-C243 | Culvert Creek | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862920210220-10Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting862920210220-10Dozer D6 or equal- After Jan 105657.4Inv#114 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8629 | 20210220-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day clearing snow from Neys East and Culvert Creek on dozer. | 6 | C237-C243 | Culvert Creek | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862920210220-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting862920210220-10Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8629 | 20210220-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day clearing snow from Neys East and Culvert Creek on dozer. | 6 | C237-C243 | Culvert Creek | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862920210220-10Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting862920210220-10Operator - Principle - After Jan 105375Inv#114 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8630 | 20210220-11 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on DZ doing road maintenance in Hare Lake all day - Widening road and clearing snow | 6 | C257-C267 | Hare Lake Road | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting863020210220-11Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting863020210220-11Dozer D6 or equal- After Jan 10101314.8Inv#114 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8630 | 20210220-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on DZ doing road maintenance in Hare Lake all day - Widening road and clearing snow | 6 | C257-C267 | Hare Lake Road | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting863020210220-11L.O.A.1210 | Corbiere and Sons Contracting863020210220-11L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8630 | 20210220-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on DZ doing road maintenance in Hare Lake all day - Widening road and clearing snow | 6 | C257-C267 | Hare Lake Road | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting863020210220-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting863020210220-11Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8610 | 20210220-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran grader in Prairie River Rd | 6 | C171-C185 | Prairie River | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861020210220-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting861020210220-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8610 | 20210220-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran grader in Prairie River Rd | 6 | C171-C185 | Prairie River | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861020210220-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting861020210220-3Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8610 | 20210220-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran grader in Prairie River Rd | 6 | C171-C185 | Prairie River | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861020210220-3L.O.A.1210 | Corbiere and Sons Contracting861020210220-3L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8610 | 20210220-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran grader in Prairie River Rd | 6 | C171-C185 | Prairie River | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861020210220-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting861020210220-3Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8611 | 20210220-4 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert CreekDoug floated Jordan in and Jordan did road maintenance on EXRick did road maintenance until machine broke down | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861120210220-4Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting861120210220-4Excavator - 30 ton- After Jan 103415.35Inv#114 | [5 empty] | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8611 | 20210220-4 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert CreekDoug floated Jordan in and Jordan did road maintenance on EXRick did road maintenance until machine broke down | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861120210220-4Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting861120210220-4Excavator - 36 ton- After Jan 104587.84Inv#114 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8611 | 20210220-4 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert CreekDoug floated Jordan in and Jordan did road maintenance on EXRick did road maintenance until machine broke down | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861120210220-4Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting861120210220-4Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#114 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8611 | 20210220-4 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert CreekDoug floated Jordan in and Jordan did road maintenance on EXRick did road maintenance until machine broke down | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861120210220-4Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting861120210220-4Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#114 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8611 | 20210220-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert CreekDoug floated Jordan in and Jordan did road maintenance on EXRick did road maintenance until machine broke down | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861120210220-4Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting861120210220-4Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#114 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8611 | 20210220-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert CreekDoug floated Jordan in and Jordan did road maintenance on EXRick did road maintenance until machine broke down | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861120210220-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting861120210220-4Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8611 | 20210220-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert CreekDoug floated Jordan in and Jordan did road maintenance on EXRick did road maintenance until machine broke down | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861120210220-4Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting861120210220-4Tractor Trailer - 60 Ton- After Jan 105611.95Inv#114 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8611 | 20210220-4 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert CreekDoug floated Jordan in and Jordan did road maintenance on EXRick did road maintenance until machine broke down | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861120210220-4L.O.A.4840 | Corbiere and Sons Contracting861120210220-4L.O.A.4840Inv#114 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8611 | 20210220-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert CreekDoug floated Jordan in and Jordan did road maintenance on EXRick did road maintenance until machine broke down | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861120210220-4Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting861120210220-4Operator - Principle - After Jan 10161200Inv#114 | [5 empty] | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8611 | 20210220-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert CreekDoug floated Jordan in and Jordan did road maintenance on EXRick did road maintenance until machine broke down | 6 | C219-C236 | Neys | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861120210220-4Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting861120210220-4Driver - AZ - After Jan 105350Inv#114 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8612 | 20210220-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861220210220-5Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting861220210220-5Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#114 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8612 | 20210220-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued on grader in Neys and Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 44251 |  | 37 | 44251 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting861220210220-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting861220210220-5Operator - Principle - After Jan 105375Inv#114 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8628 | 20210220-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day clearing snow from Neys East and Culvert Creek on dozer. | 6 | C219-C236 | Neys | 0 | 44253 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862820210220-9Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting862820210220-9Dozer D6 or equal- After Jan 105657.4Inv#114 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8628 | 20210220-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day clearing snow from Neys East and Culvert Creek on dozer. | 6 | C219-C236 | Neys | 0 | 44253 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862820210220-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting862820210220-9Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8628 | 20210220-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day clearing snow from Neys East and Culvert Creek on dozer. | 6 | C219-C236 | Neys | 0 | 44253 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862820210220-9L.O.A.1210 | Corbiere and Sons Contracting862820210220-9L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8628 | 20210220-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-20 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day clearing snow from Neys East and Culvert Creek on dozer. | 6 | C219-C236 | Neys | 0 | 44253 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting862820210220-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting862820210220-9Operator - Principle - After Jan 106450Inv#114 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8654 | 20210221-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine sanded Santoy Mountain and Santoy Lake | 6 | C158 - C170 | Santoy Mountain | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865420210221-10Pickup w/ plow and sander3240 | Corbiere and Sons Contracting865420210221-10Pickup w/ plow and sander3240Inv#114 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8654 | 20210221-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine sanded Santoy Mountain and Santoy Lake | 6 | C158 - C170 | Santoy Mountain | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865420210221-10Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting865420210221-10Operator - Intermdiate - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8655 | 20210221-11 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim continuing widening road and snow removal on Hare Lake Dustin coordianting snow removal activities | 6 | C257-C267 | Hare Lake | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865520210221-11Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting865520210221-11Dozer D6 or equal- After Jan 10101314.8Inv#114 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8655 | 20210221-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim continuing widening road and snow removal on Hare Lake Dustin coordianting snow removal activities | 6 | C257-C267 | Hare Lake | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865520210221-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting865520210221-11Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8655 | 20210221-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim continuing widening road and snow removal on Hare Lake Dustin coordianting snow removal activities | 6 | C257-C267 | Hare Lake | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865520210221-11L.O.A.1210 | Corbiere and Sons Contracting865520210221-11L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8655 | 20210221-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim continuing widening road and snow removal on Hare Lake Dustin coordianting snow removal activities | 6 | C257-C267 | Hare Lake | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865520210221-11Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting865520210221-11Operator - Principle - After Jan 10141050Inv#114 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8636 | 20210221-5 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Prairie road hammering directed by Valard. | 6 | C171-C185 | Prairie River | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting863620210221-5Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting863620210221-5Excavator - 36 ton- After Jan 1081175.68Inv#114 | [5 empty] | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8636 | 20210221-5 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Prairie road hammering directed by Valard. | 6 | C171-C185 | Prairie River | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting863620210221-5Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting863620210221-5Excavator Hammer - 30 - 50 ton- After Jan 108507.04Inv#114 | [5 empty] | 1 | 507.04 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8636 | 20210221-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Prairie road hammering directed by Valard. | 6 | C171-C185 | Prairie River | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting863620210221-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting863620210221-5Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8636 | 20210221-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Prairie road hammering directed by Valard. | 6 | C171-C185 | Prairie River | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting863620210221-5L.O.A.1210 | Corbiere and Sons Contracting863620210221-5L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8636 | 20210221-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Prairie road hammering directed by Valard. | 6 | C171-C185 | Prairie River | 0 | 44254 |  | 37 | 44256 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting863620210221-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting863620210221-5Operator - Principle - After Jan 1012900Inv#114 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8650 | 20210221-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked on grader in Cooks West all day | 5 | C076-C116 | Cook Lake | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting865020210221-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting865020210221-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8650 | 20210221-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked on grader in Cooks West all day | 5 | C076-C116 | Cook Lake | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting865020210221-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting865020210221-6Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8650 | 20210221-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked on grader in Cooks West all day | 5 | C076-C116 | Cook Lake | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting865020210221-6L.O.A.1210 | Corbiere and Sons Contracting865020210221-6L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8650 | 20210221-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked on grader in Cooks West all day | 5 | C076-C116 | Cook Lake | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting865020210221-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting865020210221-6Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8651 | 20210221-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader across Neys and Culvert all dayJordan and Darrel spent day at Neys doing road maintenanceDustin coordinatoring snow removal activities | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865120210221-7Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting865120210221-7Dozer D6 or equal- After Jan 10101314.8Inv#114 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8651 | 20210221-7 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader across Neys and Culvert all dayJordan and Darrel spent day at Neys doing road maintenanceDustin coordinatoring snow removal activities | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865120210221-7Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting865120210221-7Excavator - 30 ton- After Jan 10101384.5Inv#114 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8651 | 20210221-7 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader across Neys and Culvert all dayJordan and Darrel spent day at Neys doing road maintenanceDustin coordinatoring snow removal activities | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865120210221-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting865120210221-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#114 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8651 | 20210221-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader across Neys and Culvert all dayJordan and Darrel spent day at Neys doing road maintenanceDustin coordinatoring snow removal activities | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865120210221-7Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting865120210221-7Grader - Cat 12 to 14 or equal- After Jan 105.5698.39Inv#114 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8651 | 20210221-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader across Neys and Culvert all dayJordan and Darrel spent day at Neys doing road maintenanceDustin coordinatoring snow removal activities | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865120210221-7Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting865120210221-7Light Truck - Pick up- After Jan 103731.25Inv#114 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8651 | 20210221-7 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader across Neys and Culvert all dayJordan and Darrel spent day at Neys doing road maintenanceDustin coordinatoring snow removal activities | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865120210221-7L.O.A.4840 | Corbiere and Sons Contracting865120210221-7L.O.A.4840Inv#114 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8651 | 20210221-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 31.5 | HR |  |  | 75 | 0 | 2362.5 | 307.125 | 2669.625 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader across Neys and Culvert all dayJordan and Darrel spent day at Neys doing road maintenanceDustin coordinatoring snow removal activities | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865120210221-7Operator - Principle - After Jan 1031.52362.5 | Corbiere and Sons Contracting865120210221-7Operator - Principle - After Jan 1031.52362.5Inv#114 | [5 empty] | 1 | 2362.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8652 | 20210221-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader across Neys and Culvert all dayDustin coordinatoring snow removal activities | 6 | C237-C243 | Culvert Creek | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865220210221-8Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting865220210221-8Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#114 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8652 | 20210221-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader across Neys and Culvert all dayDustin coordinatoring snow removal activities | 6 | C237-C243 | Culvert Creek | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865220210221-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting865220210221-8Operator - Principle - After Jan 108600Inv#114 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8653 | 20210221-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine sanded Santoy Mountain and Santoy Lake | 6 | C155-C157 | Santoy Mountain | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865320210221-9Pickup w/ plow and sander3240 | Corbiere and Sons Contracting865320210221-9Pickup w/ plow and sander3240Inv#114 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8653 | 20210221-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine sanded Santoy Mountain and Santoy Lake | 6 | C155-C157 | Santoy Mountain | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865320210221-9L.O.A.1210 | Corbiere and Sons Contracting865320210221-9L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8653 | 20210221-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine sanded Santoy Mountain and Santoy Lake | 6 | C155-C157 | Santoy Mountain | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865320210221-9Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting865320210221-9Operator - Principle - After Jan 102150Inv#114 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8653 | 20210221-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-21 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine sanded Santoy Mountain and Santoy Lake | 6 | C155-C157 | Santoy Mountain | 0 | 44259 |  | 37 | 44263 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865320210221-9Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting865320210221-9Operator - Intermdiate - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8662 | 20210222-10 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day repairing road from C-236 for crane access. | 6 | C268-C279 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866220210222-10Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting866220210222-10Excavator - 30 ton- After Jan 10101384.5Inv#114 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8662 | 20210222-10 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day repairing road from C-236 for crane access. | 6 | C268-C279 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866220210222-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting866220210222-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#114 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8662 | 20210222-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day repairing road from C-236 for crane access. | 6 | C268-C279 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866220210222-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting866220210222-10Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8662 | 20210222-10 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 2 | HR | 0 | 0 |  |  | 100 | 13 | 113 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day repairing road from C-236 for crane access. | 6 | C268-C279 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866220210222-10Pickup w/ plow2100 | Corbiere and Sons Contracting866220210222-10Pickup w/ plow2100Inv#114 | [5 empty] | 1 | 100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8662 | 20210222-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day repairing road from C-236 for crane access. | 6 | C268-C279 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866220210222-10L.O.A.1210 | Corbiere and Sons Contracting866220210222-10L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8662 | 20210222-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day repairing road from C-236 for crane access. | 6 | C268-C279 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866220210222-10Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting866220210222-10Operator - Principle - After Jan 1013975Inv#114 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8663 | 20210222-11 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed float time for grader on original submission - Grader floated into Little Red Sucker Creek. | 6 | C2488-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866320210222-11Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting866320210222-11Tractor Trailer - 60 Ton- After Jan 103367.17Inv#114 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8663 | 20210222-11 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed float time for grader on original submission - Grader floated into Little Red Sucker Creek. | 6 | C2488-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866320210222-11Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting866320210222-11Driver - AZ - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8657 | 20210222-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued in Cooks on grader and got to the 2.5km on East Side. | 5 | C076-C116 | Cook Lake | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting865720210222-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting865720210222-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8657 | 20210222-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued in Cooks on grader and got to the 2.5km on East Side. | 5 | C076-C116 | Cook Lake | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting865720210222-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting865720210222-5Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8657 | 20210222-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued in Cooks on grader and got to the 2.5km on East Side. | 5 | C076-C116 | Cook Lake | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting865720210222-5L.O.A.1210 | Corbiere and Sons Contracting865720210222-5L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8657 | 20210222-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued in Cooks on grader and got to the 2.5km on East Side. | 5 | C076-C116 | Cook Lake | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting865720210222-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting865720210222-5Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8658 | 20210222-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader on Prairie in the morning and then was floated over to Red Sucker for afternoon to work there. | 6 | C171-C185 | Prairie River | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865820210222-6Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting865820210222-6Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#114 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8658 | 20210222-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader on Prairie in the morning and then was floated over to Red Sucker for afternoon to work there. | 6 | C171-C185 | Prairie River | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865820210222-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting865820210222-6Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8658 | 20210222-6 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 2 | HR | 0 | 0 |  |  | 100 | 13 | 113 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader on Prairie in the morning and then was floated over to Red Sucker for afternoon to work there. | 6 | C171-C185 | Prairie River | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865820210222-6Pickup w/ plow2100 | Corbiere and Sons Contracting865820210222-6Pickup w/ plow2100Inv#114 | [5 empty] | 1 | 100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8658 | 20210222-6 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader on Prairie in the morning and then was floated over to Red Sucker for afternoon to work there. | 6 | C171-C185 | Prairie River | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865820210222-6L.O.A.2420 | Corbiere and Sons Contracting865820210222-6L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8658 | 20210222-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader on Prairie in the morning and then was floated over to Red Sucker for afternoon to work there. | 6 | C171-C185 | Prairie River | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865820210222-6Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting865820210222-6Operator - Principle - After Jan 108600Inv#114 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8659 | 20210222-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader on Prairie in the morning and then was floated over to Red Sucker for afternoon to work there. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865920210222-7Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting865920210222-7Grader - Cat 12 to 14 or equal- After Jan 102253.96Inv#114 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8659 | 20210222-7 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 2 | HR | 0 | 0 |  |  | 100 | 13 | 113 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader on Prairie in the morning and then was floated over to Red Sucker for afternoon to work there. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865920210222-7Pickup w/ plow2100 | Corbiere and Sons Contracting865920210222-7Pickup w/ plow2100Inv#114 | [5 empty] | 1 | 100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8659 | 20210222-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan worked grader on Prairie in the morning and then was floated over to Red Sucker for afternoon to work there. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting865920210222-7Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting865920210222-7Operator - Principle - After Jan 107525Inv#114 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8661 | 20210222-9 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf performed road maintenance on Peninsula West all day | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866120210222-9Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting866120210222-9Excavator - 30 ton- After Jan 10101384.5Inv#114 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8661 | 20210222-9 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf performed road maintenance on Peninsula West all day | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866120210222-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting866120210222-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#114 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8661 | 20210222-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf performed road maintenance on Peninsula West all day | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866120210222-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting866120210222-9Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8661 | 20210222-9 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 2 | HR | 0 | 0 |  |  | 100 | 13 | 113 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf performed road maintenance on Peninsula West all day | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866120210222-9Pickup w/ plow2100 | Corbiere and Sons Contracting866120210222-9Pickup w/ plow2100Inv#114 | [5 empty] | 1 | 100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8661 | 20210222-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf performed road maintenance on Peninsula West all day | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866120210222-9L.O.A.1210 | Corbiere and Sons Contracting866120210222-9L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8661 | 20210222-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-02-22 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf performed road maintenance on Peninsula West all day | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866120210222-9Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting866120210222-9Operator - Principle - After Jan 1013975Inv#114 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8664 | 20210223-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan working on grader finishing up Little Red Sucker and was then floated back to Prairie River Road. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866420210223-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting866420210223-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#114 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8664 | 20210223-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan working on grader finishing up Little Red Sucker and was then floated back to Prairie River Road. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866420210223-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting866420210223-5Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8664 | 20210223-5 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan working on grader finishing up Little Red Sucker and was then floated back to Prairie River Road. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866420210223-5Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting866420210223-5Tractor Trailer - 60 Ton- After Jan 106734.34Inv#114 | [5 empty] | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8664 | 20210223-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan working on grader finishing up Little Red Sucker and was then floated back to Prairie River Road. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866420210223-5L.O.A.2420 | Corbiere and Sons Contracting866420210223-5L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8664 | 20210223-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan working on grader finishing up Little Red Sucker and was then floated back to Prairie River Road. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866420210223-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting866420210223-5Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8664 | 20210223-5 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan working on grader finishing up Little Red Sucker and was then floated back to Prairie River Road. | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866420210223-5Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting866420210223-5Driver - AZ - After Jan 106420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8665 | 20210223-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader in Neys Road - Grader was down for 2 hours.Jordan spent day doing road maintenance for crane at KM6; Darrel continued on dozer clearing snow and widening corners for crane access from KM6-7.5Dustin coordinating snow removal activities. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866520210223-6Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting866520210223-6Dozer D6 or equal- After Jan 10101314.8Inv#114 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8665 | 20210223-6 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader in Neys Road - Grader was down for 2 hours.Jordan spent day doing road maintenance for crane at KM6; Darrel continued on dozer clearing snow and widening corners for crane access from KM6-7.5Dustin coordinating snow removal activities. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866520210223-6Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting866520210223-6Excavator - 30 ton- After Jan 10101384.5Inv#114 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8665 | 20210223-6 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader in Neys Road - Grader was down for 2 hours.Jordan spent day doing road maintenance for crane at KM6; Darrel continued on dozer clearing snow and widening corners for crane access from KM6-7.5Dustin coordinating snow removal activities. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866520210223-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting866520210223-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#114 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8665 | 20210223-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader in Neys Road - Grader was down for 2 hours.Jordan spent day doing road maintenance for crane at KM6; Darrel continued on dozer clearing snow and widening corners for crane access from KM6-7.5Dustin coordinating snow removal activities. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866520210223-6Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting866520210223-6Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#114 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8665 | 20210223-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader in Neys Road - Grader was down for 2 hours.Jordan spent day doing road maintenance for crane at KM6; Darrel continued on dozer clearing snow and widening corners for crane access from KM6-7.5Dustin coordinating snow removal activities. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866520210223-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting866520210223-6Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8665 | 20210223-6 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader in Neys Road - Grader was down for 2 hours.Jordan spent day doing road maintenance for crane at KM6; Darrel continued on dozer clearing snow and widening corners for crane access from KM6-7.5Dustin coordinating snow removal activities. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866520210223-6L.O.A.3630 | Corbiere and Sons Contracting866520210223-6L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8665 | 20210223-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 37 | HR |  |  | 75 | 0 | 2775 | 360.75 | 3135.75 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on grader in Neys Road - Grader was down for 2 hours.Jordan spent day doing road maintenance for crane at KM6; Darrel continued on dozer clearing snow and widening corners for crane access from KM6-7.5Dustin coordinating snow removal activities. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866520210223-6Operator - Principle - After Jan 10372775 | Corbiere and Sons Contracting866520210223-6Operator - Principle - After Jan 10372775Inv#114 | [5 empty] | 1 | 2775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8666 | 20210223-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine worked on grader in Lake A scratching up raods on East Side. | 6 | C129-C151 | Lake A | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866620210223-7Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting866620210223-7Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#114 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8666 | 20210223-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine worked on grader in Lake A scratching up raods on East Side. | 6 | C129-C151 | Lake A | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866620210223-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting866620210223-7Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8666 | 20210223-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine worked on grader in Lake A scratching up raods on East Side. | 6 | C129-C151 | Lake A | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866620210223-7L.O.A.1210 | Corbiere and Sons Contracting866620210223-7L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8666 | 20210223-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine worked on grader in Lake A scratching up raods on East Side. | 6 | C129-C151 | Lake A | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866620210223-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting866620210223-7Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8667 | 20210223-8 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 20 | Dynamic | 103.84 | 0 |  |  | 2769 | 359.97 | 3128.97 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf and Doug on EX and hammer doing road maintenance on Peninsula West filling voids and hammering high spots. | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866720210223-8Excavator - 30 ton- After Jan 10202769 | Corbiere and Sons Contracting866720210223-8Excavator - 30 ton- After Jan 10202769Inv#114 | [5 empty] | 1 | 2769 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8667 | 20210223-8 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf and Doug on EX and hammer doing road maintenance on Peninsula West filling voids and hammering high spots. | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866720210223-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting866720210223-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#114 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8667 | 20210223-8 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10 | HR | 47.54 | 0 |  |  | 633.8 | 82.394 | 716.194 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf and Doug on EX and hammer doing road maintenance on Peninsula West filling voids and hammering high spots. | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866720210223-8Excavator Hammer - 30 - 50 ton- After Jan 1010633.8 | Corbiere and Sons Contracting866720210223-8Excavator Hammer - 30 - 50 ton- After Jan 1010633.8Inv#114 | [5 empty] | 1 | 633.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8667 | 20210223-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf and Doug on EX and hammer doing road maintenance on Peninsula West filling voids and hammering high spots. | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866720210223-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting866720210223-8Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8667 | 20210223-8 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf and Doug on EX and hammer doing road maintenance on Peninsula West filling voids and hammering high spots. | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866720210223-8L.O.A.2420 | Corbiere and Sons Contracting866720210223-8L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8667 | 20210223-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2021-02-23 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf and Doug on EX and hammer doing road maintenance on Peninsula West filling voids and hammering high spots. | 6 | C268-C279 | Peninsula Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting866720210223-8Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting866720210223-8Operator - Principle - After Jan 10221650Inv#114 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8810 | 20210224-10 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated moved Evan from Prairie River to Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881020210224-10Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting881020210224-10Grader - Cat 12 to 14 or equal- After Jan 102253.96Inv#114 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8810 | 20210224-10 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated moved Evan from Prairie River to Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881020210224-10Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting881020210224-10Tractor Trailer - 60 Ton- After Jan 103367.17Inv#114 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8810 | 20210224-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated moved Evan from Prairie River to Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881020210224-10L.O.A.1210 | Corbiere and Sons Contracting881020210224-10L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8810 | 20210224-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated moved Evan from Prairie River to Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881020210224-10Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting881020210224-10Operator - Principle - After Jan 105375Inv#114 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8810 | 20210224-10 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated moved Evan from Prairie River to Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881020210224-10Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting881020210224-10Driver - AZ - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8811 | 20210224-11 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake A | 6 | C130-C151 | Lake A | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881120210224-11Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting881120210224-11Grader - Cat 12 to 14 or equal- After Jan 107888.86Inv#114 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8811 | 20210224-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake A | 6 | C130-C151 | Lake A | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881120210224-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting881120210224-11Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8811 | 20210224-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake A | 6 | C130-C151 | Lake A | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881120210224-11L.O.A.1210 | Corbiere and Sons Contracting881120210224-11L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8811 | 20210224-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake A | 6 | C130-C151 | Lake A | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881120210224-11Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting881120210224-11Operator - Principle - After Jan 108600Inv#114 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8812 | 20210224-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working across hills in Santoy Mountain | 6 | C155-C157 | Santoy Mountain | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881220210224-12Pickup w/ plow and sander5400 | Corbiere and Sons Contracting881220210224-12Pickup w/ plow and sander5400Inv#114 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8812 | 20210224-12 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working across hills in Santoy Mountain | 6 | C155-C157 | Santoy Mountain | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881220210224-12L.O.A.1210 | Corbiere and Sons Contracting881220210224-12L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8812 | 20210224-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working across hills in Santoy Mountain | 6 | C155-C157 | Santoy Mountain | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting881220210224-12Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting881220210224-12Operator - Intermdiate - After Jan 105350Inv#114 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8669 | 20210224-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4.5 | Dynamic | 98.61 | 0 |  |  | 591.66 | 76.9158 | 668.5758 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued snow removal in Cooks after being floated back from WF1. | 5 | C076-C116 | Cooks Lake Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting866920210224-5Dozer D6 or equal- After Jan 104.5591.66 | Corbiere and Sons Contracting866920210224-5Dozer D6 or equal- After Jan 104.5591.66Inv#114 | [5 empty] | 1 | 591.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8669 | 20210224-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued snow removal in Cooks after being floated back from WF1. | 5 | C076-C116 | Cooks Lake Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting866920210224-5L.O.A.1210 | Corbiere and Sons Contracting866920210224-5L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8669 | 20210224-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry continued snow removal in Cooks after being floated back from WF1. | 5 | C076-C116 | Cooks Lake Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting866920210224-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting866920210224-5Operator - Principle - After Jan 105375Inv#114 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8807 | 20210224-7 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan on Ex doing road maintenance on Neys East for Crane Access - Len working on Grader all day across Neys Road | 6 | C219-C236 | Neys | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880720210224-7Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting880720210224-7Excavator - 30 ton- After Jan 10101384.5Inv#114 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8807 | 20210224-7 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan on Ex doing road maintenance on Neys East for Crane Access - Len working on Grader all day across Neys Road | 6 | C219-C236 | Neys | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880720210224-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting880720210224-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#114 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8807 | 20210224-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan on Ex doing road maintenance on Neys East for Crane Access - Len working on Grader all day across Neys Road | 6 | C219-C236 | Neys | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880720210224-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting880720210224-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#114 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8807 | 20210224-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan on Ex doing road maintenance on Neys East for Crane Access - Len working on Grader all day across Neys Road | 6 | C219-C236 | Neys | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880720210224-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting880720210224-7Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8807 | 20210224-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan on Ex doing road maintenance on Neys East for Crane Access - Len working on Grader all day across Neys Road | 6 | C219-C236 | Neys | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880720210224-7L.O.A.2420 | Corbiere and Sons Contracting880720210224-7L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8807 | 20210224-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22.5 | HR |  |  | 75 | 0 | 1687.5 | 219.375 | 1906.875 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan on Ex doing road maintenance on Neys East for Crane Access - Len working on Grader all day across Neys Road | 6 | C219-C236 | Neys | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880720210224-7Operator - Principle - After Jan 1022.51687.5 | Corbiere and Sons Contracting880720210224-7Operator - Principle - After Jan 1022.51687.5Inv#114 | [5 empty] | 1 | 1687.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8808 | 20210224-8 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 13 | Dynamic | 103.84 | 0 |  |  | 1799.85 | 233.9805 | 2033.8305 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Peninsula | 6 | C270-C277 | Peninsula | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880820210224-8Excavator - 30 ton- After Jan 10131799.85 | Corbiere and Sons Contracting880820210224-8Excavator - 30 ton- After Jan 10131799.85Inv#114 | [5 empty] | 1 | 1799.85 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8808 | 20210224-8 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Peninsula | 6 | C270-C277 | Peninsula | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880820210224-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting880820210224-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#114 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8808 | 20210224-8 | 53510611 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Peninsula | 6 | C270-C277 | Peninsula | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880820210224-8Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting880820210224-8Excavator Hammer - 30 - 50 ton- After Jan 105316.9Inv#114 | [5 empty] | 1 | 316.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8808 | 20210224-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Peninsula | 6 | C270-C277 | Peninsula | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880820210224-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting880820210224-8Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8808 | 20210224-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Peninsula | 6 | C270-C277 | Peninsula | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880820210224-8Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting880820210224-8Operator - Principle - After Jan 1013975Inv#114 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8809 | 20210224-9 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan Roy ran grader in Prairie River for part of the day | 6 | C171-C185 | Prairie River | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880920210224-9Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting880920210224-9Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#114 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8809 | 20210224-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan Roy ran grader in Prairie River for part of the day | 6 | C171-C185 | Prairie River | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880920210224-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting880920210224-9Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8809 | 20210224-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan Roy ran grader in Prairie River for part of the day | 6 | C171-C185 | Prairie River | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880920210224-9L.O.A.1210 | Corbiere and Sons Contracting880920210224-9L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8809 | 20210224-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-24 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan Roy ran grader in Prairie River for part of the day | 6 | C171-C185 | Prairie River | 0 | 44270 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting880920210224-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting880920210224-9Operator - Principle - After Jan 106450Inv#114 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8679 | 20210225-10 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent day scratching hills and working across Lake A from KM9 back to entrance.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C129-C151 | Lake A | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867920210225-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting867920210225-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8679 | 20210225-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent day scratching hills and working across Lake A from KM9 back to entrance.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C129-C151 | Lake A | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867920210225-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting867920210225-10Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8679 | 20210225-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent day scratching hills and working across Lake A from KM9 back to entrance.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C129-C151 | Lake A | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867920210225-10Pickup w/ plow and sander4320 | Corbiere and Sons Contracting867920210225-10Pickup w/ plow and sander4320Inv#114 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8679 | 20210225-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent day scratching hills and working across Lake A from KM9 back to entrance.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C129-C151 | Lake A | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867920210225-10L.O.A.1210 | Corbiere and Sons Contracting867920210225-10L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8679 | 20210225-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent day scratching hills and working across Lake A from KM9 back to entrance.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C129-C151 | Lake A | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867920210225-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting867920210225-10Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8679 | 20210225-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary spent day scratching hills and working across Lake A from KM9 back to entrance.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C129-C151 | Lake A | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867920210225-10Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting867920210225-10Operator - Intermdiate - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8680 | 20210225-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C257-C267 | Hare Lake Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting868020210225-11Pickup w/ plow and sander4320 | Corbiere and Sons Contracting868020210225-11Pickup w/ plow and sander4320Inv#114 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8680 | 20210225-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C257-C267 | Hare Lake Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting868020210225-11L.O.A.1210 | Corbiere and Sons Contracting868020210225-11L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8680 | 20210225-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C257-C267 | Hare Lake Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting868020210225-11Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting868020210225-11Operator - Intermdiate - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8672 | 20210225-3 | 53510411 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn floated D6 into Cavers; Dan Frasier and dozer completed snow removal. | 4 | C028-C029 | Cavers Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting867220210225-3Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting867220210225-3Dozer D6 or equal- After Jan 106788.88Inv#114 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8672 | 20210225-3 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn floated D6 into Cavers; Dan Frasier and dozer completed snow removal. | 4 | C028-C029 | Cavers Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting867220210225-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting867220210225-3Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8672 | 20210225-3 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn floated D6 into Cavers; Dan Frasier and dozer completed snow removal. | 4 | C028-C029 | Cavers Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting867220210225-3Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting867220210225-3Tractor Trailer - 60 Ton- After Jan 103367.17Inv#114 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8672 | 20210225-3 | 53510411 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn floated D6 into Cavers; Dan Frasier and dozer completed snow removal. | 4 | C028-C029 | Cavers Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting867220210225-3L.O.A.2420 | Corbiere and Sons Contracting867220210225-3L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8672 | 20210225-3 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn floated D6 into Cavers; Dan Frasier and dozer completed snow removal. | 4 | C028-C029 | Cavers Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting867220210225-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting867220210225-3Operator - Principle - After Jan 109675Inv#114 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8672 | 20210225-3 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn floated D6 into Cavers; Dan Frasier and dozer completed snow removal. | 4 | C028-C029 | Cavers Road | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting867220210225-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting867220210225-3Driver - AZ - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8673 | 20210225-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved second dozer into Church; Terry Ellis cleared snow all day. | 5 | C028-C029 | Church | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting867320210225-4Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting867320210225-4Dozer D6 or equal- After Jan 1081051.84Inv#114 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8673 | 20210225-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved second dozer into Church; Terry Ellis cleared snow all day. | 5 | C028-C029 | Church | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting867320210225-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting867320210225-4Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8673 | 20210225-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved second dozer into Church; Terry Ellis cleared snow all day. | 5 | C028-C029 | Church | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting867320210225-4Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting867320210225-4Tractor Trailer - 60 Ton- After Jan 103367.17Inv#114 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8673 | 20210225-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved second dozer into Church; Terry Ellis cleared snow all day. | 5 | C028-C029 | Church | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting867320210225-4L.O.A.1210 | Corbiere and Sons Contracting867320210225-4L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8673 | 20210225-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved second dozer into Church; Terry Ellis cleared snow all day. | 5 | C028-C029 | Church | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting867320210225-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting867320210225-4Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8673 | 20210225-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and float moved second dozer into Church; Terry Ellis cleared snow all day. | 5 | C028-C029 | Church | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting867320210225-4Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting867320210225-4Driver - AZ - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8675 | 20210225-6 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day on road maintenance across Neys for Crane accessLen continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867520210225-6Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting867520210225-6Excavator - 30 ton- After Jan 10101384.5Inv#114 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8675 | 20210225-6 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day on road maintenance across Neys for Crane accessLen continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867520210225-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting867520210225-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#114 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8675 | 20210225-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day on road maintenance across Neys for Crane accessLen continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867520210225-6Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting867520210225-6Grader - Cat 12 to 14 or equal- After Jan 105.5698.39Inv#114 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8675 | 20210225-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day on road maintenance across Neys for Crane accessLen continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867520210225-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting867520210225-6Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8675 | 20210225-6 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day on road maintenance across Neys for Crane accessLen continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867520210225-6Pickup w/ plow5250 | Corbiere and Sons Contracting867520210225-6Pickup w/ plow5250Inv#114 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8675 | 20210225-6 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day on road maintenance across Neys for Crane accessLen continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867520210225-6L.O.A.2420 | Corbiere and Sons Contracting867520210225-6L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8675 | 20210225-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22.5 | HR |  |  | 75 | 0 | 1687.5 | 219.375 | 1906.875 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan spent day on road maintenance across Neys for Crane accessLen continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C219-C236 | Neys | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867520210225-6Operator - Principle - After Jan 1022.51687.5 | Corbiere and Sons Contracting867520210225-6Operator - Principle - After Jan 1022.51687.5Inv#114 | [5 empty] | 1 | 1687.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8676 | 20210225-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C237-C243 | Culvert Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867620210225-7Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting867620210225-7Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#114 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8676 | 20210225-7 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 6 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C237-C243 | Culvert Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867620210225-7Pickup w/ plow6300 | Corbiere and Sons Contracting867620210225-7Pickup w/ plow6300Inv#114 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8676 | 20210225-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C237-C243 | Culvert Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867620210225-7L.O.A.2420 | Corbiere and Sons Contracting867620210225-7L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8676 | 20210225-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len continued across Neys and Culvert Creek.Dustin spent day plowing entrances and looking after coordination of snow removal. | 6 | C237-C243 | Culvert Creek | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867620210225-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting867620210225-7Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8678 | 20210225-9 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran grader from Santoy Lake all day.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C158-C170 | Santoy Lake | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867820210225-9Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting867820210225-9Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8678 | 20210225-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran grader from Santoy Lake all day.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C158-C170 | Santoy Lake | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867820210225-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting867820210225-9Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8678 | 20210225-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran grader from Santoy Lake all day.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C158-C170 | Santoy Lake | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867820210225-9Pickup w/ plow and sander3240 | Corbiere and Sons Contracting867820210225-9Pickup w/ plow and sander3240Inv#114 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8678 | 20210225-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran grader from Santoy Lake all day.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C158-C170 | Santoy Lake | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867820210225-9L.O.A.1210 | Corbiere and Sons Contracting867820210225-9L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8678 | 20210225-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran grader from Santoy Lake all day.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C158-C170 | Santoy Lake | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867820210225-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting867820210225-9Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8678 | 20210225-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-25 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan ran grader from Santoy Lake all day.Richard Pine spent day on pickup w/sander and plow working across a variety of acess roads from Hare Westward. | 6 | C158-C170 | Santoy Lake | 0 | 44259 |  | 37 | 44264 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting867820210225-9Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting867820210225-9Operator - Intermdiate - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8721 | 20210226-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 9 |  | 0 | 0 |  |  | 720 | 93.6 | 813.6 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across roads from C215 to C218 | 6 | C215-C218 | Little Pic River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872120210226-10Pickup w/ plow and sander9720 | Corbiere and Sons Contracting872120210226-10Pickup w/ plow and sander9720Inv#114 | [5 empty] | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8721 | 20210226-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across roads from C215 to C218 | 6 | C215-C218 | Little Pic River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872120210226-10L.O.A.1210 | Corbiere and Sons Contracting872120210226-10L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8721 | 20210226-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 9 | HR |  |  | 70 | 0 | 630 | 81.9 | 711.9 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across roads from C215 to C218 | 6 | C215-C218 | Little Pic River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872120210226-10Operator - Intermdiate - After Jan 109630 | Corbiere and Sons Contracting872120210226-10Operator - Intermdiate - After Jan 109630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8722 | 20210226-11 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 20 | Dynamic | 103.84 | 0 |  |  | 2769 | 359.97 | 3128.97 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872220210226-11Excavator - 30 ton- After Jan 10202769 | Corbiere and Sons Contracting872220210226-11Excavator - 30 ton- After Jan 10202769Inv#114 | [5 empty] | 1 | 2769 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8722 | 20210226-11 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 20 | HR | 9.16 | 0 |  |  | 244.2 | 31.746 | 275.946 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872220210226-11Excavator Thumb - 30 - 50 ton- After Jan 1020244.2 | Corbiere and Sons Contracting872220210226-11Excavator Thumb - 30 - 50 ton- After Jan 1020244.2Inv#114 | [5 empty] | 1 | 244.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8722 | 20210226-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872220210226-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting872220210226-11Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8722 | 20210226-11 | 53510611 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872220210226-11Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting872220210226-11Rock Truck - 30 Ton- After Jan 10101380.5Inv#114 | [5 empty] | 1 | 1380.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8722 | 20210226-11 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872220210226-11L.O.A.3630 | Corbiere and Sons Contracting872220210226-11L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8722 | 20210226-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872220210226-11Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting872220210226-11Operator - Principle - After Jan 10332475Inv#114 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8714 | 20210226-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot moved Grader into Antler and Gary worked across access sroads for rest of day | 5 | C050-C069 | Antler Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting871420210226-3Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting871420210226-3Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#114 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8714 | 20210226-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot moved Grader into Antler and Gary worked across access sroads for rest of day | 5 | C050-C069 | Antler Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting871420210226-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting871420210226-3Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8714 | 20210226-3 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot moved Grader into Antler and Gary worked across access sroads for rest of day | 5 | C050-C069 | Antler Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting871420210226-3Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting871420210226-3Tractor Trailer - 60 Ton- After Jan 103367.17Inv#114 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8714 | 20210226-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot moved Grader into Antler and Gary worked across access sroads for rest of day | 5 | C050-C069 | Antler Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting871420210226-3L.O.A.2420 | Corbiere and Sons Contracting871420210226-3L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8714 | 20210226-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot moved Grader into Antler and Gary worked across access sroads for rest of day | 5 | C050-C069 | Antler Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting871420210226-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting871420210226-3Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8714 | 20210226-3 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot moved Grader into Antler and Gary worked across access sroads for rest of day | 5 | C050-C069 | Antler Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting871420210226-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting871420210226-3Driver - AZ - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8715 | 20210226-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry and DZ working on Snow Removal in Cavers Road | 5 | C029 | Cavers | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting871520210226-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting871520210226-4Dozer D6 or equal- After Jan 10101314.8Inv#114 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8715 | 20210226-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry and DZ working on Snow Removal in Cavers Road | 5 | C029 | Cavers | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting871520210226-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting871520210226-4Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8715 | 20210226-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry and DZ working on Snow Removal in Cavers Road | 5 | C029 | Cavers | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting871520210226-4L.O.A.1210 | Corbiere and Sons Contracting871520210226-4L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8715 | 20210226-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry and DZ working on Snow Removal in Cavers Road | 5 | C029 | Cavers | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting871520210226-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting871520210226-4Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8719 | 20210226-8 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Neys Road Access - Jordan doing road maintenance for Crane access - Dustin working with plow truck and coordinating activities | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting871920210226-8Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting871920210226-8Excavator - 30 ton- After Jan 10101384.5Inv#114 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8719 | 20210226-8 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Neys Road Access - Jordan doing road maintenance for Crane access - Dustin working with plow truck and coordinating activities | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting871920210226-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting871920210226-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#114 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8719 | 20210226-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Neys Road Access - Jordan doing road maintenance for Crane access - Dustin working with plow truck and coordinating activities | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting871920210226-8Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting871920210226-8Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8719 | 20210226-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Neys Road Access - Jordan doing road maintenance for Crane access - Dustin working with plow truck and coordinating activities | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting871920210226-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting871920210226-8Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8719 | 20210226-8 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Neys Road Access - Jordan doing road maintenance for Crane access - Dustin working with plow truck and coordinating activities | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting871920210226-8Pickup w/ plow11550 | Corbiere and Sons Contracting871920210226-8Pickup w/ plow11550Inv#114 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8719 | 20210226-8 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Neys Road Access - Jordan doing road maintenance for Crane access - Dustin working with plow truck and coordinating activities | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting871920210226-8L.O.A.3630 | Corbiere and Sons Contracting871920210226-8L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8719 | 20210226-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Neys Road Access - Jordan doing road maintenance for Crane access - Dustin working with plow truck and coordinating activities | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting871920210226-8Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting871920210226-8Operator - Principle - After Jan 10332475Inv#114 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8720 | 20210226-9 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake A Access | 6 | C130-C149 | Lake A | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872020210226-9Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting872020210226-9Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8720 | 20210226-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake A Access | 6 | C130-C149 | Lake A | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872020210226-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting872020210226-9Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8720 | 20210226-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake A Access | 6 | C130-C149 | Lake A | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872020210226-9L.O.A.1210 | Corbiere and Sons Contracting872020210226-9L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8720 | 20210226-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-26 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lake A Access | 6 | C130-C149 | Lake A | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872020210226-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting872020210226-9Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8732 | 20210227-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Deadhorse for snow removal - Flaggers needed | 6 | C203-C209 | Dead Horse Creek | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873220210227-10Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting873220210227-10Dozer D6 or equal- After Jan 102262.96Inv#114 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8732 | 20210227-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Deadhorse for snow removal - Flaggers needed | 6 | C203-C209 | Dead Horse Creek | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873220210227-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting873220210227-10Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8732 | 20210227-10 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Deadhorse for snow removal - Flaggers needed | 6 | C203-C209 | Dead Horse Creek | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873220210227-10Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting873220210227-10Tractor Trailer - 60 Ton- After Jan 104489.56Inv#114 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8732 | 20210227-10 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Deadhorse for snow removal - Flaggers needed | 6 | C203-C209 | Dead Horse Creek | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873220210227-10Pickup w/ plow11550 | Corbiere and Sons Contracting873220210227-10Pickup w/ plow11550Inv#114 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8732 | 20210227-10 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Deadhorse for snow removal - Flaggers needed | 6 | C203-C209 | Dead Horse Creek | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873220210227-10L.O.A.4840 | Corbiere and Sons Contracting873220210227-10L.O.A.4840Inv#114 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8732 | 20210227-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Deadhorse for snow removal - Flaggers needed | 6 | C203-C209 | Dead Horse Creek | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873220210227-10Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting873220210227-10Operator - Principle - After Jan 10161200Inv#114 | [5 empty] | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8732 | 20210227-10 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Deadhorse for snow removal - Flaggers needed | 6 | C203-C209 | Dead Horse Creek | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873220210227-10Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting873220210227-10Driver - AZ - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8732 | 20210227-10 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Deadhorse for snow removal - Flaggers needed | 6 | C203-C209 | Dead Horse Creek | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873220210227-10Labourer - General - After Jan 108480 | Corbiere and Sons Contracting873220210227-10Labourer - General - After Jan 108480Inv#114 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8725 | 20210227-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ in Cooks - John S. plowed float turn around - Terry ran DZ in Cooks for snow removal | 5 | C076-C116 | Cook Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872520210227-3Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting872520210227-3Dozer D6 or equal- After Jan 1081051.84Inv#114 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8725 | 20210227-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ in Cooks - John S. plowed float turn around - Terry ran DZ in Cooks for snow removal | 5 | C076-C116 | Cook Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872520210227-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting872520210227-3Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8725 | 20210227-3 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3.5 | Dynamic | 91.79 | 0 |  |  | 428.365 | 55.6874 | 484.0525 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ in Cooks - John S. plowed float turn around - Terry ran DZ in Cooks for snow removal | 5 | C076-C116 | Cook Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872520210227-3Tractor Trailer - 60 Ton- After Jan 103.5428.365 | Corbiere and Sons Contracting872520210227-3Tractor Trailer - 60 Ton- After Jan 103.5428.365Inv#114 | [5 empty] | 1 | 428.365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8725 | 20210227-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ in Cooks - John S. plowed float turn around - Terry ran DZ in Cooks for snow removal | 5 | C076-C116 | Cook Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872520210227-3Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting872520210227-3Pickup w/ plow and sander2.5200Inv#114 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8725 | 20210227-3 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ in Cooks - John S. plowed float turn around - Terry ran DZ in Cooks for snow removal | 5 | C076-C116 | Cook Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872520210227-3L.O.A.3630 | Corbiere and Sons Contracting872520210227-3L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8725 | 20210227-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ in Cooks - John S. plowed float turn around - Terry ran DZ in Cooks for snow removal | 5 | C076-C116 | Cook Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872520210227-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting872520210227-3Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8725 | 20210227-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ in Cooks - John S. plowed float turn around - Terry ran DZ in Cooks for snow removal | 5 | C076-C116 | Cook Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872520210227-3Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting872520210227-3Operator - Intermdiate - After Jan 102.5175Inv#114 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8725 | 20210227-3 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3.5 | HR |  |  | 70 | 0 | 245 | 31.85 | 276.85 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ in Cooks - John S. plowed float turn around - Terry ran DZ in Cooks for snow removal | 5 | C076-C116 | Cook Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872520210227-3Driver - AZ - After Jan 103.5245 | Corbiere and Sons Contracting872520210227-3Driver - AZ - After Jan 103.5245Inv#114 | [5 empty] | 1 | 245 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8726 | 20210227-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snowplowing float turn around | 5 | C031-C035 | Pays Plat River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872620210227-4Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting872620210227-4Pickup w/ plow and sander2.5200Inv#114 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8726 | 20210227-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snowplowing float turn around | 5 | C031-C035 | Pays Plat River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872620210227-4Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting872620210227-4Operator - Intermdiate - After Jan 102.5175Inv#114 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8727 | 20210227-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Grader across Antler Lake Road - Made it to KM5 | 5 | C050-C069 | Antler Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872720210227-5Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting872720210227-5Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv#114 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8727 | 20210227-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Grader across Antler Lake Road - Made it to KM5 | 5 | C050-C069 | Antler Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872720210227-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting872720210227-5Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8727 | 20210227-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Grader across Antler Lake Road - Made it to KM5 | 5 | C050-C069 | Antler Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872720210227-5L.O.A.1210 | Corbiere and Sons Contracting872720210227-5L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8727 | 20210227-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Grader across Antler Lake Road - Made it to KM5 | 5 | C050-C069 | Antler Lake | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting872720210227-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting872720210227-5Operator - Principle - After Jan 1012900Inv#114 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8728 | 20210227-6 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 20 | Dynamic | 103.84 | 0 |  |  | 2769 | 359.97 | 3128.97 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872820210227-6Excavator - 30 ton- After Jan 10202769 | Corbiere and Sons Contracting872820210227-6Excavator - 30 ton- After Jan 10202769Inv#114 | [5 empty] | 1 | 2769 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8728 | 20210227-6 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 20 | HR | 9.16 | 0 |  |  | 244.2 | 31.746 | 275.946 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872820210227-6Excavator Thumb - 30 - 50 ton- After Jan 1020244.2 | Corbiere and Sons Contracting872820210227-6Excavator Thumb - 30 - 50 ton- After Jan 1020244.2Inv#114 | [5 empty] | 1 | 244.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8728 | 20210227-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872820210227-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting872820210227-6Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8728 | 20210227-6 | 53510611 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872820210227-6Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting872820210227-6Rock Truck - 30 Ton- After Jan 10101380.5Inv#114 | [5 empty] | 1 | 1380.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8728 | 20210227-6 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872820210227-6L.O.A.3630 | Corbiere and Sons Contracting872820210227-6L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8728 | 20210227-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872820210227-6Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting872820210227-6Operator - Principle - After Jan 10332475Inv#114 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8729 | 20210227-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S. plowing and sanding Little Pic River | 6 | C215-C218 | Little pic River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872920210227-7Pickup w/ plow and sander6480 | Corbiere and Sons Contracting872920210227-7Pickup w/ plow and sander6480Inv#114 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8729 | 20210227-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S. plowing and sanding Little Pic River | 6 | C215-C218 | Little pic River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting872920210227-7Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting872920210227-7Operator - Intermdiate - After Jan 106420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8730 | 20210227-8 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across west side of Neys for the day - Ex doing maintenance for crane access | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873020210227-8Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting873020210227-8Excavator - 30 ton- After Jan 10101384.5Inv#114 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8730 | 20210227-8 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across west side of Neys for the day - Ex doing maintenance for crane access | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873020210227-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting873020210227-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#114 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8730 | 20210227-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across west side of Neys for the day - Ex doing maintenance for crane access | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873020210227-8Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting873020210227-8Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#114 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8730 | 20210227-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across west side of Neys for the day - Ex doing maintenance for crane access | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873020210227-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting873020210227-8Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8730 | 20210227-8 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across west side of Neys for the day - Ex doing maintenance for crane access | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873020210227-8L.O.A.2420 | Corbiere and Sons Contracting873020210227-8L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8730 | 20210227-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22.5 | HR |  |  | 75 | 0 | 1687.5 | 219.375 | 1906.875 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across west side of Neys for the day - Ex doing maintenance for crane access | 6 | C219-C236 | Neys | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873020210227-8Operator - Principle - After Jan 1022.51687.5 | Corbiere and Sons Contracting873020210227-8Operator - Principle - After Jan 1022.51687.5Inv#114 | [5 empty] | 1 | 1687.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8731 | 20210227-9 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader conitnuing work on Lake A access | 6 | C130-C149 | Lake A | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873120210227-9Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting873120210227-9Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8731 | 20210227-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader conitnuing work on Lake A access | 6 | C130-C149 | Lake A | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873120210227-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting873120210227-9Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8731 | 20210227-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader conitnuing work on Lake A access | 6 | C130-C149 | Lake A | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873120210227-9L.O.A.1210 | Corbiere and Sons Contracting873120210227-9L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8731 | 20210227-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-27 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader conitnuing work on Lake A access | 6 | C130-C149 | Lake A | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873120210227-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting873120210227-9Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8773 | 20210228-11 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued on Grader on Neys road, pulling in snow and regrading - Jordan pleason continued on Ex doing road maintenance - Dustin Coordinating all snow removal activities | 6 | C219-C236 | Neys Road | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877320210228-11Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting877320210228-11Excavator - 30 ton- After Jan 1081107.6Inv#114 | [5 empty] | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8773 | 20210228-11 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued on Grader on Neys road, pulling in snow and regrading - Jordan pleason continued on Ex doing road maintenance - Dustin Coordinating all snow removal activities | 6 | C219-C236 | Neys Road | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877320210228-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting877320210228-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#114 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8773 | 20210228-11 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued on Grader on Neys road, pulling in snow and regrading - Jordan pleason continued on Ex doing road maintenance - Dustin Coordinating all snow removal activities | 6 | C219-C236 | Neys Road | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877320210228-11Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting877320210228-11Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#114 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8773 | 20210228-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued on Grader on Neys road, pulling in snow and regrading - Jordan pleason continued on Ex doing road maintenance - Dustin Coordinating all snow removal activities | 6 | C219-C236 | Neys Road | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877320210228-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting877320210228-11Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8773 | 20210228-11 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued on Grader on Neys road, pulling in snow and regrading - Jordan pleason continued on Ex doing road maintenance - Dustin Coordinating all snow removal activities | 6 | C219-C236 | Neys Road | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877320210228-11Pickup w/ plow11550 | Corbiere and Sons Contracting877320210228-11Pickup w/ plow11550Inv#114 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8773 | 20210228-11 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued on Grader on Neys road, pulling in snow and regrading - Jordan pleason continued on Ex doing road maintenance - Dustin Coordinating all snow removal activities | 6 | C219-C236 | Neys Road | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877320210228-11L.O.A.3630 | Corbiere and Sons Contracting877320210228-11L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8773 | 20210228-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30.5 | HR |  |  | 75 | 0 | 2287.5 | 297.375 | 2584.875 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continued on Grader on Neys road, pulling in snow and regrading - Jordan pleason continued on Ex doing road maintenance - Dustin Coordinating all snow removal activities | 6 | C219-C236 | Neys Road | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877320210228-11Operator - Principle - After Jan 1030.52287.5 | Corbiere and Sons Contracting877320210228-11Operator - Principle - After Jan 1030.52287.5Inv#114 | [5 empty] | 1 | 2287.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8774 | 20210228-12 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Grader for nightshift in Lake A | 6 | C130-C151 | Lake A | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877420210228-12Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting877420210228-12Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8774 | 20210228-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Grader for nightshift in Lake A | 6 | C130-C151 | Lake A | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877420210228-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting877420210228-12Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8774 | 20210228-12 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Grader for nightshift in Lake A | 6 | C130-C151 | Lake A | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877420210228-12L.O.A.1210 | Corbiere and Sons Contracting877420210228-12L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8774 | 20210228-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Grader for nightshift in Lake A | 6 | C130-C151 | Lake A | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877420210228-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting877420210228-12Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8775 | 20210228-13 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry Boucher spent 5 hours clearing road and turn around for tractor trailers | 6 | C203-C209 | Deadhorse | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877520210228-13Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting877520210228-13Dozer D6 or equal- After Jan 105657.4Inv#114 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8775 | 20210228-13 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry Boucher spent 5 hours clearing road and turn around for tractor trailers | 6 | C203-C209 | Deadhorse | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877520210228-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting877520210228-13Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8775 | 20210228-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry Boucher spent 5 hours clearing road and turn around for tractor trailers | 6 | C203-C209 | Deadhorse | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877520210228-13L.O.A.1210 | Corbiere and Sons Contracting877520210228-13L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8775 | 20210228-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry Boucher spent 5 hours clearing road and turn around for tractor trailers | 6 | C203-C209 | Deadhorse | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877520210228-13Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting877520210228-13Operator - Principle - After Jan 105375Inv#114 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8776 | 20210228-14 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3.5 | Dynamic | 98.61 | 0 |  |  | 460.18 | 59.8234 | 520.0034 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Ripple - 2 flaggers - DZ starting clearing in Ripple | 6 | C196-C202 | Ripple Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877620210228-14Dozer D6 or equal- After Jan 103.5460.18 | Corbiere and Sons Contracting877620210228-14Dozer D6 or equal- After Jan 103.5460.18Inv#114 | [5 empty] | 1 | 460.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8776 | 20210228-14 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Ripple - 2 flaggers - DZ starting clearing in Ripple | 6 | C196-C202 | Ripple Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877620210228-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting877620210228-14Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8776 | 20210228-14 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Ripple - 2 flaggers - DZ starting clearing in Ripple | 6 | C196-C202 | Ripple Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877620210228-14Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting877620210228-14Tractor Trailer - 60 Ton- After Jan 103367.17Inv#114 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8776 | 20210228-14 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Ripple - 2 flaggers - DZ starting clearing in Ripple | 6 | C196-C202 | Ripple Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877620210228-14L.O.A.2420 | Corbiere and Sons Contracting877620210228-14L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8776 | 20210228-14 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Ripple - 2 flaggers - DZ starting clearing in Ripple | 6 | C196-C202 | Ripple Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877620210228-14Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting877620210228-14Operator - Principle - After Jan 106450Inv#114 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8776 | 20210228-14 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Ripple - 2 flaggers - DZ starting clearing in Ripple | 6 | C196-C202 | Ripple Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877620210228-14Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting877620210228-14Driver - AZ - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8776 | 20210228-14 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated into Ripple - 2 flaggers - DZ starting clearing in Ripple | 6 | C196-C202 | Ripple Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877620210228-14Labourer - General - After Jan 108480 | Corbiere and Sons Contracting877620210228-14Labourer - General - After Jan 108480Inv#114 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8999 | 20210228-15 | 53510311 | Access | 0 | 3rd Party Charges | 1 | 377 | unit |  |  |  |  | 377 | 49.01 | 426.01 | 2021-02-28 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sand from Red Rock pit to use on access roads in WF3 | 3 | B078-B193 | WF3 | 0 | 44284 |  | 36 | 44291 | 202021378 | Screened Sand for Road |  |  |  | Mike Lecocq | 03 | Corbiere and Sons Contracting899920210228-153rd Party Charges377377 | Corbiere and Sons Contracting899920210228-153rd Party Charges377377Inv#122 | [5 empty] | 1 | 377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8737 | 20210228-3 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873720210228-3Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting873720210228-3Excavator - 30 ton- After Jan 1081107.6Inv#114 | [5 empty] | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8737 | 20210228-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873720210228-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting873720210228-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#114 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8737 | 20210228-3 | 53510611 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873720210228-3Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting873720210228-3Rock Truck - 30 Ton- After Jan 104552.2Inv#114 | [5 empty] | 1 | 552.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8737 | 20210228-3 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873720210228-3L.O.A.3630 | Corbiere and Sons Contracting873720210228-3L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8737 | 20210228-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore crew doing road repair on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44262 |  | 37 | 44271 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting873720210228-3Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting873720210228-3Operator - Principle - After Jan 10151125Inv#114 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8767 | 20210228-5 | 53510411 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John and plow truck with Sander working across Nishin road | 4 | C015-C027 | Nishin Road | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting876720210228-5Pickup w/ plow and sander4320 | Corbiere and Sons Contracting876720210228-5Pickup w/ plow and sander4320Inv#114 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8767 | 20210228-5 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John and plow truck with Sander working across Nishin road | 4 | C015-C027 | Nishin Road | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting876720210228-5L.O.A.1210 | Corbiere and Sons Contracting876720210228-5L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8767 | 20210228-5 | 53510411 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John and plow truck with Sander working across Nishin road | 4 | C015-C027 | Nishin Road | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting876720210228-5Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting876720210228-5Operator - Intermdiate - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8768 | 20210228-6 | 53510411 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John and plow truck with Sander working across Cavers Road | 4 | C028 | Cavers | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting876820210228-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting876820210228-6Pickup w/ plow and sander4320Inv#114 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8768 | 20210228-6 | 53510411 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John and plow truck with Sander working across Cavers Road | 4 | C028 | Cavers | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting876820210228-6Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting876820210228-6Operator - Intermdiate - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8769 | 20210228-7 | 53510411 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John and plow truck with Sander working across Gravel River Road | 4 | B217-B014 | Gravel River | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting876920210228-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting876920210228-7Pickup w/ plow and sander3240Inv#114 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8769 | 20210228-7 | 53510411 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John and plow truck with Sander working across Gravel River Road | 4 | B217-B014 | Gravel River | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting876920210228-7Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting876920210228-7Operator - Intermdiate - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8770 | 20210228-8 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continuing snow removal in Cooks Lake Road - Made it to C094 | 5 | C076-C116 | Cook Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting877020210228-8Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting877020210228-8Dozer D6 or equal- After Jan 1081051.84Inv#114 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8770 | 20210228-8 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continuing snow removal in Cooks Lake Road - Made it to C094 | 5 | C076-C116 | Cook Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting877020210228-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting877020210228-8Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8770 | 20210228-8 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continuing snow removal in Cooks Lake Road - Made it to C094 | 5 | C076-C116 | Cook Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting877020210228-8L.O.A.1210 | Corbiere and Sons Contracting877020210228-8L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8770 | 20210228-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continuing snow removal in Cooks Lake Road - Made it to C094 | 5 | C076-C116 | Cook Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting877020210228-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting877020210228-8Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8771 | 20210228-9 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Grader across Antler Lake Road all day - Made it to Tower to C069 | 5 | C050-C069 | Antler Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting877120210228-9Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting877120210228-9Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#114 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8771 | 20210228-9 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Grader across Antler Lake Road all day - Made it to Tower to C069 | 5 | C050-C069 | Antler Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting877120210228-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting877120210228-9Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8771 | 20210228-9 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Grader across Antler Lake Road all day - Made it to Tower to C069 | 5 | C050-C069 | Antler Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting877120210228-9L.O.A.1210 | Corbiere and Sons Contracting877120210228-9L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8771 | 20210228-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-02-28 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Grader across Antler Lake Road all day - Made it to Tower to C069 | 5 | C050-C069 | Antler Lake | 0 | 44264 |  | 37 | 44271 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting877120210228-9Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting877120210228-9Operator - Principle - After Jan 1011.5862.5Inv#114 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8777 | 20210301-3 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed Camp Road 81 to Retrieve Zoom Boom | 3 | C145-C149 | Camp 81 Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting877720210301-3Pickup w/ plow and sander5400 | Corbiere and Sons Contracting877720210301-3Pickup w/ plow and sander5400Inv#114 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8777 | 20210301-3 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed Camp Road 81 to Retrieve Zoom Boom | 3 | C145-C149 | Camp 81 Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting877720210301-3L.O.A.1210 | Corbiere and Sons Contracting877720210301-3L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8777 | 20210301-3 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed Camp Road 81 to Retrieve Zoom Boom | 3 | C145-C149 | Camp 81 Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting877720210301-3Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting877720210301-3Operator - Intermdiate - After Jan 105350Inv#114 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8778 | 20210301-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continuing on grader on Neys Road pulling in snow to regrade | 6 | C076-C116 | Neys | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877820210301-4Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting877820210301-4Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#114 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8778 | 20210301-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continuing on grader on Neys Road pulling in snow to regrade | 6 | C076-C116 | Neys | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877820210301-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting877820210301-4Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8778 | 20210301-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continuing on grader on Neys Road pulling in snow to regrade | 6 | C076-C116 | Neys | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877820210301-4L.O.A.1210 | Corbiere and Sons Contracting877820210301-4L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8778 | 20210301-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary continuing on grader on Neys Road pulling in snow to regrade | 6 | C076-C116 | Neys | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877820210301-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting877820210301-4Operator - Principle - After Jan 1011.5862.5Inv#114 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8779 | 20210301-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Grader in Lake A for nightshift | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877920210301-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting877920210301-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8779 | 20210301-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Grader in Lake A for nightshift | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877920210301-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting877920210301-5Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8779 | 20210301-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Grader in Lake A for nightshift | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877920210301-5L.O.A.1210 | Corbiere and Sons Contracting877920210301-5L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8779 | 20210301-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on Grader in Lake A for nightshift | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting877920210301-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting877920210301-5Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8780 | 20210301-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader in Prairie River road after being floated in | 6 | C171-C185 | Prairie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878020210301-6Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting878020210301-6Grader - Cat 12 to 14 or equal- After Jan 107888.86Inv#114 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8780 | 20210301-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader in Prairie River road after being floated in | 6 | C171-C185 | Prairie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878020210301-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting878020210301-6Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8780 | 20210301-6 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader in Prairie River road after being floated in | 6 | C171-C185 | Prairie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878020210301-6Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting878020210301-6Tractor Trailer - 60 Ton- After Jan 102244.78Inv#114 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8780 | 20210301-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader in Prairie River road after being floated in | 6 | C171-C185 | Prairie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878020210301-6L.O.A.1210 | Corbiere and Sons Contracting878020210301-6L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8780 | 20210301-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader in Prairie River road after being floated in | 6 | C171-C185 | Prairie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878020210301-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting878020210301-6Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8780 | 20210301-6 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader in Prairie River road after being floated in | 6 | C171-C185 | Prairie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878020210301-6Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting878020210301-6Driver - AZ - After Jan 102140Inv#114 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8781 | 20210301-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed dozer into Little Pic - 2 Flaggers - Colin did Orientation - Dustin coordinating all snow removal activites and working on pickup w/plow for entrances | 6 | C215-C218 | Little Pie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878120210301-7Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting878120210301-7Dozer D6 or equal- After Jan 106788.88Inv#114 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8781 | 20210301-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed dozer into Little Pic - 2 Flaggers - Colin did Orientation - Dustin coordinating all snow removal activites and working on pickup w/plow for entrances | 6 | C215-C218 | Little Pie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878120210301-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting878120210301-7Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8781 | 20210301-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed dozer into Little Pic - 2 Flaggers - Colin did Orientation - Dustin coordinating all snow removal activites and working on pickup w/plow for entrances | 6 | C215-C218 | Little Pie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878120210301-7Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting878120210301-7Tractor Trailer - 60 Ton- After Jan 102244.78Inv#114 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8781 | 20210301-7 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed dozer into Little Pic - 2 Flaggers - Colin did Orientation - Dustin coordinating all snow removal activites and working on pickup w/plow for entrances | 6 | C215-C218 | Little Pie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878120210301-7Pickup w/ plow11550 | Corbiere and Sons Contracting878120210301-7Pickup w/ plow11550Inv#114 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8781 | 20210301-7 | 53510611 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed dozer into Little Pic - 2 Flaggers - Colin did Orientation - Dustin coordinating all snow removal activites and working on pickup w/plow for entrances | 6 | C215-C218 | Little Pie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878120210301-7L.O.A.61260 | Corbiere and Sons Contracting878120210301-7L.O.A.61260Inv#114 | [5 empty] | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8781 | 20210301-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed dozer into Little Pic - 2 Flaggers - Colin did Orientation - Dustin coordinating all snow removal activites and working on pickup w/plow for entrances | 6 | C215-C218 | Little Pie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878120210301-7Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting878120210301-7Operator - Principle - After Jan 10201500Inv#114 | [5 empty] | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8781 | 20210301-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed dozer into Little Pic - 2 Flaggers - Colin did Orientation - Dustin coordinating all snow removal activites and working on pickup w/plow for entrances | 6 | C215-C218 | Little Pie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878120210301-7Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting878120210301-7Operator - Intermdiate - After Jan 105350Inv#114 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8781 | 20210301-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed dozer into Little Pic - 2 Flaggers - Colin did Orientation - Dustin coordinating all snow removal activites and working on pickup w/plow for entrances | 6 | C215-C218 | Little Pie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878120210301-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting878120210301-7Driver - AZ - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8781 | 20210301-7 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed dozer into Little Pic - 2 Flaggers - Colin did Orientation - Dustin coordinating all snow removal activites and working on pickup w/plow for entrances | 6 | C215-C218 | Little Pie River | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878120210301-7Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting878120210301-7Labourer - General - After Jan 1010600Inv#114 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8782 | 20210301-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S. and pickup w/plow and Sander working across various areas including Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878220210301-8Pickup w/ plow and sander8640 | Corbiere and Sons Contracting878220210301-8Pickup w/ plow and sander8640Inv#114 | [5 empty] | 1 | 640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8782 | 20210301-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S. and pickup w/plow and Sander working across various areas including Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878220210301-8L.O.A.1210 | Corbiere and Sons Contracting878220210301-8L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8782 | 20210301-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-03-01 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S. and pickup w/plow and Sander working across various areas including Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878220210301-8Operator - Intermdiate - After Jan 108560 | Corbiere and Sons Contracting878220210301-8Operator - Intermdiate - After Jan 108560Inv#114 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8783 | 20210302-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry working on Grader in Antler, made it to C067 but couldn't get up big hill | 5 | C050-C069 | Antler Lake | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878320210302-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting878320210302-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8783 | 20210302-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry working on Grader in Antler, made it to C067 but couldn't get up big hill | 5 | C050-C069 | Antler Lake | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878320210302-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting878320210302-4Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8783 | 20210302-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry working on Grader in Antler, made it to C067 but couldn't get up big hill | 5 | C050-C069 | Antler Lake | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878320210302-4L.O.A.1210 | Corbiere and Sons Contracting878320210302-4L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8783 | 20210302-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry working on Grader in Antler, made it to C067 but couldn't get up big hill | 5 | C050-C069 | Antler Lake | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878320210302-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting878320210302-4Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8784 | 20210302-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug moved Grader into Little Red Sucker Creek - Gary Gallinger ran the grader on nightshift | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878420210302-5Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting878420210302-5Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv#114 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8784 | 20210302-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug moved Grader into Little Red Sucker Creek - Gary Gallinger ran the grader on nightshift | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878420210302-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting878420210302-5Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8784 | 20210302-5 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug moved Grader into Little Red Sucker Creek - Gary Gallinger ran the grader on nightshift | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878420210302-5Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting878420210302-5Tractor Trailer - 60 Ton- After Jan 103367.17Inv#114 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8784 | 20210302-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug moved Grader into Little Red Sucker Creek - Gary Gallinger ran the grader on nightshift | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878420210302-5L.O.A.2420 | Corbiere and Sons Contracting878420210302-5L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8784 | 20210302-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug moved Grader into Little Red Sucker Creek - Gary Gallinger ran the grader on nightshift | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878420210302-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting878420210302-5Operator - Principle - After Jan 1012900Inv#114 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8784 | 20210302-5 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug moved Grader into Little Red Sucker Creek - Gary Gallinger ran the grader on nightshift | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878420210302-5Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting878420210302-5Driver - AZ - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8785 | 20210302-6-R1 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader being run in Lake A on nightshift | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878520210302-6-R1Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting878520210302-6-R1Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8785 | 20210302-6-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader being run in Lake A on nightshift | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878520210302-6-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting878520210302-6-R1Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8785 | 20210302-6-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader being run in Lake A on nightshift | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878520210302-6-R1L.O.A.1210 | Corbiere and Sons Contracting878520210302-6-R1L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8785 | 20210302-6-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader being run in Lake A on nightshift | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878520210302-6-R1Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting878520210302-6-R1Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8786 | 20210302-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 95.24 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated LEN back into Culvert Creek to continue road maintenance with grader - Dustin working on Pickup w/plow and coordinating snow removal activities | 6 | C237-C243 | Culvert Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878620210302-7Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting878620210302-7Grader - Cat 12 to 14 or equal- After Jan 108.51079.33Inv#114 | [5 empty] | 1 | 1079.33 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8786 | 20210302-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated LEN back into Culvert Creek to continue road maintenance with grader - Dustin working on Pickup w/plow and coordinating snow removal activities | 6 | C237-C243 | Culvert Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878620210302-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting878620210302-7Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8786 | 20210302-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated LEN back into Culvert Creek to continue road maintenance with grader - Dustin working on Pickup w/plow and coordinating snow removal activities | 6 | C237-C243 | Culvert Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878620210302-7Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting878620210302-7Tractor Trailer - 60 Ton- After Jan 103367.17Inv#114 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8786 | 20210302-7 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated LEN back into Culvert Creek to continue road maintenance with grader - Dustin working on Pickup w/plow and coordinating snow removal activities | 6 | C237-C243 | Culvert Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878620210302-7Pickup w/ plow11550 | Corbiere and Sons Contracting878620210302-7Pickup w/ plow11550Inv#114 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8786 | 20210302-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated LEN back into Culvert Creek to continue road maintenance with grader - Dustin working on Pickup w/plow and coordinating snow removal activities | 6 | C237-C243 | Culvert Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878620210302-7L.O.A.2420 | Corbiere and Sons Contracting878620210302-7L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8786 | 20210302-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated LEN back into Culvert Creek to continue road maintenance with grader - Dustin working on Pickup w/plow and coordinating snow removal activities | 6 | C237-C243 | Culvert Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878620210302-7Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting878620210302-7Operator - Principle - After Jan 10221650Inv#114 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8786 | 20210302-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug floated LEN back into Culvert Creek to continue road maintenance with grader - Dustin working on Pickup w/plow and coordinating snow removal activities | 6 | C237-C243 | Culvert Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878620210302-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting878620210302-7Driver - AZ - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8787 | 20210302-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S. continuing work with Pickup w/plow and sander across Peninsula Road | 6 | C270-C277 | Peninsula Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878720210302-8Pickup w/ plow and sander11880 | Corbiere and Sons Contracting878720210302-8Pickup w/ plow and sander11880Inv#114 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8787 | 20210302-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S. continuing work with Pickup w/plow and sander across Peninsula Road | 6 | C270-C277 | Peninsula Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878720210302-8L.O.A.1210 | Corbiere and Sons Contracting878720210302-8L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8787 | 20210302-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-03-02 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S. continuing work with Pickup w/plow and sander across Peninsula Road | 6 | C270-C277 | Peninsula Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting878720210302-8Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting878720210302-8Operator - Intermdiate - After Jan 1011770Inv#114 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8788 | 20210303-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated in to Mill road for snow removal - John S. working with pickup and sander truck | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878820210303-3Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting878820210303-3Dozer D6 or equal- After Jan 107920.36Inv#114 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8788 | 20210303-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated in to Mill road for snow removal - John S. working with pickup and sander truck | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878820210303-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting878820210303-3Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8788 | 20210303-3 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2.5 | Dynamic | 91.79 | 0 |  |  | 305.975 | 39.7767 | 345.7518 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated in to Mill road for snow removal - John S. working with pickup and sander truck | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878820210303-3Tractor Trailer - 60 Ton- After Jan 102.5305.975 | Corbiere and Sons Contracting878820210303-3Tractor Trailer - 60 Ton- After Jan 102.5305.975Inv#114 | [5 empty] | 1 | 305.975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8788 | 20210303-3 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 4 | HR | 0 | 0 |  |  | 200 | 26 | 226 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated in to Mill road for snow removal - John S. working with pickup and sander truck | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878820210303-3Pickup w/ plow4200 | Corbiere and Sons Contracting878820210303-3Pickup w/ plow4200Inv#114 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8788 | 20210303-3 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated in to Mill road for snow removal - John S. working with pickup and sander truck | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878820210303-3L.O.A.3630 | Corbiere and Sons Contracting878820210303-3L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8788 | 20210303-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated in to Mill road for snow removal - John S. working with pickup and sander truck | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878820210303-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting878820210303-3Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8788 | 20210303-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated in to Mill road for snow removal - John S. working with pickup and sander truck | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878820210303-3Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting878820210303-3Operator - Intermdiate - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8788 | 20210303-3 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer floated in to Mill road for snow removal - John S. working with pickup and sander truck | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878820210303-3Driver - AZ - After Jan 102.5175 | Corbiere and Sons Contracting878820210303-3Driver - AZ - After Jan 102.5175Inv#114 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8789 | 20210303-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Cooks in the morning - Terry ran it rest of day, made it from C100-KM6 | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878920210303-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting878920210303-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#114 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8789 | 20210303-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Cooks in the morning - Terry ran it rest of day, made it from C100-KM6 | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878920210303-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting878920210303-4Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8789 | 20210303-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Cooks in the morning - Terry ran it rest of day, made it from C100-KM6 | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878920210303-4L.O.A.1210 | Corbiere and Sons Contracting878920210303-4L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8789 | 20210303-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Cooks in the morning - Terry ran it rest of day, made it from C100-KM6 | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878920210303-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting878920210303-4Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8789 | 20210303-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Cooks in the morning - Terry ran it rest of day, made it from C100-KM6 | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting878920210303-4Driver - AZ - After Jan 102.5175 | Corbiere and Sons Contracting878920210303-4Driver - AZ - After Jan 102.5175Inv#114 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8790 | 20210303-5-R1 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 19 | Dynamic | 95.24 | 0 |  |  | 2412.62 | 313.6406 | 2726.2606 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader over to deadhorse, Len working on it for dayshift, gary ran it at night - Dustin working on Pickup w/plow and coordinating snowr removal activities | 6 | C203-C209 | Dead Horse Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879020210303-5-R1Grader - Cat 12 to 14 or equal- After Jan 10192412.62 | Corbiere and Sons Contracting879020210303-5-R1Grader - Cat 12 to 14 or equal- After Jan 10192412.62Inv#114 | [5 empty] | 1 | 2412.62 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8790 | 20210303-5-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader over to deadhorse, Len working on it for dayshift, gary ran it at night - Dustin working on Pickup w/plow and coordinating snowr removal activities | 6 | C203-C209 | Dead Horse Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879020210303-5-R1Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting879020210303-5-R1Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8790 | 20210303-5-R1 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader over to deadhorse, Len working on it for dayshift, gary ran it at night - Dustin working on Pickup w/plow and coordinating snowr removal activities | 6 | C203-C209 | Dead Horse Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879020210303-5-R1Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting879020210303-5-R1Tractor Trailer - 60 Ton- After Jan 103367.17Inv#114 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8790 | 20210303-5-R1 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader over to deadhorse, Len working on it for dayshift, gary ran it at night - Dustin working on Pickup w/plow and coordinating snowr removal activities | 6 | C203-C209 | Dead Horse Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879020210303-5-R1Pickup w/ plow11550 | Corbiere and Sons Contracting879020210303-5-R1Pickup w/ plow11550Inv#114 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8790 | 20210303-5-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader over to deadhorse, Len working on it for dayshift, gary ran it at night - Dustin working on Pickup w/plow and coordinating snowr removal activities | 6 | C203-C209 | Dead Horse Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879020210303-5-R1L.O.A.3630 | Corbiere and Sons Contracting879020210303-5-R1L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8790 | 20210303-5-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader over to deadhorse, Len working on it for dayshift, gary ran it at night - Dustin working on Pickup w/plow and coordinating snowr removal activities | 6 | C203-C209 | Dead Horse Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879020210303-5-R1Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting879020210303-5-R1Operator - Principle - After Jan 10332475Inv#114 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8790 | 20210303-5-R1 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader over to deadhorse, Len working on it for dayshift, gary ran it at night - Dustin working on Pickup w/plow and coordinating snowr removal activities | 6 | C203-C209 | Dead Horse Creek | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879020210303-5-R1Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting879020210303-5-R1Driver - AZ - After Jan 103210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8791 | 20210303-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on grader in Lake A overnight, fixing hills and refreezing roads | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879120210303-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting879120210303-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8791 | 20210303-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on grader in Lake A overnight, fixing hills and refreezing roads | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879120210303-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting879120210303-6Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8791 | 20210303-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on grader in Lake A overnight, fixing hills and refreezing roads | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879120210303-6L.O.A.1210 | Corbiere and Sons Contracting879120210303-6L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8791 | 20210303-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-03 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard continuing on grader in Lake A overnight, fixing hills and refreezing roads | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44272 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879120210303-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting879120210303-6Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8792 | 20210304-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 15 | Dynamic | 95.24 | 0 |  |  | 1904.7 | 247.611 | 2152.311 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to White sands to begin clearing - Len on day, Gary on night - Blade and Ben Flagging - Dustin coordinating all snow removal activities | 5 | C070-C075 | White Sand | 0 | 44266 |  | 37 | 44249 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879220210304-3Grader - Cat 12 to 14 or equal- After Jan 10151904.7 | Corbiere and Sons Contracting879220210304-3Grader - Cat 12 to 14 or equal- After Jan 10151904.7Inv#122 | [5 empty] | 1 | 1904.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8792 | 20210304-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to White sands to begin clearing - Len on day, Gary on night - Blade and Ben Flagging - Dustin coordinating all snow removal activities | 5 | C070-C075 | White Sand | 0 | 44266 |  | 37 | 44249 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879220210304-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting879220210304-3Light Truck - Pick up- After Jan 103731.25Inv#122 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8792 | 20210304-3 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to White sands to begin clearing - Len on day, Gary on night - Blade and Ben Flagging - Dustin coordinating all snow removal activities | 5 | C070-C075 | White Sand | 0 | 44266 |  | 37 | 44249 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879220210304-3Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting879220210304-3Tractor Trailer - 60 Ton- After Jan 106734.34Inv#122 | [5 empty] | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8792 | 20210304-3 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to White sands to begin clearing - Len on day, Gary on night - Blade and Ben Flagging - Dustin coordinating all snow removal activities | 5 | C070-C075 | White Sand | 0 | 44266 |  | 37 | 44249 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879220210304-3Pickup w/ plow11550 | Corbiere and Sons Contracting879220210304-3Pickup w/ plow11550Inv#122 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8792 | 20210304-3 | 53510511 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to White sands to begin clearing - Len on day, Gary on night - Blade and Ben Flagging - Dustin coordinating all snow removal activities | 5 | C070-C075 | White Sand | 0 | 44266 |  | 37 | 44249 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879220210304-3L.O.A.61260 | Corbiere and Sons Contracting879220210304-3L.O.A.61260Inv#122 | [5 empty] | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8792 | 20210304-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30 | HR |  |  | 75 | 0 | 2250 | 292.5 | 2542.5 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to White sands to begin clearing - Len on day, Gary on night - Blade and Ben Flagging - Dustin coordinating all snow removal activities | 5 | C070-C075 | White Sand | 0 | 44266 |  | 37 | 44249 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879220210304-3Operator - Principle - After Jan 10302250 | Corbiere and Sons Contracting879220210304-3Operator - Principle - After Jan 10302250Inv#122 | [5 empty] | 1 | 2250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8792 | 20210304-3 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to White sands to begin clearing - Len on day, Gary on night - Blade and Ben Flagging - Dustin coordinating all snow removal activities | 5 | C070-C075 | White Sand | 0 | 44266 |  | 37 | 44249 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879220210304-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting879220210304-3Driver - AZ - After Jan 103210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8792 | 20210304-3 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to White sands to begin clearing - Len on day, Gary on night - Blade and Ben Flagging - Dustin coordinating all snow removal activities | 5 | C070-C075 | White Sand | 0 | 44266 |  | 37 | 44249 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879220210304-3Labourer - General - After Jan 105300 | Corbiere and Sons Contracting879220210304-3Labourer - General - After Jan 105300Inv#122 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8793 | 20210304-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rick continued on DZ in Mill Road clearing snow - John S came in to plow turn around and sand | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879320210304-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting879320210304-4Dozer D6 or equal- After Jan 10101314.8Inv#122 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8793 | 20210304-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rick continued on DZ in Mill Road clearing snow - John S came in to plow turn around and sand | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879320210304-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting879320210304-4Light Truck - Pick up- After Jan 101243.75Inv#122 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8793 | 20210304-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rick continued on DZ in Mill Road clearing snow - John S came in to plow turn around and sand | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879320210304-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting879320210304-4Pickup w/ plow and sander4320Inv#122 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8793 | 20210304-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rick continued on DZ in Mill Road clearing snow - John S came in to plow turn around and sand | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879320210304-4L.O.A.2420 | Corbiere and Sons Contracting879320210304-4L.O.A.2420Inv#122 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8793 | 20210304-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rick continued on DZ in Mill Road clearing snow - John S came in to plow turn around and sand | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879320210304-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting879320210304-4Operator - Principle - After Jan 1011825Inv#122 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8793 | 20210304-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rick continued on DZ in Mill Road clearing snow - John S came in to plow turn around and sand | 5 | C117-C124 | Mill Road | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879320210304-4Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting879320210304-4Operator - Intermdiate - After Jan 104280Inv#122 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8794 | 20210304-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved rager from Little Pic to Cooks - 2 Flaggers - Collin ran DZ for rest of day in Cooks - Terry ran grader in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879420210304-5Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting879420210304-5Dozer D6 or equal- After Jan 103394.44Inv#122 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8794 | 20210304-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved rager from Little Pic to Cooks - 2 Flaggers - Collin ran DZ for rest of day in Cooks - Terry ran grader in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879420210304-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting879420210304-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#122 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8794 | 20210304-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved rager from Little Pic to Cooks - 2 Flaggers - Collin ran DZ for rest of day in Cooks - Terry ran grader in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879420210304-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting879420210304-5Light Truck - Pick up- After Jan 102487.5Inv#122 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8794 | 20210304-5 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved rager from Little Pic to Cooks - 2 Flaggers - Collin ran DZ for rest of day in Cooks - Terry ran grader in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879420210304-5Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting879420210304-5Tractor Trailer - 60 Ton- After Jan 103367.17Inv#122 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8794 | 20210304-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved rager from Little Pic to Cooks - 2 Flaggers - Collin ran DZ for rest of day in Cooks - Terry ran grader in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879420210304-5L.O.A.2420 | Corbiere and Sons Contracting879420210304-5L.O.A.2420Inv#122 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8794 | 20210304-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved rager from Little Pic to Cooks - 2 Flaggers - Collin ran DZ for rest of day in Cooks - Terry ran grader in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879420210304-5Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting879420210304-5Operator - Principle - After Jan 10171275Inv#122 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8794 | 20210304-5 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved rager from Little Pic to Cooks - 2 Flaggers - Collin ran DZ for rest of day in Cooks - Terry ran grader in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879420210304-5Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting879420210304-5Driver - AZ - After Jan 103210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8794 | 20210304-5 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved rager from Little Pic to Cooks - 2 Flaggers - Collin ran DZ for rest of day in Cooks - Terry ran grader in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting879420210304-5Labourer - General - After Jan 105300 | Corbiere and Sons Contracting879420210304-5Labourer - General - After Jan 105300Inv#122 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8795 | 20210304-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard worked across Lake A fixing hills and regrading hills | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879520210304-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting879520210304-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#122 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8795 | 20210304-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard worked across Lake A fixing hills and regrading hills | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879520210304-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting879520210304-6Light Truck - Pick up- After Jan 101243.75Inv#122 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8795 | 20210304-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard worked across Lake A fixing hills and regrading hills | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879520210304-6L.O.A.1210 | Corbiere and Sons Contracting879520210304-6L.O.A.1210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8795 | 20210304-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard worked across Lake A fixing hills and regrading hills | 6 | C130-C151 | Lake A | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879520210304-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting879520210304-6Operator - Principle - After Jan 1011825Inv#122 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8796 | 20210304-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across deadhorse in the morning | 6 | C203-C209 | Dead Horse Creek | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879620210304-7Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting879620210304-7Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#122 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8796 | 20210304-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across deadhorse in the morning | 6 | C203-C209 | Dead Horse Creek | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879620210304-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting879620210304-7Operator - Principle - After Jan 103225Inv#122 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8797 | 20210304-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 7 |  | 0 | 0 |  |  | 560 | 72.8 | 632.8 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S. working on snowdrifts in Peninsula | 6 | C270 | Peninsula | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879720210304-8Pickup w/ plow and sander7560 | Corbiere and Sons Contracting879720210304-8Pickup w/ plow and sander7560Inv#122 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8797 | 20210304-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-03-04 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | John S. working on snowdrifts in Peninsula | 6 | C270 | Peninsula | 0 | 44266 |  | 37 | 44277 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting879720210304-8Operator - Intermdiate - After Jan 107490 | Corbiere and Sons Contracting879720210304-8Operator - Intermdiate - After Jan 107490Inv#122 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8748 | 20210305-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader from C076-C092 - Collin worked on DZ from C099-C110 - Dustin Corbiere coorindating all snow removal activities and worked on Plow Truck | 5 | C076-C116 | Cook Lake | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874820210305-3Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting874820210305-3Dozer D6 or equal- After Jan 10101314.8Inv#122 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8748 | 20210305-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader from C076-C092 - Collin worked on DZ from C099-C110 - Dustin Corbiere coorindating all snow removal activities and worked on Plow Truck | 5 | C076-C116 | Cook Lake | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874820210305-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting874820210305-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv#122 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8748 | 20210305-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader from C076-C092 - Collin worked on DZ from C099-C110 - Dustin Corbiere coorindating all snow removal activities and worked on Plow Truck | 5 | C076-C116 | Cook Lake | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874820210305-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting874820210305-3Light Truck - Pick up- After Jan 102487.5Inv#122 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8748 | 20210305-3 | 53510511 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader from C076-C092 - Collin worked on DZ from C099-C110 - Dustin Corbiere coorindating all snow removal activities and worked on Plow Truck | 5 | C076-C116 | Cook Lake | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874820210305-3Pickup w/ plow11550 | Corbiere and Sons Contracting874820210305-3Pickup w/ plow11550Inv#122 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8748 | 20210305-3 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader from C076-C092 - Collin worked on DZ from C099-C110 - Dustin Corbiere coorindating all snow removal activities and worked on Plow Truck | 5 | C076-C116 | Cook Lake | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874820210305-3L.O.A.3630 | Corbiere and Sons Contracting874820210305-3L.O.A.3630Inv#122 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8748 | 20210305-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34 | HR |  |  | 75 | 0 | 2550 | 331.5 | 2881.5 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len worked on Grader from C076-C092 - Collin worked on DZ from C099-C110 - Dustin Corbiere coorindating all snow removal activities and worked on Plow Truck | 5 | C076-C116 | Cook Lake | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874820210305-3Operator - Principle - After Jan 10342550 | Corbiere and Sons Contracting874820210305-3Operator - Principle - After Jan 10342550Inv#122 | [5 empty] | 1 | 2550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8749 | 20210305-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Whitesands and operator worked at this location for rest of day | 5 | C070-C075 | White Sand | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874920210305-4Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting874920210305-4Dozer D6 or equal- After Jan 1081051.84Inv#122 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8749 | 20210305-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Whitesands and operator worked at this location for rest of day | 5 | C070-C075 | White Sand | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874920210305-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting874920210305-4Light Truck - Pick up- After Jan 101243.75Inv#122 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8749 | 20210305-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Whitesands and operator worked at this location for rest of day | 5 | C070-C075 | White Sand | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874920210305-4Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting874920210305-4Tractor Trailer - 60 Ton- After Jan 103367.17Inv#122 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8749 | 20210305-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Whitesands and operator worked at this location for rest of day | 5 | C070-C075 | White Sand | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874920210305-4L.O.A.2420 | Corbiere and Sons Contracting874920210305-4L.O.A.2420Inv#122 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8749 | 20210305-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Whitesands and operator worked at this location for rest of day | 5 | C070-C075 | White Sand | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874920210305-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting874920210305-4Operator - Principle - After Jan 1011825Inv#122 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8749 | 20210305-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Whitesands and operator worked at this location for rest of day | 5 | C070-C075 | White Sand | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting874920210305-4Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting874920210305-4Driver - AZ - After Jan 103210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8750 | 20210305-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2.5 | Dynamic | 98.61 | 0 |  |  | 328.7 | 42.731 | 371.431 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rick Kratky spent 2.5 hours at Mills before being moved over to Middleton - Ticket says Whitesands but should read Mill | 5 | C117-C124 | Mill Road | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting875020210305-5Dozer D6 or equal- After Jan 102.5328.7 | Corbiere and Sons Contracting875020210305-5Dozer D6 or equal- After Jan 102.5328.7Inv#122 | [5 empty] | 1 | 328.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8750 | 20210305-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rick Kratky spent 2.5 hours at Mills before being moved over to Middleton - Ticket says Whitesands but should read Mill | 5 | C117-C124 | Mill Road | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting875020210305-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting875020210305-5Light Truck - Pick up- After Jan 101243.75Inv#122 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8750 | 20210305-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rick Kratky spent 2.5 hours at Mills before being moved over to Middleton - Ticket says Whitesands but should read Mill | 5 | C117-C124 | Mill Road | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting875020210305-5L.O.A.1210 | Corbiere and Sons Contracting875020210305-5L.O.A.1210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8750 | 20210305-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2.5 | HR |  |  | 75 | 0 | 187.5 | 24.375 | 211.875 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rick Kratky spent 2.5 hours at Mills before being moved over to Middleton - Ticket says Whitesands but should read Mill | 5 | C117-C124 | Mill Road | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting875020210305-5Operator - Principle - After Jan 102.5187.5 | Corbiere and Sons Contracting875020210305-5Operator - Principle - After Jan 102.5187.5Inv#122 | [5 empty] | 1 | 187.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8751 | 20210305-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader continuing on access roads in Lake A throughout the night | 6 | C130-C149 | Lake A | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875120210305-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting875120210305-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#122 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8751 | 20210305-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader continuing on access roads in Lake A throughout the night | 6 | C130-C149 | Lake A | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875120210305-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting875120210305-6Light Truck - Pick up- After Jan 101243.75Inv#122 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8751 | 20210305-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader continuing on access roads in Lake A throughout the night | 6 | C130-C149 | Lake A | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875120210305-6L.O.A.1210 | Corbiere and Sons Contracting875120210305-6L.O.A.1210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8751 | 20210305-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader continuing on access roads in Lake A throughout the night | 6 | C130-C149 | Lake A | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875120210305-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting875120210305-6Operator - Principle - After Jan 1011825Inv#122 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8752 | 20210305-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 98.61 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Middleton and OP cleared snow rest of day - 2 flaggers needed | 6 | C210-C214 | Middleton | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875220210305-7Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting875220210305-7Dozer D6 or equal- After Jan 105.5723.14Inv#122 | [5 empty] | 1 | 723.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8752 | 20210305-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Middleton and OP cleared snow rest of day - 2 flaggers needed | 6 | C210-C214 | Middleton | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875220210305-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting875220210305-7Light Truck - Pick up- After Jan 101243.75Inv#122 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8752 | 20210305-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Middleton and OP cleared snow rest of day - 2 flaggers needed | 6 | C210-C214 | Middleton | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875220210305-7Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting875220210305-7Tractor Trailer - 60 Ton- After Jan 104489.56Inv#122 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8752 | 20210305-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Middleton and OP cleared snow rest of day - 2 flaggers needed | 6 | C210-C214 | Middleton | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875220210305-7L.O.A.2420 | Corbiere and Sons Contracting875220210305-7L.O.A.2420Inv#122 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8752 | 20210305-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Middleton and OP cleared snow rest of day - 2 flaggers needed | 6 | C210-C214 | Middleton | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875220210305-7Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting875220210305-7Operator - Principle - After Jan 108.5637.5Inv#122 | [5 empty] | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8752 | 20210305-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Middleton and OP cleared snow rest of day - 2 flaggers needed | 6 | C210-C214 | Middleton | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875220210305-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting875220210305-7Driver - AZ - After Jan 104280Inv#122 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8752 | 20210305-7 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ into Middleton and OP cleared snow rest of day - 2 flaggers needed | 6 | C210-C214 | Middleton | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875220210305-7Labourer - General - After Jan 108480 | Corbiere and Sons Contracting875220210305-7Labourer - General - After Jan 108480Inv#122 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8753 | 20210305-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across various areas in WF6 | 6 | C258-C269 | Hare Lake Road | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875320210305-8Pickup w/ plow and sander11880 | Corbiere and Sons Contracting875320210305-8Pickup w/ plow and sander11880Inv#122 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8753 | 20210305-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across various areas in WF6 | 6 | C258-C269 | Hare Lake Road | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875320210305-8L.O.A.1210 | Corbiere and Sons Contracting875320210305-8L.O.A.1210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8753 | 20210305-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-03-05 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across various areas in WF6 | 6 | C258-C269 | Hare Lake Road | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875320210305-8Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting875320210305-8Operator - Intermdiate - After Jan 1011770Inv#122 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8757 | 20210306-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing snow in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting875720210306-4Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting875720210306-4Dozer D6 or equal- After Jan 105657.4Inv#122 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8757 | 20210306-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing snow in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting875720210306-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting875720210306-4Light Truck - Pick up- After Jan 101243.75Inv#122 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8757 | 20210306-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing snow in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting875720210306-4L.O.A.1210 | Corbiere and Sons Contracting875720210306-4L.O.A.1210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8757 | 20210306-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing snow in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting875720210306-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting875720210306-4Operator - Principle - After Jan 105375Inv#122 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8758 | 20210306-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3.5 | Dynamic | 98.61 | 0 |  |  | 460.18 | 59.8234 | 520.0034 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing to tower C075 with Dozer | 5 | C070-C075 | White Sand | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting875820210306-5Dozer D6 or equal- After Jan 103.5460.18 | Corbiere and Sons Contracting875820210306-5Dozer D6 or equal- After Jan 103.5460.18Inv#122 | [5 empty] | 1 | 460.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8758 | 20210306-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing to tower C075 with Dozer | 5 | C070-C075 | White Sand | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting875820210306-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting875820210306-5Operator - Principle - After Jan 105375Inv#122 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8759 | 20210306-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing off last 2 towers in Middleton with DZ - | 6 | C210-C214 | Middleton | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875920210306-6Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting875920210306-6Dozer D6 or equal- After Jan 104525.92Inv#122 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8759 | 20210306-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing off last 2 towers in Middleton with DZ - | 6 | C210-C214 | Middleton | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting875920210306-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting875920210306-6Operator - Principle - After Jan 104300Inv#122 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8760 | 20210306-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from White Sands to Prairie River Road - Richard Pine spent half night there - Dustin Coordinated all snow removal activities and working with plow truck | 6 | C171-C185 | Prairie River | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting876020210306-7Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting876020210306-7Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#122 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8760 | 20210306-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from White Sands to Prairie River Road - Richard Pine spent half night there - Dustin Coordinated all snow removal activities and working with plow truck | 6 | C171-C185 | Prairie River | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting876020210306-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting876020210306-7Light Truck - Pick up- After Jan 101243.75Inv#122 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8760 | 20210306-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from White Sands to Prairie River Road - Richard Pine spent half night there - Dustin Coordinated all snow removal activities and working with plow truck | 6 | C171-C185 | Prairie River | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting876020210306-7Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting876020210306-7Tractor Trailer - 60 Ton- After Jan 104489.56Inv#122 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8760 | 20210306-7 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 11 | HR | 0 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from White Sands to Prairie River Road - Richard Pine spent half night there - Dustin Coordinated all snow removal activities and working with plow truck | 6 | C171-C185 | Prairie River | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting876020210306-7Pickup w/ plow11550 | Corbiere and Sons Contracting876020210306-7Pickup w/ plow11550Inv#122 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8760 | 20210306-7 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from White Sands to Prairie River Road - Richard Pine spent half night there - Dustin Coordinated all snow removal activities and working with plow truck | 6 | C171-C185 | Prairie River | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting876020210306-7L.O.A.3630 | Corbiere and Sons Contracting876020210306-7L.O.A.3630Inv#122 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8760 | 20210306-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16.5 | HR |  |  | 75 | 0 | 1237.5 | 160.875 | 1398.375 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from White Sands to Prairie River Road - Richard Pine spent half night there - Dustin Coordinated all snow removal activities and working with plow truck | 6 | C171-C185 | Prairie River | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting876020210306-7Operator - Principle - After Jan 1016.51237.5 | Corbiere and Sons Contracting876020210306-7Operator - Principle - After Jan 1016.51237.5Inv#122 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8760 | 20210306-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader from White Sands to Prairie River Road - Richard Pine spent half night there - Dustin Coordinated all snow removal activities and working with plow truck | 6 | C171-C185 | Prairie River | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting876020210306-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting876020210306-7Driver - AZ - After Jan 104280Inv#122 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8761 | 20210306-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine running grader in Lake A for part of night | 6 | C130-C149 | Lake A | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting876120210306-8Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting876120210306-8Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#122 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8761 | 20210306-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2021-03-06 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard Pine running grader in Lake A for part of night | 6 | C130-C149 | Lake A | 0 | 44263 |  | 36 | 44263 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting876120210306-8Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting876120210306-8Operator - Principle - After Jan 105.5412.5Inv#122 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8847 | 20210307-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim ran dozer in Cooks lake road for 7 hours and then dozer for rest of day - Doug moved dozer back to cooks - 2 flaggers needed - Dustin coordinating all snow removal activities | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884720210307-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting884720210307-3Dozer D6 or equal- After Jan 103394.44Inv#114 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8847 | 20210307-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim ran dozer in Cooks lake road for 7 hours and then dozer for rest of day - Doug moved dozer back to cooks - 2 flaggers needed - Dustin coordinating all snow removal activities | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884720210307-3Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting884720210307-3Grader - Cat 12 to 14 or equal- After Jan 107888.86Inv#114 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8847 | 20210307-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim ran dozer in Cooks lake road for 7 hours and then dozer for rest of day - Doug moved dozer back to cooks - 2 flaggers needed - Dustin coordinating all snow removal activities | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884720210307-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting884720210307-3Light Truck - Pick up- After Jan 102487.5Inv#114 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8847 | 20210307-3 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim ran dozer in Cooks lake road for 7 hours and then dozer for rest of day - Doug moved dozer back to cooks - 2 flaggers needed - Dustin coordinating all snow removal activities | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884720210307-3Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting884720210307-3Tractor Trailer - 60 Ton- After Jan 104489.56Inv#114 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8847 | 20210307-3 | 53510511 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim ran dozer in Cooks lake road for 7 hours and then dozer for rest of day - Doug moved dozer back to cooks - 2 flaggers needed - Dustin coordinating all snow removal activities | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884720210307-3L.O.A.4840 | Corbiere and Sons Contracting884720210307-3L.O.A.4840Inv#114 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8847 | 20210307-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 19 | HR |  |  | 75 | 0 | 1425 | 185.25 | 1610.25 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim ran dozer in Cooks lake road for 7 hours and then dozer for rest of day - Doug moved dozer back to cooks - 2 flaggers needed - Dustin coordinating all snow removal activities | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884720210307-3Operator - Principle - After Jan 10191425 | Corbiere and Sons Contracting884720210307-3Operator - Principle - After Jan 10191425Inv#114 | [5 empty] | 1 | 1425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8847 | 20210307-3 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim ran dozer in Cooks lake road for 7 hours and then dozer for rest of day - Doug moved dozer back to cooks - 2 flaggers needed - Dustin coordinating all snow removal activities | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884720210307-3Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting884720210307-3Driver - AZ - After Jan 104280Inv#114 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8847 | 20210307-3 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim ran dozer in Cooks lake road for 7 hours and then dozer for rest of day - Doug moved dozer back to cooks - 2 flaggers needed - Dustin coordinating all snow removal activities | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884720210307-3Labourer - General - After Jan 106360 | Corbiere and Sons Contracting884720210307-3Labourer - General - After Jan 106360Inv#114 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8848 | 20210307-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow with DZ, sanding hills from C070 to C071 | 5 | C070-C075 | White Sand | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884820210307-4Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting884820210307-4Dozer D6 or equal- After Jan 1091183.32Inv#114 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8848 | 20210307-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow with DZ, sanding hills from C070 to C071 | 5 | C070-C075 | White Sand | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884820210307-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting884820210307-4Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8848 | 20210307-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow with DZ, sanding hills from C070 to C071 | 5 | C070-C075 | White Sand | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884820210307-4Pickup w/ plow and sander6480 | Corbiere and Sons Contracting884820210307-4Pickup w/ plow and sander6480Inv#114 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8848 | 20210307-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow with DZ, sanding hills from C070 to C071 | 5 | C070-C075 | White Sand | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884820210307-4L.O.A.2420 | Corbiere and Sons Contracting884820210307-4L.O.A.2420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8848 | 20210307-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow with DZ, sanding hills from C070 to C071 | 5 | C070-C075 | White Sand | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884820210307-4Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting884820210307-4Operator - Principle - After Jan 1010750Inv#114 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8848 | 20210307-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow with DZ, sanding hills from C070 to C071 | 5 | C070-C075 | White Sand | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting884820210307-4Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting884820210307-4Operator - Intermdiate - After Jan 106420Inv#114 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8849 | 20210307-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader continuing on Lake A for the night fixing hills | 6 | C130-C151 | Lake A | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting884920210307-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting884920210307-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8849 | 20210307-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader continuing on Lake A for the night fixing hills | 6 | C130-C151 | Lake A | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting884920210307-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting884920210307-5Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8849 | 20210307-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader continuing on Lake A for the night fixing hills | 6 | C130-C151 | Lake A | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting884920210307-5L.O.A.1210 | Corbiere and Sons Contracting884920210307-5L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8849 | 20210307-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-07 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader continuing on Lake A for the night fixing hills | 6 | C130-C151 | Lake A | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting884920210307-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting884920210307-5Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8800 | 20210308-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-03-08 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim and Dz continue snow clearing in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 36 | 44268 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting880020210308-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting880020210308-3Dozer D6 or equal- After Jan 10111446.28Inv#122 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8800 | 20210308-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-08 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim and Dz continue snow clearing in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 36 | 44268 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting880020210308-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting880020210308-3Light Truck - Pick up- After Jan 101243.75Inv#122 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8800 | 20210308-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-08 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim and Dz continue snow clearing in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 36 | 44268 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting880020210308-3L.O.A.1210 | Corbiere and Sons Contracting880020210308-3L.O.A.1210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8800 | 20210308-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-03-08 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim and Dz continue snow clearing in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44266 |  | 36 | 44268 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting880020210308-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting880020210308-3Operator - Principle - After Jan 1012900Inv#122 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8815 | 20210309-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-03-09 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening | 5 | C076-C116 | Cook Lake | 0 | 44271 |  | 36 | 44271 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting881520210309-3Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting881520210309-3Dozer D6 or equal- After Jan 10101314.8Inv#114 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8815 | 20210309-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-09 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening | 5 | C076-C116 | Cook Lake | 0 | 44271 |  | 36 | 44271 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting881520210309-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting881520210309-3Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8815 | 20210309-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-09 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening | 5 | C076-C116 | Cook Lake | 0 | 44271 |  | 36 | 44271 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting881520210309-3L.O.A.1210 | Corbiere and Sons Contracting881520210309-3L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8815 | 20210309-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-09 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening | 5 | C076-C116 | Cook Lake | 0 | 44271 |  | 36 | 44271 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting881520210309-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting881520210309-3Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8816 | 20210309-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-09 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on Standby | 6 | C130-C277 | Standby | 0 | 44271 |  | 36 | 44273 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting881620210309-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting881620210309-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8816 | 20210309-4 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-03-09 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on Standby | 6 | C130-C277 | Standby | 0 | 44271 |  | 36 | 44273 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting881620210309-4Pickup w/ plow5250 | Corbiere and Sons Contracting881620210309-4Pickup w/ plow5250Inv#114 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8816 | 20210309-4 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-03-09 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on Standby | 6 | C130-C277 | Standby | 0 | 44271 |  | 36 | 44273 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting881620210309-4L.O.A.3630 | Corbiere and Sons Contracting881620210309-4L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8816 | 20210309-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-03-09 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on Standby | 6 | C130-C277 | Standby | 0 | 44271 |  | 36 | 44273 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting881620210309-4Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting881620210309-4Operator - Principle - After Jan 1010750Inv#114 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8816 | 20210309-4 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-03-09 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on Standby | 6 | C130-C277 | Standby | 0 | 44271 |  | 36 | 44273 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting881620210309-4Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting881620210309-4Operator - Intermdiate - After Jan 105350Inv#114 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8852 | 20210310-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-03-10 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting885220210310-3Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting885220210310-3Dozer D6 or equal- After Jan 10101314.8Inv#114 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8852 | 20210310-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-10 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting885220210310-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting885220210310-3Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8852 | 20210310-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-10 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting885220210310-3L.O.A.1210 | Corbiere and Sons Contracting885220210310-3L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8852 | 20210310-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-10 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting885220210310-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting885220210310-3Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8853 | 20210310-4 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-03-10 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on SB - Rick Kratky cleared snow from C214 with DZ | 6 | C130-C277 | Middleton | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885320210310-4Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting885320210310-4Dozer D6 or equal- After Jan 1081051.84Inv#114 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8853 | 20210310-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-10 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on SB - Rick Kratky cleared snow from C214 with DZ | 6 | C130-C277 | Middleton | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885320210310-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting885320210310-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8853 | 20210310-4 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-03-10 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on SB - Rick Kratky cleared snow from C214 with DZ | 6 | C130-C277 | Middleton | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885320210310-4Pickup w/ plow5250 | Corbiere and Sons Contracting885320210310-4Pickup w/ plow5250Inv#114 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8853 | 20210310-4 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-03-10 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on SB - Rick Kratky cleared snow from C214 with DZ | 6 | C130-C277 | Middleton | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885320210310-4L.O.A.4840 | Corbiere and Sons Contracting885320210310-4L.O.A.4840Inv#114 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8853 | 20210310-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 19 | HR |  |  | 75 | 0 | 1425 | 185.25 | 1610.25 | 2021-03-10 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on SB - Rick Kratky cleared snow from C214 with DZ | 6 | C130-C277 | Middleton | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885320210310-4Operator - Principle - After Jan 10191425 | Corbiere and Sons Contracting885320210310-4Operator - Principle - After Jan 10191425Inv#114 | [5 empty] | 1 | 1425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8853 | 20210310-4 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-03-10 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal Equipment on SB - Rick Kratky cleared snow from C214 with DZ | 6 | C130-C277 | Middleton | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885320210310-4Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting885320210310-4Operator - Intermdiate - After Jan 105350Inv#114 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8857 | 20210311-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-03-11 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening and cleaning up fingers to towers | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting885720210311-3Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting885720210311-3Dozer D6 or equal- After Jan 10101314.8Inv#114 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8857 | 20210311-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-11 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening and cleaning up fingers to towers | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting885720210311-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting885720210311-3Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8857 | 20210311-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-11 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening and cleaning up fingers to towers | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting885720210311-3L.O.A.1210 | Corbiere and Sons Contracting885720210311-3L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8857 | 20210311-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-11 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim working on DZ across Cooks Lake Road with continued road widening and cleaning up fingers to towers | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting885720210311-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting885720210311-3Operator - Principle - After Jan 1011825Inv#114 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8858 | 20210311-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-11 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie worked in Prairie River road for 5 hours on Grader - Other Grader + Plow truck on SB | 6 | C130-C277 | Prairie River | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885820210311-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting885820210311-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8858 | 20210311-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-11 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie worked in Prairie River road for 5 hours on Grader - Other Grader + Plow truck on SB | 6 | C130-C277 | Prairie River | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885820210311-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting885820210311-4Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8858 | 20210311-4 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-03-11 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie worked in Prairie River road for 5 hours on Grader - Other Grader + Plow truck on SB | 6 | C130-C277 | Prairie River | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885820210311-4Pickup w/ plow5250 | Corbiere and Sons Contracting885820210311-4Pickup w/ plow5250Inv#114 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8858 | 20210311-4 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-03-11 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie worked in Prairie River road for 5 hours on Grader - Other Grader + Plow truck on SB | 6 | C130-C277 | Prairie River | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885820210311-4L.O.A.3630 | Corbiere and Sons Contracting885820210311-4L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8858 | 20210311-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-03-11 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie worked in Prairie River road for 5 hours on Grader - Other Grader + Plow truck on SB | 6 | C130-C277 | Prairie River | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885820210311-4Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting885820210311-4Operator - Principle - After Jan 1010750Inv#114 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8858 | 20210311-4 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-03-11 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jodie worked in Prairie River road for 5 hours on Grader - Other Grader + Plow truck on SB | 6 | C130-C277 | Prairie River | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting885820210311-4Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting885820210311-4Operator - Intermdiate - After Jan 105350Inv#114 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8863 | 20210312-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-03-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim went back to finish towers C091 and C092 | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting886320210312-3Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting886320210312-3Dozer D6 or equal- After Jan 107920.36Inv#114 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8863 | 20210312-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim went back to finish towers C091 and C092 | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting886320210312-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting886320210312-3Light Truck - Pick up- After Jan 101243.75Inv#114 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8863 | 20210312-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim went back to finish towers C091 and C092 | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting886320210312-3L.O.A.1210 | Corbiere and Sons Contracting886320210312-3L.O.A.1210Inv#114 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8863 | 20210312-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-03-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim went back to finish towers C091 and C092 | 5 | C076-C116 | Cook Lake | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting886320210312-3Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting886320210312-3Operator - Principle - After Jan 108600Inv#114 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8864 | 20210312-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow on SB | 6 | C130-C277 | WF6 | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting886420210312-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting886420210312-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#114 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8864 | 20210312-4 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-03-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow on SB | 6 | C130-C277 | WF6 | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting886420210312-4Pickup w/ plow5250 | Corbiere and Sons Contracting886420210312-4Pickup w/ plow5250Inv#114 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8864 | 20210312-4 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-03-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow on SB | 6 | C130-C277 | WF6 | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting886420210312-4L.O.A.3630 | Corbiere and Sons Contracting886420210312-4L.O.A.3630Inv#114 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8864 | 20210312-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-03-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow on SB | 6 | C130-C277 | WF6 | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting886420210312-4Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting886420210312-4Operator - Principle - After Jan 1010750Inv#114 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8864 | 20210312-4 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-03-12 | 0 | Inv#114 | 44273 | 146 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow on SB | 6 | C130-C277 | WF6 | 0 | 44272 |  | 36 | 44272 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting886420210312-4Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting886420210312-4Operator - Intermdiate - After Jan 105350Inv#114 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8939 | 20210313-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-03-13 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow and SB | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting893920210313-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting893920210313-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#122 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8939 | 20210313-3 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-03-13 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow and SB | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting893920210313-3Pickup w/ plow5250 | Corbiere and Sons Contracting893920210313-3Pickup w/ plow5250Inv#122 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8939 | 20210313-3 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-03-13 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow and SB | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting893920210313-3L.O.A.3630 | Corbiere and Sons Contracting893920210313-3L.O.A.3630Inv#122 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8939 | 20210313-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-03-13 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow and SB | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting893920210313-3Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting893920210313-3Operator - Principle - After Jan 1010750Inv#122 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8939 | 20210313-3 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-03-13 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow and SB | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting893920210313-3Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting893920210313-3Operator - Intermdiate - After Jan 105350Inv#122 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8942 | 20210314-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 |  | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow and SB | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting894220210314-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting894220210314-3Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#122 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8942 | 20210314-3 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 5 | HR | 0 | 0 |  |  | 250 | 32.5 | 282.5 |  | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow and SB | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting894220210314-3Pickup w/ plow5250 | Corbiere and Sons Contracting894220210314-3Pickup w/ plow5250Inv#122 | [5 empty] | 1 | 250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8942 | 20210314-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 |  | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow and SB | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting894220210314-3L.O.A.2420 | Corbiere and Sons Contracting894220210314-3L.O.A.2420Inv#122 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8942 | 20210314-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 |  | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow and SB | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting894220210314-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting894220210314-3Operator - Principle - After Jan 105375Inv#122 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8942 | 20210314-3 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 |  | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and Pickup w/plow and SB | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting894220210314-3Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting894220210314-3Operator - Intermdiate - After Jan 105350Inv#122 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8943 | 20210314-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2021-03-14 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader moved to Antler and worked there for day - Demob of plow truck with sander | 5 | C051-C069 | Antler Lake | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting894320210314-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting894320210314-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#122 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8943 | 20210314-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-03-14 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader moved to Antler and worked there for day - Demob of plow truck with sander | 5 | C051-C069 | Antler Lake | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting894320210314-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting894320210314-4Light Truck - Pick up- After Jan 101243.75Inv#122 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8943 | 20210314-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-03-14 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader moved to Antler and worked there for day - Demob of plow truck with sander | 5 | C051-C069 | Antler Lake | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting894320210314-4Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting894320210314-4Tractor Trailer - 60 Ton- After Jan 103367.17Inv#122 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8943 | 20210314-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-03-14 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader moved to Antler and worked there for day - Demob of plow truck with sander | 5 | C051-C069 | Antler Lake | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting894320210314-4Pickup w/ plow and sander6480 | Corbiere and Sons Contracting894320210314-4Pickup w/ plow and sander6480Inv#122 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8943 | 20210314-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-03-14 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader moved to Antler and worked there for day - Demob of plow truck with sander | 5 | C051-C069 | Antler Lake | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting894320210314-4L.O.A.2420 | Corbiere and Sons Contracting894320210314-4L.O.A.2420Inv#122 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8943 | 20210314-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-03-14 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader moved to Antler and worked there for day - Demob of plow truck with sander | 5 | C051-C069 | Antler Lake | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting894320210314-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting894320210314-4Operator - Principle - After Jan 1011825Inv#122 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8943 | 20210314-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-03-14 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader moved to Antler and worked there for day - Demob of plow truck with sander | 5 | C051-C069 | Antler Lake | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting894320210314-4Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting894320210314-4Operator - Intermdiate - After Jan 106420Inv#122 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8943 | 20210314-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-03-14 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader moved to Antler and worked there for day - Demob of plow truck with sander | 5 | C051-C069 | Antler Lake | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting894320210314-4Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting894320210314-4Driver - AZ - After Jan 103210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8947 | 20210315-3 | 53510611 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2021-03-15 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demobbed of 2 plow attachments and 1 sander box back to Dorion Yard | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting894720210315-3Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting894720210315-3Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#122 | [5 empty] | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8947 | 20210315-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-15 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demobbed of 2 plow attachments and 1 sander box back to Dorion Yard | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting894720210315-3L.O.A.1210 | Corbiere and Sons Contracting894720210315-3L.O.A.1210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8947 | 20210315-3 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-03-15 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demobbed of 2 plow attachments and 1 sander box back to Dorion Yard | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting894720210315-3Labourer - General - After Jan 108480 | Corbiere and Sons Contracting894720210315-3Labourer - General - After Jan 108480Inv#122 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8948 | 20210315-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-03-15 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float demobbed Grader back to Thunder Bay | 5 | C051-C069 | Antler Lake | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting894820210315-4Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting894820210315-4Tractor Trailer - 60 Ton- After Jan 108979.12Inv#122 | [5 empty] | 1 | 979.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8948 | 20210315-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-03-15 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jeff and float demobbed Grader back to Thunder Bay | 5 | C051-C069 | Antler Lake | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting894820210315-4Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting894820210315-4Driver - AZ - After Jan 108560Inv#122 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8952 | 20210316-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-03-16 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of a grader from Prairie River back to Terrace Bay laydown | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting895220210316-3Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting895220210316-3Tractor Trailer - 60 Ton- After Jan 103367.17Inv#122 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8952 | 20210316-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-03-16 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of a grader from Prairie River back to Terrace Bay laydown | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting895220210316-3L.O.A.1210 | Corbiere and Sons Contracting895220210316-3L.O.A.1210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 8952 | 20210316-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-03-16 | 0 | Inv#122 | 44273 | 149 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of a grader from Prairie River back to Terrace Bay laydown | 6 | C130-C277 | WF6 | 0 | 44278 |  | 36 | 44289 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting895220210316-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting895220210316-3Driver - AZ - After Jan 103210Inv#122 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9140 | 20210512-1 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-05-12 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Repairs from C021 to C028 | 4 | C021-C028 | NISHIN RD | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914020210512-1Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting914020210512-1Excavator - 36 ton- After Jan 1081175.68Inv#131 | [5 empty] | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9140 | 20210512-1 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-05-12 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Repairs from C021 to C028 | 4 | C021-C028 | NISHIN RD | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914020210512-1Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting914020210512-1Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#131 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9140 | 20210512-1 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-12 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Repairs from C021 to C028 | 4 | C021-C028 | NISHIN RD | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914020210512-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting914020210512-1Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9140 | 20210512-1 | 53510412 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-05-12 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Repairs from C021 to C028 | 4 | C021-C028 | NISHIN RD | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914020210512-1Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting914020210512-1Tractor Trailer - 60 Ton- After Jan 103367.17Inv#131 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9140 | 20210512-1 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-05-12 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Repairs from C021 to C028 | 4 | C021-C028 | NISHIN RD | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914020210512-1Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting914020210512-1Operator - Principle - After Jan 109675Inv#131 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9140 | 20210512-1 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-05-12 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Repairs from C021 to C028 | 4 | C021-C028 | NISHIN RD | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914020210512-1Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting914020210512-1Driver - AZ - After Jan 103210Inv#131 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9141 | 20210513-1 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-05-13 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914120210513-1Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting914120210513-1Excavator - 36 ton- After Jan 10101469.6Inv#131 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9141 | 20210513-1 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-13 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914120210513-1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting914120210513-1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#131 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9141 | 20210513-1 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-13 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914120210513-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting914120210513-1Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9141 | 20210513-1 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-05-13 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914120210513-1Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting914120210513-1Operator - Principle - After Jan 1011825Inv#131 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9142 | 20210514-1 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-05-14 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914220210514-1Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting914220210514-1Excavator - 36 ton- After Jan 10101469.6Inv#131 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9142 | 20210514-1 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-14 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914220210514-1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting914220210514-1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#131 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9142 | 20210514-1 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-14 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914220210514-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting914220210514-1Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9142 | 20210514-1 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-05-14 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914220210514-1Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting914220210514-1Operator - Principle - After Jan 1011825Inv#131 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9143 | 20210514-2 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-05-14 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B194-B201 | 4 | B194-B201 | Little Gravel Road | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914320210514-2Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting914320210514-2Excavator - 36 ton- After Jan 10101469.6Inv#131 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9143 | 20210514-2 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-14 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B194-B201 | 4 | B194-B201 | Little Gravel Road | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914320210514-2Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting914320210514-2Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#131 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9143 | 20210514-2 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-14 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B194-B201 | 4 | B194-B201 | Little Gravel Road | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914320210514-2Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting914320210514-2Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9143 | 20210514-2 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-05-14 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B194-B201 | 4 | B194-B201 | Little Gravel Road | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914320210514-2Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting914320210514-2Operator - Principle - After Jan 1011825Inv#131 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9144 | 20210515-1 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-05-15 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914420210515-1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting914420210515-1Excavator - 36 ton- After Jan 10111616.56Inv#131 | [5 empty] | 1 | 1616.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9144 | 20210515-1 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-05-15 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914420210515-1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting914420210515-1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31Inv#131 | [5 empty] | 1 | 134.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9144 | 20210515-1 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-15 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914420210515-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting914420210515-1Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9144 | 20210515-1 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-05-15 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance continuing across Nishin Road | 4 | C021-C028 | Nishin Rd | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914420210515-1Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting914420210515-1Operator - Principle - After Jan 1012900Inv#131 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9145 | 20210515-2 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-05-15 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B194-B201 | 4 | B194-B201 | Little Gravel Road | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914520210515-2Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting914520210515-2Excavator - 36 ton- After Jan 10111616.56Inv#131 | [5 empty] | 1 | 1616.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9145 | 20210515-2 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-05-15 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B194-B201 | 4 | B194-B201 | Little Gravel Road | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914520210515-2Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting914520210515-2Excavator Thumb - 30 - 50 ton- After Jan 1011134.31Inv#131 | [5 empty] | 1 | 134.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9145 | 20210515-2 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-15 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B194-B201 | 4 | B194-B201 | Little Gravel Road | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914520210515-2Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting914520210515-2Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9145 | 20210515-2 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-05-15 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B194-B201 | 4 | B194-B201 | Little Gravel Road | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914520210515-2Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting914520210515-2Operator - Principle - After Jan 1012900Inv#131 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9147 | 20210516-1 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-05-16 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B201-B204 | 4 | B194-B201 | Little Gravel River | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914720210516-1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting914720210516-1Excavator - 36 ton- After Jan 1091322.64Inv#131 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9147 | 20210516-1 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-05-16 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B201-B204 | 4 | B194-B201 | Little Gravel River | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914720210516-1Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting914720210516-1Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#131 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9147 | 20210516-1 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-16 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B201-B204 | 4 | B194-B201 | Little Gravel River | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914720210516-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting914720210516-1Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9147 | 20210516-1 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-05-16 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Little Gravel River Road from B201-B204 | 4 | B194-B201 | Little Gravel River | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914720210516-1Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting914720210516-1Operator - Principle - After Jan 1010750Inv#131 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9148 | 20210517-1 | 53510412 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-05-17 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of Ex-09 from Gravel River Road to Blair Lake Road - Wlak Ex-08 to rescue valard pick up | 4 | B194-B201 | Little Gravel Road | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914820210517-1Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting914820210517-1Tractor Trailer - 60 Ton- After Jan 103367.17Inv#131 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9148 | 20210517-1 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-05-17 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of Ex-09 from Gravel River Road to Blair Lake Road - Wlak Ex-08 to rescue valard pick up | 4 | B194-B201 | Little Gravel Road | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting914820210517-1Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting914820210517-1Driver - AZ - After Jan 103210Inv#131 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9150 | 20210524-1 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 20 | Dynamic | 110.22 | 0 |  |  | 2939.2 | 382.096 | 3321.296 | 2021-05-24 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094-C097 | 5 | C094-C097 | Cook Lake | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915020210524-1Excavator - 36 ton- After Jan 10202939.2 | Corbiere and Sons Contracting915020210524-1Excavator - 36 ton- After Jan 10202939.2Inv#131 | [5 empty] | 1 | 2939.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9150 | 20210524-1 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-24 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094-C097 | 5 | C094-C097 | Cook Lake | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915020210524-1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting915020210524-1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#131 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9150 | 20210524-1 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-24 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094-C097 | 5 | C094-C097 | Cook Lake | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915020210524-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting915020210524-1Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9150 | 20210524-1 | 53510512 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-05-24 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094-C097 | 5 | C094-C097 | Cook Lake | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915020210524-1L.O.A.2420 | Corbiere and Sons Contracting915020210524-1L.O.A.2420Inv#131 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9150 | 20210524-1 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2021-05-24 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094-C097 | 5 | C094-C097 | Cook Lake | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915020210524-1Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting915020210524-1Operator - Principle - After Jan 10221650Inv#131 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9151 | 20210525-1 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-05-25 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 | 5 | C094-C097 | Cook Lake | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915120210525-1Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting915120210525-1Excavator - 36 ton- After Jan 106881.76Inv#131 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9151 | 20210525-1 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-05-25 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 | 5 | C094-C097 | Cook Lake | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915120210525-1Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting915120210525-1Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#131 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9151 | 20210525-1 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-05-25 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 | 5 | C094-C097 | Cook Lake | 0 | 44343 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915120210525-1Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting915120210525-1Operator - Principle - After Jan 106450Inv#131 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9197 | 20210525-3 | 53510212 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2021-05-25 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Access work across Land Fill Road | 2 | B065-B084 | Land Fill Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting919720210525-3Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting919720210525-3Excavator - 30 ton- After Jan 105.5761.475Inv# 135-R03 | [5 empty] | 1 | 761.475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9197 | 20210525-3 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-05-25 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Access work across Land Fill Road | 2 | B065-B084 | Land Fill Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting919720210525-3Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting919720210525-3Excavator Thumb - 30 - 50 ton- After Jan 105.567.155Inv# 135-R03 | [5 empty] | 1 | 67.155 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9197 | 20210525-3 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-05-25 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Access work across Land Fill Road | 2 | B065-B084 | Land Fill Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting919720210525-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting919720210525-3Operator - Principle - After Jan 106450Inv# 135-R03 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9152 | 20210526-1 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-05-26 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915220210526-1Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting915220210526-1Excavator - 36 ton- After Jan 10121763.52Inv#131 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9152 | 20210526-1 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-26 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915220210526-1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting915220210526-1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#131 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9152 | 20210526-1 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-26 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915220210526-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting915220210526-1Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9152 | 20210526-1 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-05-26 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915220210526-1L.O.A.1210 | Corbiere and Sons Contracting915220210526-1L.O.A.1210Inv#131 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9152 | 20210526-1 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-05-26 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915220210526-1Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting915220210526-1Operator - Principle - After Jan 1013975Inv#131 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9199 | 20210526-3 | 53510412 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4.5 | Dynamic | 103.84 | 0 |  |  | 623.025 | 80.9933 | 704.0182 | 2021-05-26 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex into Nishin to start Road work | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting919920210526-3Excavator - 30 ton- After Jan 104.5623.025 | Corbiere and Sons Contracting919920210526-3Excavator - 30 ton- After Jan 104.5623.025Inv# 135-R03 | [5 empty] | 1 | 623.025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9199 | 20210526-3 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4.5 | HR | 9.16 | 0 |  |  | 54.945 | 7.1429 | 62.0879 | 2021-05-26 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex into Nishin to start Road work | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting919920210526-3Excavator Thumb - 30 - 50 ton- After Jan 104.554.945 | Corbiere and Sons Contracting919920210526-3Excavator Thumb - 30 - 50 ton- After Jan 104.554.945Inv# 135-R03 | [5 empty] | 1 | 54.945 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9199 | 20210526-3 | 53510412 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-05-26 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex into Nishin to start Road work | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting919920210526-3Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting919920210526-3Tractor Trailer - 60 Ton- After Jan 103367.17Inv# 135-R03 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9199 | 20210526-3 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2021-05-26 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex into Nishin to start Road work | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting919920210526-3Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting919920210526-3Operator - Principle - After Jan 106.5487.5Inv# 135-R03 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9199 | 20210526-3 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-05-26 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex into Nishin to start Road work | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting919920210526-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting919920210526-3Driver - AZ - After Jan 103210Inv# 135-R03 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9200 | 20210526-4 | 53510612 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-05-26 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moving excavator out of Prairie River to 3 Finger | 6 | C171-C185 | Prairie River | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting920020210526-4Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting920020210526-4Tractor Trailer - 60 Ton- After Jan 103367.17Inv# 135-R03 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9200 | 20210526-4 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-05-26 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moving excavator out of Prairie River to 3 Finger | 6 | C171-C185 | Prairie River | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting920020210526-4Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting920020210526-4Driver - AZ - After Jan 103210Inv# 135-R03 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9153 | 20210527-1 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 and mobilization of 2 excavators | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915320210527-1Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting915320210527-1Excavator - 30 ton- After Jan 103415.35Inv#131 | [5 empty] | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9153 | 20210527-1 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 17 | Dynamic | 110.22 | 0 |  |  | 2498.32 | 324.7816 | 2823.1016 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 and mobilization of 2 excavators | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915320210527-1Excavator - 36 ton- After Jan 10172498.32 | Corbiere and Sons Contracting915320210527-1Excavator - 36 ton- After Jan 10172498.32Inv#131 | [5 empty] | 1 | 2498.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9153 | 20210527-1 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 and mobilization of 2 excavators | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915320210527-1Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting915320210527-1Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#131 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9153 | 20210527-1 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 and mobilization of 2 excavators | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915320210527-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting915320210527-1Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9153 | 20210527-1 | 53510512 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 7 | Dynamic | 103.54 | 0 |  |  | 966.35 | 125.6255 | 1091.9755 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 and mobilization of 2 excavators | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915320210527-1Rock Truck - 30 Ton- After Jan 107966.35 | Corbiere and Sons Contracting915320210527-1Rock Truck - 30 Ton- After Jan 107966.35Inv#131 | [5 empty] | 1 | 966.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9153 | 20210527-1 | 53510512 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 28 | Dynamic | 91.79 | 0 |  |  | 3426.92 | 445.4996 | 3872.4196 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 and mobilization of 2 excavators | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915320210527-1Tractor Trailer - 60 Ton- After Jan 10283426.92 | Corbiere and Sons Contracting915320210527-1Tractor Trailer - 60 Ton- After Jan 10283426.92Inv#131 | [5 empty] | 1 | 3426.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9153 | 20210527-1 | 53510512 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 and mobilization of 2 excavators | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915320210527-1Foreman4380 | Corbiere and Sons Contracting915320210527-1Foreman4380Inv#131 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9153 | 20210527-1 | 53510512 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 and mobilization of 2 excavators | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915320210527-1L.O.A.3630 | Corbiere and Sons Contracting915320210527-1L.O.A.3630Inv#131 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9153 | 20210527-1 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 29 | HR |  |  | 75 | 0 | 2175 | 282.75 | 2457.75 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 and mobilization of 2 excavators | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915320210527-1Operator - Principle - After Jan 10292175 | Corbiere and Sons Contracting915320210527-1Operator - Principle - After Jan 10292175Inv#131 | [5 empty] | 1 | 2175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9153 | 20210527-1 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 28 | HR |  |  | 70 | 0 | 1960 | 254.8 | 2214.8 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Cooks Lake from C094 and mobilization of 2 excavators | 5 | C094-C097 | Cook Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915320210527-1Driver - AZ - After Jan 10281960 | Corbiere and Sons Contracting915320210527-1Driver - AZ - After Jan 10281960Inv#131 | [5 empty] | 1 | 1960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9154 | 20210527-2 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scott spent 3 hours with an environmental technician checking dams and cleaning up washed silt fence at WC7210 | 5 | C050-C069 | Antler Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915420210527-2Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting915420210527-2Excavator - 36 ton- After Jan 103440.88Inv#131 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9154 | 20210527-2 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scott spent 3 hours with an environmental technician checking dams and cleaning up washed silt fence at WC7210 | 5 | C050-C069 | Antler Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915420210527-2Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting915420210527-2Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#131 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9154 | 20210527-2 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-05-27 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scott spent 3 hours with an environmental technician checking dams and cleaning up washed silt fence at WC7210 | 5 | C050-C069 | Antler Lake | 0 | 44346 |  | 37 | 44348 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915420210527-2Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting915420210527-2Operator - Principle - After Jan 103225Inv#131 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9201 | 20210527-3 | 53510412 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-05-27 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing on Nishin Road | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44364 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920120210527-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting920120210527-3Excavator - 30 ton- After Jan 105692.25Inv# 135-R03 | [5 empty] | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9201 | 20210527-3 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-05-27 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing on Nishin Road | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44364 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920120210527-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting920120210527-3Operator - Principle - After Jan 106450Inv# 135-R03 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9202 | 20210527-4 | 53510712 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-05-27 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on 3 Finger Lake | 0 |  | 3 Finger Lake WF7 | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting920220210527-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting920220210527-4Excavator - 36 ton- After Jan 105734.8Inv# 135-R03 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9202 | 20210527-4 | 53510712 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-05-27 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on 3 Finger Lake | 0 |  | 3 Finger Lake WF7 | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting920220210527-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting920220210527-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv# 135-R03 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9202 | 20210527-4 | 53510712 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-27 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on 3 Finger Lake | 0 |  | 3 Finger Lake WF7 | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting920220210527-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting920220210527-4Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9202 | 20210527-4 | 53510712 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-05-27 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on 3 Finger Lake | 0 |  | 3 Finger Lake WF7 | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting920220210527-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting920220210527-4Operator - Principle - After Jan 106450Inv# 135-R03 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9156 | 20210528-2 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitneancne from C094 and C095 | 5 | C076-C116 | Cook Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915620210528-2Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting915620210528-2Excavator - 30 ton- After Jan 10101384.5Inv#131 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9156 | 20210528-2 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitneancne from C094 and C095 | 5 | C076-C116 | Cook Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915620210528-2Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting915620210528-2Excavator - 36 ton- After Jan 105734.8Inv#131 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9156 | 20210528-2 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitneancne from C094 and C095 | 5 | C076-C116 | Cook Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915620210528-2Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting915620210528-2Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#131 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9156 | 20210528-2 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitneancne from C094 and C095 | 5 | C076-C116 | Cook Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915620210528-2Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting915620210528-2Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9156 | 20210528-2 | 53510512 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitneancne from C094 and C095 | 5 | C076-C116 | Cook Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915620210528-2Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting915620210528-2Rock Truck - 30 Ton- After Jan 105690.25Inv#131 | [5 empty] | 1 | 690.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9156 | 20210528-2 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitneancne from C094 and C095 | 5 | C076-C116 | Cook Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915620210528-2L.O.A.1210 | Corbiere and Sons Contracting915620210528-2L.O.A.1210Inv#131 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9156 | 20210528-2 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitneancne from C094 and C095 | 5 | C076-C116 | Cook Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915620210528-2Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting915620210528-2Operator - Principle - After Jan 10211575Inv#131 | [5 empty] | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9157 | 20210528-3 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915720210528-3Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting915720210528-3Excavator - 30 ton- After Jan 10101384.5Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9157 | 20210528-3 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915720210528-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting915720210528-3Excavator - 36 ton- After Jan 10111616.56Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1616.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9157 | 20210528-3 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915720210528-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting915720210528-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9157 | 20210528-3 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915720210528-3Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting915720210528-3Excavator Hammer - 30 - 50 ton- After Jan 108507.04Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 507.04 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9157 | 20210528-3 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915720210528-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting915720210528-3Light Truck - Pick up- After Jan 101243.75Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9157 | 20210528-3 | 53510502 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915720210528-3Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting915720210528-3Rock Truck - 30 Ton- After Jan 10101380.5Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1380.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9157 | 20210528-3 | 53510502 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915720210528-3L.O.A.4840 | Corbiere and Sons Contracting915720210528-3L.O.A.4840Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9157 | 20210528-3 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34 | HR |  |  | 75 | 0 | 2550 | 331.5 | 2881.5 | 2021-05-28 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting915720210528-3Operator - Principle - After Jan 10342550 | Corbiere and Sons Contracting915720210528-3Operator - Principle - After Jan 10342550Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 2550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9203 | 20210528-4 | 53510412 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2021-05-28 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from C010 | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920320210528-4Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting920320210528-4Excavator - 30 ton- After Jan 1010.51453.725Inv# 135-R03 | [5 empty] | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9203 | 20210528-4 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2021-05-28 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from C010 | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920320210528-4Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting920320210528-4Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv# 135-R03 | [5 empty] | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9203 | 20210528-4 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-28 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from C010 | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920320210528-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting920320210528-4Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9203 | 20210528-4 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-05-28 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from C010 | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920320210528-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting920320210528-4Operator - Principle - After Jan 1011.5862.5Inv# 135-R03 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9204 | 20210528-5 | 53510412 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-05-28 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered Cuvlerts to Gurney | 4 | B194-B200 | Gurney | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920420210528-5Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting920420210528-5Tractor Trailer - 60 Ton- After Jan 102244.78Inv# 135-R03 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9204 | 20210528-5 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-05-28 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered Cuvlerts to Gurney | 4 | B194-B200 | Gurney | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920420210528-5Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting920420210528-5Driver - AZ - After Jan 102140Inv# 135-R03 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9161 | 20210529-3 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf continuing Road Maintenance for swamp area from C097 | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916120210529-3Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting916120210529-3Excavator - 30 ton- After Jan 10101384.5Inv#131 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9161 | 20210529-3 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf continuing Road Maintenance for swamp area from C097 | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916120210529-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting916120210529-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#131 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9161 | 20210529-3 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf continuing Road Maintenance for swamp area from C097 | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916120210529-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting916120210529-3Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9161 | 20210529-3 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf continuing Road Maintenance for swamp area from C097 | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916120210529-3L.O.A.1210 | Corbiere and Sons Contracting916120210529-3L.O.A.1210Inv#131 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9161 | 20210529-3 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ingolf continuing Road Maintenance for swamp area from C097 | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916120210529-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting916120210529-3Operator - Principle - After Jan 1011825Inv#131 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting916220210529-4Excavator - 30 ton- After Jan 10101384.5Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting916220210529-4Excavator - 36 ton- After Jan 10101469.6Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting916220210529-4Excavator - 36 ton- After Jan 1091322.64Inv#131 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting916220210529-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting916220210529-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#131 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 570.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting916220210529-4Light Truck - Pick up- After Jan 102487.5Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53510502 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting916220210529-4Rock Truck - 30 Ton- After Jan 10101380.5Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1380.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53510502 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4Foreman121140 | Corbiere and Sons Contracting916220210529-4Foreman121140Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53510502 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4L.O.A.4840 | Corbiere and Sons Contracting916220210529-4L.O.A.4840Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4L.O.A.1210 | Corbiere and Sons Contracting916220210529-4L.O.A.1210Inv#131 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting916220210529-4Operator - Principle - After Jan 10332475Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9162 | 20210529-4 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-05-29 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916220210529-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting916220210529-4Operator - Principle - After Jan 1011825Inv#131 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9165 | 20210530-3 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916520210530-3Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting916520210530-3Excavator - 30 ton- After Jan 1081107.6Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9165 | 20210530-3 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916520210530-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting916520210530-3Excavator - 36 ton- After Jan 10101469.6Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9165 | 20210530-3 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916520210530-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting916520210530-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9165 | 20210530-3 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916520210530-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting916520210530-3Light Truck - Pick up- After Jan 102487.5Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9165 | 20210530-3 | 53510502 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916520210530-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting916520210530-3Rock Truck - 30 Ton- After Jan 1091242.45Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1242.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9165 | 20210530-3 | 53510502 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916520210530-3L.O.A.3630 | Corbiere and Sons Contracting916520210530-3L.O.A.3630Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9165 | 20210530-3 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916520210530-3Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting916520210530-3Operator - Principle - After Jan 10332475Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9166 | 20210530-4 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator Mobed into Antler Lake Road for Maintenance at C055 | 5 | C070 - C075 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916620210530-4Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting916620210530-4Excavator - 36 ton- After Jan 104587.84Inv#131 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9166 | 20210530-4 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator Mobed into Antler Lake Road for Maintenance at C055 | 5 | C070 - C075 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916620210530-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting916620210530-4Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9166 | 20210530-4 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator Mobed into Antler Lake Road for Maintenance at C055 | 5 | C070 - C075 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916620210530-4L.O.A.1210 | Corbiere and Sons Contracting916620210530-4L.O.A.1210Inv#131 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9166 | 20210530-4 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-05-30 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator Mobed into Antler Lake Road for Maintenance at C055 | 5 | C070 - C075 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916620210530-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting916620210530-4Operator - Principle - After Jan 105375Inv#131 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9169 | 20210531-3 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916920210531-3Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting916920210531-3Excavator - 30 ton- After Jan 10101384.5Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9169 | 20210531-3 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916920210531-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting916920210531-3Excavator - 36 ton- After Jan 10101469.6Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9169 | 20210531-3 | 53550603 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting916920210531-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting916920210531-3Excavator - 36 ton- After Jan 10101469.6Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9169 | 20210531-3 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916920210531-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting916920210531-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9169 | 20210531-3 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916920210531-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting916920210531-3Light Truck - Pick up- After Jan 102487.5Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9169 | 20210531-3 | 53510502 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916920210531-3Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting916920210531-3Rock Truck - 30 Ton- After Jan 1081104.4Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9169 | 20210531-3 | 53510502 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916920210531-3L.O.A.3630 | Corbiere and Sons Contracting916920210531-3L.O.A.3630Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9169 | 20210531-3 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30 | HR |  |  | 75 | 0 | 2250 | 292.5 | 2542.5 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road towards tower C061 | 5 | C061 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting916920210531-3Operator - Principle - After Jan 10302250 | Corbiere and Sons Contracting916920210531-3Operator - Principle - After Jan 10302250Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 2250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9170 | 20210531-4 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan was doing road Maitnenance from C060 | 5 | C055 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917020210531-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting917020210531-4Excavator - 36 ton- After Jan 105734.8Inv#131 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9170 | 20210531-4 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan was doing road Maitnenance from C060 | 5 | C055 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917020210531-4L.O.A.1210 | Corbiere and Sons Contracting917020210531-4L.O.A.1210Inv#131 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9170 | 20210531-4 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan was doing road Maitnenance from C060 | 5 | C055 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917020210531-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting917020210531-4Operator - Principle - After Jan 106450Inv#131 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9172 | 20210531-6 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from C042 and C048 | 5 | C042-C048 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917220210531-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting917220210531-6Excavator - 36 ton- After Jan 10101469.6Inv#131 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9172 | 20210531-6 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from C042 and C048 | 5 | C042-C048 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917220210531-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting917220210531-6Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9172 | 20210531-6 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from C042 and C048 | 5 | C042-C048 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917220210531-6L.O.A.1210 | Corbiere and Sons Contracting917220210531-6L.O.A.1210Inv#131 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9172 | 20210531-6 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-05-31 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from C042 and C048 | 5 | C042-C048 | Antler Lake | 0 | 44350 |  | 37 | 44351 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917220210531-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting917220210531-6Operator - Principle - After Jan 1011825Inv#131 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9206 | 20210531-7 | 53510412 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-05-31 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from Nishin Road - Float moved Ex to Little Gravel | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920620210531-7Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting920620210531-7Excavator - 30 ton- After Jan 10101384.5Inv# 135-R03 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9206 | 20210531-7 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-05-31 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from Nishin Road - Float moved Ex to Little Gravel | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920620210531-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting920620210531-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9206 | 20210531-7 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-05-31 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from Nishin Road - Float moved Ex to Little Gravel | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920620210531-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting920620210531-7Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9206 | 20210531-7 | 53510412 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-05-31 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from Nishin Road - Float moved Ex to Little Gravel | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920620210531-7Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting920620210531-7Tractor Trailer - 60 Ton- After Jan 103367.17Inv# 135-R03 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9206 | 20210531-7 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-05-31 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from Nishin Road - Float moved Ex to Little Gravel | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920620210531-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting920620210531-7Operator - Principle - After Jan 1012900Inv# 135-R03 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9206 | 20210531-7 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-05-31 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from Nishin Road - Float moved Ex to Little Gravel | 4 | C007-C014 | Nishin Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920620210531-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting920620210531-7Driver - AZ - After Jan 103210Inv# 135-R03 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9175 | 20210601-3 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan Pleason spent day continuing on road towards C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917520210601-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting917520210601-3Excavator - 36 ton- After Jan 10101469.6Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9175 | 20210601-3 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan Pleason spent day continuing on road towards C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917520210601-3L.O.A.1210 | Corbiere and Sons Contracting917520210601-3L.O.A.1210Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9175 | 20210601-3 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan Pleason spent day continuing on road towards C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917520210601-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting917520210601-3Operator - Principle - After Jan 1011825Inv#131 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9176 | 20210601-4 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan Frasier continued on maintenance from KM3.5 to KM1 | 5 | C060 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917620210601-4Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting917620210601-4Excavator - 36 ton- After Jan 10111616.56Inv#131 | [5 empty] | 1 | 1616.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9176 | 20210601-4 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan Frasier continued on maintenance from KM3.5 to KM1 | 5 | C060 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917620210601-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting917620210601-4Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9176 | 20210601-4 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan Frasier continued on maintenance from KM3.5 to KM1 | 5 | C060 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917620210601-4L.O.A.1210 | Corbiere and Sons Contracting917620210601-4L.O.A.1210Inv#131 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9176 | 20210601-4 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan Frasier continued on maintenance from KM3.5 to KM1 | 5 | C060 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917620210601-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting917620210601-4Operator - Principle - After Jan 1011825Inv#131 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9177 | 20210601-5 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day on Rock Hammer for ROW at C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917720210601-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting917720210601-5Excavator - 36 ton- After Jan 10101469.6Inv#131 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9177 | 20210601-5 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10 | HR | 47.54 | 0 |  |  | 633.8 | 82.394 | 716.194 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day on Rock Hammer for ROW at C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917720210601-5Excavator Hammer - 30 - 50 ton- After Jan 1010633.8 | Corbiere and Sons Contracting917720210601-5Excavator Hammer - 30 - 50 ton- After Jan 1010633.8Inv#131 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 633.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9177 | 20210601-5 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day on Rock Hammer for ROW at C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917720210601-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting917720210601-5Light Truck - Pick up- After Jan 101243.75Inv#131 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9177 | 20210601-5 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day on Rock Hammer for ROW at C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917720210601-5L.O.A.1210 | Corbiere and Sons Contracting917720210601-5L.O.A.1210Inv#131 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9177 | 20210601-5 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent day on Rock Hammer for ROW at C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917720210601-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting917720210601-5Operator - Principle - After Jan 1011825Inv#131 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9178 | 20210601-6 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from C042 and C048 completed and excavator demobbed | 5 | C042-C048 | Pays Plat River | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917820210601-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting917820210601-6Excavator - 36 ton- After Jan 10101469.6Inv#131 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9178 | 20210601-6 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from C042 and C048 completed and excavator demobbed | 5 | C042-C048 | Pays Plat River | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917820210601-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting917820210601-6Light Truck - Pick up- After Jan 101243.75Inv#131 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9178 | 20210601-6 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from C042 and C048 completed and excavator demobbed | 5 | C042-C048 | Pays Plat River | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917820210601-6L.O.A.1210 | Corbiere and Sons Contracting917820210601-6L.O.A.1210Inv#131 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9178 | 20210601-6 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-01 | 0 | Inv#131 | 44354 | 152 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from C042 and C048 completed and excavator demobbed | 5 | C042-C048 | Pays Plat River | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting917820210601-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting917820210601-6Operator - Principle - After Jan 1011825Inv#131 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9207 | 20210601-8 | 53510412 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2021-06-01 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44364 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920720210601-8Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting920720210601-8Excavator - 30 ton- After Jan 1010.51453.725Inv# 135-R03 | [5 empty] | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9207 | 20210601-8 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2021-06-01 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44364 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920720210601-8Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting920720210601-8Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv# 135-R03 | [5 empty] | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9207 | 20210601-8 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-01 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44364 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920720210601-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting920720210601-8Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9207 | 20210601-8 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-06-01 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44364 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920720210601-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting920720210601-8Operator - Principle - After Jan 1011.5862.5Inv# 135-R03 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9182 | 20210602-3 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew finishing up work to C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918220210602-3Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting918220210602-3Excavator - 30 ton- After Jan 104553.8Inv# 135-R03 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9182 | 20210602-3 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew finishing up work to C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918220210602-3Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting918220210602-3Excavator - 36 ton- After Jan 104587.84Inv# 135-R03 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9182 | 20210602-3 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew finishing up work to C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918220210602-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting918220210602-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv# 135-R03 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9182 | 20210602-3 | 53510502 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew finishing up work to C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918220210602-3Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting918220210602-3Rock Truck - 30 Ton- After Jan 104552.2Inv# 135-R03 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 552.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9182 | 20210602-3 | 53510502 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew finishing up work to C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918220210602-3L.O.A.3630 | Corbiere and Sons Contracting918220210602-3L.O.A.3630Inv# 135-R03 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9182 | 20210602-3 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew finishing up work to C061 | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918220210602-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting918220210602-3Operator - Principle - After Jan 1012900Inv# 135-R03 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9183 | 20210602-4 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent 3 hours ditching water and fixing wetspots | 5 | C060 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918320210602-4Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting918320210602-4Excavator - 36 ton- After Jan 103440.88Inv# 135-R03 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9183 | 20210602-4 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel spent 3 hours ditching water and fixing wetspots | 5 | C060 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918320210602-4Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting918320210602-4Operator - Principle - After Jan 103225Inv# 135-R03 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9184 | 20210602-5 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan Frasier did rock hammering from C061 all day to complete access | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918420210602-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting918420210602-5Excavator - 36 ton- After Jan 10101469.6Inv# 135-R03 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9184 | 20210602-5 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10 | HR | 47.54 | 0 |  |  | 633.8 | 82.394 | 716.194 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan Frasier did rock hammering from C061 all day to complete access | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918420210602-5Excavator Hammer - 30 - 50 ton- After Jan 1010633.8 | Corbiere and Sons Contracting918420210602-5Excavator Hammer - 30 - 50 ton- After Jan 1010633.8Inv# 135-R03 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 633.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9184 | 20210602-5 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan Frasier did rock hammering from C061 all day to complete access | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918420210602-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting918420210602-5Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9184 | 20210602-5 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan Frasier did rock hammering from C061 all day to complete access | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918420210602-5L.O.A.1210 | Corbiere and Sons Contracting918420210602-5L.O.A.1210Inv# 135-R03 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9184 | 20210602-5 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dan Frasier did rock hammering from C061 all day to complete access | 5 | C061 | Antler Lake | 0 | 44353 |  | 37 | 44354 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting918420210602-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting918420210602-5Operator - Principle - After Jan 1011825Inv# 135-R03 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9209 | 20210602-7 | 53510412 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road working continuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920920210602-7Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting920920210602-7Excavator - 30 ton- After Jan 10101384.5Inv# 135-R03 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9209 | 20210602-7 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road working continuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920920210602-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting920920210602-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9209 | 20210602-7 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road working continuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920920210602-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting920920210602-7Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9209 | 20210602-7 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-02 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road working continuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting920920210602-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting920920210602-7Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9210 | 20210603-4 | 53510412 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-06-03 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from C194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting921020210603-4Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting921020210603-4Excavator - 30 ton- After Jan 10101384.5Inv# 135-R03 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9210 | 20210603-4 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-03 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from C194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting921020210603-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting921020210603-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9210 | 20210603-4 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-03 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from C194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting921020210603-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting921020210603-4Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9210 | 20210603-4 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-03 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from C194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting921020210603-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting921020210603-4Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9211 | 20210604-4 | 53510412 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-06-04 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work conitnuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting921120210604-4Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting921120210604-4Excavator - 30 ton- After Jan 10101384.5Inv# 135-R03 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9211 | 20210604-4 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-04 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work conitnuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting921120210604-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting921120210604-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9211 | 20210604-4 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-04 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work conitnuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting921120210604-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting921120210604-4Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9211 | 20210604-4 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-04 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work conitnuing from B194-B200 | 4 | B194-B200 | Little Gravel River Road | 0 | 44358 |  | 37 | 44363 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting921120210604-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting921120210604-4Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9212 | 20210605-5 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 1 | Dynamic | 103.84 | 0 |  |  | 138.45 | 17.9985 | 156.4485 | 2021-06-05 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work at C061 | 5 | C061 | Antler Lake | 0 | 44358 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting921220210605-5Excavator - 30 ton- After Jan 101138.45 | Corbiere and Sons Contracting921220210605-5Excavator - 30 ton- After Jan 101138.45Inv# 135-R03 | [5 empty] | 1 | 138.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9212 | 20210605-5 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2021-06-05 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work at C061 | 5 | C061 | Antler Lake | 0 | 44358 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting921220210605-5Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting921220210605-5Excavator - 36 ton- After Jan 101146.96Inv# 135-R03 | [5 empty] | 1 | 146.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9212 | 20210605-5 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-06-05 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work at C061 | 5 | C061 | Antler Lake | 0 | 44358 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting921220210605-5Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting921220210605-5Excavator Thumb - 30 - 50 ton- After Jan 10112.21Inv# 135-R03 | [5 empty] | 1 | 12.21 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9212 | 20210605-5 | 53510512 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 1 | Dynamic | 103.54 | 0 |  |  | 138.05 | 17.9465 | 155.9965 | 2021-06-05 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work at C061 | 5 | C061 | Antler Lake | 0 | 44358 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting921220210605-5Rock Truck - 30 Ton- After Jan 101138.05 | Corbiere and Sons Contracting921220210605-5Rock Truck - 30 Ton- After Jan 101138.05Inv# 135-R03 | [5 empty] | 1 | 138.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9212 | 20210605-5 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-06-05 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work at C061 | 5 | C061 | Antler Lake | 0 | 44358 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting921220210605-5Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting921220210605-5Operator - Principle - After Jan 103225Inv# 135-R03 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9221 | 20210607-5 | 53510412 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-06-07 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B197 | 4 | B194-B197 | Little Gravel River Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 04 | Corbiere and Sons Contracting922120210607-5Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting922120210607-5Excavator - 30 ton- After Jan 10101384.5Inv# 135-R03 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9221 | 20210607-5 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-07 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B197 | 4 | B194-B197 | Little Gravel River Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 04 | Corbiere and Sons Contracting922120210607-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting922120210607-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9221 | 20210607-5 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-07 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B197 | 4 | B194-B197 | Little Gravel River Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 04 | Corbiere and Sons Contracting922120210607-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting922120210607-5Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9221 | 20210607-5 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-07 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B197 | 4 | B194-B197 | Little Gravel River Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 04 | Corbiere and Sons Contracting922120210607-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting922120210607-5Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9222 | 20210607-6 | 53510512 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-06-07 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked in Cooks Lake Road | 5 | C087-C116 | Cooks Lake Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting922220210607-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting922220210607-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv# 135-R03 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9222 | 20210607-6 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-07 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked in Cooks Lake Road | 5 | C087-C116 | Cooks Lake Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting922220210607-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting922220210607-6Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9222 | 20210607-6 | 53510512 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-06-07 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked in Cooks Lake Road | 5 | C087-C116 | Cooks Lake Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting922220210607-6Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting922220210607-6Tractor Trailer - 60 Ton- After Jan 105611.95Inv# 135-R03 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9222 | 20210607-6 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-07 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked in Cooks Lake Road | 5 | C087-C116 | Cooks Lake Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting922220210607-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting922220210607-6Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9222 | 20210607-6 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-06-07 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked in Cooks Lake Road | 5 | C087-C116 | Cooks Lake Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting922220210607-6Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting922220210607-6Driver - AZ - After Jan 104280Inv# 135-R03 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9227 | 20210608-5 | 53510412 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Little Gravel and ex float demob excavator | 4 | B194-B200 | Little Gravel River Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 04 | Corbiere and Sons Contracting922720210608-5Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting922720210608-5Excavator - 30 ton- After Jan 107969.15Inv# 135-R03 | [5 empty] | 1 | 969.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9227 | 20210608-5 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Little Gravel and ex float demob excavator | 4 | B194-B200 | Little Gravel River Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 04 | Corbiere and Sons Contracting922720210608-5Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting922720210608-5Excavator Thumb - 30 - 50 ton- After Jan 10785.47Inv# 135-R03 | [5 empty] | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9227 | 20210608-5 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Little Gravel and ex float demob excavator | 4 | B194-B200 | Little Gravel River Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 04 | Corbiere and Sons Contracting922720210608-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting922720210608-5Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9227 | 20210608-5 | 53510412 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Little Gravel and ex float demob excavator | 4 | B194-B200 | Little Gravel River Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 04 | Corbiere and Sons Contracting922720210608-5Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting922720210608-5Tractor Trailer - 60 Ton- After Jan 104489.56Inv# 135-R03 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9227 | 20210608-5 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Little Gravel and ex float demob excavator | 4 | B194-B200 | Little Gravel River Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 04 | Corbiere and Sons Contracting922720210608-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting922720210608-5Operator - Principle - After Jan 108600Inv# 135-R03 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9227 | 20210608-5 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Little Gravel and ex float demob excavator | 4 | B194-B200 | Little Gravel River Road | 0 | 44359 |  | 57 | 44359 | [6 empty] | 04 | Corbiere and Sons Contracting922720210608-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting922720210608-5Driver - AZ - After Jan 104280Inv# 135-R03 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9228 | 20210608-6 | 53510512 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader work continued on Cooks Lake Road and then was demobed | 5 | C087-C116 | Cook Lake | 0 | 44359 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting922820210608-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting922820210608-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv# 135-R03 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9228 | 20210608-6 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader work continued on Cooks Lake Road and then was demobed | 5 | C087-C116 | Cook Lake | 0 | 44359 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting922820210608-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting922820210608-6Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9228 | 20210608-6 | 53510512 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader work continued on Cooks Lake Road and then was demobed | 5 | C087-C116 | Cook Lake | 0 | 44359 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting922820210608-6Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting922820210608-6Tractor Trailer - 60 Ton- After Jan 105611.95Inv# 135-R03 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9228 | 20210608-6 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader work continued on Cooks Lake Road and then was demobed | 5 | C087-C116 | Cook Lake | 0 | 44359 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting922820210608-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting922820210608-6Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9228 | 20210608-6 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-06-08 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader work continued on Cooks Lake Road and then was demobed | 5 | C087-C116 | Cook Lake | 0 | 44359 |  | 57 | 44359 | [6 empty] | 05 | Corbiere and Sons Contracting922820210608-6Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting922820210608-6Driver - AZ - After Jan 105350Inv# 135-R03 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9266 | 20210611-5 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Miantenance work on Antler from entrance to KM2.8 | 5 | C050-C069 | Antler Lake | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926620210611-5Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting926620210611-5Excavator - 36 ton- After Jan 105734.8Inv# 135-R03 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9266 | 20210611-5 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Miantenance work on Antler from entrance to KM2.8 | 5 | C050-C069 | Antler Lake | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926620210611-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting926620210611-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv# 135-R03 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9266 | 20210611-5 | 53510512 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 5 | Dynamic | 41.4 | 0 |  |  | 276 | 35.88 | 311.88 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Miantenance work on Antler from entrance to KM2.8 | 5 | C050-C069 | Antler Lake | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926620210611-5Dump - Triaxle- After Jan 105276 | Corbiere and Sons Contracting926620210611-5Dump - Triaxle- After Jan 105276Inv# 135-R03 | [5 empty] | 1 | 276 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9266 | 20210611-5 | 53510512 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Miantenance work on Antler from entrance to KM2.8 | 5 | C050-C069 | Antler Lake | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926620210611-5Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting926620210611-5Tractor Trailer - 60 Ton- After Jan 105611.95Inv# 135-R03 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9266 | 20210611-5 | 53510512 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Miantenance work on Antler from entrance to KM2.8 | 5 | C050-C069 | Antler Lake | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926620210611-5L.O.A.2420 | Corbiere and Sons Contracting926620210611-5L.O.A.2420Inv# 135-R03 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9266 | 20210611-5 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Miantenance work on Antler from entrance to KM2.8 | 5 | C050-C069 | Antler Lake | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926620210611-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting926620210611-5Operator - Principle - After Jan 1012900Inv# 135-R03 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9266 | 20210611-5 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Miantenance work on Antler from entrance to KM2.8 | 5 | C050-C069 | Antler Lake | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926620210611-5Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting926620210611-5Driver - AZ - After Jan 105350Inv# 135-R03 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9267 | 20210611-6 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C075 on Whitesands | 5 | C075 | White Sand | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926720210611-6Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting926720210611-6Excavator - 30 ton- After Jan 10101384.5Inv# 135-R03 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9267 | 20210611-6 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C075 on Whitesands | 5 | C075 | White Sand | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926720210611-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting926720210611-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9267 | 20210611-6 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C075 on Whitesands | 5 | C075 | White Sand | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926720210611-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting926720210611-6Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9267 | 20210611-6 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-06-11 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C075 on Whitesands | 5 | C075 | White Sand | 0 | 44367 |  | 36 | 44369 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting926720210611-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting926720210611-6Operator - Principle - After Jan 1012900Inv# 135-R03 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9281 | 20210614-9 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-06-14 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work on Blair Lake Road | 3 | B182-B186 | Blair Lake Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting928120210614-9Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting928120210614-9Excavator - 30 ton- After Jan 1091246.05Inv# 135-R03 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9281 | 20210614-9 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-06-14 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work on Blair Lake Road | 3 | B182-B186 | Blair Lake Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting928120210614-9Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting928120210614-9Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv# 135-R03 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9281 | 20210614-9 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-14 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work on Blair Lake Road | 3 | B182-B186 | Blair Lake Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting928120210614-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting928120210614-9Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9281 | 20210614-9 | 53510312 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2021-06-14 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work on Blair Lake Road | 3 | B182-B186 | Blair Lake Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting928120210614-9Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting928120210614-9Tractor Trailer - 60 Ton- After Jan 10101223.9Inv# 135-R03 | [5 empty] | 1 | 1223.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9281 | 20210614-9 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-06-14 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work on Blair Lake Road | 3 | B182-B186 | Blair Lake Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting928120210614-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting928120210614-9Operator - Principle - After Jan 1012900Inv# 135-R03 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9281 | 20210614-9 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2021-06-14 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work on Blair Lake Road | 3 | B182-B186 | Blair Lake Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting928120210614-9Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting928120210614-9Driver - AZ - After Jan 1010700Inv# 135-R03 | [5 empty] | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9290 | 20210616-8 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-06-16 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little gravel River Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929020210616-8Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting929020210616-8Excavator - 36 ton- After Jan 103440.88Inv# 135-R03 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9290 | 20210616-8 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-06-16 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little gravel River Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929020210616-8Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting929020210616-8Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv# 135-R03 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9290 | 20210616-8 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-16 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little gravel River Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929020210616-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting929020210616-8Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9290 | 20210616-8 | 53510412 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-06-16 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little gravel River Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929020210616-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting929020210616-8Tractor Trailer - 60 Ton- After Jan 104489.56Inv# 135-R03 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9290 | 20210616-8 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-06-16 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little gravel River Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929020210616-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting929020210616-8Operator - Principle - After Jan 105375Inv# 135-R03 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9290 | 20210616-8 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-06-16 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little gravel River Road | 0 | 44367 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929020210616-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting929020210616-8Driver - AZ - After Jan 104280Inv# 135-R03 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9296 | 20210617-8 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-06-17 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little Gravel River Road | 0 | 44368 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929620210617-8Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting929620210617-8Excavator - 36 ton- After Jan 10101469.6Inv# 135-R03 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9296 | 20210617-8 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-17 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little Gravel River Road | 0 | 44368 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929620210617-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting929620210617-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9296 | 20210617-8 | 53510412 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2021-06-17 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little Gravel River Road | 0 | 44368 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929620210617-8Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting929620210617-8Light Truck w/ Tandum Trailer- After Jan 101337.5Inv# 135-R03 | [5 empty] | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9296 | 20210617-8 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-17 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little Gravel River Road | 0 | 44368 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929620210617-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting929620210617-8Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9296 | 20210617-8 | 53510412 | Access | 0 | Labourer - General - After Jan 10 | 60 | 7 | HR |  |  | 60 | 0 | 420 | 54.6 | 474.6 | 2021-06-17 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little Gravel River Road | 0 | 44368 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting929620210617-8Labourer - General - After Jan 107420 | Corbiere and Sons Contracting929620210617-8Labourer - General - After Jan 107420Inv# 135-R03 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9301 | 20210618-8 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-06-18 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little Gravel River Road | 0 | 44370 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting930120210618-8Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting930120210618-8Excavator - 36 ton- After Jan 10101469.6Inv# 135-R03 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9301 | 20210618-8 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-18 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little Gravel River Road | 0 | 44370 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting930120210618-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting930120210618-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9301 | 20210618-8 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-06-18 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little Gravel River Road | 0 | 44370 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting930120210618-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting930120210618-8Light Truck - Pick up- After Jan 102487.5Inv# 135-R03 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9301 | 20210618-8 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-18 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little Gravel River Road | 0 | 44370 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting930120210618-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting930120210618-8Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9301 | 20210618-8 | 53510412 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-06-18 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance work across Little Gravel River Road | 4 | B194-B216 | Little Gravel River Road | 0 | 44370 |  | 36 | 44370 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting930120210618-8Labourer - General - After Jan 106360 | Corbiere and Sons Contracting930120210618-8Labourer - General - After Jan 106360Inv# 135-R03 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9349 | 20210621-5 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-06-21 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Road work continuing on Little Gravle River Road from B196-B206 | 4 | B194-B206 | Little Gravel River Road | 0 | 44373 | [9 empty] | 04 | Corbiere and Sons Contracting934920210621-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting934920210621-5Excavator - 36 ton- After Jan 10101469.6Inv# 135-R03 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9349 | 20210621-5 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-21 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Road work continuing on Little Gravle River Road from B196-B206 | 4 | B194-B206 | Little Gravel River Road | 0 | 44373 | [9 empty] | 04 | Corbiere and Sons Contracting934920210621-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting934920210621-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9349 | 20210621-5 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-06-21 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Road work continuing on Little Gravle River Road from B196-B206 | 4 | B194-B206 | Little Gravel River Road | 0 | 44373 | [9 empty] | 04 | Corbiere and Sons Contracting934920210621-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting934920210621-5Light Truck - Pick up- After Jan 102487.5Inv# 135-R03 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9349 | 20210621-5 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-21 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Road work continuing on Little Gravle River Road from B196-B206 | 4 | B194-B206 | Little Gravel River Road | 0 | 44373 | [9 empty] | 04 | Corbiere and Sons Contracting934920210621-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting934920210621-5Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9349 | 20210621-5 | 53510412 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2021-06-21 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Road work continuing on Little Gravle River Road from B196-B206 | 4 | B194-B206 | Little Gravel River Road | 0 | 44373 | [9 empty] | 04 | Corbiere and Sons Contracting934920210621-5Labourer - General - After Jan 102120 | Corbiere and Sons Contracting934920210621-5Labourer - General - After Jan 102120Inv# 135-R03 | [5 empty] | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9350 | 20210622-6 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-06-22 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B196 | 4 | B194-B196 | Little Gravel River Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting935020210622-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting935020210622-6Excavator - 36 ton- After Jan 10101469.6Inv# 135-R03 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9350 | 20210622-6 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-22 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B196 | 4 | B194-B196 | Little Gravel River Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting935020210622-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting935020210622-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9350 | 20210622-6 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-22 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B196 | 4 | B194-B196 | Little Gravel River Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting935020210622-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting935020210622-6Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9350 | 20210622-6 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-22 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from B194-B196 | 4 | B194-B196 | Little Gravel River Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting935020210622-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting935020210622-6Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9351 | 20210623-5 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-06-23 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Gurney from B187-B193 | 3 | B187-B193 | Gurney Lake Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting935120210623-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting935120210623-5Excavator - 36 ton- After Jan 10101469.6Inv# 135-R03 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9351 | 20210623-5 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-23 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Gurney from B187-B193 | 3 | B187-B193 | Gurney Lake Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting935120210623-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting935120210623-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9351 | 20210623-5 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-23 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Gurney from B187-B193 | 3 | B187-B193 | Gurney Lake Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting935120210623-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting935120210623-5Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9351 | 20210623-5 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-23 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Gurney from B187-B193 | 3 | B187-B193 | Gurney Lake Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting935120210623-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting935120210623-5Operator - Principle - After Jan 1011825Inv# 135-R03 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9352 | 20210624-5 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-06-24 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Cooks Lake Road from C085-C088 | 5 | C085-C088 | Cooks Lake Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935220210624-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting935220210624-5Excavator - 36 ton- After Jan 10101469.6Inv# 135-R03 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9352 | 20210624-5 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-06-24 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Cooks Lake Road from C085-C088 | 5 | C085-C088 | Cooks Lake Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935220210624-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting935220210624-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv# 135-R03 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9352 | 20210624-5 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-24 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Cooks Lake Road from C085-C088 | 5 | C085-C088 | Cooks Lake Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935220210624-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting935220210624-5Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9352 | 20210624-5 | 53510512 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-06-24 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Cooks Lake Road from C085-C088 | 5 | C085-C088 | Cooks Lake Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935220210624-5Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting935220210624-5Tractor Trailer - 60 Ton- After Jan 104489.56Inv# 135-R03 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9352 | 20210624-5 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-06-24 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Cooks Lake Road from C085-C088 | 5 | C085-C088 | Cooks Lake Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935220210624-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting935220210624-5Operator - Principle - After Jan 1012900Inv# 135-R03 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9352 | 20210624-5 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-06-24 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Cooks Lake Road from C085-C088 | 5 | C085-C088 | Cooks Lake Road | 0 | 44373 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935220210624-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting935220210624-5Driver - AZ - After Jan 104280Inv# 135-R03 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9353 | 20210625-5 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2021-06-25 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Cooks Lake road and ex demobbed | 5 | C085-C088 | Cooks Lake Road | 0 | 44374 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935320210625-5Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting935320210625-5Excavator - 36 ton- After Jan 102293.92Inv# 135-R03 | [5 empty] | 1 | 293.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9353 | 20210625-5 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-06-25 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Cooks Lake road and ex demobbed | 5 | C085-C088 | Cooks Lake Road | 0 | 44374 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935320210625-5Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting935320210625-5Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv# 135-R03 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9353 | 20210625-5 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-25 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Cooks Lake road and ex demobbed | 5 | C085-C088 | Cooks Lake Road | 0 | 44374 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935320210625-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting935320210625-5Light Truck - Pick up- After Jan 101243.75Inv# 135-R03 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9353 | 20210625-5 | 53510512 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-06-25 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Cooks Lake road and ex demobbed | 5 | C085-C088 | Cooks Lake Road | 0 | 44374 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935320210625-5Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting935320210625-5Tractor Trailer - 60 Ton- After Jan 104489.56Inv# 135-R03 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9353 | 20210625-5 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-06-25 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Cooks Lake road and ex demobbed | 5 | C085-C088 | Cooks Lake Road | 0 | 44374 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935320210625-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting935320210625-5Operator - Principle - After Jan 105375Inv# 135-R03 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9353 | 20210625-5 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-06-25 | 0 | Inv# 135-R03 | 44382 | 154 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work completed on Cooks Lake road and ex demobbed | 5 | C085-C088 | Cooks Lake Road | 0 | 44374 |  | 37 | 44375 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting935320210625-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting935320210625-5Driver - AZ - After Jan 104280Inv# 135-R03 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9530 | 20210629-6 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2021-06-29 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader mobilized to Santoy Lake to fix spot at KM3.5 | 6 | C159 | Santoy Lake | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting953020210629-6Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting953020210629-6Grader - Cat 12 to 14 or equal- After Jan 107888.86Inv#139 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9530 | 20210629-6 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-29 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader mobilized to Santoy Lake to fix spot at KM3.5 | 6 | C159 | Santoy Lake | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting953020210629-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting953020210629-6Light Truck - Pick up- After Jan 101243.75Inv#139 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9530 | 20210629-6 | 53510612 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 9 | Dynamic | 91.79 | 0 |  |  | 1101.51 | 143.1963 | 1244.7063 | 2021-06-29 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader mobilized to Santoy Lake to fix spot at KM3.5 | 6 | C159 | Santoy Lake | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting953020210629-6Tractor Trailer - 60 Ton- After Jan 1091101.51 | Corbiere and Sons Contracting953020210629-6Tractor Trailer - 60 Ton- After Jan 1091101.51Inv#139 | [5 empty] | 1 | 1101.51 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9530 | 20210629-6 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-29 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader mobilized to Santoy Lake to fix spot at KM3.5 | 6 | C159 | Santoy Lake | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting953020210629-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting953020210629-6Operator - Principle - After Jan 1011825Inv#139 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9530 | 20210629-6 | 53510612 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 9 | HR |  |  | 70 | 0 | 630 | 81.9 | 711.9 | 2021-06-29 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader mobilized to Santoy Lake to fix spot at KM3.5 | 6 | C159 | Santoy Lake | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting953020210629-6Driver - AZ - After Jan 109630 | Corbiere and Sons Contracting953020210629-6Driver - AZ - After Jan 109630Inv#139 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9533 | 20210630-6 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-06-30 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex mob into to Antler Lake Road to fix hill from KM6.5 | 5 | C050-C069 | Antler Lake Road | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting953320210630-6Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting953320210630-6Excavator - 36 ton- After Jan 1081175.68Inv#139 | [5 empty] | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9533 | 20210630-6 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-06-30 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex mob into to Antler Lake Road to fix hill from KM6.5 | 5 | C050-C069 | Antler Lake Road | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting953320210630-6Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting953320210630-6Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#139 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9533 | 20210630-6 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-06-30 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex mob into to Antler Lake Road to fix hill from KM6.5 | 5 | C050-C069 | Antler Lake Road | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting953320210630-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting953320210630-6Light Truck - Pick up- After Jan 101243.75Inv#139 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9533 | 20210630-6 | 53510512 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 7 | Dynamic | 91.79 | 0 |  |  | 856.73 | 111.3749 | 968.1049 | 2021-06-30 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex mob into to Antler Lake Road to fix hill from KM6.5 | 5 | C050-C069 | Antler Lake Road | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting953320210630-6Tractor Trailer - 60 Ton- After Jan 107856.73 | Corbiere and Sons Contracting953320210630-6Tractor Trailer - 60 Ton- After Jan 107856.73Inv#139 | [5 empty] | 1 | 856.73 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9533 | 20210630-6 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-06-30 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex mob into to Antler Lake Road to fix hill from KM6.5 | 5 | C050-C069 | Antler Lake Road | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting953320210630-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting953320210630-6Operator - Principle - After Jan 1011825Inv#139 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9533 | 20210630-6 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-06-30 | 0 | Inv#139 | 44401 | 157 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex mob into to Antler Lake Road to fix hill from KM6.5 | 5 | C050-C069 | Antler Lake Road | 0 | 44384 |  | 37 | 44398 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting953320210630-6Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting953320210630-6Driver - AZ - After Jan 107490Inv#139 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting964520210801-3Excavator - 30 ton- After Jan 1081107.6Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting964520210801-3Excavator - 30 ton- After Jan 1081107.6Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting964520210801-3Excavator - 36 ton- After Jan 1081175.68Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting964520210801-3Excavator - 36 ton- After Jan 1081175.68Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting964520210801-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting964520210801-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting964520210801-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting964520210801-3Light Truck - Pick up- After Jan 104975Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Marooka- After Jan 105723 | Corbiere and Sons Contracting964520210801-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 723 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting964520210801-3Rock Truck - 30 Ton- After Jan 1081104.4Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting964520210801-3Rock Truck - 30 Ton- After Jan 1081104.4Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Foreman111045 | Corbiere and Sons Contracting964520210801-3Foreman111045Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3L.O.A.81680 | Corbiere and Sons Contracting964520210801-3L.O.A.81680Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 66 | HR |  |  | 75 | 0 | 4950 | 643.5 | 5593.5 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Operator - Principle - After Jan 10664950 | Corbiere and Sons Contracting964520210801-3Operator - Principle - After Jan 10664950Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9645 | 20210801-3 | 53511002 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-01 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM39 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44411 |  | 37 | 44418 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting964520210801-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting964520210801-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting966520210802-3Excavator - 30 ton- After Jan 1091246.05Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting966520210802-3Excavator - 30 ton- After Jan 1091246.05Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting966520210802-3Excavator - 30 ton- After Jan 1091246.05Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting966520210802-3Excavator - 36 ton- After Jan 1091322.64Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting966520210802-3Excavator - 36 ton- After Jan 1091322.64Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting966520210802-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting966520210802-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting966520210802-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting966520210802-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting966520210802-3Light Truck - Pick up- After Jan 1051218.75Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Marooka- After Jan 105723 | Corbiere and Sons Contracting966520210802-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 723 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting966520210802-3Rock Truck - 30 Ton- After Jan 1091242.45Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1242.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Foreman121140 | Corbiere and Sons Contracting966520210802-3Foreman121140Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3L.O.A.81680 | Corbiere and Sons Contracting966520210802-3L.O.A.81680Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 66 | HR |  |  | 75 | 0 | 4950 | 643.5 | 5593.5 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Operator - Principle - After Jan 10664950 | Corbiere and Sons Contracting966520210802-3Operator - Principle - After Jan 10664950Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9665 | 20210802-3 | 53511002 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-02 | 0 | Inv#142-R01 | 44427 | 159 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 44412 |  | 43 | 44413 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting966520210802-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting966520210802-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-Access | WF10-Access |  | 1 | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9738 | 20210816-4 | 53510512 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2021-08-16 | 0 | INV #148 | 44461 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of grader and then working on roads across Antler | 5 | C050-C069 | Antler Lake | 0 | 44438 |  | 36 | 44460 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting973820210816-4Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting973820210816-4Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #148 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9738 | 20210816-4 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-16 | 0 | INV #148 | 44461 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of grader and then working on roads across Antler | 5 | C050-C069 | Antler Lake | 0 | 44438 |  | 36 | 44460 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting973820210816-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting973820210816-4Light Truck - Pick up- After Jan 101243.75INV #148 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9738 | 20210816-4 | 53510512 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 7 | Dynamic | 91.79 | 0 |  |  | 856.73 | 111.3749 | 968.1049 | 2021-08-16 | 0 | INV #148 | 44461 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of grader and then working on roads across Antler | 5 | C050-C069 | Antler Lake | 0 | 44438 |  | 36 | 44460 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting973820210816-4Tractor Trailer - 60 Ton- After Jan 107856.73 | Corbiere and Sons Contracting973820210816-4Tractor Trailer - 60 Ton- After Jan 107856.73INV #148 | [5 empty] | 1 | 856.73 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9738 | 20210816-4 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-16 | 0 | INV #148 | 44461 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of grader and then working on roads across Antler | 5 | C050-C069 | Antler Lake | 0 | 44438 |  | 36 | 44460 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting973820210816-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting973820210816-4Operator - Principle - After Jan 1011825INV #148 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9738 | 20210816-4 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-08-16 | 0 | INV #148 | 44461 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of grader and then working on roads across Antler | 5 | C050-C069 | Antler Lake | 0 | 44438 |  | 36 | 44460 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting973820210816-4Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting973820210816-4Driver - AZ - After Jan 107490INV #148 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9739 | 20210817-4 | 53510512 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-08-17 | 0 | INV #148 | 44461 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Whitesands access road | 5 | C070-C075 | White Sand | 0 | 44438 |  | 36 | 44460 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting973920210817-4Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting973920210817-4Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #148 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9739 | 20210817-4 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-17 | 0 | INV #148 | 44461 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Whitesands access road | 5 | C070-C075 | White Sand | 0 | 44438 |  | 36 | 44460 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting973920210817-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting973920210817-4Light Truck - Pick up- After Jan 101243.75INV #148 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9739 | 20210817-4 | 53510512 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4.5 | Dynamic | 91.79 | 0 |  |  | 550.755 | 71.5982 | 622.3532 | 2021-08-17 | 0 | INV #148 | 44461 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Whitesands access road | 5 | C070-C075 | White Sand | 0 | 44438 |  | 36 | 44460 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting973920210817-4Tractor Trailer - 60 Ton- After Jan 104.5550.755 | Corbiere and Sons Contracting973920210817-4Tractor Trailer - 60 Ton- After Jan 104.5550.755INV #148 | [5 empty] | 1 | 550.755 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9739 | 20210817-4 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-08-17 | 0 | INV #148 | 44461 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Whitesands access road | 5 | C070-C075 | White Sand | 0 | 44438 |  | 36 | 44460 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting973920210817-4Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting973920210817-4Operator - Principle - After Jan 107525INV #148 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 9739 | 20210817-4 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4.5 | HR |  |  | 70 | 0 | 315 | 40.95 | 355.95 | 2021-08-17 | 0 | INV #148 | 44461 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Whitesands access road | 5 | C070-C075 | White Sand | 0 | 44438 |  | 36 | 44460 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting973920210817-4Driver - AZ - After Jan 104.5315 | Corbiere and Sons Contracting973920210817-4Driver - AZ - After Jan 104.5315INV #148 | [5 empty] | 1 | 315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10001 | 20210922-13 | 53510312 | Access | 0 | Loader JD 744 to 844 or equal | 162 | 1 | HR | 121.5 | 0 |  |  | 162 | 21.06 | 183.06 | 2021-09-22 | 0 | INV #149 | 44477 | 164 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Labourers loaded ashpalt and delivere dto Fire Hill and filled potholes, raked and packed from highway to ROW | 3 | B126-B127 | Fire Hill Road | 0 | 44469 |  | 36 | 44471 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1000120210922-13Loader JD 744 to 844 or equal1162 | Corbiere and Sons Contracting1000120210922-13Loader JD 744 to 844 or equal1162INV #149 | [5 empty] | 1 | 162 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10001 | 20210922-13 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-22 | 0 | INV #149 | 44477 | 164 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Labourers loaded ashpalt and delivere dto Fire Hill and filled potholes, raked and packed from highway to ROW | 3 | B126-B127 | Fire Hill Road | 0 | 44469 |  | 36 | 44471 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1000120210922-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1000120210922-13Light Truck - Pick up- After Jan 101243.75INV #149 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10001 | 20210922-13 | 53510312 | Access | 0 | Labourer - General - After Jan 10 | 60 | 16 | HR |  |  | 60 | 0 | 960 | 124.8 | 1084.8 | 2021-09-22 | 0 | INV #149 | 44477 | 164 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Labourers loaded ashpalt and delivere dto Fire Hill and filled potholes, raked and packed from highway to ROW | 3 | B126-B127 | Fire Hill Road | 0 | 44469 |  | 36 | 44471 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1000120210922-13Labourer - General - After Jan 1016960 | Corbiere and Sons Contracting1000120210922-13Labourer - General - After Jan 1016960INV #149 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10221 | 20211008-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-08 | 0 | INV #151 | 44490 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | WF6 | WF5 | 0 | 44484 |  | 58 | 44485 | [6 empty] | 06 | Corbiere and Sons Contracting1022120211008-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1022120211008-3Light Truck - Pick up- After Jan 101243.75INV #151 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10221 | 20211008-3 | 53510612 | Access | 0 | Safety Advisor | 85 | 7 | HR |  |  | 85 | 0 | 595 | 77.35 | 672.35 | 2021-10-08 | 0 | INV #151 | 44490 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | WF6 | WF5 | 0 | 44484 |  | 58 | 44485 | [6 empty] | 06 | Corbiere and Sons Contracting1022120211008-3Safety Advisor7595 | Corbiere and Sons Contracting1022120211008-3Safety Advisor7595INV #151 | [5 empty] | 1 | 595 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10221 | 20211008-3 | 53510612 | Access | 0 | L.O.A. | 210 | 0.5 | DAY |  |  |  | 0 | 105 | 13.65 | 118.65 | 2021-10-08 | 0 | INV #151 | 44490 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | WF6 | WF5 | 0 | 44484 |  | 58 | 44485 | [6 empty] | 06 | Corbiere and Sons Contracting1022120211008-3L.O.A.0.5105 | Corbiere and Sons Contracting1022120211008-3L.O.A.0.5105INV #151 | [5 empty] | 1 | 105 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10255 | 20211014-4 | 53511007 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-10-14 | 0 | INV #151 | 44490 | 168 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  | This CC may need to be changed to the WF11 CC for mob demob |  | Approved |  |  | Float demobbed 330 from WF11 after receiving notice from Betty | 6 | F118-F127 | Hensen Road | 0 | 44487 |  | 58 | 44488 | [6 empty] | 10 | Corbiere and Sons Contracting1025520211014-4Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1025520211014-4Tractor Trailer - 60 Ton- After Jan 10121468.68INV #151 |  | WF10-Access | WF10-Access |  | 1 | 1 | 1468.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10255 | 20211014-4 | 53511007 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-14 | 0 | INV #151 | 44490 | 168 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  | This CC may need to be changed to the WF11 CC for mob demob |  | Approved |  |  | Float demobbed 330 from WF11 after receiving notice from Betty | 6 | F118-F127 | Hensen Road | 0 | 44487 |  | 58 | 44488 | [6 empty] | 10 | Corbiere and Sons Contracting1025520211014-4L.O.A.1210 | Corbiere and Sons Contracting1025520211014-4L.O.A.1210INV #151 |  | WF10-Access | WF10-Access |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10255 | 20211014-4 | 53511007 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-10-14 | 0 | INV #151 | 44490 | 168 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  | This CC may need to be changed to the WF11 CC for mob demob |  | Approved |  |  | Float demobbed 330 from WF11 after receiving notice from Betty | 6 | F118-F127 | Hensen Road | 0 | 44487 |  | 58 | 44488 | [6 empty] | 10 | Corbiere and Sons Contracting1025520211014-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1025520211014-4Driver - AZ - After Jan 1012840INV #151 |  | WF10-Access | WF10-Access |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10332 | 20211025-3 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-25 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Cavers - Widening Road for Crane Access - Shawn dropped Western Star at Cavers at end of day and then carried on to Marathon | 5 | C028-C029 | Cavers | 0 | 44501 |  | 36 | 44502 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1033220211025-3Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1033220211025-3Excavator - 36 ton- After Jan 1071028.72INV #155 | [5 empty] | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10332 | 20211025-3 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-25 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Cavers - Widening Road for Crane Access - Shawn dropped Western Star at Cavers at end of day and then carried on to Marathon | 5 | C028-C029 | Cavers | 0 | 44501 |  | 36 | 44502 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1033220211025-3Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1033220211025-3Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #155 | [5 empty] | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10332 | 20211025-3 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-25 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Cavers - Widening Road for Crane Access - Shawn dropped Western Star at Cavers at end of day and then carried on to Marathon | 5 | C028-C029 | Cavers | 0 | 44501 |  | 36 | 44502 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1033220211025-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1033220211025-3Light Truck - Pick up- After Jan 101243.75INV #155 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10332 | 20211025-3 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-25 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Cavers - Widening Road for Crane Access - Shawn dropped Western Star at Cavers at end of day and then carried on to Marathon | 5 | C028-C029 | Cavers | 0 | 44501 |  | 36 | 44502 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1033220211025-3L.O.A.1210 | Corbiere and Sons Contracting1033220211025-3L.O.A.1210INV #155 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10332 | 20211025-3 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-10-25 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Cavers - Widening Road for Crane Access - Shawn dropped Western Star at Cavers at end of day and then carried on to Marathon | 5 | C028-C029 | Cavers | 0 | 44501 |  | 36 | 44502 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1033220211025-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1033220211025-3Operator - Principle - After Jan 1011825INV #155 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10332 | 20211025-3 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-10-25 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Cavers - Widening Road for Crane Access - Shawn dropped Western Star at Cavers at end of day and then carried on to Marathon | 5 | C028-C029 | Cavers | 0 | 44501 |  | 36 | 44502 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1033220211025-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1033220211025-3Driver - AZ - After Jan 103210INV #155 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10608 | 20211027-4 | 53510212 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2021-10-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex moved to spread recycled ashpalt and reestablish ditches - Invoice for material attached. | 2 | B054 | Lofty Davies | 0 | 44538 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1060820211027-4Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting1060820211027-4Excavator - 30 ton- After Jan 102276.9INV# 157 | [5 empty] | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10608 | 20211027-4 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-10-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex moved to spread recycled ashpalt and reestablish ditches - Invoice for material attached. | 2 | B054 | Lofty Davies | 0 | 44538 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1060820211027-4Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting1060820211027-4Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV# 157 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10608 | 20211027-4 | 53510212 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 2 | Dynamic | 41.4 | 0 |  |  | 110.4 | 14.352 | 124.752 | 2021-10-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex moved to spread recycled ashpalt and reestablish ditches - Invoice for material attached. | 2 | B054 | Lofty Davies | 0 | 44538 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1060820211027-4Dump - Triaxle- After Jan 102110.4 | Corbiere and Sons Contracting1060820211027-4Dump - Triaxle- After Jan 102110.4INV# 157 | [5 empty] | 1 | 110.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10608 | 20211027-4 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex moved to spread recycled ashpalt and reestablish ditches - Invoice for material attached. | 2 | B054 | Lofty Davies | 0 | 44538 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1060820211027-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1060820211027-4Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10608 | 20211027-4 | 53510212 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-10-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex moved to spread recycled ashpalt and reestablish ditches - Invoice for material attached. | 2 | B054 | Lofty Davies | 0 | 44538 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1060820211027-4Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1060820211027-4Tractor Trailer - 60 Ton- After Jan 106734.34INV# 157 | [5 empty] | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10608 | 20211027-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-10-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex moved to spread recycled ashpalt and reestablish ditches - Invoice for material attached. | 2 | B054 | Lofty Davies | 0 | 44538 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1060820211027-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1060820211027-4Operator - Principle - After Jan 106450INV# 157 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10608 | 20211027-4 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-10-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex moved to spread recycled ashpalt and reestablish ditches - Invoice for material attached. | 2 | B054 | Lofty Davies | 0 | 44538 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1060820211027-4Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1060820211027-4Driver - AZ - After Jan 106420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10608 | 20211027-4 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-10-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex moved to spread recycled ashpalt and reestablish ditches - Invoice for material attached. | 2 | B054 | Lofty Davies | 0 | 44538 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1060820211027-4Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting1060820211027-4Driver - AZ - After Jan 102140INV# 157 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10608 | 20211027-4 | 53510212 | Access | 0 | 3rd Party Charges | 1 | 357.28 | unit |  |  |  |  | 357.28 | 46.4464 | 403.7264 | 2021-10-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex moved to spread recycled ashpalt and reestablish ditches - Invoice for material attached. | 2 | B054 | Lofty Davies | 0 | 44538 |  | 36 | 44540 | 489 | Recycled Ashpalt |  |  |  | Mike Lecocq | 02 | Corbiere and Sons Contracting1060820211027-43rd Party Charges357.28357.28 | Corbiere and Sons Contracting1060820211027-43rd Party Charges357.28357.28INV# 157 | [5 empty] | 1 | 357.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10706 | 20211119-3 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-11-19 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed Ex into Gurney Lake Road do to winter maintenance | 4 | B187-B201 | Gurney Lake Road | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070620211119-3Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1070620211119-3Tractor Trailer - 60 Ton- After Jan 103367.17INV# 157 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10706 | 20211119-3 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-11-19 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed Ex into Gurney Lake Road do to winter maintenance | 4 | B187-B201 | Gurney Lake Road | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070620211119-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1070620211119-3Driver - AZ - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10707 | 20211120-3 | 53510411 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-20 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance from B194-B200 | 4 | B187-B201 | Gurney Lake Road | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070720211120-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1070720211120-3Excavator - 36 ton- After Jan 10101469.6INV# 157 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10707 | 20211120-3 | 53510411 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-20 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance from B194-B200 | 4 | B187-B201 | Gurney Lake Road | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070720211120-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1070720211120-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10707 | 20211120-3 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-20 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance from B194-B200 | 4 | B187-B201 | Gurney Lake Road | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070720211120-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1070720211120-3Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10707 | 20211120-3 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-20 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance from B194-B200 | 4 | B187-B201 | Gurney Lake Road | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070720211120-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1070720211120-3Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10708 | 20211121-3 | 53510411 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-21 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070820211121-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1070820211121-3Excavator - 36 ton- After Jan 10101469.6INV# 157 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10708 | 20211121-3 | 53510411 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-21 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070820211121-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1070820211121-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10708 | 20211121-3 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-21 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070820211121-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1070820211121-3Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10708 | 20211121-3 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-21 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070820211121-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1070820211121-3Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10563 | 20211122-4 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-11-22 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056320211122-4Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting1056320211122-4Excavator - 30 ton- After Jan 107969.15INV #155 | [5 empty] | 1 | 969.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10563 | 20211122-4 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-11-22 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056320211122-4Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1056320211122-4Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #155 | [5 empty] | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10563 | 20211122-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-22 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056320211122-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1056320211122-4Light Truck - Pick up- After Jan 101243.75INV #155 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10563 | 20211122-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-11-22 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056320211122-4Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1056320211122-4Tractor Trailer - 60 Ton- After Jan 103367.17INV #155 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10563 | 20211122-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-22 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056320211122-4L.O.A.1210 | Corbiere and Sons Contracting1056320211122-4L.O.A.1210INV #155 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10563 | 20211122-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-22 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056320211122-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1056320211122-4Operator - Principle - After Jan 1011825INV #155 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10563 | 20211122-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-11-22 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056320211122-4Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1056320211122-4Driver - AZ - After Jan 103210INV #155 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10709 | 20211122-5 | 53510411 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-22 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070920211122-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1070920211122-5Excavator - 36 ton- After Jan 10101469.6INV# 157 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10709 | 20211122-5 | 53510411 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 0 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-22 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070920211122-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1070920211122-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10709 | 20211122-5 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-22 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070920211122-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1070920211122-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10709 | 20211122-5 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-11-22 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1070920211122-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1070920211122-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10565 | 20211123-4 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-11-23 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road - D6 mobilized | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056520211123-4Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1056520211123-4Excavator - 30 ton- After Jan 10101384.5INV #155 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10565 | 20211123-4 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-23 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road - D6 mobilized | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056520211123-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1056520211123-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #155 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10565 | 20211123-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-23 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road - D6 mobilized | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056520211123-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1056520211123-4Light Truck - Pick up- After Jan 101243.75INV #155 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10565 | 20211123-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-11-23 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road - D6 mobilized | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056520211123-4Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1056520211123-4Tractor Trailer - 60 Ton- After Jan 103367.17INV #155 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10565 | 20211123-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-23 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road - D6 mobilized | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056520211123-4L.O.A.1210 | Corbiere and Sons Contracting1056520211123-4L.O.A.1210INV #155 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10565 | 20211123-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-23 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road - D6 mobilized | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056520211123-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1056520211123-4Operator - Principle - After Jan 1011825INV #155 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10565 | 20211123-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-11-23 | 0 | INV #155 | 44532 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance for stringers on Cooks Lake Road - D6 mobilized | 5 | C076-C116 | Cook Lake | 0 | 44525 |  | 36 | 44526 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1056520211123-4Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1056520211123-4Driver - AZ - After Jan 103210INV #155 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10710 | 20211123-5 | 53510411 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-23 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071020211123-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1071020211123-5Excavator - 36 ton- After Jan 10101469.6INV# 157 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10710 | 20211123-5 | 53510411 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 0 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-23 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071020211123-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1071020211123-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10710 | 20211123-5 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-23 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071020211123-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1071020211123-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10710 | 20211123-5 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-11-23 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071020211123-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1071020211123-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10571 | 20211124-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057120211124-5Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1057120211124-5Dozer D6 or equal- After Jan 104525.92INV# 157 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10571 | 20211124-5 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057120211124-5Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1057120211124-5Excavator - 30 ton- After Jan 10101384.5INV# 157 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10571 | 20211124-5 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057120211124-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1057120211124-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10571 | 20211124-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057120211124-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1057120211124-5Light Truck - Pick up- After Jan 102487.5INV# 157 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10571 | 20211124-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057120211124-5L.O.A.2420 | Corbiere and Sons Contracting1057120211124-5L.O.A.2420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10571 | 20211124-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057120211124-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1057120211124-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10571 | 20211124-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057120211124-5Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1057120211124-5Operator - Principle - After Jan 104300INV# 157 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10571 | 20211124-5 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057120211124-5Labourer - General - After Jan 105300 | Corbiere and Sons Contracting1057120211124-5Labourer - General - After Jan 105300INV# 157 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10711 | 20211124-6 | 53510411 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071120211124-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1071120211124-6Excavator - 36 ton- After Jan 10101469.6INV# 157 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10711 | 20211124-6 | 53510411 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 0 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071120211124-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1071120211124-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10711 | 20211124-6 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071120211124-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1071120211124-6Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10711 | 20211124-6 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-11-24 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071120211124-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1071120211124-6Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11422 | 20211124-7 | 53510606 | Access | 0 | 3rd Party Charges | 1 | 1322.4 | unit |  |  |  |  | 1322.4 | 171.912 | 1494.312 | 2021-11-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Flagging Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 44592 |  | 36 | 44604 | no number provided | Dead Horse Creek |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1142220211124-73rd Party Charges1322.41322.4 | Corbiere and Sons Contracting1142220211124-73rd Party Charges1322.41322.4INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1322.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10573 | 20211125-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew - Grader Mobilized | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057320211125-4Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1057320211125-4Dozer D6 or equal- After Jan 104525.92INV# 157 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10573 | 20211125-4 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew - Grader Mobilized | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057320211125-4Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1057320211125-4Excavator - 30 ton- After Jan 10101384.5INV# 157 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10573 | 20211125-4 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew - Grader Mobilized | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057320211125-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1057320211125-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10573 | 20211125-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew - Grader Mobilized | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057320211125-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1057320211125-4Light Truck - Pick up- After Jan 102487.5INV# 157 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10573 | 20211125-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew - Grader Mobilized | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057320211125-4Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1057320211125-4Tractor Trailer - 60 Ton- After Jan 10222692.58INV# 157 | [5 empty] | 1 | 2692.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10573 | 20211125-4 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew - Grader Mobilized | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057320211125-4L.O.A.3630 | Corbiere and Sons Contracting1057320211125-4L.O.A.3630INV# 157 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10573 | 20211125-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew - Grader Mobilized | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057320211125-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1057320211125-4Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10573 | 20211125-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew - Grader Mobilized | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057320211125-4Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1057320211125-4Operator - Principle - After Jan 104300INV# 157 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10573 | 20211125-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew - Grader Mobilized | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057320211125-4Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1057320211125-4Driver - AZ - After Jan 10221540INV# 157 | [5 empty] | 1 | 1540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10573 | 20211125-4 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on Winter Road Maintenance on Cooks for Stringing Crew - Grader Mobilized | 5 | C076-C116 | Cook Lake | 0 | 44529 |  | 36 | 44532 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1057320211125-4Labourer - General - After Jan 105300 | Corbiere and Sons Contracting1057320211125-4Labourer - General - After Jan 105300INV# 157 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10712 | 20211125-5 | 53510411 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071220211125-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1071220211125-5Excavator - 36 ton- After Jan 10101469.6INV# 157 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10712 | 20211125-5 | 53510411 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 0 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071220211125-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1071220211125-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10712 | 20211125-5 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071220211125-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1071220211125-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10712 | 20211125-5 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-11-25 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071220211125-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1071220211125-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10612 | 20211126-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-11-26 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44537 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1061220211126-5Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1061220211126-5Grader - Cat 12 to 14 or equal- After Jan 105634.9INV# 157 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10612 | 20211126-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-26 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44537 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1061220211126-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1061220211126-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10612 | 20211126-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-26 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44537 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1061220211126-5L.O.A.1210 | Corbiere and Sons Contracting1061220211126-5L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10612 | 20211126-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-26 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44537 |  | 36 | 44540 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1061220211126-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1061220211126-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10613 | 20211126-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-11-26 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup with plow and sander working at Antler Lake Road entrance | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 36 | 44539 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1061320211126-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1061320211126-6Pickup w/ plow and sander4320INV# 157 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10613 | 20211126-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-11-26 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup with plow and sander working at Antler Lake Road entrance | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 36 | 44539 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1061320211126-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1061320211126-6Operator - Principle - After Jan 104300INV# 157 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10713 | 20211126-7 | 53510411 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-26 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071320211126-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1071320211126-7Excavator - 36 ton- After Jan 10101469.6INV# 157 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10713 | 20211126-7 | 53510411 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 0 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-26 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071320211126-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1071320211126-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10713 | 20211126-7 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-26 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071320211126-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1071320211126-7Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10713 | 20211126-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-11-26 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from B194-B200 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071320211126-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1071320211126-7Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11423 | 20211126-8 | 53510606 | Access | 0 | 3rd Party Charges | 1 | 1322.4 | unit |  |  |  |  | 1322.4 | 171.912 | 1494.312 | 2021-11-26 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Flagging Lake A | 6 | C130-C151 | Lake A | 0 | 44592 |  | 36 | 44604 | no number provided | Flagging done by Best Towing - Flagging Lake A |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1142320211126-83rd Party Charges1322.41322.4 | Corbiere and Sons Contracting1142320211126-83rd Party Charges1322.41322.4INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1322.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10616 | 20211127-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-11-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1061620211127-5Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1061620211127-5Grader - Cat 12 to 14 or equal- After Jan 105634.9INV# 157 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10616 | 20211127-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1061620211127-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1061620211127-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10616 | 20211127-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1061620211127-5L.O.A.1210 | Corbiere and Sons Contracting1061620211127-5L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10616 | 20211127-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-11-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1061620211127-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1061620211127-5Operator - Principle - After Jan 106450INV# 157 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10617 | 20211127-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-11-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Antler Lake Road | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1061720211127-6Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1061720211127-6Grader - Cat 12 to 14 or equal- After Jan 104507.92INV# 157 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10617 | 20211127-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-11-27 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Antler Lake Road | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1061720211127-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1061720211127-6Operator - Principle - After Jan 105375INV# 157 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10715 | 20211128-10 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | G&G moved Ex from Deadhorse to Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1071520211128-10Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting1071520211128-10Tractor Trailer - 60 Ton- After Jan 102244.78INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10715 | 20211128-10 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | G&G moved Ex from Deadhorse to Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1071520211128-10Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting1071520211128-10Driver - AZ - After Jan 102140INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10716 | 20211128-11 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | G&G Float moved DZ and Grader into Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1071620211128-11Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1071620211128-11Tractor Trailer - 60 Ton- After Jan 104489.56INV# 157 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10716 | 20211128-11 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | G&G Float moved DZ and Grader into Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1071620211128-11Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1071620211128-11Driver - AZ - After Jan 104280INV# 157 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10622 | 20211128-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062220211128-6Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1062220211128-6Grader - Cat 12 to 14 or equal- After Jan 105634.9INV# 157 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10622 | 20211128-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062220211128-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1062220211128-6Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10622 | 20211128-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062220211128-6L.O.A.1210 | Corbiere and Sons Contracting1062220211128-6L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10622 | 20211128-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062220211128-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1062220211128-6Operator - Principle - After Jan 106450INV# 157 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10623 | 20211128-7 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Antler Lake Road - DZ working for part of day | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062320211128-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1062320211128-7Dozer D6 or equal- After Jan 104525.92INV# 157 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10623 | 20211128-7 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Antler Lake Road - DZ working for part of day | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062320211128-7Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1062320211128-7Grader - Cat 12 to 14 or equal- After Jan 104507.92INV# 157 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10623 | 20211128-7 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Antler Lake Road - DZ working for part of day | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062320211128-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1062320211128-7Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10623 | 20211128-7 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Antler Lake Road - DZ working for part of day | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062320211128-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1062320211128-7Operator - Principle - After Jan 105375INV# 157 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10623 | 20211128-7 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Antler Lake Road - DZ working for part of day | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062320211128-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1062320211128-7Operator - Principle - After Jan 105375INV# 157 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10624 | 20211128-8 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Gravel River Road | 4 | B217-C013 | Gravel River | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1062420211128-8Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1062420211128-8Grader - Cat 12 to 14 or equal- After Jan 107888.86INV# 157 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10624 | 20211128-8 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Gravel River Road | 4 | B217-C013 | Gravel River | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1062420211128-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1062420211128-8Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10624 | 20211128-8 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Gravel River Road | 4 | B217-C013 | Gravel River | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1062420211128-8L.O.A.1210 | Corbiere and Sons Contracting1062420211128-8L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10624 | 20211128-8 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Gravel River Road | 4 | B217-C013 | Gravel River | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1062420211128-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1062420211128-8Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10714 | 20211128-9 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | G&G mobilized D6 into Lake A - for winter roadd freeze work | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1071420211128-9Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1071420211128-9Tractor Trailer - 60 Ton- After Jan 104489.56INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10714 | 20211128-9 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-11-28 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | G&G mobilized D6 into Lake A - for winter roadd freeze work | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1071420211128-9Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1071420211128-9Driver - AZ - After Jan 104280INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10717 | 20211129-10 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of Ex from WF4 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071720211129-10Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1071720211129-10Tractor Trailer - 60 Ton- After Jan 103367.17INV# 157 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10717 | 20211129-10 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of Ex from WF4 | 4 | B187-B201 | Gurney | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting1071720211129-10Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1071720211129-10Driver - AZ - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10718 | 20211129-11 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | G&G Float mobilized secondary D6 to WF5 for winter maintenance | 5 | C030-C128 | WF5 | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1071820211129-11Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1071820211129-11Tractor Trailer - 60 Ton- After Jan 105611.95INV# 157 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10718 | 20211129-11 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | G&G Float mobilized secondary D6 to WF5 for winter maintenance | 5 | C030-C128 | WF5 | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1071820211129-11Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1071820211129-11Driver - AZ - After Jan 105350INV# 157 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10719 | 20211129-12 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | G&G Float mobilizing 350 Hitachi into Lake A for Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1071920211129-12Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1071920211129-12Tractor Trailer - 60 Ton- After Jan 106734.34INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10719 | 20211129-12 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | G&G Float mobilizing 350 Hitachi into Lake A for Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1071920211129-12Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1071920211129-12Driver - AZ - After Jan 106420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10625 | 20211129-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062520211129-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1062520211129-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10625 | 20211129-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062520211129-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1062520211129-3Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10625 | 20211129-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062520211129-3L.O.A.1210 | Corbiere and Sons Contracting1062520211129-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10625 | 20211129-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062520211129-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1062520211129-3Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10626 | 20211129-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062620211129-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1062620211129-4Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10626 | 20211129-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1062620211129-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1062620211129-4Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10627 | 20211129-5 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Gravel River Road | 4 | B217-C013 | Gravel River | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1062720211129-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1062720211129-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10627 | 20211129-5 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Gravel River Road | 4 | B217-C013 | Gravel River | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1062720211129-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1062720211129-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10627 | 20211129-5 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Gravel River Road | 4 | B217-C013 | Gravel River | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1062720211129-5L.O.A.1210 | Corbiere and Sons Contracting1062720211129-5L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10627 | 20211129-5 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Gravel River Road | 4 | B217-C013 | Gravel River | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1062720211129-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1062720211129-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10628 | 20211129-6 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew working on Winter Road in Lake A - Sheldon mobilizing supplies | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062820211129-6Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting1062820211129-6Excavator - 30 ton- After Jan 1081107.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10628 | 20211129-6 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew working on Winter Road in Lake A - Sheldon mobilizing supplies | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062820211129-6Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1062820211129-6Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10628 | 20211129-6 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew working on Winter Road in Lake A - Sheldon mobilizing supplies | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062820211129-6Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1062820211129-6Light Truck - Pick up- After Jan 103731.25INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10628 | 20211129-6 | 53510606 | Access | 0 | Foreman | 95 | 9 | HR |  |  | 95 | 0 | 855 | 111.15 | 966.15 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew working on Winter Road in Lake A - Sheldon mobilizing supplies | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062820211129-6Foreman9855 | Corbiere and Sons Contracting1062820211129-6Foreman9855INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10628 | 20211129-6 | 53510606 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew working on Winter Road in Lake A - Sheldon mobilizing supplies | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062820211129-6L.O.A.4840 | Corbiere and Sons Contracting1062820211129-6L.O.A.4840INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10628 | 20211129-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew working on Winter Road in Lake A - Sheldon mobilizing supplies | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062820211129-6Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1062820211129-6Operator - Principle - After Jan 109675INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10628 | 20211129-6 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 9 | HR |  |  | 60 | 0 | 540 | 70.2 | 610.2 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew working on Winter Road in Lake A - Sheldon mobilizing supplies | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062820211129-6Labourer - General - After Jan 109540 | Corbiere and Sons Contracting1062820211129-6Labourer - General - After Jan 109540INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10628 | 20211129-6 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew working on Winter Road in Lake A - Sheldon mobilizing supplies | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062820211129-6Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1062820211129-6Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10629 | 20211129-7 | 53560601 | Water Crossings | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC 611 | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 |  |  | 611 |  | Bridge | Harold Furlong | 06 | Corbiere and Sons Contracting1062920211129-7Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting1062920211129-7Excavator - 30 ton- After Jan 102276.9INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10629 | 20211129-7 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC 611 | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 |  |  | 611 |  | Bridge | Harold Furlong | 06 | Corbiere and Sons Contracting1062920211129-7Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting1062920211129-7Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10629 | 20211129-7 | 53560601 | Water Crossings | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC 611 | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 |  |  | 611 |  | Bridge | Harold Furlong | 06 | Corbiere and Sons Contracting1062920211129-7Foreman2190 | Corbiere and Sons Contracting1062920211129-7Foreman2190INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10629 | 20211129-7 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 |  | 150 | 19.5 | 169.5 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC 611 | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 |  |  | 611 |  | Bridge | Harold Furlong | 06 | Corbiere and Sons Contracting1062920211129-7Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1062920211129-7Operator - Principle - After Jan 102150INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10629 | 20211129-7 | 53560601 | Water Crossings | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2021-11-29 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC 611 | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44539 |  |  | 611 |  | Bridge | Harold Furlong | 06 | Corbiere and Sons Contracting1062920211129-7Labourer - General - After Jan 102120 | Corbiere and Sons Contracting1062920211129-7Labourer - General - After Jan 102120INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10639 | 20211130-10 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work on Freeze-in of Lake A and mobilization of supplies and equipment continued | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063920211130-10Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1063920211130-10Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10639 | 20211130-10 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work on Freeze-in of Lake A and mobilization of supplies and equipment continued | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063920211130-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1063920211130-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10639 | 20211130-10 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work on Freeze-in of Lake A and mobilization of supplies and equipment continued | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063920211130-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1063920211130-10Light Truck - Pick up- After Jan 103731.25INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10639 | 20211130-10 | 53510606 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work on Freeze-in of Lake A and mobilization of supplies and equipment continued | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063920211130-10Foreman111045 | Corbiere and Sons Contracting1063920211130-10Foreman111045INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10639 | 20211130-10 | 53510606 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work on Freeze-in of Lake A and mobilization of supplies and equipment continued | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063920211130-10L.O.A.4840 | Corbiere and Sons Contracting1063920211130-10L.O.A.4840INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10639 | 20211130-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work on Freeze-in of Lake A and mobilization of supplies and equipment continued | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063920211130-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1063920211130-10Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10639 | 20211130-10 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work on Freeze-in of Lake A and mobilization of supplies and equipment continued | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063920211130-10Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1063920211130-10Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10639 | 20211130-10 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work on Freeze-in of Lake A and mobilization of supplies and equipment continued | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063920211130-10Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1063920211130-10Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10640 | 20211130-11 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot mobilized 336 to Prairie River Road | 6 | C171-C185 | Prairie River Road | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064020211130-11Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1064020211130-11Tractor Trailer - 60 Ton- After Jan 106734.34INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10640 | 20211130-11 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot mobilized 336 to Prairie River Road | 6 | C171-C185 | Prairie River Road | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064020211130-11Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1064020211130-11Driver - AZ - After Jan 106420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10766 | 20211130-12 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 16 | Dynamic | 91.79 | 0 |  |  | 1958.24 | 254.5712 | 2212.8112 | 2021-11-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of RT from Hensen Road in Wawa to Manatoulin Island. Used for road maintenance in WF10/WF11 for august and early September and than sat on Henson broke down for 3 months. | 6 | F118-F127 | Henson Road | 0 | 44550 |  | 36 | 44559 | [5 empty] | Mike Lecocq | 10 | Corbiere and Sons Contracting1076620211130-12Tractor Trailer - 60 Ton- After Jan 10161958.24 | Corbiere and Sons Contracting1076620211130-12Tractor Trailer - 60 Ton- After Jan 10161958.24INV #162 | [5 empty] | 1 | 1958.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10766 | 20211130-12 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of RT from Hensen Road in Wawa to Manatoulin Island. Used for road maintenance in WF10/WF11 for august and early September and than sat on Henson broke down for 3 months. | 6 | F118-F127 | Henson Road | 0 | 44550 |  | 36 | 44559 | [5 empty] | Mike Lecocq | 10 | Corbiere and Sons Contracting1076620211130-12L.O.A.1210 | Corbiere and Sons Contracting1076620211130-12L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10766 | 20211130-12 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 16 | HR |  |  | 70 | 0 | 1120 | 145.6 | 1265.6 | 2021-11-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of RT from Hensen Road in Wawa to Manatoulin Island. Used for road maintenance in WF10/WF11 for august and early September and than sat on Henson broke down for 3 months. | 6 | F118-F127 | Henson Road | 0 | 44550 |  | 36 | 44559 | [5 empty] | Mike Lecocq | 10 | Corbiere and Sons Contracting1076620211130-12Driver - AZ - After Jan 10161120 | Corbiere and Sons Contracting1076620211130-12Driver - AZ - After Jan 10161120INV #162 | [5 empty] | 1 | 1120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10632 | 20211130-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063220211130-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1063220211130-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10632 | 20211130-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063220211130-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1063220211130-3Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10632 | 20211130-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063220211130-3L.O.A.1210 | Corbiere and Sons Contracting1063220211130-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10632 | 20211130-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44539 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063220211130-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1063220211130-3Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10633 | 20211130-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road - Pickup w/plow and sand truck also working here | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063320211130-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1063320211130-4Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10633 | 20211130-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road - Pickup w/plow and sand truck also working here | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063320211130-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1063320211130-4Pickup w/ plow and sander4320INV# 157 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10633 | 20211130-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road - Pickup w/plow and sand truck also working here | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063320211130-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1063320211130-4Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10633 | 20211130-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road - Pickup w/plow and sand truck also working here | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063320211130-4Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1063320211130-4Operator - Intermdiate - After Jan 104280INV# 157 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10634 | 20211130-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Pickup w/plow and sand truck also working here | 5 | C031-C049 | Pays Plat River | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063420211130-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1063420211130-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV# 157 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10634 | 20211130-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Pickup w/plow and sand truck also working here | 5 | C031-C049 | Pays Plat River | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063420211130-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1063420211130-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10634 | 20211130-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Pickup w/plow and sand truck also working here | 5 | C031-C049 | Pays Plat River | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063420211130-5Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1063420211130-5Pickup w/ plow and sander4320INV# 157 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10634 | 20211130-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Pickup w/plow and sand truck also working here | 5 | C031-C049 | Pays Plat River | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063420211130-5L.O.A.1210 | Corbiere and Sons Contracting1063420211130-5L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10634 | 20211130-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Pickup w/plow and sand truck also working here | 5 | C031-C049 | Pays Plat River | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063420211130-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1063420211130-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10634 | 20211130-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Pickup w/plow and sand truck also working here | 5 | C031-C049 | Pays Plat River | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1063420211130-5Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1063420211130-5Operator - Intermdiate - After Jan 104280INV# 157 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10635 | 20211130-6 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers help gravel trucks stuck on road to North Shore pit | 3 |  | North Shore Pit | 0 | 44538 |  | 36 | 44539 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1063520211130-6Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1063520211130-6Pickup w/ plow and sander5400INV# 157 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10635 | 20211130-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers help gravel trucks stuck on road to North Shore pit | 3 |  | North Shore Pit | 0 | 44538 |  | 36 | 44539 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1063520211130-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1063520211130-6Operator - Principle - After Jan 105375INV# 157 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10635 | 20211130-6 | 53510311 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-11-30 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers help gravel trucks stuck on road to North Shore pit | 3 |  | North Shore Pit | 0 | 44538 |  | 36 | 44539 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1063520211130-6Labourer - General - After Jan 105300 | Corbiere and Sons Contracting1063520211130-6Labourer - General - After Jan 105300INV# 157 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10636 | 20211130-7-R1 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1339.8 | unit |  |  |  |  | 1339.8 | 174.174 | 1513.974 | 2021-11-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Mike disputed and had hours reduced |  | Approved |  |  | Mob of army truck (Gas Tank) from Dorion to Marathon - 2 hour delay caused by corbiere removed | 6 |  | WF6 | 0 | 44538 |  | 36 | 44567 | 380 | Mobilization of Army Truck with Gas Tank |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1063620211130-7-R13rd Party Charges1339.81339.8 | Corbiere and Sons Contracting1063620211130-7-R13rd Party Charges1339.81339.8INV #162 | [5 empty] | 1 | 1339.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10641 | 20211201-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064120211201-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1064120211201-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10641 | 20211201-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064120211201-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1064120211201-3Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10641 | 20211201-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064120211201-3L.O.A.1210 | Corbiere and Sons Contracting1064120211201-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10641 | 20211201-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064120211201-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1064120211201-3Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10642 | 20211201-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064220211201-4Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1064220211201-4Dozer D6 or equal- After Jan 102262.96INV# 157 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10642 | 20211201-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064220211201-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1064220211201-4Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10642 | 20211201-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road | 5 | C050-C069 | Antler Lake | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064220211201-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1064220211201-4Operator - Principle - After Jan 105375INV# 157 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10643 | 20211201-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7.5 | Dynamic | 95.24 | 0 |  |  | 952.35 | 123.8055 | 1076.1555 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road | 5 | C031-C049 | Pays Plat River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064320211201-5Grader - Cat 12 to 14 or equal- After Jan 107.5952.35 | Corbiere and Sons Contracting1064320211201-5Grader - Cat 12 to 14 or equal- After Jan 107.5952.35INV# 157 | [5 empty] | 1 | 952.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10643 | 20211201-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road | 5 | C031-C049 | Pays Plat River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064320211201-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1064320211201-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10643 | 20211201-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road | 5 | C031-C049 | Pays Plat River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064320211201-5L.O.A.1210 | Corbiere and Sons Contracting1064320211201-5L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10643 | 20211201-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road | 5 | C031-C049 | Pays Plat River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064320211201-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1064320211201-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10645 | 20211201-7 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064520211201-7Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1064520211201-7Excavator - 36 ton- After Jan 1091322.64INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10645 | 20211201-7 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064520211201-7Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1064520211201-7Excavator - 36 ton- After Jan 1091322.64INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10645 | 20211201-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064520211201-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1064520211201-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10645 | 20211201-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064520211201-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1064520211201-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10645 | 20211201-7 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064520211201-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1064520211201-7Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10645 | 20211201-7 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064520211201-7L.O.A.2420 | Corbiere and Sons Contracting1064520211201-7L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10645 | 20211201-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064520211201-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1064520211201-7Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10645 | 20211201-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064520211201-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1064520211201-7Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10646 | 20211201-8 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064620211201-8Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting1064620211201-8Excavator - 30 ton- After Jan 1081107.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10646 | 20211201-8 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064620211201-8Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1064620211201-8Excavator - 36 ton- After Jan 1081175.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10646 | 20211201-8 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064620211201-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1064620211201-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10646 | 20211201-8 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064620211201-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1064620211201-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10646 | 20211201-8 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064620211201-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1064620211201-8Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10646 | 20211201-8 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064620211201-8L.O.A.2420 | Corbiere and Sons Contracting1064620211201-8L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10646 | 20211201-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064620211201-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1064620211201-8Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10646 | 20211201-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C171-C185 | Prairie River | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064620211201-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1064620211201-8Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting1064720211201-9Dozer D6 or equal- After Jan 106788.88INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1064720211201-9Excavator - 30 ton- After Jan 10101384.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1064720211201-9Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1064720211201-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1064720211201-9Light Truck - Pick up- After Jan 104975INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1064720211201-9Tractor Trailer - 60 Ton- After Jan 10111346.29INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1346.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Foreman121140 | Corbiere and Sons Contracting1064720211201-9Foreman121140INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9L.O.A.71470 | Corbiere and Sons Contracting1064720211201-9L.O.A.71470INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1064720211201-9Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1064720211201-9Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1064720211201-9Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1064720211201-9Operator - Principle - After Jan 105375INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1064720211201-9Driver - AZ - After Jan 1011770INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10647 | 20211201-9 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-01 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A - Shawn mobilized Hose Trailer - Jason did Orientation | 6 | C130-C151 | Lake A | 0 | 44538 |  | 37 | 44540 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1064720211201-9Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1064720211201-9Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10655 | 20211202-10 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C186 - C190 | Prairie River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065520211202-10Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting1065520211202-10Excavator - 30 ton- After Jan 107969.15INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 969.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10655 | 20211202-10 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C186 - C190 | Prairie River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065520211202-10Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1065520211202-10Excavator - 36 ton- After Jan 1071028.72INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10655 | 20211202-10 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C186 - C190 | Prairie River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065520211202-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1065520211202-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10655 | 20211202-10 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C186 - C190 | Prairie River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065520211202-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1065520211202-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10655 | 20211202-10 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C186 - C190 | Prairie River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065520211202-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1065520211202-10Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10655 | 20211202-10 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C186 - C190 | Prairie River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065520211202-10L.O.A.2420 | Corbiere and Sons Contracting1065520211202-10L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10655 | 20211202-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C186 - C190 | Prairie River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065520211202-10Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1065520211202-10Operator - Principle - After Jan 108600INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10655 | 20211202-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Prairie River | 6 | C186 - C190 | Prairie River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065520211202-10Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1065520211202-10Operator - Principle - After Jan 108600INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 1 | Dynamic | 98.61 | 0 |  |  | 131.48 | 17.0924 | 148.5724 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12Dozer D6 or equal- After Jan 101131.48 | Corbiere and Sons Contracting1065720211202-12Dozer D6 or equal- After Jan 101131.48INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 131.48 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting1065720211202-12Excavator - 30 ton- After Jan 1081107.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1065720211202-12Excavator - 36 ton- After Jan 105734.8INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1065720211202-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1065720211202-12Light Truck - Pick up- After Jan 104975INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12Foreman121140 | Corbiere and Sons Contracting1065720211202-12Foreman121140INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12L.O.A.51050 | Corbiere and Sons Contracting1065720211202-12L.O.A.51050INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1065720211202-12Operator - Principle - After Jan 108600INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1065720211202-12Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1065720211202-12Operator - Principle - After Jan 105375INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10657 | 20211202-12 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065720211202-12Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1065720211202-12Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10648 | 20211202-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12 | Dynamic | 95.24 | 0 |  |  | 1523.76 | 198.0888 | 1721.8488 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064820211202-3Grader - Cat 12 to 14 or equal- After Jan 10121523.76 | Corbiere and Sons Contracting1064820211202-3Grader - Cat 12 to 14 or equal- After Jan 10121523.76INV# 157 | [5 empty] | 1 | 1523.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10648 | 20211202-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064820211202-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1064820211202-3Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10648 | 20211202-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064820211202-3L.O.A.1210 | Corbiere and Sons Contracting1064820211202-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10648 | 20211202-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Road Maintenance in Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44538 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064820211202-3Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1064820211202-3Operator - Principle - After Jan 1013975INV# 157 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10649 | 20211202-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road - Mark Tustin Sanding and Plowing - 3rd party Float moved D6 into Antler | 5 | C050-C069 | Antler Lake | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064920211202-4Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1064920211202-4Dozer D6 or equal- After Jan 103394.44INV# 157 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10649 | 20211202-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road - Mark Tustin Sanding and Plowing - 3rd party Float moved D6 into Antler | 5 | C050-C069 | Antler Lake | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064920211202-4Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1064920211202-4Pickup w/ plow and sander2.5200INV# 157 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10649 | 20211202-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road - Mark Tustin Sanding and Plowing - 3rd party Float moved D6 into Antler | 5 | C050-C069 | Antler Lake | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064920211202-4Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1064920211202-4Operator - Principle - After Jan 104300INV# 157 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10649 | 20211202-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road - Mark Tustin Sanding and Plowing - 3rd party Float moved D6 into Antler | 5 | C050-C069 | Antler Lake | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1064920211202-4Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1064920211202-4Operator - Intermdiate - After Jan 102.5175INV# 157 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10649 | 20211202-4 | 53510511 | Access | 0 | 3rd Party Charges | 1 | 765.6 | unit |  |  |  |  | 765.6 | 99.528 | 865.128 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on Winter Road Maintenance on Antler Lake Road - Mark Tustin Sanding and Plowing - 3rd party Float moved D6 into Antler | 5 | C050-C069 | Antler Lake | 0 | 44539 |  | 37 | 44542 | 381 | $660 marked up to $765 |  |  |  | Harold Furlong | 05 | Corbiere and Sons Contracting1064920211202-43rd Party Charges765.6765.6 | Corbiere and Sons Contracting1064920211202-43rd Party Charges765.6765.6INV# 157 | [5 empty] | 1 | 765.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10650 | 20211202-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Mark Tustin Sanding and Plowing | 5 | C031-C049 | Pays Plat River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1065020211202-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1065020211202-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10650 | 20211202-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Mark Tustin Sanding and Plowing | 5 | C031-C049 | Pays Plat River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1065020211202-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1065020211202-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10650 | 20211202-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Mark Tustin Sanding and Plowing | 5 | C031-C049 | Pays Plat River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1065020211202-5Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1065020211202-5Pickup w/ plow and sander4320INV# 157 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10650 | 20211202-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Mark Tustin Sanding and Plowing | 5 | C031-C049 | Pays Plat River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1065020211202-5L.O.A.1210 | Corbiere and Sons Contracting1065020211202-5L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10650 | 20211202-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Mark Tustin Sanding and Plowing | 5 | C031-C049 | Pays Plat River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1065020211202-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1065020211202-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10650 | 20211202-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Mark Tustin Sanding and Plowing | 5 | C031-C049 | Pays Plat River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1065020211202-5Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1065020211202-5Operator - Intermdiate - After Jan 104280INV# 157 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10651 | 20211202-6 | 53510411 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing on Gravel River Road | 4 | B217-C013 | Gravel River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1065120211202-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1065120211202-6Pickup w/ plow and sander3240INV# 157 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10651 | 20211202-6 | 53510411 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing on Gravel River Road | 4 | B217-C013 | Gravel River | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1065120211202-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1065120211202-6Operator - Intermdiate - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10654 | 20211202-9 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065420211202-9Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1065420211202-9Dozer D6 or equal- After Jan 107920.36INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10654 | 20211202-9 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065420211202-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1065420211202-9Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10654 | 20211202-9 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065420211202-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1065420211202-9Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10654 | 20211202-9 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065420211202-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1065420211202-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10654 | 20211202-9 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065420211202-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1065420211202-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10654 | 20211202-9 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065420211202-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1065420211202-9Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10654 | 20211202-9 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065420211202-9L.O.A.2420 | Corbiere and Sons Contracting1065420211202-9L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10654 | 20211202-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065420211202-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1065420211202-9Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10654 | 20211202-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065420211202-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1065420211202-9Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10654 | 20211202-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-12-02 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road work on Peninsula | 6 | C268-D005 | Peninsula | 0 | 44539 |  | 37 | 44542 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1065420211202-9Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1065420211202-9Operator - Principle - After Jan 107525INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10668 | 20211203-11 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066820211203-11Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1066820211203-11Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10668 | 20211203-11 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066820211203-11Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1066820211203-11Excavator - 36 ton- After Jan 1081175.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10668 | 20211203-11 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066820211203-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1066820211203-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10668 | 20211203-11 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066820211203-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1066820211203-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10668 | 20211203-11 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066820211203-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1066820211203-11Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10668 | 20211203-11 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066820211203-11L.O.A.2420 | Corbiere and Sons Contracting1066820211203-11L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10668 | 20211203-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066820211203-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1066820211203-11Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10668 | 20211203-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066820211203-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1066820211203-11Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8.5 | Dynamic | 103.84 | 0 |  |  | 1176.825 | 152.9872 | 1329.8122 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Excavator - 30 ton- After Jan 108.51176.825 | Corbiere and Sons Contracting1066920211203-12Excavator - 30 ton- After Jan 108.51176.825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1176.825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1066920211203-12Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1066920211203-12Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8.5 | HR | 9.16 | 0 |  |  | 103.785 | 13.4921 | 117.2771 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785 | Corbiere and Sons Contracting1066920211203-12Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 103.785 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1066920211203-12Light Truck - Pick up- After Jan 103731.25INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting1066920211203-12Tractor Trailer - 60 Ton- After Jan 108979.12INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 979.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Foreman121140 | Corbiere and Sons Contracting1066920211203-12Foreman121140INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12L.O.A.51050 | Corbiere and Sons Contracting1066920211203-12L.O.A.51050INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1066920211203-12Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1066920211203-12Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting1066920211203-12Driver - AZ - After Jan 108560INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10669 | 20211203-12 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads being built in Prairie - Float D6 and mobilized Sea Can with supplies | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066920211203-12Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1066920211203-12Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10670 | 20211203-13 | 53560601 | Water Crossings | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moving bridges into Prarie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7038/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1067020211203-13Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1067020211203-13Tractor Trailer - 60 Ton- After Jan 104489.56INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10670 | 20211203-13 | 53560601 | Water Crossings | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moving bridges into Prarie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7038/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1067020211203-13Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1067020211203-13Tractor Trailer - 60 Ton- After Jan 104489.56INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10670 | 20211203-13 | 53560601 | Water Crossings | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moving bridges into Prarie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7038/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1067020211203-13Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1067020211203-13Driver - AZ - After Jan 104280INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10670 | 20211203-13 | 53560601 | Water Crossings | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moving bridges into Prarie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7038/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1067020211203-13Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1067020211203-13Driver - AZ - After Jan 104280INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10671 | 20211203-14 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067120211203-14Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1067120211203-14Excavator - 30 ton- After Jan 10101384.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10671 | 20211203-14 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067120211203-14Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1067120211203-14Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10671 | 20211203-14 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067120211203-14Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1067120211203-14Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10671 | 20211203-14 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067120211203-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1067120211203-14Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10671 | 20211203-14 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067120211203-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1067120211203-14Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10671 | 20211203-14 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067120211203-14L.O.A.2420 | Corbiere and Sons Contracting1067120211203-14L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10671 | 20211203-14 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067120211203-14Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1067120211203-14Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10671 | 20211203-14 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067120211203-14Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1067120211203-14Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10660 | 20211203-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066020211203-3Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1066020211203-3Grader - Cat 12 to 14 or equal- After Jan 103380.94INV# 157 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10660 | 20211203-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066020211203-3L.O.A.1210 | Corbiere and Sons Contracting1066020211203-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10660 | 20211203-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066020211203-3Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1066020211203-3Operator - Principle - After Jan 103225INV# 157 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10661 | 20211203-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to work for day - DZ clearing snow and scrapping | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066120211203-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1066120211203-4Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10661 | 20211203-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to work for day - DZ clearing snow and scrapping | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066120211203-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1066120211203-4Grader - Cat 12 to 14 or equal- After Jan 106761.88INV# 157 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10661 | 20211203-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to work for day - DZ clearing snow and scrapping | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066120211203-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1066120211203-4Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10661 | 20211203-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to work for day - DZ clearing snow and scrapping | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066120211203-4Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1066120211203-4Tractor Trailer - 60 Ton- After Jan 103367.17INV# 157 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10661 | 20211203-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to work for day - DZ clearing snow and scrapping | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066120211203-4L.O.A.2420 | Corbiere and Sons Contracting1066120211203-4L.O.A.2420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10661 | 20211203-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to work for day - DZ clearing snow and scrapping | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066120211203-4Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1066120211203-4Operator - Principle - After Jan 108600INV# 157 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10661 | 20211203-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to work for day - DZ clearing snow and scrapping | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066120211203-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1066120211203-4Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10661 | 20211203-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated over to work for day - DZ clearing snow and scrapping | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066120211203-4Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1066120211203-4Driver - AZ - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10662 | 20211203-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Plow Truck with Sander working on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066220211203-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1066220211203-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10662 | 20211203-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Plow Truck with Sander working on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066220211203-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1066220211203-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10662 | 20211203-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Plow Truck with Sander working on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066220211203-5Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1066220211203-5Pickup w/ plow and sander2.5200INV# 157 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10662 | 20211203-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Plow Truck with Sander working on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066220211203-5L.O.A.1210 | Corbiere and Sons Contracting1066220211203-5L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10662 | 20211203-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Plow Truck with Sander working on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066220211203-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1066220211203-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10662 | 20211203-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Pays Plat Road - Plow Truck with Sander working on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066220211203-5Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1066220211203-5Operator - Intermdiate - After Jan 102.5175INV# 157 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10663 | 20211203-6 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over to Whitesands and it worked there for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066320211203-6Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1066320211203-6Dozer D6 or equal- After Jan 1091183.32INV# 157 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10663 | 20211203-6 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over to Whitesands and it worked there for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066320211203-6Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1066320211203-6Tractor Trailer - 60 Ton- After Jan 103367.17INV# 157 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10663 | 20211203-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over to Whitesands and it worked there for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066320211203-6L.O.A.1210 | Corbiere and Sons Contracting1066320211203-6L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10663 | 20211203-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over to Whitesands and it worked there for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066320211203-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1066320211203-6Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10663 | 20211203-6 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over to Whitesands and it worked there for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066320211203-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1066320211203-6Driver - AZ - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10664 | 20211203-7 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized PU for 3rd Grader Operator | 5 | C028-C128 | WF5 | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066420211203-7Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1066420211203-7Tractor Trailer - 60 Ton- After Jan 105611.95INV# 157 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10664 | 20211203-7 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized PU for 3rd Grader Operator | 5 | C028-C128 | WF5 | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1066420211203-7Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1066420211203-7Driver - AZ - After Jan 105350INV# 157 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10665 | 20211203-8 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and Sanding on Camp Road 81 | 3 | B145-B147 | Camp 81 | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1066520211203-8Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1066520211203-8Pickup w/ plow and sander2160INV# 157 | [5 empty] | 1 | 160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10665 | 20211203-8 | 53510311 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-12-03 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and Sanding on Camp Road 81 | 3 | B145-B147 | Camp 81 | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1066520211203-8Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1066520211203-8Operator - Intermdiate - After Jan 102140INV# 157 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10679 | 20211204-10 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067920211204-10Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1067920211204-10Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10679 | 20211204-10 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067920211204-10Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1067920211204-10Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10679 | 20211204-10 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067920211204-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1067920211204-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10679 | 20211204-10 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067920211204-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1067920211204-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10679 | 20211204-10 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067920211204-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1067920211204-10Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10679 | 20211204-10 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067920211204-10L.O.A.2420 | Corbiere and Sons Contracting1067920211204-10L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10679 | 20211204-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067920211204-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1067920211204-10Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10679 | 20211204-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C268-D005 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067920211204-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1067920211204-10Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10680 | 20211204-11 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8.5 | Dynamic | 103.84 | 0 |  |  | 1176.825 | 152.9872 | 1329.8122 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068020211204-11Excavator - 30 ton- After Jan 108.51176.825 | Corbiere and Sons Contracting1068020211204-11Excavator - 30 ton- After Jan 108.51176.825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1176.825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10680 | 20211204-11 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068020211204-11Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1068020211204-11Excavator - 36 ton- After Jan 1081175.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10680 | 20211204-11 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068020211204-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1068020211204-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10680 | 20211204-11 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8.5 | HR | 9.16 | 0 |  |  | 103.785 | 13.4921 | 117.2771 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068020211204-11Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785 | Corbiere and Sons Contracting1068020211204-11Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 103.785 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10680 | 20211204-11 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068020211204-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1068020211204-11Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10680 | 20211204-11 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068020211204-11L.O.A.2420 | Corbiere and Sons Contracting1068020211204-11L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10680 | 20211204-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068020211204-11Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1068020211204-11Operator - Principle - After Jan 109675INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10680 | 20211204-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068020211204-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1068020211204-11Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10681 | 20211204-12 | 53560601 | Water Crossings | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot delivering WC's and Cody working on 1 for 2 hours - Ron hauling in Bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1068120211204-12Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1068120211204-12Dozer D6 or equal- After Jan 105657.4INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10681 | 20211204-12 | 53560601 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot delivering WC's and Cody working on 1 for 2 hours - Ron hauling in Bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1068120211204-12Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting1068120211204-12Excavator - 36 ton- After Jan 102293.92INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 293.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10681 | 20211204-12 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot delivering WC's and Cody working on 1 for 2 hours - Ron hauling in Bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1068120211204-12Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting1068120211204-12Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10681 | 20211204-12 | 53560601 | Water Crossings | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot delivering WC's and Cody working on 1 for 2 hours - Ron hauling in Bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1068120211204-12Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1068120211204-12Tractor Trailer - 60 Ton- After Jan 10111346.29INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 1346.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10681 | 20211204-12 | 53560601 | Water Crossings | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot delivering WC's and Cody working on 1 for 2 hours - Ron hauling in Bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1068120211204-12L.O.A.2420 | Corbiere and Sons Contracting1068120211204-12L.O.A.2420INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10681 | 20211204-12 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot delivering WC's and Cody working on 1 for 2 hours - Ron hauling in Bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1068120211204-12Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1068120211204-12Operator - Principle - After Jan 102150INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10681 | 20211204-12 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot delivering WC's and Cody working on 1 for 2 hours - Ron hauling in Bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1068120211204-12Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1068120211204-12Operator - Principle - After Jan 106450INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10681 | 20211204-12 | 53560601 | Water Crossings | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot delivering WC's and Cody working on 1 for 2 hours - Ron hauling in Bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1068120211204-12Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1068120211204-12Driver - AZ - After Jan 1011770INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10684 | 20211204-15 | 53560601 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling in Bridges to Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 |  |  | 611 |  | Rig Mat | Mike Lecocq | 06 | Corbiere and Sons Contracting1068420211204-15Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1068420211204-15Excavator - 36 ton- After Jan 105734.8INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10684 | 20211204-15 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling in Bridges to Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 |  |  | 611 |  | Rig Mat | Mike Lecocq | 06 | Corbiere and Sons Contracting1068420211204-15Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1068420211204-15Operator - Principle - After Jan 106450INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10685 | 20211204-16 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068520211204-16Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1068520211204-16Excavator - 30 ton- After Jan 10101384.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10685 | 20211204-16 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068520211204-16Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1068520211204-16Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10685 | 20211204-16 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068520211204-16Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1068520211204-16Light Truck - Pick up- After Jan 103731.25INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10685 | 20211204-16 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068520211204-16Foreman121140 | Corbiere and Sons Contracting1068520211204-16Foreman121140INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10685 | 20211204-16 | 53510606 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068520211204-16L.O.A.3630 | Corbiere and Sons Contracting1068520211204-16L.O.A.3630INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10685 | 20211204-16 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068520211204-16Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1068520211204-16Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10685 | 20211204-16 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Lake A | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1068520211204-16Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1068520211204-16Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10672 | 20211204-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader over to Cooks and then he spent the day there | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067220211204-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1067220211204-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV# 157 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10672 | 20211204-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader over to Cooks and then he spent the day there | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067220211204-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1067220211204-3Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10672 | 20211204-3 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader over to Cooks and then he spent the day there | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067220211204-3Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting1067220211204-3Tractor Trailer - 60 Ton- After Jan 102244.78INV# 157 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10672 | 20211204-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader over to Cooks and then he spent the day there | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067220211204-3L.O.A.1210 | Corbiere and Sons Contracting1067220211204-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10672 | 20211204-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader over to Cooks and then he spent the day there | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067220211204-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1067220211204-3Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10672 | 20211204-3 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Grader over to Cooks and then he spent the day there | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067220211204-3Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting1067220211204-3Driver - AZ - After Jan 102140INV# 157 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10673 | 20211204-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067320211204-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1067320211204-4Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10673 | 20211204-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067320211204-4L.O.A.1210 | Corbiere and Sons Contracting1067320211204-4L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10673 | 20211204-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067320211204-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1067320211204-4Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10674 | 20211204-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader WAM for 2 hours, DZ for entire day | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067420211204-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1067420211204-5Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10674 | 20211204-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader WAM for 2 hours, DZ for entire day | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067420211204-5Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting1067420211204-5Grader - Cat 12 to 14 or equal- After Jan 102253.96INV# 157 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10674 | 20211204-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader WAM for 2 hours, DZ for entire day | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067420211204-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1067420211204-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10674 | 20211204-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader WAM for 2 hours, DZ for entire day | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067420211204-5L.O.A.1210 | Corbiere and Sons Contracting1067420211204-5L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10674 | 20211204-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader WAM for 2 hours, DZ for entire day | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067420211204-5Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1067420211204-5Operator - Principle - After Jan 102150INV# 157 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10674 | 20211204-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader WAM for 2 hours, DZ for entire day | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067420211204-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1067420211204-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10675 | 20211204-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler - Float moved grader | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067520211204-6Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1067520211204-6Grader - Cat 12 to 14 or equal- After Jan 107888.86INV# 157 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10675 | 20211204-6 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler - Float moved grader | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067520211204-6Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting1067520211204-6Tractor Trailer - 60 Ton- After Jan 102244.78INV# 157 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10675 | 20211204-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler - Float moved grader | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067520211204-6L.O.A.1210 | Corbiere and Sons Contracting1067520211204-6L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10675 | 20211204-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler - Float moved grader | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067520211204-6Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1067520211204-6Operator - Principle - After Jan 109675INV# 157 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10675 | 20211204-6 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler - Float moved grader | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1067520211204-6Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting1067520211204-6Driver - AZ - After Jan 102140INV# 157 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10678 | 20211204-9 | 53510511 | Access | 0 | 3rd Party Charges | 1 | 865.8 | unit |  |  |  |  | 865.8 | 112.554 | 978.354 | 2021-12-04 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sand | 5 | C030-C128 | WF5 | 0 | 44541 |  | 36 | 44544 | 342 | Sand for Roads |  |  |  | Mike Lecocq | 05 | Corbiere and Sons Contracting1067820211204-93rd Party Charges865.8865.8 | Corbiere and Sons Contracting1067820211204-93rd Party Charges865.8865.8INV# 157 | [5 empty] | 1 | 865.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10693 | 20211205-10 | 53560601 | Water Crossings | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on WCs, DZ dragging them in, float delivering | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1069320211205-10Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1069320211205-10Dozer D6 or equal- After Jan 105657.4INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10693 | 20211205-10 | 53560601 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on WCs, DZ dragging them in, float delivering | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1069320211205-10Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1069320211205-10Excavator - 36 ton- After Jan 103440.88INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10693 | 20211205-10 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on WCs, DZ dragging them in, float delivering | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1069320211205-10Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1069320211205-10Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10693 | 20211205-10 | 53560601 | Water Crossings | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on WCs, DZ dragging them in, float delivering | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1069320211205-10Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1069320211205-10Tractor Trailer - 60 Ton- After Jan 10111346.29INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 1346.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10693 | 20211205-10 | 53560601 | Water Crossings | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on WCs, DZ dragging them in, float delivering | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1069320211205-10L.O.A.1210 | Corbiere and Sons Contracting1069320211205-10L.O.A.1210INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10693 | 20211205-10 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on WCs, DZ dragging them in, float delivering | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1069320211205-10Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1069320211205-10Operator - Principle - After Jan 103225INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10693 | 20211205-10 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on WCs, DZ dragging them in, float delivering | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1069320211205-10Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1069320211205-10Operator - Principle - After Jan 106450INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10693 | 20211205-10 | 53560601 | Water Crossings | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on WCs, DZ dragging them in, float delivering | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1069320211205-10Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1069320211205-10Driver - AZ - After Jan 1011770INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10694 | 20211205-11 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069420211205-11Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1069420211205-11Excavator - 30 ton- After Jan 10101384.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10694 | 20211205-11 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069420211205-11Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1069420211205-11Excavator - 36 ton- After Jan 105734.8INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10694 | 20211205-11 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069420211205-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1069420211205-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10694 | 20211205-11 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069420211205-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1069420211205-11Light Truck - Pick up- After Jan 102487.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10694 | 20211205-11 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069420211205-11L.O.A.2420 | Corbiere and Sons Contracting1069420211205-11L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10694 | 20211205-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069420211205-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1069420211205-11Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10694 | 20211205-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069420211205-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1069420211205-11Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10686 | 20211205-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44909 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068620211205-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1068620211205-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10686 | 20211205-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44909 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068620211205-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1068620211205-3Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10686 | 20211205-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44909 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068620211205-3L.O.A.1210 | Corbiere and Sons Contracting1068620211205-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10686 | 20211205-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C076-C116 | Cook Lake | 0 | 44541 |  | 36 | 44909 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068620211205-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1068620211205-3Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10687 | 20211205-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068720211205-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1068720211205-4Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10687 | 20211205-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068720211205-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1068720211205-4Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10687 | 20211205-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068720211205-4L.O.A.1210 | Corbiere and Sons Contracting1068720211205-4L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10687 | 20211205-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068720211205-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1068720211205-4Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10688 | 20211205-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on WAM in Antler | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068820211205-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1068820211205-5Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10688 | 20211205-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on WAM in Antler | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068820211205-5L.O.A.1210 | Corbiere and Sons Contracting1068820211205-5L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10688 | 20211205-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working on WAM in Antler | 5 | C031-C049 | Pays Plat River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068820211205-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1068820211205-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10689 | 20211205-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44531 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068920211205-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1068920211205-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10689 | 20211205-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44531 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068920211205-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1068920211205-6Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10689 | 20211205-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44531 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068920211205-6L.O.A.1210 | Corbiere and Sons Contracting1068920211205-6L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10689 | 20211205-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44541 |  | 36 | 44531 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1068920211205-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1068920211205-6Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10690 | 20211205-7 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula, 1 ex floated to Red Sucker at end of day | 6 | C267-C277 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069020211205-7Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1069020211205-7Excavator - 36 ton- After Jan 1091322.64INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10690 | 20211205-7 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula, 1 ex floated to Red Sucker at end of day | 6 | C267-C277 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069020211205-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1069020211205-7Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10690 | 20211205-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula, 1 ex floated to Red Sucker at end of day | 6 | C267-C277 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069020211205-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1069020211205-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10690 | 20211205-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula, 1 ex floated to Red Sucker at end of day | 6 | C267-C277 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069020211205-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1069020211205-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10690 | 20211205-7 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula, 1 ex floated to Red Sucker at end of day | 6 | C267-C277 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069020211205-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1069020211205-7Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10690 | 20211205-7 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula, 1 ex floated to Red Sucker at end of day | 6 | C267-C277 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069020211205-7L.O.A.2420 | Corbiere and Sons Contracting1069020211205-7L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10690 | 20211205-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula, 1 ex floated to Red Sucker at end of day | 6 | C267-C277 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069020211205-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1069020211205-7Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10690 | 20211205-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula, 1 ex floated to Red Sucker at end of day | 6 | C267-C277 | Peninsula | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069020211205-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1069020211205-7Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10691 | 20211205-8 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069120211205-8Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1069120211205-8Excavator - 30 ton- After Jan 10101384.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10691 | 20211205-8 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069120211205-8Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1069120211205-8Excavator - 36 ton- After Jan 1071028.72INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10691 | 20211205-8 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069120211205-8Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1069120211205-8Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10691 | 20211205-8 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069120211205-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1069120211205-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10691 | 20211205-8 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069120211205-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1069120211205-8Light Truck - Pick up- After Jan 103731.25INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10691 | 20211205-8 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069120211205-8Foreman121140 | Corbiere and Sons Contracting1069120211205-8Foreman121140INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10691 | 20211205-8 | 53510606 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069120211205-8L.O.A.4840 | Corbiere and Sons Contracting1069120211205-8L.O.A.4840INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10691 | 20211205-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069120211205-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1069120211205-8Operator - Principle - After Jan 108600INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10691 | 20211205-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069120211205-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1069120211205-8Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10691 | 20211205-8 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-05 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44541 |  | 36 | 44544 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1069120211205-8Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1069120211205-8Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10704 | 20211206-10 | 53560601 | Water Crossings | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ hauling in bridges into Prairire River Road for the day - 6.1m WC8000, 6.1m WC7938, 9.1m WC7870, 12.2m WC7880 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 |  |  | 7880/7870/7938/8000 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1070420211206-10Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1070420211206-10Dozer D6 or equal- After Jan 10101314.8INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10704 | 20211206-10 | 53560601 | Water Crossings | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ hauling in bridges into Prairire River Road for the day - 6.1m WC8000, 6.1m WC7938, 9.1m WC7870, 12.2m WC7880 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 |  |  | 7880/7870/7938/8000 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1070420211206-10L.O.A.1210 | Corbiere and Sons Contracting1070420211206-10L.O.A.1210INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10704 | 20211206-10 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ hauling in bridges into Prairire River Road for the day - 6.1m WC8000, 6.1m WC7938, 9.1m WC7870, 12.2m WC7880 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 |  |  | 7880/7870/7938/8000 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1070420211206-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1070420211206-10Operator - Principle - After Jan 1011825INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10705 | 20211206-11 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070520211206-11Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1070520211206-11Excavator - 30 ton- After Jan 10101384.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10705 | 20211206-11 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070520211206-11Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1070520211206-11Excavator - 36 ton- After Jan 1081175.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10705 | 20211206-11 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070520211206-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1070520211206-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10705 | 20211206-11 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070520211206-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1070520211206-11Light Truck - Pick up- After Jan 102487.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10705 | 20211206-11 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070520211206-11L.O.A.2420 | Corbiere and Sons Contracting1070520211206-11L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10705 | 20211206-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070520211206-11Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1070520211206-11Operator - Principle - After Jan 108600INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10705 | 20211206-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070520211206-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1070520211206-11Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10697 | 20211206-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069720211206-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1069720211206-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10697 | 20211206-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069720211206-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1069720211206-3Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10697 | 20211206-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069720211206-3Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1069720211206-3Pickup w/ plow and sander3240INV# 157 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10697 | 20211206-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069720211206-3L.O.A.2420 | Corbiere and Sons Contracting1069720211206-3L.O.A.2420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10697 | 20211206-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069720211206-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1069720211206-3Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10697 | 20211206-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069720211206-3Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1069720211206-3Operator - Intermdiate - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10698 | 20211206-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day - Pickup w/ plow and Sander here for part of day | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069820211206-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1069820211206-4Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10698 | 20211206-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day - Pickup w/ plow and Sander here for part of day | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069820211206-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1069820211206-4Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10698 | 20211206-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day - Pickup w/ plow and Sander here for part of day | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069820211206-4Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1069820211206-4Pickup w/ plow and sander2160INV# 157 | [5 empty] | 1 | 160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10698 | 20211206-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day - Pickup w/ plow and Sander here for part of day | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069820211206-4L.O.A.1210 | Corbiere and Sons Contracting1069820211206-4L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10698 | 20211206-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day - Pickup w/ plow and Sander here for part of day | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069820211206-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1069820211206-4Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10698 | 20211206-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day - Pickup w/ plow and Sander here for part of day | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069820211206-4Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1069820211206-4Operator - Intermdiate - After Jan 102140INV# 157 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10699 | 20211206-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069920211206-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1069920211206-5Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10699 | 20211206-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069920211206-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1069920211206-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10699 | 20211206-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069920211206-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1069920211206-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10699 | 20211206-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069920211206-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1069920211206-5Pickup w/ plow and sander3240INV# 157 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10699 | 20211206-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069920211206-5L.O.A.2420 | Corbiere and Sons Contracting1069920211206-5L.O.A.2420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10699 | 20211206-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069920211206-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1069920211206-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10699 | 20211206-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069920211206-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1069920211206-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10699 | 20211206-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1069920211206-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1069920211206-5Operator - Intermdiate - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10700 | 20211206-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1070020211206-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1070020211206-6Pickup w/ plow and sander3240INV# 157 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10700 | 20211206-6 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1070020211206-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1070020211206-6Operator - Intermdiate - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10701 | 20211206-7 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads freeze in in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070120211206-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1070120211206-7Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10701 | 20211206-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads freeze in in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070120211206-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1070120211206-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10701 | 20211206-7 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads freeze in in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070120211206-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1070120211206-7Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10701 | 20211206-7 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads freeze in in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070120211206-7L.O.A.1210 | Corbiere and Sons Contracting1070120211206-7L.O.A.1210INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10701 | 20211206-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads freeze in in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070120211206-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1070120211206-7Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10703 | 20211206-9 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070320211206-9Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1070320211206-9Excavator - 30 ton- After Jan 10101384.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10703 | 20211206-9 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070320211206-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1070320211206-9Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10703 | 20211206-9 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070320211206-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1070320211206-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10703 | 20211206-9 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070320211206-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1070320211206-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10703 | 20211206-9 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070320211206-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1070320211206-9Light Truck - Pick up- After Jan 102487.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10703 | 20211206-9 | 53510606 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070320211206-9L.O.A.3630 | Corbiere and Sons Contracting1070320211206-9L.O.A.3630INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10703 | 20211206-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070320211206-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1070320211206-9Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10703 | 20211206-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070320211206-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1070320211206-9Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10703 | 20211206-9 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-06 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44545 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070320211206-9Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1070320211206-9Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10728 | 20211207-11 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072820211207-11Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting1072820211207-11Excavator - 30 ton- After Jan 1081107.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10728 | 20211207-11 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072820211207-11Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1072820211207-11Excavator - 36 ton- After Jan 1081175.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10728 | 20211207-11 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072820211207-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1072820211207-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10728 | 20211207-11 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072820211207-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1072820211207-11Light Truck - Pick up- After Jan 102487.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10728 | 20211207-11 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072820211207-11L.O.A.2420 | Corbiere and Sons Contracting1072820211207-11L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10728 | 20211207-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072820211207-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1072820211207-11Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10728 | 20211207-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072820211207-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1072820211207-11Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10730 | 20211207-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | Marathon Camp | Marathon Camp | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073020211207-13Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1073020211207-13Pickup w/ plow and sander2.5200INV# 157 | [5 empty] | 1 | 200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10730 | 20211207-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | Marathon Camp | Marathon Camp | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073020211207-13Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1073020211207-13Operator - Intermdiate - After Jan 102.5175INV# 157 | [5 empty] | 1 | 175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10720 | 20211207-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C117 - C128 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072020211207-3Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1072020211207-3Grader - Cat 12 to 14 or equal- After Jan 103380.94INV# 157 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10720 | 20211207-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C117 - C128 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072020211207-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1072020211207-3Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10720 | 20211207-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C117 - C128 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072020211207-3L.O.A.1210 | Corbiere and Sons Contracting1072020211207-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10720 | 20211207-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Cooks for the day | 5 | C117 - C128 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072020211207-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1072020211207-3Operator - Principle - After Jan 105375INV# 157 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10721 | 20211207-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072120211207-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1072120211207-4Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10721 | 20211207-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072120211207-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1072120211207-4Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10721 | 20211207-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072120211207-4L.O.A.1210 | Corbiere and Sons Contracting1072120211207-4L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10721 | 20211207-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ doing WAM in Whitesands for the day | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072120211207-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1072120211207-4Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10722 | 20211207-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072220211207-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1072220211207-5Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10722 | 20211207-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072220211207-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1072220211207-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10722 | 20211207-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072220211207-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1072220211207-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10722 | 20211207-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072220211207-5L.O.A.2420 | Corbiere and Sons Contracting1072220211207-5L.O.A.2420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10722 | 20211207-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072220211207-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1072220211207-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10722 | 20211207-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1072220211207-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1072220211207-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10723 | 20211207-6 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072320211207-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1072320211207-6Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10723 | 20211207-6 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072320211207-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1072320211207-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10723 | 20211207-6 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072320211207-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1072320211207-6Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10723 | 20211207-6 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072320211207-6L.O.A.1210 | Corbiere and Sons Contracting1072320211207-6L.O.A.1210INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10723 | 20211207-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Peninsula | 6 | C268-D005 | Peninsula | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072320211207-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1072320211207-6Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10725 | 20211207-8 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072520211207-8Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1072520211207-8Excavator - 30 ton- After Jan 10101384.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10725 | 20211207-8 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072520211207-8Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1072520211207-8Excavator - 36 ton- After Jan 1091322.64INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10725 | 20211207-8 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072520211207-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1072520211207-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10725 | 20211207-8 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072520211207-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1072520211207-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10725 | 20211207-8 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072520211207-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1072520211207-8Light Truck - Pick up- After Jan 103731.25INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10725 | 20211207-8 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072520211207-8Foreman121140 | Corbiere and Sons Contracting1072520211207-8Foreman121140INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10725 | 20211207-8 | 53510606 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072520211207-8L.O.A.4840 | Corbiere and Sons Contracting1072520211207-8L.O.A.4840INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10725 | 20211207-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072520211207-8Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1072520211207-8Operator - Principle - After Jan 1010750INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10725 | 20211207-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072520211207-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1072520211207-8Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10725 | 20211207-8 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072520211207-8Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1072520211207-8Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10726 | 20211207-9 | 53560601 | Water Crossings | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 1 hour installing WC in Prairie - Ron spent 8 hours hauling in bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1072620211207-9Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1072620211207-9Dozer D6 or equal- After Jan 107920.36INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10726 | 20211207-9 | 53560601 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 1 hour installing WC in Prairie - Ron spent 8 hours hauling in bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1072620211207-9Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting1072620211207-9Excavator - 36 ton- After Jan 101146.96INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 146.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10726 | 20211207-9 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 1 hour installing WC in Prairie - Ron spent 8 hours hauling in bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1072620211207-9Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting1072620211207-9Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 12.21 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10726 | 20211207-9 | 53560601 | Water Crossings | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 1 hour installing WC in Prairie - Ron spent 8 hours hauling in bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1072620211207-9L.O.A.1210 | Corbiere and Sons Contracting1072620211207-9L.O.A.1210INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10726 | 20211207-9 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 1 hour installing WC in Prairie - Ron spent 8 hours hauling in bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1072620211207-9Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting1072620211207-9Operator - Principle - After Jan 10175INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10726 | 20211207-9 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-07 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 1 hour installing WC in Prairie - Ron spent 8 hours hauling in bridges with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1072620211207-9Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1072620211207-9Operator - Principle - After Jan 108600INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10740 | 20211208-10 | 53560601 | Water Crossings | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs and Ron spent 2 hours dragging WCs with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1074020211208-10Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1074020211208-10Dozer D6 or equal- After Jan 102262.96INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10740 | 20211208-10 | 53560601 | Water Crossings | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs and Ron spent 2 hours dragging WCs with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1074020211208-10Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting1074020211208-10Excavator - 30 ton- After Jan 102276.9INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10740 | 20211208-10 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs and Ron spent 2 hours dragging WCs with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1074020211208-10Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting1074020211208-10Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10740 | 20211208-10 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs and Ron spent 2 hours dragging WCs with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1074020211208-10Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1074020211208-10Operator - Principle - After Jan 102150INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10740 | 20211208-10 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs and Ron spent 2 hours dragging WCs with DZ | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000/7938/7870/7880 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1074020211208-10Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1074020211208-10Operator - Principle - After Jan 102150INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10742 | 20211208-12 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074220211208-12Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1074220211208-12Excavator - 30 ton- After Jan 10101384.5INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10742 | 20211208-12 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074220211208-12Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1074220211208-12Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10742 | 20211208-12 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074220211208-12Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1074220211208-12Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10742 | 20211208-12 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074220211208-12Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1074220211208-12Light Truck - Pick up- After Jan 104975INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10742 | 20211208-12 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074220211208-12Foreman121140 | Corbiere and Sons Contracting1074220211208-12Foreman121140INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10742 | 20211208-12 | 53510606 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074220211208-12L.O.A.4840 | Corbiere and Sons Contracting1074220211208-12L.O.A.4840INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10742 | 20211208-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074220211208-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1074220211208-12Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10742 | 20211208-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074220211208-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1074220211208-12Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10742 | 20211208-12 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074220211208-12Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1074220211208-12Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10733 | 20211208-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073320211208-3Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1073320211208-3Pickup w/ plow and sander4320INV# 157 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10733 | 20211208-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073320211208-3L.O.A.1210 | Corbiere and Sons Contracting1073320211208-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10733 | 20211208-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073320211208-3Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1073320211208-3Operator - Intermdiate - After Jan 104280INV# 157 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10734 | 20211208-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073420211208-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1073420211208-4Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10734 | 20211208-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073420211208-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1073420211208-4Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10734 | 20211208-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073420211208-4Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1073420211208-4Pickup w/ plow and sander3240INV# 157 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10734 | 20211208-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073420211208-4L.O.A.1210 | Corbiere and Sons Contracting1073420211208-4L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10734 | 20211208-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073420211208-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1073420211208-4Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10734 | 20211208-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073420211208-4Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1073420211208-4Operator - Intermdiate - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10735 | 20211208-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073520211208-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1073520211208-5Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10735 | 20211208-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073520211208-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1073520211208-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10735 | 20211208-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073520211208-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1073520211208-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10735 | 20211208-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073520211208-5Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1073520211208-5Pickup w/ plow and sander4320INV# 157 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10735 | 20211208-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073520211208-5L.O.A.2420 | Corbiere and Sons Contracting1073520211208-5L.O.A.2420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10735 | 20211208-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073520211208-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1073520211208-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10735 | 20211208-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073520211208-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1073520211208-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10735 | 20211208-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073520211208-5Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1073520211208-5Operator - Intermdiate - After Jan 104280INV# 157 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10736 | 20211208-6 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of 3rd grader for WAM | 5 | C030-C128 | WF5 | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073620211208-6Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1073620211208-6Tractor Trailer - 60 Ton- After Jan 10222692.58INV# 157 | [5 empty] | 1 | 2692.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10736 | 20211208-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of 3rd grader for WAM | 5 | C030-C128 | WF5 | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073620211208-6L.O.A.1210 | Corbiere and Sons Contracting1073620211208-6L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10736 | 20211208-6 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of 3rd grader for WAM | 5 | C030-C128 | WF5 | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1073620211208-6Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1073620211208-6Driver - AZ - After Jan 10221540INV# 157 | [5 empty] | 1 | 1540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10737 | 20211208-7 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073720211208-7Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1073720211208-7Excavator - 36 ton- After Jan 1091322.64INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10737 | 20211208-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073720211208-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1073720211208-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10737 | 20211208-7 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073720211208-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1073720211208-7Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10737 | 20211208-7 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073720211208-7L.O.A.1210 | Corbiere and Sons Contracting1073720211208-7L.O.A.1210INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10737 | 20211208-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073720211208-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1073720211208-7Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10738 | 20211208-8 | 53560602 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1073820211208-8Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1073820211208-8Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10738 | 20211208-8 | 53560602 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1073820211208-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1073820211208-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10738 | 20211208-8 | 53560602 | Water Crossings | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1073820211208-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1073820211208-8Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10738 | 20211208-8 | 53560602 | Water Crossings | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1073820211208-8L.O.A.1210 | Corbiere and Sons Contracting1073820211208-8L.O.A.1210INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10738 | 20211208-8 | 53560602 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1073820211208-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1073820211208-8Operator - Principle - After Jan 1011825INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10739 | 20211208-9 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 1 | Dynamic | 103.84 | 0 |  |  | 138.45 | 17.9985 | 156.4485 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073920211208-9Excavator - 30 ton- After Jan 101138.45 | Corbiere and Sons Contracting1073920211208-9Excavator - 30 ton- After Jan 101138.45INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 138.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10739 | 20211208-9 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073920211208-9Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1073920211208-9Excavator - 36 ton- After Jan 1081175.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10739 | 20211208-9 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073920211208-9Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting1073920211208-9Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 12.21 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10739 | 20211208-9 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073920211208-9Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1073920211208-9Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10739 | 20211208-9 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073920211208-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1073920211208-9Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10739 | 20211208-9 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073920211208-9L.O.A.2420 | Corbiere and Sons Contracting1073920211208-9L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10739 | 20211208-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073920211208-9Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1073920211208-9Operator - Principle - After Jan 109675INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10739 | 20211208-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-12-08 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073920211208-9Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1073920211208-9Operator - Principle - After Jan 104300INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10752 | 20211209-10 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075220211209-10Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1075220211209-10Excavator - 30 ton- After Jan 105692.25INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10752 | 20211209-10 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075220211209-10Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1075220211209-10Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10752 | 20211209-10 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075220211209-10Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1075220211209-10Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10752 | 20211209-10 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075220211209-10Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1075220211209-10Light Truck - Pick up- After Jan 104975INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10752 | 20211209-10 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075220211209-10Foreman121140 | Corbiere and Sons Contracting1075220211209-10Foreman121140INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10752 | 20211209-10 | 53510606 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075220211209-10L.O.A.4840 | Corbiere and Sons Contracting1075220211209-10L.O.A.4840INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10752 | 20211209-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075220211209-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1075220211209-10Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10752 | 20211209-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075220211209-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1075220211209-10Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10752 | 20211209-10 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075220211209-10Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1075220211209-10Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10745 | 20211209-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074520211209-3Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1074520211209-3Pickup w/ plow and sander11880INV# 157 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10745 | 20211209-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074520211209-3L.O.A.1210 | Corbiere and Sons Contracting1074520211209-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10745 | 20211209-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074520211209-3Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1074520211209-3Operator - Intermdiate - After Jan 1011770INV# 157 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10746 | 20211209-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074620211209-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1074620211209-4Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10746 | 20211209-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074620211209-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1074620211209-4Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10746 | 20211209-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074620211209-4Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1074620211209-4Pickup w/ plow and sander5400INV# 157 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10746 | 20211209-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074620211209-4L.O.A.2420 | Corbiere and Sons Contracting1074620211209-4L.O.A.2420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10746 | 20211209-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074620211209-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1074620211209-4Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10746 | 20211209-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074620211209-4Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting1074620211209-4Operator - Intermdiate - After Jan 105350INV# 157 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10747 | 20211209-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074720211209-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1074720211209-5Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10747 | 20211209-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074720211209-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1074720211209-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10747 | 20211209-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074720211209-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1074720211209-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10747 | 20211209-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074720211209-5Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1074720211209-5Pickup w/ plow and sander5400INV# 157 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10747 | 20211209-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074720211209-5L.O.A.2420 | Corbiere and Sons Contracting1074720211209-5L.O.A.2420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10747 | 20211209-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074720211209-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1074720211209-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10747 | 20211209-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074720211209-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1074720211209-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10747 | 20211209-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1074720211209-5Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting1074720211209-5Operator - Intermdiate - After Jan 105350INV# 157 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10748 | 20211209-6 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074820211209-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1074820211209-6Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10748 | 20211209-6 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074820211209-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1074820211209-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10748 | 20211209-6 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074820211209-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1074820211209-6Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10748 | 20211209-6 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074820211209-6L.O.A.1210 | Corbiere and Sons Contracting1074820211209-6L.O.A.1210INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10748 | 20211209-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074820211209-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1074820211209-6Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10749 | 20211209-7 | 53560602 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1074920211209-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1074920211209-7Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10749 | 20211209-7 | 53560602 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1074920211209-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1074920211209-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10749 | 20211209-7 | 53560602 | Water Crossings | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1074920211209-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1074920211209-7Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10749 | 20211209-7 | 53560602 | Water Crossings | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1074920211209-7L.O.A.1210 | Corbiere and Sons Contracting1074920211209-7L.O.A.1210INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10749 | 20211209-7 | 53560602 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1074920211209-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1074920211209-7Operator - Principle - After Jan 1011825INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10750 | 20211209-8 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075020211209-8Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting1075020211209-8Dozer D6 or equal- After Jan 106788.88INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10750 | 20211209-8 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075020211209-8Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1075020211209-8Excavator - 36 ton- After Jan 1081175.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10750 | 20211209-8 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075020211209-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1075020211209-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10750 | 20211209-8 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075020211209-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1075020211209-8Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10750 | 20211209-8 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075020211209-8L.O.A.2420 | Corbiere and Sons Contracting1075020211209-8L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10750 | 20211209-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075020211209-8Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1075020211209-8Operator - Principle - After Jan 109675INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10750 | 20211209-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075020211209-8Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1075020211209-8Operator - Principle - After Jan 107525INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10751 | 20211209-9 | 53560602 | Water Crossings | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs and Ron spent 4 hours dragging WCs with DZ, WC 8000, WC 7938, WC 7870, WC 7880 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000, 7938, 7870, 7880 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1075120211209-9Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1075120211209-9Dozer D6 or equal- After Jan 104525.92INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10751 | 20211209-9 | 53560601 | Water Crossings | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs and Ron spent 4 hours dragging WCs with DZ, WC 8000, WC 7938, WC 7870, WC 7880 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000, 7938, 7870, 7880 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1075120211209-9Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting1075120211209-9Excavator - 30 ton- After Jan 102276.9INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10751 | 20211209-9 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs and Ron spent 4 hours dragging WCs with DZ, WC 8000, WC 7938, WC 7870, WC 7880 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000, 7938, 7870, 7880 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1075120211209-9Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting1075120211209-9Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10751 | 20211209-9 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs and Ron spent 4 hours dragging WCs with DZ, WC 8000, WC 7938, WC 7870, WC 7880 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000, 7938, 7870, 7880 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1075120211209-9Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1075120211209-9Operator - Principle - After Jan 102150INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10751 | 20211209-9 | 53560602 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-12-09 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs and Ron spent 4 hours dragging WCs with DZ, WC 8000, WC 7938, WC 7870, WC 7880 | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000, 7938, 7870, 7880 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1075120211209-9Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1075120211209-9Operator - Principle - After Jan 104300INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10760 | 20211210-10 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  |  |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1076020211210-10Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1076020211210-10Dozer D6 or equal- After Jan 1091183.32INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10760 | 20211210-10 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  |  |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1076020211210-10Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1076020211210-10Excavator - 36 ton- After Jan 1071028.72INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10760 | 20211210-10 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  |  |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1076020211210-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1076020211210-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10760 | 20211210-10 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  |  |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1076020211210-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1076020211210-10Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10760 | 20211210-10 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  |  |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1076020211210-10L.O.A.2420 | Corbiere and Sons Contracting1076020211210-10L.O.A.2420INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10760 | 20211210-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  |  |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1076020211210-10Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1076020211210-10Operator - Principle - After Jan 108600INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10760 | 20211210-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  |  |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1076020211210-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1076020211210-10Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10761 | 20211210-11 | 53560601 | Water Crossings | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000, 7938, 7870, 7880 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1076120211210-11Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting1076120211210-11Excavator - 30 ton- After Jan 102276.9INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10761 | 20211210-11 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000, 7938, 7870, 7880 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1076120211210-11Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting1076120211210-11Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10761 | 20211210-11 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cody spent 2 hours on WCs | 6 | C171-C185 | Prairie River | 0 | 44542 |  | 36 | 44546 |  |  | 8000, 7938, 7870, 7880 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1076120211210-11Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1076120211210-11Operator - Principle - After Jan 102150INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10762 | 20211210-12 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 1 | Dynamic | 103.84 | 0 |  |  | 138.45 | 17.9985 | 156.4485 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076220211210-12Excavator - 30 ton- After Jan 101138.45 | Corbiere and Sons Contracting1076220211210-12Excavator - 30 ton- After Jan 101138.45INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 138.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10762 | 20211210-12 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076220211210-12Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1076220211210-12Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10762 | 20211210-12 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076220211210-12Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting1076220211210-12Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 12.21 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10762 | 20211210-12 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076220211210-12Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1076220211210-12Light Truck - Pick up- After Jan 104975INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10762 | 20211210-12 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076220211210-12Foreman121140 | Corbiere and Sons Contracting1076220211210-12Foreman121140INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10762 | 20211210-12 | 53510606 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076220211210-12L.O.A.4840 | Corbiere and Sons Contracting1076220211210-12L.O.A.4840INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10762 | 20211210-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076220211210-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1076220211210-12Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10762 | 20211210-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076220211210-12Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1076220211210-12Operator - Principle - After Jan 105375INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10762 | 20211210-12 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076220211210-12Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1076220211210-12Labourer - General - After Jan 1011660INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10753 | 20211210-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075320211210-3Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1075320211210-3Pickup w/ plow and sander11880INV# 157 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10753 | 20211210-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075320211210-3L.O.A.1210 | Corbiere and Sons Contracting1075320211210-3L.O.A.1210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10753 | 20211210-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and sander working in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075320211210-3Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1075320211210-3Operator - Intermdiate - After Jan 1011770INV# 157 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10754 | 20211210-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3.5 | Dynamic | 98.61 | 0 |  |  | 460.18 | 59.8234 | 520.0034 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by DZ and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075420211210-4Dozer D6 or equal- After Jan 103.5460.18 | Corbiere and Sons Contracting1075420211210-4Dozer D6 or equal- After Jan 103.5460.18INV# 157 | [5 empty] | 1 | 460.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10754 | 20211210-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by DZ and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075420211210-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1075420211210-4Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10754 | 20211210-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by DZ and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075420211210-4Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1075420211210-4Pickup w/ plow and sander3240INV# 157 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10754 | 20211210-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by DZ and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075420211210-4L.O.A.2420 | Corbiere and Sons Contracting1075420211210-4L.O.A.2420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10754 | 20211210-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by DZ and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075420211210-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1075420211210-4Operator - Principle - After Jan 105375INV# 157 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10754 | 20211210-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities by DZ and pickup w/plow and sander | 5 | C070-C075 | White Sand | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075420211210-4Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1075420211210-4Operator - Intermdiate - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10755 | 20211210-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075520211210-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1075520211210-5Dozer D6 or equal- After Jan 10101314.8INV# 157 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10755 | 20211210-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075520211210-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1075520211210-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV# 157 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10755 | 20211210-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075520211210-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1075520211210-5Light Truck - Pick up- After Jan 101243.75INV# 157 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10755 | 20211210-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075520211210-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1075520211210-5Pickup w/ plow and sander3240INV# 157 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10755 | 20211210-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075520211210-5L.O.A.2420 | Corbiere and Sons Contracting1075520211210-5L.O.A.2420INV# 157 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10755 | 20211210-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075520211210-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1075520211210-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10755 | 20211210-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 |  | 825 | 107.25 | 932.25 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075520211210-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1075520211210-5Operator - Principle - After Jan 1011825INV# 157 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10755 | 20211210-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075520211210-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1075520211210-5Operator - Intermdiate - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10756 | 20211210-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities | 5 | C031-C049 | Pays Plat River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075620211210-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1075620211210-6Pickup w/ plow and sander3240INV# 157 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10756 | 20211210-6 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities | 5 | C031-C049 | Pays Plat River | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075620211210-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1075620211210-6Operator - Intermdiate - After Jan 103210INV# 157 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10757 | 20211210-7 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C028-C029 | Cavers | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075720211210-7Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1075720211210-7Pickup w/ plow and sander2160INV# 157 | [5 empty] | 1 | 160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10757 | 20211210-7 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C028-C029 | Cavers | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1075720211210-7Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1075720211210-7Operator - Intermdiate - After Jan 102140INV# 157 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10758 | 20211210-8 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075820211210-8Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1075820211210-8Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10758 | 20211210-8 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075820211210-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1075820211210-8Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10758 | 20211210-8 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075820211210-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1075820211210-8Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10758 | 20211210-8 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075820211210-8L.O.A.1210 | Corbiere and Sons Contracting1075820211210-8L.O.A.1210INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10758 | 20211210-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1075820211210-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1075820211210-8Operator - Principle - After Jan 1011825INV# 157 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10759 | 20211210-9 | 53560602 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1075920211210-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1075920211210-9Excavator - 36 ton- After Jan 10101469.6INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10759 | 20211210-9 | 53560602 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1075920211210-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1075920211210-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10759 | 20211210-9 | 53560602 | Water Crossings | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1075920211210-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1075920211210-9Light Truck - Pick up- After Jan 101243.75INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10759 | 20211210-9 | 53560602 | Water Crossings | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1075920211210-9L.O.A.1210 | Corbiere and Sons Contracting1075920211210-9L.O.A.1210INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10759 | 20211210-9 | 53560602 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-10 | 0 | INV# 157 | 44547 | 173 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 |  |  | 8390 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1075920211210-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1075920211210-9Operator - Principle - After Jan 1011825INV# 157 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10773 | 20211211-10 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Ex into Neys road and OP started on Road towards C230 | 6 | C219-C235 | Neys | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077320211211-10Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1077320211211-10Excavator - 36 ton- After Jan 1071028.72INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10773 | 20211211-10 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Ex into Neys road and OP started on Road towards C230 | 6 | C219-C235 | Neys | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077320211211-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1077320211211-10Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10773 | 20211211-10 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 91.79 | 0 |  |  | 673.145 | 87.5088 | 760.6539 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Ex into Neys road and OP started on Road towards C230 | 6 | C219-C235 | Neys | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077320211211-10Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting1077320211211-10Tractor Trailer - 60 Ton- After Jan 105.5673.145INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 673.145 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10773 | 20211211-10 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Ex into Neys road and OP started on Road towards C230 | 6 | C219-C235 | Neys | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077320211211-10L.O.A.2420 | Corbiere and Sons Contracting1077320211211-10L.O.A.2420INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10773 | 20211211-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Ex into Neys road and OP started on Road towards C230 | 6 | C219-C235 | Neys | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077320211211-10Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1077320211211-10Operator - Principle - After Jan 109675INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10773 | 20211211-10 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Ex into Neys road and OP started on Road towards C230 | 6 | C219-C235 | Neys | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077320211211-10Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting1077320211211-10Driver - AZ - After Jan 105.5385INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10774 | 20211211-11 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4.5 | Dynamic | 98.61 | 0 |  |  | 591.66 | 76.9158 | 668.5758 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over to Santoy and OP got started on Roads | 6 | C158-C170 | Santoy Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077420211211-11Dozer D6 or equal- After Jan 104.5591.66 | Corbiere and Sons Contracting1077420211211-11Dozer D6 or equal- After Jan 104.5591.66INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 591.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10774 | 20211211-11 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 91.79 | 0 |  |  | 673.145 | 87.5088 | 760.6539 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over to Santoy and OP got started on Roads | 6 | C158-C170 | Santoy Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077420211211-11Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting1077420211211-11Tractor Trailer - 60 Ton- After Jan 105.5673.145INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 673.145 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10774 | 20211211-11 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over to Santoy and OP got started on Roads | 6 | C158-C170 | Santoy Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077420211211-11L.O.A.1210 | Corbiere and Sons Contracting1077420211211-11L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10774 | 20211211-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over to Santoy and OP got started on Roads | 6 | C158-C170 | Santoy Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077420211211-11Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting1077420211211-11Operator - Principle - After Jan 106.5487.5INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10774 | 20211211-11 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over to Santoy and OP got started on Roads | 6 | C158-C170 | Santoy Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077420211211-11Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting1077420211211-11Driver - AZ - After Jan 105.5385INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10775 | 20211211-12 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077520211211-12Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1077520211211-12Excavator - 30 ton- After Jan 10101384.5INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10775 | 20211211-12 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077520211211-12Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1077520211211-12Excavator - 36 ton- After Jan 10101469.6INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10775 | 20211211-12 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077520211211-12Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1077520211211-12Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10775 | 20211211-12 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077520211211-12Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1077520211211-12Light Truck - Pick up- After Jan 104975INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10775 | 20211211-12 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077520211211-12Foreman121140 | Corbiere and Sons Contracting1077520211211-12Foreman121140INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10775 | 20211211-12 | 53510606 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077520211211-12L.O.A.4840 | Corbiere and Sons Contracting1077520211211-12L.O.A.4840INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10775 | 20211211-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077520211211-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1077520211211-12Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10775 | 20211211-12 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077520211211-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1077520211211-12Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10775 | 20211211-12 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077520211211-12Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1077520211211-12Labourer - General - After Jan 1011660INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10764 | 20211211-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12 | Dynamic | 95.24 | 0 |  |  | 1523.76 | 198.0888 | 1721.8488 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44543 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076420211211-3Grader - Cat 12 to 14 or equal- After Jan 10121523.76 | Corbiere and Sons Contracting1076420211211-3Grader - Cat 12 to 14 or equal- After Jan 10121523.76INV #162 | [5 empty] | 1 | 1523.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10764 | 20211211-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44543 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076420211211-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1076420211211-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10764 | 20211211-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44543 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076420211211-3Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1076420211211-3Pickup w/ plow and sander5.5440INV #162 | [5 empty] | 1 | 440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10764 | 20211211-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44543 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076420211211-3L.O.A.2420 | Corbiere and Sons Contracting1076420211211-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10764 | 20211211-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44543 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076420211211-3Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1076420211211-3Operator - Principle - After Jan 1013975INV #162 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10764 | 20211211-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44543 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076420211211-3Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1076420211211-3Operator - Intermdiate - After Jan 105.5385INV #162 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10765 | 20211211-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 | 44543 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076520211211-4Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1076520211211-4Pickup w/ plow and sander3240INV #162 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10765 | 20211211-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 | 44543 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076520211211-4L.O.A.1210 | Corbiere and Sons Contracting1076520211211-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10765 | 20211211-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 | 44543 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076520211211-4Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1076520211211-4Operator - Intermdiate - After Jan 103210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10768 | 20211211-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076820211211-5Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1076820211211-5Dozer D6 or equal- After Jan 10121577.76INV #162 | [5 empty] | 1 | 1577.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10768 | 20211211-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12 | Dynamic | 95.24 | 0 |  |  | 1523.76 | 198.0888 | 1721.8488 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076820211211-5Grader - Cat 12 to 14 or equal- After Jan 10121523.76 | Corbiere and Sons Contracting1076820211211-5Grader - Cat 12 to 14 or equal- After Jan 10121523.76INV #162 | [5 empty] | 1 | 1523.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10768 | 20211211-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076820211211-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1076820211211-5Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10768 | 20211211-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076820211211-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1076820211211-5Pickup w/ plow and sander3240INV #162 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10768 | 20211211-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076820211211-5L.O.A.2420 | Corbiere and Sons Contracting1076820211211-5L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10768 | 20211211-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076820211211-5Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1076820211211-5Operator - Principle - After Jan 1013975INV #162 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10768 | 20211211-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076820211211-5Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1076820211211-5Operator - Principle - After Jan 1013975INV #162 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10768 | 20211211-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1076820211211-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1076820211211-5Operator - Intermdiate - After Jan 103210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10769 | 20211211-6 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076920211211-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1076920211211-6Excavator - 36 ton- After Jan 10101469.6INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10769 | 20211211-6 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076920211211-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1076920211211-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10769 | 20211211-6 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076920211211-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1076920211211-6Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10769 | 20211211-6 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076920211211-6L.O.A.1210 | Corbiere and Sons Contracting1076920211211-6L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10769 | 20211211-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1076920211211-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1076920211211-6Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10770 | 20211211-7 | 53560602 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077020211211-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1077020211211-7Excavator - 36 ton- After Jan 10101469.6INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10770 | 20211211-7 | 53560602 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077020211211-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1077020211211-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10770 | 20211211-7 | 53560602 | Water Crossings | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077020211211-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1077020211211-7Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10770 | 20211211-7 | 53560602 | Water Crossings | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077020211211-7L.O.A.1210 | Corbiere and Sons Contracting1077020211211-7L.O.A.1210INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10770 | 20211211-7 | 53560602 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on WC8390 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44542 |  | 36 | 44546 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077020211211-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1077020211211-7Operator - Principle - After Jan 1011825INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10771 | 20211211-8 | 53560601 | Water Crossings | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 1 | Dynamic | 98.61 | 0 |  |  | 131.48 | 17.0924 | 148.5724 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing up WC603 | 6 | C171-C185 | Prairie River | 0 | 44546 |  | 36 | 44546 |  |  | 603 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1077120211211-8Dozer D6 or equal- After Jan 101131.48 | Corbiere and Sons Contracting1077120211211-8Dozer D6 or equal- After Jan 101131.48INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 131.48 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10771 | 20211211-8 | 53560601 | Water Crossings | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing up WC603 | 6 | C171-C185 | Prairie River | 0 | 44546 |  | 36 | 44546 |  |  | 603 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1077120211211-8Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting1077120211211-8Excavator - 30 ton- After Jan 102276.9INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10771 | 20211211-8 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing up WC603 | 6 | C171-C185 | Prairie River | 0 | 44546 |  | 36 | 44546 |  |  | 603 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1077120211211-8Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting1077120211211-8Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10771 | 20211211-8 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing up WC603 | 6 | C171-C185 | Prairie River | 0 | 44546 |  | 36 | 44546 |  |  | 603 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1077120211211-8Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1077120211211-8Operator - Principle - After Jan 102150INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10771 | 20211211-8 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2021-12-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing up WC603 | 6 | C171-C185 | Prairie River | 0 | 44546 |  | 36 | 44546 |  |  | 603 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1077120211211-8Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting1077120211211-8Operator - Principle - After Jan 10175INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10882 | 20211212-10 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088220211212-10Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1088220211212-10Excavator - 30 ton- After Jan 10101384.5INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10882 | 20211212-10 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088220211212-10Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1088220211212-10Excavator - 36 ton- After Jan 10101469.6INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10882 | 20211212-10 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088220211212-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1088220211212-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10882 | 20211212-10 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088220211212-10Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1088220211212-10Light Truck - Pick up- After Jan 104975INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10882 | 20211212-10 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088220211212-10Foreman121140 | Corbiere and Sons Contracting1088220211212-10Foreman121140INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10882 | 20211212-10 | 53510606 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088220211212-10L.O.A.4840 | Corbiere and Sons Contracting1088220211212-10L.O.A.4840INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10882 | 20211212-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088220211212-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1088220211212-10Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10882 | 20211212-10 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088220211212-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1088220211212-10Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10882 | 20211212-10 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088220211212-10Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1088220211212-10Labourer - General - After Jan 1011660INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10875 | 20211212-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087520211212-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1087520211212-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10875 | 20211212-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087520211212-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1087520211212-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10875 | 20211212-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087520211212-3Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1087520211212-3Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10875 | 20211212-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087520211212-3L.O.A.2420 | Corbiere and Sons Contracting1087520211212-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10875 | 20211212-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087520211212-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1087520211212-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10875 | 20211212-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087520211212-3Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1087520211212-3Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10876 | 20211212-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087620211212-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1087620211212-4Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10876 | 20211212-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087620211212-4Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1087620211212-4Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10877 | 20211212-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087720211212-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1087720211212-5Dozer D6 or equal- After Jan 10101314.8INV #162 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10877 | 20211212-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087720211212-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1087720211212-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10877 | 20211212-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087720211212-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1087720211212-5Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10877 | 20211212-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087720211212-5Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1087720211212-5Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10877 | 20211212-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087720211212-5L.O.A.2420 | Corbiere and Sons Contracting1087720211212-5L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10877 | 20211212-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087720211212-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1087720211212-5Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10877 | 20211212-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087720211212-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1087720211212-5Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10877 | 20211212-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1087720211212-5Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1087720211212-5Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10878 | 20211212-6 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1087820211212-6Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1087820211212-6Excavator - 36 ton- After Jan 105734.8INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10878 | 20211212-6 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1087820211212-6Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1087820211212-6Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10878 | 20211212-6 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1087820211212-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1087820211212-6Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10878 | 20211212-6 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1087820211212-6L.O.A.1210 | Corbiere and Sons Contracting1087820211212-6L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10878 | 20211212-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Hare Lake | 6 | C257-C267 | Hare Lake Creek | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1087820211212-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1087820211212-6Operator - Principle - After Jan 106450INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10880 | 20211212-8 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Santoy Lake - Freeze in | 6 | C158-C170 | Santoy Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088020211212-8Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1088020211212-8Dozer D6 or equal- After Jan 102262.96INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10880 | 20211212-8 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Santoy Lake - Freeze in | 6 | C158-C170 | Santoy Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088020211212-8L.O.A.1210 | Corbiere and Sons Contracting1088020211212-8L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10880 | 20211212-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Santoy Lake - Freeze in | 6 | C158-C170 | Santoy Lake | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088020211212-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1088020211212-8Operator - Principle - After Jan 105375INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10881 | 20211212-9 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088120211212-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1088120211212-9Excavator - 36 ton- After Jan 10101469.6INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10881 | 20211212-9 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088120211212-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1088120211212-9Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10881 | 20211212-9 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088120211212-9L.O.A.1210 | Corbiere and Sons Contracting1088120211212-9L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10881 | 20211212-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-12 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44561 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088120211212-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1088120211212-9Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10887 | 20211213-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 37 | 44570 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088720211213-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1088720211213-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10887 | 20211213-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 37 | 44570 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088720211213-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1088720211213-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10887 | 20211213-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 37 | 44570 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088720211213-3Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1088720211213-3Pickup w/ plow and sander11880INV #162 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10887 | 20211213-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 37 | 44570 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088720211213-3L.O.A.2420 | Corbiere and Sons Contracting1088720211213-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10887 | 20211213-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 37 | 44570 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088720211213-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1088720211213-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10887 | 20211213-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44561 |  | 37 | 44570 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088720211213-3Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1088720211213-3Operator - Intermdiate - After Jan 1011770INV #162 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10888 | 20211213-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088820211213-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1088820211213-4Dozer D6 or equal- After Jan 10101314.8INV #162 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10888 | 20211213-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088820211213-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1088820211213-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10888 | 20211213-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088820211213-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1088820211213-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10888 | 20211213-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088820211213-4Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1088820211213-4Pickup w/ plow and sander11880INV #162 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10888 | 20211213-4 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  | 0 | 0 | 630 | 81.9 | 711.9 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088820211213-4L.O.A.3630 | Corbiere and Sons Contracting1088820211213-4L.O.A.3630INV #162 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10888 | 20211213-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088820211213-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1088820211213-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10888 | 20211213-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088820211213-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1088820211213-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10888 | 20211213-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1088820211213-4Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1088820211213-4Operator - Intermdiate - After Jan 1011770INV #162 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10889 | 20211213-5 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work completed to C234 and then machine demobed | 6 | C234 | Neys | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1088920211213-5Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1088920211213-5Excavator - 36 ton- After Jan 1071028.72INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10889 | 20211213-5 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work completed to C234 and then machine demobed | 6 | C234 | Neys | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1088920211213-5Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1088920211213-5Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10889 | 20211213-5 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work completed to C234 and then machine demobed | 6 | C234 | Neys | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1088920211213-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1088920211213-5Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10889 | 20211213-5 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work completed to C234 and then machine demobed | 6 | C234 | Neys | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1088920211213-5L.O.A.1210 | Corbiere and Sons Contracting1088920211213-5L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10889 | 20211213-5 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work completed to C234 and then machine demobed | 6 | C234 | Neys | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1088920211213-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1088920211213-5Operator - Principle - After Jan 108600INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10890 | 20211213-6 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex over to Jackfish and work continued there for rest of day; | 6 | C152-C157 | Jackfish Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089020211213-6Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1089020211213-6Excavator - 36 ton- After Jan 1091322.64INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10890 | 20211213-6 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex over to Jackfish and work continued there for rest of day; | 6 | C152-C157 | Jackfish Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089020211213-6Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1089020211213-6Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10890 | 20211213-6 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex over to Jackfish and work continued there for rest of day; | 6 | C152-C157 | Jackfish Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089020211213-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1089020211213-6Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10890 | 20211213-6 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex over to Jackfish and work continued there for rest of day; | 6 | C152-C157 | Jackfish Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089020211213-6Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1089020211213-6Tractor Trailer - 60 Ton- After Jan 103367.17INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10890 | 20211213-6 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex over to Jackfish and work continued there for rest of day; | 6 | C152-C157 | Jackfish Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089020211213-6L.O.A.2420 | Corbiere and Sons Contracting1089020211213-6L.O.A.2420INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10890 | 20211213-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex over to Jackfish and work continued there for rest of day; | 6 | C152-C157 | Jackfish Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089020211213-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1089020211213-6Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10890 | 20211213-6 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved ex over to Jackfish and work continued there for rest of day; | 6 | C152-C157 | Jackfish Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089020211213-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1089020211213-6Driver - AZ - After Jan 103210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10891 | 20211213-7 | 53560601 | Water Crossings | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  | Snow fill and mat bridge |  | Approved |  |  | Ron spent 3 hours finishing of WC's in Santoy Lake - | 6 | C158-C170 | Santoy Lake | 0 | 44561 |  | 37 | 44567 |  |  | 7820 / 7851 |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1089120211213-7Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1089120211213-7Dozer D6 or equal- After Jan 103394.44INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10891 | 20211213-7 | 53560601 | Water Crossings | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  | Snow fill and mat bridge |  | Approved |  |  | Ron spent 3 hours finishing of WC's in Santoy Lake - | 6 | C158-C170 | Santoy Lake | 0 | 44561 |  | 37 | 44567 |  |  | 7820 / 7851 |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1089120211213-7L.O.A.1210 | Corbiere and Sons Contracting1089120211213-7L.O.A.1210INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10891 | 20211213-7 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  | Snow fill and mat bridge |  | Approved |  |  | Ron spent 3 hours finishing of WC's in Santoy Lake - | 6 | C158-C170 | Santoy Lake | 0 | 44561 |  | 37 | 44567 |  |  | 7820 / 7851 |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1089120211213-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1089120211213-7Operator - Principle - After Jan 103225INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10892 | 20211213-8 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron finished up WRF while demobbing to be floated from Santoy | 6 | C158-C170 | Santoy Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089220211213-8Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1089220211213-8Dozer D6 or equal- After Jan 102262.96INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10892 | 20211213-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron finished up WRF while demobbing to be floated from Santoy | 6 | C158-C170 | Santoy Lake | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089220211213-8Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1089220211213-8Operator - Principle - After Jan 102150INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1089320211213-9Dozer D6 or equal- After Jan 104525.92INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1089320211213-9Excavator - 30 ton- After Jan 10101384.5INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1089320211213-9Excavator - 36 ton- After Jan 10101469.6INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1089320211213-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1089320211213-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1089320211213-9Light Truck - Pick up- After Jan 104975INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1089320211213-9Tractor Trailer - 60 Ton- After Jan 103367.17INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Foreman121140 | Corbiere and Sons Contracting1089320211213-9Foreman121140INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9L.O.A.4840 | Corbiere and Sons Contracting1089320211213-9L.O.A.4840INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1089320211213-9Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1089320211213-9Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1089320211213-9Operator - Principle - After Jan 106450INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1089320211213-9Driver - AZ - After Jan 103210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10893 | 20211213-9 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-13 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads | 6 | C130-C151 | Lake A | 0 | 44561 |  | 37 | 44567 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1089320211213-9Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1089320211213-9Labourer - General - After Jan 1011660INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10895 | 20211214-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089520211214-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1089520211214-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10895 | 20211214-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089520211214-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1089520211214-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10895 | 20211214-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089520211214-3Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1089520211214-3Pickup w/ plow and sander11880INV #162 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10895 | 20211214-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089520211214-3L.O.A.2420 | Corbiere and Sons Contracting1089520211214-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10895 | 20211214-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089520211214-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1089520211214-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10895 | 20211214-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089520211214-3Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1089520211214-3Operator - Intermdiate - After Jan 1011770INV #162 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10896 | 20211214-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089620211214-4Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1089620211214-4Dozer D6 or equal- After Jan 107920.36INV #162 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10896 | 20211214-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089620211214-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1089620211214-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10896 | 20211214-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089620211214-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1089620211214-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10896 | 20211214-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089620211214-4Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1089620211214-4Pickup w/ plow and sander11880INV #162 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10896 | 20211214-4 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089620211214-4L.O.A.3630 | Corbiere and Sons Contracting1089620211214-4L.O.A.3630INV #162 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10896 | 20211214-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089620211214-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1089620211214-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10896 | 20211214-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089620211214-4Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1089620211214-4Operator - Principle - After Jan 108600INV #162 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10896 | 20211214-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1089620211214-4Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1089620211214-4Operator - Intermdiate - After Jan 1011770INV #162 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10898 | 20211214-6 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed JD300 from KM4.5 on Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089820211214-6Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting1089820211214-6Excavator - 30 ton- After Jan 104553.8INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10898 | 20211214-6 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed JD300 from KM4.5 on Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089820211214-6Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1089820211214-6Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10898 | 20211214-6 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed JD300 from KM4.5 on Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089820211214-6L.O.A.1210 | Corbiere and Sons Contracting1089820211214-6L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10898 | 20211214-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed JD300 from KM4.5 on Prairie River Road | 6 | C171-C185 | Prairie River | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089820211214-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1089820211214-6Operator - Principle - After Jan 105375INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10899 | 20211214-7 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed 350 Hitachi from KM4, 329 CAT from KM5; | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089920211214-7Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting1089920211214-7Excavator - 30 ton- After Jan 104553.8INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10899 | 20211214-7 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed 350 Hitachi from KM4, 329 CAT from KM5; | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089920211214-7Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting1089920211214-7Excavator - 36 ton- After Jan 104587.84INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10899 | 20211214-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed 350 Hitachi from KM4, 329 CAT from KM5; | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089920211214-7Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1089920211214-7Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10899 | 20211214-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed 350 Hitachi from KM4, 329 CAT from KM5; | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089920211214-7Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1089920211214-7Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10899 | 20211214-7 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed 350 Hitachi from KM4, 329 CAT from KM5; | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089920211214-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1089920211214-7Light Truck - Pick up- After Jan 102487.5INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10899 | 20211214-7 | 53510606 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed 350 Hitachi from KM4, 329 CAT from KM5; | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089920211214-7Foreman6570 | Corbiere and Sons Contracting1089920211214-7Foreman6570INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10899 | 20211214-7 | 53510606 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed 350 Hitachi from KM4, 329 CAT from KM5; | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089920211214-7L.O.A.3630 | Corbiere and Sons Contracting1089920211214-7L.O.A.3630INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10899 | 20211214-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed 350 Hitachi from KM4, 329 CAT from KM5; | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089920211214-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1089920211214-7Operator - Principle - After Jan 108600INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10899 | 20211214-7 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP demobbed 350 Hitachi from KM4, 329 CAT from KM5; | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1089920211214-7Labourer - General - After Jan 105300 | Corbiere and Sons Contracting1089920211214-7Labourer - General - After Jan 105300INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10900 | 20211214-8 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | This should be under our snowfill crossing cost code as thats what these were for |  | Approved |  |  | Demobbing of rig mats and other debris from Lake A - This should be under our snowfill crossing cost code as thats what these were for | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 |  |  |  | ANWIN - Winter Only | Other | Mike Lecocq | 06 | Corbiere and Sons Contracting1090020211214-8Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1090020211214-8Dozer D6 or equal- After Jan 1091183.32INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10900 | 20211214-8 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | This should be under our snowfill crossing cost code as thats what these were for |  | Approved |  |  | Demobbing of rig mats and other debris from Lake A - This should be under our snowfill crossing cost code as thats what these were for | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 |  |  |  | ANWIN - Winter Only | Other | Mike Lecocq | 06 | Corbiere and Sons Contracting1090020211214-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1090020211214-8Light Truck - Pick up- After Jan 102487.5INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10900 | 20211214-8 | 53510606 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | This should be under our snowfill crossing cost code as thats what these were for |  | Approved |  |  | Demobbing of rig mats and other debris from Lake A - This should be under our snowfill crossing cost code as thats what these were for | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 |  |  |  | ANWIN - Winter Only | Other | Mike Lecocq | 06 | Corbiere and Sons Contracting1090020211214-8Foreman6570 | Corbiere and Sons Contracting1090020211214-8Foreman6570INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10900 | 20211214-8 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | This should be under our snowfill crossing cost code as thats what these were for |  | Approved |  |  | Demobbing of rig mats and other debris from Lake A - This should be under our snowfill crossing cost code as thats what these were for | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 |  |  |  | ANWIN - Winter Only | Other | Mike Lecocq | 06 | Corbiere and Sons Contracting1090020211214-8L.O.A.1210 | Corbiere and Sons Contracting1090020211214-8L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10900 | 20211214-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | This should be under our snowfill crossing cost code as thats what these were for |  | Approved |  |  | Demobbing of rig mats and other debris from Lake A - This should be under our snowfill crossing cost code as thats what these were for | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 |  |  |  | ANWIN - Winter Only | Other | Mike Lecocq | 06 | Corbiere and Sons Contracting1090020211214-8Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1090020211214-8Operator - Principle - After Jan 103225INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10900 | 20211214-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | This should be under our snowfill crossing cost code as thats what these were for |  | Approved |  |  | Demobbing of rig mats and other debris from Lake A - This should be under our snowfill crossing cost code as thats what these were for | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 |  |  |  | ANWIN - Winter Only | Other | Mike Lecocq | 06 | Corbiere and Sons Contracting1090020211214-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1090020211214-8Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10900 | 20211214-8 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-12-14 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | This should be under our snowfill crossing cost code as thats what these were for |  | Approved |  |  | Demobbing of rig mats and other debris from Lake A - This should be under our snowfill crossing cost code as thats what these were for | 6 | C130-C151 | Lake A | 0 | 44563 |  | 36 | 44567 |  |  |  | ANWIN - Winter Only | Other | Mike Lecocq | 06 | Corbiere and Sons Contracting1090020211214-8Labourer - General - After Jan 106360 | Corbiere and Sons Contracting1090020211214-8Labourer - General - After Jan 106360INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10901 | 20211215-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6.5 | Dynamic | 95.24 |  |  |  | 825.37 | 107.2981 | 932.6681 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090120211215-3Grader - Cat 12 to 14 or equal- After Jan 106.5825.37 | Corbiere and Sons Contracting1090120211215-3Grader - Cat 12 to 14 or equal- After Jan 106.5825.37INV #162 | [5 empty] | 1 | 825.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10901 | 20211215-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090120211215-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1090120211215-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10901 | 20211215-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090120211215-3Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1090120211215-3Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10901 | 20211215-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090120211215-3Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1090120211215-3Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10901 | 20211215-3 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090120211215-3L.O.A.3630 | Corbiere and Sons Contracting1090120211215-3L.O.A.3630INV #162 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10901 | 20211215-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7.5 | HR |  |  | 75 | 0 | 562.5 | 73.125 | 635.625 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090120211215-3Operator - Principle - After Jan 107.5562.5 | Corbiere and Sons Contracting1090120211215-3Operator - Principle - After Jan 107.5562.5INV #162 | [5 empty] | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10901 | 20211215-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090120211215-3Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1090120211215-3Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10901 | 20211215-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 36 | 44567 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090120211215-3Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1090120211215-3Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10902 | 20211215-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6.5 | Dynamic | 98.61 | 0 |  |  | 854.62 | 111.1006 | 965.7206 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090220211215-4Dozer D6 or equal- After Jan 106.5854.62 | Corbiere and Sons Contracting1090220211215-4Dozer D6 or equal- After Jan 106.5854.62INV #162 | [5 empty] | 1 | 854.62 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10902 | 20211215-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6.5 | Dynamic | 95.24 | 0 |  |  | 825.37 | 107.2981 | 932.6681 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090220211215-4Grader - Cat 12 to 14 or equal- After Jan 106.5825.37 | Corbiere and Sons Contracting1090220211215-4Grader - Cat 12 to 14 or equal- After Jan 106.5825.37INV #162 | [5 empty] | 1 | 825.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10902 | 20211215-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090220211215-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1090220211215-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10902 | 20211215-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090220211215-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1090220211215-4Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10902 | 20211215-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090220211215-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1090220211215-4Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10902 | 20211215-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090220211215-4L.O.A.2420 | Corbiere and Sons Contracting1090220211215-4L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10902 | 20211215-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7.5 | HR |  |  | 75 | 0 | 562.5 | 73.125 | 635.625 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090220211215-4Operator - Principle - After Jan 107.5562.5 | Corbiere and Sons Contracting1090220211215-4Operator - Principle - After Jan 107.5562.5INV #162 | [5 empty] | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10902 | 20211215-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7.5 | HR |  |  | 75 | 0 | 562.5 | 73.125 | 635.625 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090220211215-4Operator - Principle - After Jan 107.5562.5 | Corbiere and Sons Contracting1090220211215-4Operator - Principle - After Jan 107.5562.5INV #162 | [5 empty] | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10902 | 20211215-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090220211215-4Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1090220211215-4Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10902 | 20211215-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090220211215-4Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1090220211215-4Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10903 | 20211215-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C118-C128 | Terrace Bay | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090320211215-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1090320211215-5Pickup w/ plow and sander3240INV #162 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10903 | 20211215-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C118-C128 | Terrace Bay | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090320211215-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1090320211215-5Operator - Intermdiate - After Jan 103210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10905 | 20211215-7 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Jackfish and general demob activities | 6 | C152 - C157 | Jackfish Lake | 0 |  |  | 36 | 44573 |  |  |  | ANWIN - Winter Only |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1090520211215-7Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1090520211215-7Excavator - 36 ton- After Jan 105734.8INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10905 | 20211215-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Jackfish and general demob activities | 6 | C152 - C157 | Jackfish Lake | 0 |  |  | 36 | 44573 |  |  |  | ANWIN - Winter Only |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1090520211215-7Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1090520211215-7Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10905 | 20211215-7 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Jackfish and general demob activities | 6 | C152 - C157 | Jackfish Lake | 0 |  |  | 36 | 44573 |  |  |  | ANWIN - Winter Only |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1090520211215-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1090520211215-7Light Truck - Pick up- After Jan 102487.5INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10905 | 20211215-7 | 53510606 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Jackfish and general demob activities | 6 | C152 - C157 | Jackfish Lake | 0 |  |  | 36 | 44573 |  |  |  | ANWIN - Winter Only |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1090520211215-7Foreman111045 | Corbiere and Sons Contracting1090520211215-7Foreman111045INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10905 | 20211215-7 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Jackfish and general demob activities | 6 | C152 - C157 | Jackfish Lake | 0 |  |  | 36 | 44573 |  |  |  | ANWIN - Winter Only |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1090520211215-7L.O.A.2420 | Corbiere and Sons Contracting1090520211215-7L.O.A.2420INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10905 | 20211215-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Jackfish and general demob activities | 6 | C152 - C157 | Jackfish Lake | 0 |  |  | 36 | 44573 |  |  |  | ANWIN - Winter Only |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1090520211215-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1090520211215-7Operator - Principle - After Jan 106450INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10906 | 20211215-8 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved 329 ex into Santoy | 6 | C158-C170 | Santoy Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1090620211215-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1090620211215-8Tractor Trailer - 60 Ton- After Jan 104489.56INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10906 | 20211215-8 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved 329 ex into Santoy | 6 | C158-C170 | Santoy Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1090620211215-8L.O.A.1210 | Corbiere and Sons Contracting1090620211215-8L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10906 | 20211215-8 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-15 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved 329 ex into Santoy | 6 | C158-C170 | Santoy Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1090620211215-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1090620211215-8Driver - AZ - After Jan 104280INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1090820211216-3Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #162 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1090820211216-3Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #162 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1090820211216-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1090820211216-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1090820211216-3Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1090820211216-3Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3L.O.A.4840 | Corbiere and Sons Contracting1090820211216-3L.O.A.4840INV #162 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1090820211216-3Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1090820211216-3Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1090820211216-3Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10908 | 20211216-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090820211216-3Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1090820211216-3Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10909 | 20211216-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 0 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090920211216-4Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1090920211216-4Dozer D6 or equal- After Jan 105657.4INV #162 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10909 | 20211216-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090920211216-4Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1090920211216-4Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #162 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10909 | 20211216-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090920211216-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1090920211216-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10909 | 20211216-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090920211216-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1090920211216-4Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10909 | 20211216-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090920211216-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1090920211216-4Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10909 | 20211216-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090920211216-4L.O.A.2420 | Corbiere and Sons Contracting1090920211216-4L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10909 | 20211216-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090920211216-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1090920211216-4Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10909 | 20211216-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090920211216-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1090920211216-4Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10909 | 20211216-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090920211216-4Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1090920211216-4Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10909 | 20211216-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090920211216-4Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1090920211216-4Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10910 | 20211216-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091020211216-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1091020211216-5Pickup w/ plow and sander3240INV #162 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10910 | 20211216-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091020211216-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1091020211216-5Operator - Intermdiate - After Jan 103210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10912 | 20211216-7 | 53560601 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC7820 and WC7850.02 | 6 | C158-C170 | Santoy Lake | 0 |  |  | 36 | 44573 |  |  | 7820 / 7850.02 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1091220211216-7Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1091220211216-7Excavator - 36 ton- After Jan 1071028.72INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10912 | 20211216-7 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC7820 and WC7850.02 | 6 | C158-C170 | Santoy Lake | 0 |  |  | 36 | 44573 |  |  | 7820 / 7850.02 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1091220211216-7Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1091220211216-7Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10912 | 20211216-7 | 53560601 | Water Crossings | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC7820 and WC7850.02 | 6 | C158-C170 | Santoy Lake | 0 |  |  | 36 | 44573 |  |  | 7820 / 7850.02 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1091220211216-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1091220211216-7Light Truck - Pick up- After Jan 102487.5INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10912 | 20211216-7 | 53560601 | Water Crossings | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC7820 and WC7850.02 | 6 | C158-C170 | Santoy Lake | 0 |  |  | 36 | 44573 |  |  | 7820 / 7850.02 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1091220211216-7L.O.A.2420 | Corbiere and Sons Contracting1091220211216-7L.O.A.2420INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10912 | 20211216-7 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC7820 and WC7850.02 | 6 | C158-C170 | Santoy Lake | 0 |  |  | 36 | 44573 |  |  | 7820 / 7850.02 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1091220211216-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1091220211216-7Operator - Principle - After Jan 108600INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10912 | 20211216-7 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC7820 and WC7850.02 | 6 | C158-C170 | Santoy Lake | 0 |  |  | 36 | 44573 |  |  | 7820 / 7850.02 |  | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1091220211216-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1091220211216-7Operator - Principle - After Jan 105375INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10914 | 20211216-9 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Jackfish back to Manitoulin Island and other general demob | 6 | C152 - C157 | Jackfish Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1091420211216-9Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1091420211216-9Tractor Trailer - 60 Ton- After Jan 10222692.58INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 2692.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10914 | 20211216-9 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Jackfish back to Manitoulin Island and other general demob | 6 | C152 - C157 | Jackfish Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1091420211216-9L.O.A.1210 | Corbiere and Sons Contracting1091420211216-9L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10914 | 20211216-9 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Jackfish back to Manitoulin Island and other general demob | 6 | C152 - C157 | Jackfish Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1091420211216-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1091420211216-9Operator - Principle - After Jan 106450INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10914 | 20211216-9 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-12-16 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Jackfish back to Manitoulin Island and other general demob | 6 | C152 - C157 | Jackfish Lake | 0 |  |  | 36 | 44573 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1091420211216-9Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1091420211216-9Driver - AZ - After Jan 10221540INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 0 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting1091520211217-3Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29INV #162 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 0 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting1091520211217-3Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29INV #162 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1091520211217-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1091520211217-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1091520211217-3Pickup w/ plow and sander6480INV #162 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1091520211217-3Pickup w/ plow and sander6480INV #162 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3L.O.A.4840 | Corbiere and Sons Contracting1091520211217-3L.O.A.4840INV #162 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 0 | 0 | 862.5 | 112.125 | 974.625 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting1091520211217-3Operator - Principle - After Jan 1011.5862.5INV #162 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 0 | 0 | 862.5 | 112.125 | 974.625 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting1091520211217-3Operator - Principle - After Jan 1011.5862.5INV #162 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting1091520211217-3Operator - Intermdiate - After Jan 106420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10915 | 20211217-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091520211217-3Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting1091520211217-3Operator - Intermdiate - After Jan 106420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10916 | 20211217-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 0 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091620211217-4Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting1091620211217-4Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29INV #162 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10916 | 20211217-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091620211217-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1091620211217-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10916 | 20211217-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091620211217-4Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1091620211217-4Pickup w/ plow and sander5400INV #162 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10916 | 20211217-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091620211217-4Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1091620211217-4Pickup w/ plow and sander5400INV #162 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10916 | 20211217-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091620211217-4L.O.A.1210 | Corbiere and Sons Contracting1091620211217-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10916 | 20211217-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 0 | 0 | 862.5 | 112.125 | 974.625 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091620211217-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting1091620211217-4Operator - Principle - After Jan 1011.5862.5INV #162 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10916 | 20211217-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091620211217-4Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting1091620211217-4Operator - Intermdiate - After Jan 105350INV #162 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10916 | 20211217-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 0 | 0 | 350 | 45.5 | 395.5 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091620211217-4Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting1091620211217-4Operator - Intermdiate - After Jan 105350INV #162 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10918 | 20211217-6 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of D6 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done by Cole and Doug | 6 | C130-C151 | Lake A | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091820211217-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1091820211217-6Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10918 | 20211217-6 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of D6 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done by Cole and Doug | 6 | C130-C151 | Lake A | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091820211217-6Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1091820211217-6Tractor Trailer - 60 Ton- After Jan 10222692.58INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 2692.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10918 | 20211217-6 | 53510606 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of D6 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done by Cole and Doug | 6 | C130-C151 | Lake A | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091820211217-6L.O.A.3630 | Corbiere and Sons Contracting1091820211217-6L.O.A.3630INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10918 | 20211217-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of D6 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done by Cole and Doug | 6 | C130-C151 | Lake A | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091820211217-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1091820211217-6Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10918 | 20211217-6 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of D6 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done by Cole and Doug | 6 | C130-C151 | Lake A | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091820211217-6Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1091820211217-6Driver - AZ - After Jan 10221540INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10918 | 20211217-6 | 53510606 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-12-17 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of D6 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done by Cole and Doug | 6 | C130-C151 | Lake A | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091820211217-6Labourer - General - After Jan 105300 | Corbiere and Sons Contracting1091820211217-6Labourer - General - After Jan 105300INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1091920211218-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1091920211218-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1091920211218-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 0 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1091920211218-3Light Truck - Pick up- After Jan 102487.5INV #162 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1091920211218-3Pickup w/ plow and sander6480INV #162 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1091920211218-3Pickup w/ plow and sander6480INV #162 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3L.O.A.51050 | Corbiere and Sons Contracting1091920211218-3L.O.A.51050INV #162 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1091920211218-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1091920211218-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1091920211218-3Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting1091920211218-3Operator - Intermdiate - After Jan 106420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10919 | 20211218-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091920211218-3Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting1091920211218-3Operator - Intermdiate - After Jan 106420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10920 | 20211218-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 0 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092020211218-4Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting1092020211218-4Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29INV #162 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10920 | 20211218-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092020211218-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092020211218-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10920 | 20211218-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092020211218-4Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1092020211218-4Pickup w/ plow and sander5400INV #162 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10920 | 20211218-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092020211218-4Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1092020211218-4Pickup w/ plow and sander5400INV #162 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10920 | 20211218-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092020211218-4L.O.A.1210 | Corbiere and Sons Contracting1092020211218-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10920 | 20211218-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 0 | 0 | 862.5 | 112.125 | 974.625 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092020211218-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting1092020211218-4Operator - Principle - After Jan 1011.5862.5INV #162 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10920 | 20211218-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092020211218-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1092020211218-4Operator - Principle - After Jan 105375INV #162 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10920 | 20211218-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 0 | 0 | 350 | 45.5 | 395.5 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092020211218-4Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting1092020211218-4Operator - Intermdiate - After Jan 105350INV #162 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10920 | 20211218-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 0 | 0 | 350 | 45.5 | 395.5 | 2021-12-18 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092020211218-4Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting1092020211218-4Operator - Intermdiate - After Jan 105350INV #162 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1092420211219-3Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #162 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1092420211219-3Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #162 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092420211219-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 0 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1092420211219-3Light Truck - Pick up- After Jan 102487.5INV #162 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 7 |  | 0 | 0 |  |  | 560 | 72.8 | 632.8 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Pickup w/ plow and sander7560 | Corbiere and Sons Contracting1092420211219-3Pickup w/ plow and sander7560INV #162 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 7 |  | 0 | 0 |  |  | 560 | 72.8 | 632.8 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Pickup w/ plow and sander7560 | Corbiere and Sons Contracting1092420211219-3Pickup w/ plow and sander7560INV #162 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3L.O.A.51050 | Corbiere and Sons Contracting1092420211219-3L.O.A.51050INV #162 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1092420211219-3Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1092420211219-3Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1092420211219-3Operator - Principle - After Jan 105375INV #162 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 7 | HR |  |  | 0 | 0 | 490 | 63.7 | 553.7 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Operator - Intermdiate - After Jan 107490 | Corbiere and Sons Contracting1092420211219-3Operator - Intermdiate - After Jan 107490INV #162 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10924 | 20211219-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 7 | HR |  |  | 0 | 0 | 490 | 63.7 | 553.7 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand spent day working on Grader in Cooks Lake Road - Doug and Stacey working on pickup w/plow and sander on Cooks east and west | 5 | C076-C116 | Cook Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092420211219-3Operator - Intermdiate - After Jan 107490 | Corbiere and Sons Contracting1092420211219-3Operator - Intermdiate - After Jan 107490INV #162 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10925 | 20211219-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092520211219-4Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1092520211219-4Dozer D6 or equal- After Jan 105657.4INV #162 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10925 | 20211219-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092520211219-4Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1092520211219-4Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #162 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10925 | 20211219-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092520211219-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092520211219-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10925 | 20211219-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092520211219-4L.O.A.2420 | Corbiere and Sons Contracting1092520211219-4L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10925 | 20211219-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092520211219-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1092520211219-4Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10925 | 20211219-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-19 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1092520211219-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1092520211219-4Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10928 | 20211220-3 | 53560602 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-12-20 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished installation of WC 8390 | 6 | C248-C257 | Little Red Sucker Creek | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092820211220-3Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting1092820211220-3Excavator - 36 ton- After Jan 106881.76INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10928 | 20211220-3 | 53560602 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-12-20 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished installation of WC 8390 | 6 | C248-C257 | Little Red Sucker Creek | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092820211220-3Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting1092820211220-3Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10928 | 20211220-3 | 53560602 | Water Crossings | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-20 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished installation of WC 8390 | 6 | C248-C257 | Little Red Sucker Creek | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092820211220-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092820211220-3Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10928 | 20211220-3 | 53560602 | Water Crossings | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-20 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished installation of WC 8390 | 6 | C248-C257 | Little Red Sucker Creek | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092820211220-3L.O.A.1210 | Corbiere and Sons Contracting1092820211220-3L.O.A.1210INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10928 | 20211220-3 | 53560602 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-12-20 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished installation of WC 8390 | 6 | C248-C257 | Little Red Sucker Creek | 0 |  |  | 36 | 44571 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092820211220-3Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1092820211220-3Operator - Principle - After Jan 107525INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10929 | 20211228-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1092920211228-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1092920211228-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10929 | 20211228-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1092920211228-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1092920211228-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10929 | 20211228-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1092920211228-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092920211228-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10929 | 20211228-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1092920211228-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092920211228-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10929 | 20211228-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1092920211228-3L.O.A.2420 | Corbiere and Sons Contracting1092920211228-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10929 | 20211228-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1092920211228-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1092920211228-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10929 | 20211228-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1092920211228-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1092920211228-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10930 | 20211228-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093020211228-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1093020211228-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10930 | 20211228-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093020211228-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1093020211228-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10930 | 20211228-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093020211228-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1093020211228-4Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10930 | 20211228-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093020211228-4L.O.A.2420 | Corbiere and Sons Contracting1093020211228-4L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10930 | 20211228-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093020211228-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1093020211228-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10930 | 20211228-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2021-12-28 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093020211228-4Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1093020211228-4Operator - Principle - After Jan 104300INV #162 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10933 | 20211229-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093320211229-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1093320211229-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10933 | 20211229-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 0 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2021-12-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093320211229-3Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting1093320211229-3Grader - Cat 12 to 14 or equal- After Jan 102253.96INV #164 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10933 | 20211229-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093320211229-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1093320211229-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10933 | 20211229-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093320211229-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1093320211229-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10933 | 20211229-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093320211229-3L.O.A.1210 | Corbiere and Sons Contracting1093320211229-3L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10933 | 20211229-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093320211229-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1093320211229-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10933 | 20211229-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 0 | 0 | 150 | 19.5 | 169.5 | 2021-12-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 |  |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093320211229-3Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1093320211229-3Operator - Principle - After Jan 102150INV #164 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10934 | 20211229-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093420211229-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1093420211229-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10934 | 20211229-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093420211229-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1093420211229-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10934 | 20211229-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093420211229-4L.O.A.1210 | Corbiere and Sons Contracting1093420211229-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10934 | 20211229-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093420211229-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1093420211229-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10935 | 20211229-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Mill Road | 5 | C117-C128 | Terrace Bay | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093520211229-5Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1093520211229-5Pickup w/ plow and sander6480INV #162 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10935 | 20211229-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Mill Road | 5 | C117-C128 | Terrace Bay | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093520211229-5L.O.A.1210 | Corbiere and Sons Contracting1093520211229-5L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10935 | 20211229-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Mill Road | 5 | C117-C128 | Terrace Bay | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093520211229-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1093520211229-5Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10937 | 20211229-7 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker | 6 | C248 - C256 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093720211229-7Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1093720211229-7Excavator - 36 ton- After Jan 105734.8INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10937 | 20211229-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker | 6 | C248 - C256 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093720211229-7Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1093720211229-7Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10937 | 20211229-7 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker | 6 | C248 - C256 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093720211229-7L.O.A.1210 | Corbiere and Sons Contracting1093720211229-7L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10937 | 20211229-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2021-12-29 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker | 6 | C248 - C256 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093720211229-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1093720211229-7Operator - Principle - After Jan 106450INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10938 | 20211230-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C030-C049 | Pays Plat River | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093820211230-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1093820211230-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #162 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10938 | 20211230-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C030-C049 | Pays Plat River | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093820211230-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1093820211230-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10938 | 20211230-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C030-C049 | Pays Plat River | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093820211230-3Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1093820211230-3Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10938 | 20211230-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C030-C049 | Pays Plat River | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093820211230-3L.O.A.2420 | Corbiere and Sons Contracting1093820211230-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10938 | 20211230-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C030-C049 | Pays Plat River | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093820211230-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1093820211230-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10938 | 20211230-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C030-C049 | Pays Plat River | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093820211230-3Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1093820211230-3Operator - Principle - After Jan 104300INV #162 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10939 | 20211230-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093920211230-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1093920211230-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10939 | 20211230-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093920211230-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1093920211230-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10939 | 20211230-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093920211230-4L.O.A.1210 | Corbiere and Sons Contracting1093920211230-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10939 | 20211230-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1093920211230-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1093920211230-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10940 | 20211230-5 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker towards C254 | 6 | C248-C257 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 |  |  |  | ANWIN - Winter Only |  | Harold Furlong | 06 | Corbiere and Sons Contracting1094020211230-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1094020211230-5Excavator - 36 ton- After Jan 10101469.6INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10940 | 20211230-5 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 0 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker towards C254 | 6 | C248-C257 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 |  |  |  | ANWIN - Winter Only |  | Harold Furlong | 06 | Corbiere and Sons Contracting1094020211230-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1094020211230-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10940 | 20211230-5 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker towards C254 | 6 | C248-C257 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 |  |  |  | ANWIN - Winter Only |  | Harold Furlong | 06 | Corbiere and Sons Contracting1094020211230-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1094020211230-5Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10940 | 20211230-5 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker towards C254 | 6 | C248-C257 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 |  |  |  | ANWIN - Winter Only |  | Harold Furlong | 06 | Corbiere and Sons Contracting1094020211230-5L.O.A.1210 | Corbiere and Sons Contracting1094020211230-5L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10940 | 20211230-5 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker towards C254 | 6 | C248-C257 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 |  |  |  | ANWIN - Winter Only |  | Harold Furlong | 06 | Corbiere and Sons Contracting1094020211230-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1094020211230-5Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10944 | 20211231-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-31 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1094420211231-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1094420211231-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10944 | 20211231-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-31 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1094420211231-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1094420211231-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10944 | 20211231-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-31 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1094420211231-3L.O.A.1210 | Corbiere and Sons Contracting1094420211231-3L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10944 | 20211231-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-31 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1094420211231-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1094420211231-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10945 | 20211231-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1094520211231-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1094520211231-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10945 | 20211231-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1094520211231-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1094520211231-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10945 | 20211231-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1094520211231-4L.O.A.1210 | Corbiere and Sons Contracting1094520211231-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10945 | 20211231-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-30 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1094520211231-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1094520211231-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10946 | 20211231-5 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-31 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker towards C254 | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094620211231-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1094620211231-5Excavator - 36 ton- After Jan 10101469.6INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10946 | 20211231-5 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 0 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-31 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker towards C254 | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094620211231-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1094620211231-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10946 | 20211231-5 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-31 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker towards C254 | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094620211231-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1094620211231-5Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10946 | 20211231-5 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-31 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker towards C254 | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094620211231-5L.O.A.1210 | Corbiere and Sons Contracting1094620211231-5L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10946 | 20211231-5 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-31 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker towards C254 | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094620211231-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1094620211231-5Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10953 | 20220101-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1095320220101-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1095320220101-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #162 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10953 | 20220101-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1095320220101-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1095320220101-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10953 | 20220101-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1095320220101-3L.O.A.1210 | Corbiere and Sons Contracting1095320220101-3L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10953 | 20220101-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1095320220101-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1095320220101-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10954 | 20220101-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1095420220101-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1095420220101-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10954 | 20220101-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1095420220101-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1095420220101-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10954 | 20220101-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1095420220101-4L.O.A.1210 | Corbiere and Sons Contracting1095420220101-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10954 | 20220101-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1095420220101-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1095420220101-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10956 | 20220101-6 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 0 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker C256 | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095620220101-6Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1095620220101-6Excavator - 36 ton- After Jan 103440.88INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10956 | 20220101-6 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 0 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker C256 | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095620220101-6Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1095620220101-6Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10956 | 20220101-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-01 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Red Sucker C256 | 6 | C248-C257 | Little Red Sucker Creek | 0 | 44563 |  | 37 | 44572 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095620220101-6Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1095620220101-6Operator - Principle - After Jan 103225INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11431 | 20220102-18 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-01-02 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore float moving Grader | 5 | C031-C049 | Pays Plat River | 0 | 44592 |  | 37 | 44596 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1143120220102-18Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1143120220102-18Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11431 | 20220102-18 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-01-02 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore float moving Grader | 5 | C031-C049 | Pays Plat River | 0 | 44592 |  | 37 | 44596 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1143120220102-18Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1143120220102-18Driver - AZ - After Jan 104280INV #164 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10963 | 20220102-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096320220102-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1096320220102-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10963 | 20220102-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096320220102-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1096320220102-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10963 | 20220102-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096320220102-3L.O.A.1210 | Corbiere and Sons Contracting1096320220102-3L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10963 | 20220102-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Antler | 5 | C050-C069 | Antler Lake | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096320220102-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1096320220102-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10964 | 20220102-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096420220102-4Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1096420220102-4Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #162 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10964 | 20220102-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096420220102-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1096420220102-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10964 | 20220102-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096420220102-4L.O.A.1210 | Corbiere and Sons Contracting1096420220102-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10964 | 20220102-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096420220102-4Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1096420220102-4Operator - Principle - After Jan 103225INV #162 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10965 | 20220102-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2.5 | Dynamic | 0 | 0 |  |  | 317.45 | 41.2685 | 358.7185 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Whitesands - Float moved grader | 5 | C070-C075 | White Sand | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096520220102-5Grader - Cat 12 to 14 or equal- After Jan 102.5317.45 | Corbiere and Sons Contracting1096520220102-5Grader - Cat 12 to 14 or equal- After Jan 102.5317.45INV #162 | [5 empty] | 1 | 317.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10965 | 20220102-5 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 91.79 | 0 |  |  | 673.145 | 87.5088 | 760.6539 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Whitesands - Float moved grader | 5 | C070-C075 | White Sand | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096520220102-5Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting1096520220102-5Tractor Trailer - 60 Ton- After Jan 105.5673.145INV #162 | [5 empty] | 1 | 673.145 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10965 | 20220102-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Whitesands - Float moved grader | 5 | C070-C075 | White Sand | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096520220102-5Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1096520220102-5Operator - Principle - After Jan 104300INV #162 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10965 | 20220102-5 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Whitesands - Float moved grader | 5 | C070-C075 | White Sand | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096520220102-5Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting1096520220102-5Driver - AZ - After Jan 105.5385INV #162 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10966 | 20220102-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2.5 | Dynamic | 0 | 0 |  |  | 317.45 | 41.2685 | 358.7185 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Terrace Bay - Float moved grader | 5 | C117-C128 | Terrace Bay | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096620220102-6Grader - Cat 12 to 14 or equal- After Jan 102.5317.45 | Corbiere and Sons Contracting1096620220102-6Grader - Cat 12 to 14 or equal- After Jan 102.5317.45INV #162 | [5 empty] | 1 | 317.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10966 | 20220102-6 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 0 | 0 |  |  | 673.145 | 87.5088 | 760.6539 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Terrace Bay - Float moved grader | 5 | C117-C128 | Terrace Bay | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096620220102-6Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting1096620220102-6Tractor Trailer - 60 Ton- After Jan 105.5673.145INV #162 | [5 empty] | 1 | 673.145 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10966 | 20220102-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Terrace Bay - Float moved grader | 5 | C117-C128 | Terrace Bay | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096620220102-6L.O.A.1210 | Corbiere and Sons Contracting1096620220102-6L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10966 | 20220102-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Terrace Bay - Float moved grader | 5 | C117-C128 | Terrace Bay | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096620220102-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1096620220102-6Operator - Principle - After Jan 104300INV #162 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10966 | 20220102-6 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-02 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activities on Terrace Bay - Float moved grader | 5 | C117-C128 | Terrace Bay | 0 | 44571 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1096620220102-6Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting1096620220102-6Driver - AZ - After Jan 105.5385INV #162 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10975 | 20220103-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097520220103-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1097520220103-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10975 | 20220103-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097520220103-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1097520220103-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10975 | 20220103-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097520220103-3Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1097520220103-3Pickup w/ plow and sander3240INV #162 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10975 | 20220103-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097520220103-3L.O.A.2420 | Corbiere and Sons Contracting1097520220103-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10975 | 20220103-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097520220103-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1097520220103-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10975 | 20220103-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097520220103-3Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1097520220103-3Operator - Principle - After Jan 103225INV #162 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10976 | 20220103-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097620220103-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1097620220103-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #162 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10976 | 20220103-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097620220103-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1097620220103-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10976 | 20220103-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097620220103-4Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1097620220103-4Tractor Trailer - 60 Ton- After Jan 10111346.29INV #162 | [5 empty] | 1 | 1346.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10976 | 20220103-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097620220103-4L.O.A.2420 | Corbiere and Sons Contracting1097620220103-4L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10976 | 20220103-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097620220103-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1097620220103-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10976 | 20220103-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097620220103-4Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1097620220103-4Driver - AZ - After Jan 1011770INV #162 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10977 | 20220103-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097720220103-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1097720220103-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10977 | 20220103-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097720220103-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1097720220103-5Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10977 | 20220103-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097720220103-5L.O.A.1210 | Corbiere and Sons Contracting1097720220103-5L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10977 | 20220103-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097720220103-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1097720220103-5Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10978 | 20220103-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan worked across Mill and Antler | 5 | C117-C127 | Terrace Bay | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097820220103-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1097820220103-6Pickup w/ plow and sander3240INV #162 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10978 | 20220103-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-03 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan worked across Mill and Antler | 5 | C117-C127 | Terrace Bay | 0 | 44572 |  | 37 | 44574 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1097820220103-6Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1097820220103-6Operator - Principle - After Jan 103225INV #162 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10981 | 20220104-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098120220104-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1098120220104-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #162 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10981 | 20220104-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098120220104-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1098120220104-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10981 | 20220104-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 9 |  | 0 | 0 |  |  | 720 | 93.6 | 813.6 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098120220104-3Pickup w/ plow and sander9720 | Corbiere and Sons Contracting1098120220104-3Pickup w/ plow and sander9720INV #162 | [5 empty] | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10981 | 20220104-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098120220104-3L.O.A.2420 | Corbiere and Sons Contracting1098120220104-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10981 | 20220104-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098120220104-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1098120220104-3Operator - Principle - After Jan 1012900INV #162 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10981 | 20220104-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098120220104-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1098120220104-3Operator - Principle - After Jan 1012900INV #162 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10982 | 20220104-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098220220104-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1098220220104-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #162 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10982 | 20220104-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098220220104-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1098220220104-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10982 | 20220104-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 0 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098220220104-4Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1098220220104-4Tractor Trailer - 60 Ton- After Jan 106734.34INV #162 | [5 empty] | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10982 | 20220104-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098220220104-4L.O.A.2420 | Corbiere and Sons Contracting1098220220104-4L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10982 | 20220104-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098220220104-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1098220220104-4Operator - Principle - After Jan 1012900INV #162 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10982 | 20220104-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44573 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098220220104-4Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1098220220104-4Driver - AZ - After Jan 106420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10983 | 20220104-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098320220104-5Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1098320220104-5Dozer D6 or equal- After Jan 10111446.28INV #162 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10983 | 20220104-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098320220104-5Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1098320220104-5Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #162 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10983 | 20220104-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098320220104-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1098320220104-5Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10983 | 20220104-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098320220104-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1098320220104-5Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10983 | 20220104-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098320220104-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1098320220104-5Pickup w/ plow and sander12960INV #162 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10983 | 20220104-5 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098320220104-5L.O.A.3630 | Corbiere and Sons Contracting1098320220104-5L.O.A.3630INV #162 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10983 | 20220104-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098320220104-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1098320220104-5Operator - Principle - After Jan 108600INV #162 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10983 | 20220104-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098320220104-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1098320220104-5Operator - Principle - After Jan 1012900INV #162 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10983 | 20220104-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2022-01-04 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098320220104-5Operator - Intermdiate - After Jan 1012840 | Corbiere and Sons Contracting1098320220104-5Operator - Intermdiate - After Jan 1012840INV #162 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10984 | 20220105-3 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 0 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098420220105-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1098420220105-3Dozer D6 or equal- After Jan 10111446.28INV #162 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10984 | 20220105-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098420220105-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1098420220105-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #162 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10984 | 20220105-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098420220105-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1098420220105-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10984 | 20220105-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098420220105-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1098420220105-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10984 | 20220105-3 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098420220105-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1098420220105-3Tractor Trailer - 60 Ton- After Jan 10111346.29INV #162 | [5 empty] | 1 | 1346.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10984 | 20220105-3 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  | 0 | 0 | 630 | 81.9 | 711.9 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098420220105-3L.O.A.3630 | Corbiere and Sons Contracting1098420220105-3L.O.A.3630INV #162 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10984 | 20220105-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098420220105-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1098420220105-3Operator - Principle - After Jan 1012900INV #162 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10984 | 20220105-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098420220105-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1098420220105-3Operator - Principle - After Jan 1012900INV #162 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10984 | 20220105-3 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098420220105-3Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1098420220105-3Driver - AZ - After Jan 1011770INV #162 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10985 | 20220105-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098520220105-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1098520220105-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #162 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10985 | 20220105-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098520220105-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1098520220105-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10985 | 20220105-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098520220105-4L.O.A.1210 | Corbiere and Sons Contracting1098520220105-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10985 | 20220105-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098520220105-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1098520220105-4Operator - Principle - After Jan 1012900INV #162 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10986 | 20220105-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44876 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098620220105-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1098620220105-5Pickup w/ plow and sander12960INV #162 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10986 | 20220105-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44876 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098620220105-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1098620220105-5Pickup w/ plow and sander3240INV #162 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10986 | 20220105-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44876 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098620220105-5L.O.A.2420 | Corbiere and Sons Contracting1098620220105-5L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10986 | 20220105-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44876 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098620220105-5Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1098620220105-5Operator - Principle - After Jan 103225INV #162 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10986 | 20220105-5 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44876 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098620220105-5Operator - Intermdiate - After Jan 1012840 | Corbiere and Sons Contracting1098620220105-5Operator - Intermdiate - After Jan 1012840INV #162 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10987 | 20220105-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Whitesands | 5 | C070-C075 | White Sand | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098720220105-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1098720220105-6Pickup w/ plow and sander3240INV #162 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10987 | 20220105-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-05 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Whitesands | 5 | C070-C075 | White Sand | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1098720220105-6Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1098720220105-6Operator - Principle - After Jan 103225INV #162 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10990 | 20220106-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-06 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099020220106-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1099020220106-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10990 | 20220106-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-06 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099020220106-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1099020220106-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10990 | 20220106-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-06 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099020220106-3L.O.A.1210 | Corbiere and Sons Contracting1099020220106-3L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10990 | 20220106-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-06 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44580 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099020220106-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1099020220106-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10991 | 20220106-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099120220106-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1099120220106-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10991 | 20220106-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099120220106-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1099120220106-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10991 | 20220106-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099120220106-4Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1099120220106-4Pickup w/ plow and sander6480INV #162 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10991 | 20220106-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099120220106-4L.O.A.2420 | Corbiere and Sons Contracting1099120220106-4L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10991 | 20220106-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099120220106-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1099120220106-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10991 | 20220106-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099120220106-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1099120220106-4Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10992 | 20220106-5 | 53560601 | Water Crossings | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP walked in 329 and installed WC - Float drop off ex | 6 | C130-C151 | Lake A | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099220220106-5Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1099220220106-5Excavator - 30 ton- After Jan 105692.25INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10992 | 20220106-5 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP walked in 329 and installed WC - Float drop off ex | 6 | C130-C151 | Lake A | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099220220106-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1099220220106-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10992 | 20220106-5 | 53560601 | Water Crossings | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP walked in 329 and installed WC - Float drop off ex | 6 | C130-C151 | Lake A | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099220220106-5Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1099220220106-5Tractor Trailer - 60 Ton- After Jan 103367.17INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10992 | 20220106-5 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP walked in 329 and installed WC - Float drop off ex | 6 | C130-C151 | Lake A | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099220220106-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1099220220106-5Operator - Principle - After Jan 106450INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10992 | 20220106-5 | 53560601 | Water Crossings | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP walked in 329 and installed WC - Float drop off ex | 6 | C130-C151 | Lake A | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099220220106-5Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1099220220106-5Driver - AZ - After Jan 103210INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10993 | 20220106-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Pic River - WF7 53510711 |  | Approved |  |  | WAM Activities at Pic River - WF7 53510711 | 6 | D018-D024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099320220106-6Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1099320220106-6Pickup w/ plow and sander6480INV #162 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10993 | 20220106-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-06 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Pic River - WF7 53510711 |  | Approved |  |  | WAM Activities at Pic River - WF7 53510711 | 6 | D018-D024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099320220106-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1099320220106-6Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10995 | 20220107-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099520220107-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1099520220107-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10995 | 20220107-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099520220107-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1099520220107-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10995 | 20220107-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099520220107-3L.O.A.1210 | Corbiere and Sons Contracting1099520220107-3L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10995 | 20220107-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099520220107-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1099520220107-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10996 | 20220107-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099620220107-4Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1099620220107-4Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #162 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10996 | 20220107-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099620220107-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1099620220107-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10996 | 20220107-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 10 |  | 0 | 0 |  |  | 800 | 104 | 904 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099620220107-4Pickup w/ plow and sander10800 | Corbiere and Sons Contracting1099620220107-4Pickup w/ plow and sander10800INV #162 | [5 empty] | 1 | 800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10996 | 20220107-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099620220107-4L.O.A.2420 | Corbiere and Sons Contracting1099620220107-4L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10996 | 20220107-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099620220107-4Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1099620220107-4Operator - Principle - After Jan 108600INV #162 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10996 | 20220107-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099620220107-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1099620220107-4Operator - Principle - After Jan 1012900INV #162 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10997 | 20220107-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099720220107-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1099720220107-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #162 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10997 | 20220107-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099720220107-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1099720220107-5Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10997 | 20220107-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099720220107-5L.O.A.1210 | Corbiere and Sons Contracting1099720220107-5L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10997 | 20220107-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 0 | 0 | 675 | 87.75 | 762.75 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working at Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1099720220107-5Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1099720220107-5Operator - Principle - After Jan 109675INV #162 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10998 | 20220107-6 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP finished op Winter Road in Lake A and demobbed machine to be floated over to Neys | 6 | C130-C151 | Lake A | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099820220107-6Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1099820220107-6Excavator - 36 ton- After Jan 1081175.68INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10998 | 20220107-6 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP finished op Winter Road in Lake A and demobbed machine to be floated over to Neys | 6 | C130-C151 | Lake A | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099820220107-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1099820220107-6Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10998 | 20220107-6 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP finished op Winter Road in Lake A and demobbed machine to be floated over to Neys | 6 | C130-C151 | Lake A | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099820220107-6L.O.A.1210 | Corbiere and Sons Contracting1099820220107-6L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 10998 | 20220107-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP finished op Winter Road in Lake A and demobbed machine to be floated over to Neys | 6 | C130-C151 | Lake A | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099820220107-6Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1099820220107-6Operator - Principle - After Jan 109675INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11000 | 20220107-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floar moved Dz over to Pic River - Operated for 5 hours and other OP took over at night | 6 | D018-D0024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100020220107-8Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1100020220107-8Dozer D6 or equal- After Jan 1081051.84INV #162 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11000 | 20220107-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 7 | Dynamic | 91.79 | 0 |  |  | 856.73 | 111.3749 | 968.1049 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floar moved Dz over to Pic River - Operated for 5 hours and other OP took over at night | 6 | D018-D0024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100020220107-8Tractor Trailer - 60 Ton- After Jan 107856.73 | Corbiere and Sons Contracting1100020220107-8Tractor Trailer - 60 Ton- After Jan 107856.73INV #162 | [5 empty] | 1 | 856.73 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11000 | 20220107-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floar moved Dz over to Pic River - Operated for 5 hours and other OP took over at night | 6 | D018-D0024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100020220107-8L.O.A.1210 | Corbiere and Sons Contracting1100020220107-8L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11000 | 20220107-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floar moved Dz over to Pic River - Operated for 5 hours and other OP took over at night | 6 | D018-D0024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100020220107-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1100020220107-8Operator - Principle - After Jan 105375INV #162 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11000 | 20220107-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floar moved Dz over to Pic River - Operated for 5 hours and other OP took over at night | 6 | D018-D0024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100020220107-8Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1100020220107-8Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11000 | 20220107-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2022-01-07 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floar moved Dz over to Pic River - Operated for 5 hours and other OP took over at night | 6 | D018-D0024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100020220107-8Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting1100020220107-8Driver - AZ - After Jan 107490INV #162 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11001 | 20220108-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100120220108-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1100120220108-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11001 | 20220108-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100120220108-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1100120220108-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11001 | 20220108-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100120220108-3L.O.A.1210 | Corbiere and Sons Contracting1100120220108-3L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11001 | 20220108-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100120220108-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1100120220108-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1100220220108-4Dozer D6 or equal- After Jan 105657.4INV #162 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 0 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1100220220108-4Grader - Cat 12 to 14 or equal- After Jan 106761.88INV #162 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1100220220108-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1100220220108-4Tractor Trailer - 60 Ton- After Jan 105611.95INV #162 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1100220220108-4Pickup w/ plow and sander6480INV #162 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1100220220108-4Pickup w/ plow and sander6480INV #162 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4L.O.A.4840 | Corbiere and Sons Contracting1100220220108-4L.O.A.4840INV #162 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1100220220108-4Operator - Principle - After Jan 108600INV #162 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1100220220108-4Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1100220220108-4Operator - Principle - After Jan 105375INV #162 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting1100220220108-4Operator - Intermdiate - After Jan 106420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11002 | 20220108-4 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cooks | 5 | C076-C116 | Cook Lake | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100220220108-4Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1100220220108-4Driver - AZ - After Jan 105350INV #162 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11003 | 20220108-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100320220108-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1100320220108-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11003 | 20220108-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100320220108-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1100320220108-5Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11003 | 20220108-5 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100320220108-5Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1100320220108-5Pickup w/ plow and sander6480INV #162 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11003 | 20220108-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100320220108-5L.O.A.1210 | Corbiere and Sons Contracting1100320220108-5L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11003 | 20220108-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100320220108-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1100320220108-5Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11003 | 20220108-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100320220108-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1100320220108-5Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11004 | 20220108-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Mill Road | 5 | C117-C128 | Terrace Bay | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100420220108-6Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1100420220108-6Pickup w/ plow and sander5400INV #162 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11004 | 20220108-6 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-01-08 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Mill Road | 5 | C117-C128 | Terrace Bay | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100420220108-6Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting1100420220108-6Operator - Intermdiate - After Jan 105350INV #162 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11014 | 20220109-11 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 0 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C236 | Neys | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101420220109-11Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting1101420220109-11Excavator - 30 ton- After Jan 103415.35INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11014 | 20220109-11 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C236 | Neys | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101420220109-11Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1101420220109-11Operator - Principle - After Jan 103225INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11015 | 20220109-12 | 53560601 | Water Crossings | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 0 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WC Install on Neys | 6 | C219-C235 | Neys | 0 | 44573 |  | 37 | 44575 |  |  | 8310.01 |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1101520220109-12Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting1101520220109-12Excavator - 30 ton- After Jan 104553.8INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11015 | 20220109-12 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 0 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WC Install on Neys | 6 | C219-C235 | Neys | 0 | 44573 |  | 37 | 44575 |  |  | 8310.01 |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1101520220109-12Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1101520220109-12Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11015 | 20220109-12 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WC Install on Neys | 6 | C219-C235 | Neys | 0 | 44573 |  | 37 | 44575 |  |  | 8310.01 |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1101520220109-12Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1101520220109-12Operator - Principle - After Jan 104300INV #162 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11006 | 20220109-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100620220109-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1100620220109-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11006 | 20220109-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100620220109-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1100620220109-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11006 | 20220109-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100620220109-3Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1100620220109-3Pickup w/ plow and sander5.5440INV #162 | [5 empty] | 1 | 440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11006 | 20220109-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100620220109-3L.O.A.2420 | Corbiere and Sons Contracting1100620220109-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11006 | 20220109-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100620220109-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1100620220109-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11006 | 20220109-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100620220109-3Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1100620220109-3Operator - Intermdiate - After Jan 105.5385INV #162 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11007 | 20220109-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100720220109-4Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1100720220109-4Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #162 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11007 | 20220109-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100720220109-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1100720220109-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11007 | 20220109-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100720220109-4Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1100720220109-4Pickup w/ plow and sander5.5440INV #162 | [5 empty] | 1 | 440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11007 | 20220109-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100720220109-4L.O.A.1210 | Corbiere and Sons Contracting1100720220109-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11007 | 20220109-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 0 | 0 | 675 | 87.75 | 762.75 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100720220109-4Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1100720220109-4Operator - Principle - After Jan 109675INV #162 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11007 | 20220109-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100720220109-4Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1100720220109-4Operator - Intermdiate - After Jan 105.5385INV #162 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11008 | 20220109-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100820220109-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1100820220109-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11008 | 20220109-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100820220109-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1100820220109-5Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11008 | 20220109-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100820220109-5L.O.A.1210 | Corbiere and Sons Contracting1100820220109-5L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11008 | 20220109-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1100820220109-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1100820220109-5Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11010 | 20220109-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Mill Road | 5 | C117-C128 | Terrace Bay | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101020220109-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1101020220109-6Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11010 | 20220109-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Mill Road | 5 | C117-C128 | Terrace Bay | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101020220109-6L.O.A.1210 | Corbiere and Sons Contracting1101020220109-6L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11010 | 20220109-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Mill Road | 5 | C117-C128 | Terrace Bay | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101020220109-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1101020220109-6Operator - Principle - After Jan 104300INV #162 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11009 | 20220109-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 - 53510711 |  | Approved |  |  | OP spent morning plowing snow in Pic River - WF7 - 53510711 | 6 | D018-D024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100920220109-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1100920220109-7Dozer D6 or equal- After Jan 104525.92INV #162 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11009 | 20220109-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 - 53510711 |  | Approved |  |  | OP spent morning plowing snow in Pic River - WF7 - 53510711 | 6 | D018-D024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100920220109-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1100920220109-7Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11009 | 20220109-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 - 53510711 |  | Approved |  |  | OP spent morning plowing snow in Pic River - WF7 - 53510711 | 6 | D018-D024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100920220109-7L.O.A.1210 | Corbiere and Sons Contracting1100920220109-7L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11009 | 20220109-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-09 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 - 53510711 |  | Approved |  |  | OP spent morning plowing snow in Pic River - WF7 - 53510711 | 6 | D018-D024 | Pic River | 0 | 44572 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100920220109-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1100920220109-7Operator - Principle - After Jan 106450INV #162 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11017 | 20220110-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101720220110-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1101720220110-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11017 | 20220110-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101720220110-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1101720220110-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11017 | 20220110-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101720220110-3Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1101720220110-3Pickup w/ plow and sander5.5440INV #162 | [5 empty] | 1 | 440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11017 | 20220110-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101720220110-3L.O.A.2420 | Corbiere and Sons Contracting1101720220110-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11017 | 20220110-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101720220110-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1101720220110-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11017 | 20220110-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101720220110-3Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1101720220110-3Operator - Intermdiate - After Jan 105.5385INV #162 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11018 | 20220110-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101820220110-4Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1101820220110-4Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #162 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11018 | 20220110-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101820220110-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1101820220110-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11018 | 20220110-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101820220110-4Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1101820220110-4Pickup w/ plow and sander5.5440INV #162 | [5 empty] | 1 | 440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11018 | 20220110-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101820220110-4L.O.A.1210 | Corbiere and Sons Contracting1101820220110-4L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11018 | 20220110-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101820220110-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1101820220110-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11018 | 20220110-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101820220110-4Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1101820220110-4Operator - Intermdiate - After Jan 105.5385INV #162 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11019 | 20220110-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C031-C049 | Pays Plat River | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101920220110-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1101920220110-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11019 | 20220110-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C031-C049 | Pays Plat River | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101920220110-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1101920220110-5Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11019 | 20220110-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C031-C049 | Pays Plat River | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101920220110-5L.O.A.1210 | Corbiere and Sons Contracting1101920220110-5L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11019 | 20220110-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C031-C049 | Pays Plat River | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1101920220110-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1101920220110-5Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11020 | 20220110-6-R1 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102020220110-6-R1Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1102020220110-6-R1Excavator - 30 ton- After Jan 10101384.5INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11020 | 20220110-6-R1 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102020220110-6-R1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1102020220110-6-R1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11020 | 20220110-6-R1 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102020220110-6-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1102020220110-6-R1Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11020 | 20220110-6-R1 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102020220110-6-R1L.O.A.1210 | Corbiere and Sons Contracting1102020220110-6-R1L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11020 | 20220110-6-R1 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102020220110-6-R1Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1102020220110-6-R1Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11021 | 20220110-7 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob DZ from Lake A | 6 | C130-C151 | Lake A | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102120220110-7Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1102120220110-7Tractor Trailer - 60 Ton- After Jan 106734.34INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11021 | 20220110-7 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 18 | Dynamic | 91.79 | 0 |  |  | 2203.02 | 286.3926 | 2489.4126 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob DZ from Lake A | 6 | C130-C151 | Lake A | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102120220110-7Tractor Trailer - 60 Ton- After Jan 10182203.02 | Corbiere and Sons Contracting1102120220110-7Tractor Trailer - 60 Ton- After Jan 10182203.02INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 2203.02 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11021 | 20220110-7 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob DZ from Lake A | 6 | C130-C151 | Lake A | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102120220110-7L.O.A.1210 | Corbiere and Sons Contracting1102120220110-7L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11021 | 20220110-7 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob DZ from Lake A | 6 | C130-C151 | Lake A | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102120220110-7Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1102120220110-7Driver - AZ - After Jan 106420INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11021 | 20220110-7 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 18 | HR |  |  | 70 | 0 | 1260 | 163.8 | 1423.8 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob DZ from Lake A | 6 | C130-C151 | Lake A | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102120220110-7Driver - AZ - After Jan 10181260 | Corbiere and Sons Contracting1102120220110-7Driver - AZ - After Jan 10181260INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11022 | 20220110-8 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Lake A | 6 | C130-C151 | Lake A | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102220220110-8Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1102220220110-8Dozer D6 or equal- After Jan 102262.96INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11022 | 20220110-8 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2022-01-10 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Road in Lake A | 6 | C130-C151 | Lake A | 0 | 44573 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102220220110-8Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1102220220110-8Operator - Principle - After Jan 102150INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11027 | 20220111-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102720220111-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1102720220111-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11027 | 20220111-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102720220111-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1102720220111-3Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11027 | 20220111-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102720220111-3Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1102720220111-3Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11027 | 20220111-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102720220111-3L.O.A.2420 | Corbiere and Sons Contracting1102720220111-3L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11027 | 20220111-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102720220111-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1102720220111-3Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11027 | 20220111-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102720220111-3Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1102720220111-3Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11028 | 20220111-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102820220111-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1102820220111-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11028 | 20220111-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102820220111-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1102820220111-4Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11028 | 20220111-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102820220111-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1102820220111-4Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11028 | 20220111-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102820220111-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1102820220111-4Pickup w/ plow and sander4320INV #162 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11028 | 20220111-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102820220111-4L.O.A.2420 | Corbiere and Sons Contracting1102820220111-4L.O.A.2420INV #162 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11028 | 20220111-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102820220111-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1102820220111-4Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11028 | 20220111-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102820220111-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1102820220111-4Operator - Principle - After Jan 1012900INV #162 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11028 | 20220111-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102820220111-4Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1102820220111-4Operator - Intermdiate - After Jan 104280INV #162 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11029 | 20220111-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102920220111-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1102920220111-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11029 | 20220111-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102920220111-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1102920220111-5Light Truck - Pick up- After Jan 101243.75INV #162 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11029 | 20220111-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102920220111-5L.O.A.1210 | Corbiere and Sons Contracting1102920220111-5L.O.A.1210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11029 | 20220111-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1102920220111-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1102920220111-5Operator - Principle - After Jan 1011825INV #162 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11030 | 20220111-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1103020220111-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1103020220111-6Pickup w/ plow and sander3240INV #162 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11030 | 20220111-6 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1103020220111-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1103020220111-6Operator - Intermdiate - After Jan 103210INV #162 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11031 | 20220111-7 | 53510606 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103120220111-7Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1103120220111-7Dozer D6 or equal- After Jan 103394.44INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11031 | 20220111-7 | 53510606 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103120220111-7Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1103120220111-7Excavator - 30 ton- After Jan 10101384.5INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11031 | 20220111-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103120220111-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1103120220111-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11031 | 20220111-7 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103120220111-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1103120220111-7Light Truck - Pick up- After Jan 101243.75INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11031 | 20220111-7 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103120220111-7L.O.A.1210 | Corbiere and Sons Contracting1103120220111-7L.O.A.1210INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11031 | 20220111-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103120220111-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1103120220111-7Operator - Principle - After Jan 1011825INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11031 | 20220111-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-01-11 | 0 | INV #162 | 44578 | 175 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C235 | Neys | 0 | 44574 |  | 37 | 44575 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103120220111-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1103120220111-7Operator - Principle - After Jan 103225INV #162 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11078 | 20220112-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1107820220112-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1107820220112-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11078 | 20220112-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1107820220112-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1107820220112-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11078 | 20220112-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1107820220112-3L.O.A.2420 | Corbiere and Sons Contracting1107820220112-3L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11078 | 20220112-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1107820220112-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1107820220112-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11078 | 20220112-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1107820220112-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1107820220112-3Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11079 | 20220112-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44586 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1107920220112-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1107920220112-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11079 | 20220112-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44586 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1107920220112-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1107920220112-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11079 | 20220112-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44586 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1107920220112-4L.O.A.1210 | Corbiere and Sons Contracting1107920220112-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11079 | 20220112-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44586 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1107920220112-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1107920220112-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11080 | 20220112-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1108020220112-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1108020220112-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11080 | 20220112-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1108020220112-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1108020220112-5Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11080 | 20220112-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1108020220112-5L.O.A.1210 | Corbiere and Sons Contracting1108020220112-5L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11080 | 20220112-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1108020220112-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1108020220112-5Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11081 | 20220112-6 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF in Jackfish | 6 | C152 - C157 | Jackfish Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108120220112-6Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting1108120220112-6Excavator - 36 ton- After Jan 104587.84INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11081 | 20220112-6 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF in Jackfish | 6 | C152 - C157 | Jackfish Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108120220112-6Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1108120220112-6Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11081 | 20220112-6 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF in Jackfish | 6 | C152 - C157 | Jackfish Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108120220112-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1108120220112-6Light Truck - Pick up- After Jan 101243.75INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11081 | 20220112-6 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF in Jackfish | 6 | C152 - C157 | Jackfish Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108120220112-6Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1108120220112-6Tractor Trailer - 60 Ton- After Jan 103367.17INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11081 | 20220112-6 | 53510606 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF in Jackfish | 6 | C152 - C157 | Jackfish Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108120220112-6L.O.A.2420 | Corbiere and Sons Contracting1108120220112-6L.O.A.2420INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11081 | 20220112-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF in Jackfish | 6 | C152 - C157 | Jackfish Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108120220112-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1108120220112-6Operator - Principle - After Jan 105375INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11081 | 20220112-6 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF in Jackfish | 6 | C152 - C157 | Jackfish Lake | 0 | 44587 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108120220112-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1108120220112-6Driver - AZ - After Jan 103210INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11082 | 20220112-7 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 0 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF | 6 | C171-C185 | Prairie River | 0 | 44586 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108220220112-7Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting1108220220112-7Excavator - 36 ton- After Jan 104587.84INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11082 | 20220112-7 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 0 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF | 6 | C171-C185 | Prairie River | 0 | 44586 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108220220112-7Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1108220220112-7Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11082 | 20220112-7 | 53510606 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 0 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF | 6 | C171-C185 | Prairie River | 0 | 44586 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108220220112-7Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1108220220112-7Tractor Trailer - 60 Ton- After Jan 103367.17INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11082 | 20220112-7 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF | 6 | C171-C185 | Prairie River | 0 | 44586 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108220220112-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1108220220112-7Operator - Principle - After Jan 106450INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11082 | 20220112-7 | 53510606 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP floated over to work on WRF | 6 | C171-C185 | Prairie River | 0 | 44586 |  | 37 | 44587 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108220220112-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1108220220112-7Driver - AZ - After Jan 103210INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11155 | 20220113-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115520220113-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1115520220113-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11155 | 20220113-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115520220113-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1115520220113-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11155 | 20220113-3 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115520220113-3Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1115520220113-3Tractor Trailer - 60 Ton- After Jan 106734.34INV #164 | [5 empty] | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11155 | 20220113-3 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115520220113-3L.O.A.3630 | Corbiere and Sons Contracting1115520220113-3L.O.A.3630INV #164 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11155 | 20220113-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115520220113-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1115520220113-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11155 | 20220113-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115520220113-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1115520220113-3Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11155 | 20220113-3 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115520220113-3Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1115520220113-3Driver - AZ - After Jan 106420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11156 | 20220113-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115620220113-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1115620220113-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11156 | 20220113-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115620220113-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1115620220113-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11156 | 20220113-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115620220113-4L.O.A.1210 | Corbiere and Sons Contracting1115620220113-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11156 | 20220113-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115620220113-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1115620220113-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11157 | 20220113-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115720220113-5Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1115720220113-5Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #164 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11157 | 20220113-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115720220113-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1115720220113-5Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11157 | 20220113-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115720220113-5L.O.A.1210 | Corbiere and Sons Contracting1115720220113-5L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11157 | 20220113-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1115720220113-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1115720220113-5Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11158 | 20220113-6 | 53510606 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP spent day working on WRF in Prairie River | 6 | C171-C185 | Prairie River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115820220113-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1115820220113-6Excavator - 36 ton- After Jan 10101469.6INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11158 | 20220113-6 | 53510606 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP spent day working on WRF in Prairie River | 6 | C171-C185 | Prairie River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115820220113-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1115820220113-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11158 | 20220113-6 | 53510606 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP spent day working on WRF in Prairie River | 6 | C171-C185 | Prairie River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115820220113-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1115820220113-6Light Truck - Pick up- After Jan 101243.75INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11158 | 20220113-6 | 53510606 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP spent day working on WRF in Prairie River | 6 | C171-C185 | Prairie River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115820220113-6L.O.A.1210 | Corbiere and Sons Contracting1115820220113-6L.O.A.1210INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11158 | 20220113-6 | 53510606 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP spent day working on WRF in Prairie River | 6 | C171-C185 | Prairie River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115820220113-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1115820220113-6Operator - Principle - After Jan 1011825INV #164 |  |  | WF6-3rd Winter Access Build |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11160 | 20220113-8 | 53510711 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1116020220113-8Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1116020220113-8Pickup w/ plow and sander5.5440INV #164 | [5 empty] | 1 | 440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11160 | 20220113-8 | 53510711 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44588 |  | 37 | 44588 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1116020220113-8Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1116020220113-8Operator - Intermdiate - After Jan 105.5385INV #164 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11161 | 20220114-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116120220114-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1116120220114-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11161 | 20220114-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116120220114-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1116120220114-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11161 | 20220114-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116120220114-3L.O.A.2420 | Corbiere and Sons Contracting1116120220114-3L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11161 | 20220114-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116120220114-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1116120220114-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11161 | 20220114-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116120220114-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1116120220114-3Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11162 | 20220114-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116220220114-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1116220220114-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11162 | 20220114-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116220220114-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1116220220114-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11162 | 20220114-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116220220114-4L.O.A.1210 | Corbiere and Sons Contracting1116220220114-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11162 | 20220114-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116220220114-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1116220220114-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11163 | 20220114-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays | 5 | C050 - C069 | Pays Plat River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116320220114-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1116320220114-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11163 | 20220114-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays | 5 | C050 - C069 | Pays Plat River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116320220114-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1116320220114-5Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11163 | 20220114-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays | 5 | C050 - C069 | Pays Plat River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116320220114-5L.O.A.1210 | Corbiere and Sons Contracting1116320220114-5L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11163 | 20220114-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays | 5 | C050 - C069 | Pays Plat River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116320220114-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1116320220114-5Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11164 | 20220114-6 | 53510711 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer was floated over and cleared snow; Stacey worked on pickup w/plow and sander | 6 | D018-D024 | Pic River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1116420220114-6Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1116420220114-6Dozer D6 or equal- After Jan 103394.44INV #164 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11164 | 20220114-6 | 53510711 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer was floated over and cleared snow; Stacey worked on pickup w/plow and sander | 6 | D018-D024 | Pic River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1116420220114-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1116420220114-6Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11164 | 20220114-6 | 53510711 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer was floated over and cleared snow; Stacey worked on pickup w/plow and sander | 6 | D018-D024 | Pic River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1116420220114-6Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1116420220114-6Tractor Trailer - 60 Ton- After Jan 103367.17INV #164 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11164 | 20220114-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer was floated over and cleared snow; Stacey worked on pickup w/plow and sander | 6 | D018-D024 | Pic River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116420220114-6Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1116420220114-6Pickup w/ plow and sander5.5440INV #164 | [5 empty] | 1 | 440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11164 | 20220114-6 | 53510711 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer was floated over and cleared snow; Stacey worked on pickup w/plow and sander | 6 | D018-D024 | Pic River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1116420220114-6L.O.A.3630 | Corbiere and Sons Contracting1116420220114-6L.O.A.3630INV #164 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11164 | 20220114-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer was floated over and cleared snow; Stacey worked on pickup w/plow and sander | 6 | D018-D024 | Pic River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1116420220114-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1116420220114-6Operator - Principle - After Jan 104300INV #164 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11164 | 20220114-6 | 53510711 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer was floated over and cleared snow; Stacey worked on pickup w/plow and sander | 6 | D018-D024 | Pic River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1116420220114-6Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1116420220114-6Operator - Intermdiate - After Jan 105.5385INV #164 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11164 | 20220114-6 | 53510711 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-14 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer was floated over and cleared snow; Stacey worked on pickup w/plow and sander | 6 | D018-D024 | Pic River | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1116420220114-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1116420220114-6Driver - AZ - After Jan 103210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11167 | 20220115-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116720220115-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1116720220115-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11167 | 20220115-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116720220115-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1116720220115-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11167 | 20220115-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116720220115-3L.O.A.2420 | Corbiere and Sons Contracting1116720220115-3L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11167 | 20220115-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116720220115-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1116720220115-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11167 | 20220115-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116720220115-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1116720220115-3Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11168 | 20220115-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116820220115-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1116820220115-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11168 | 20220115-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116820220115-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1116820220115-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11168 | 20220115-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116820220115-4L.O.A.1210 | Corbiere and Sons Contracting1116820220115-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11168 | 20220115-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44588 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1116820220115-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1116820220115-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11171 | 20220115-7 | 53560601 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex was floated over to Santoy Lake and then OP fixed WC 7851.00 | 6 | C158-C170 | Santoy Lake | 0 | 44588 |  | 36 | 44588 |  |  | 7851.00 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1117120220115-7Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1117120220115-7Excavator - 36 ton- After Jan 1071028.72INV #164 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11171 | 20220115-7 | 53560601 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex was floated over to Santoy Lake and then OP fixed WC 7851.00 | 6 | C158-C170 | Santoy Lake | 0 | 44588 |  | 36 | 44588 |  |  | 7851.00 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1117120220115-7Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1117120220115-7Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #164 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11171 | 20220115-7 | 53560601 | Water Crossings | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex was floated over to Santoy Lake and then OP fixed WC 7851.00 | 6 | C158-C170 | Santoy Lake | 0 | 44588 |  | 36 | 44588 |  |  | 7851.00 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1117120220115-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1117120220115-7Light Truck - Pick up- After Jan 101243.75INV #164 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11171 | 20220115-7 | 53560601 | Water Crossings | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex was floated over to Santoy Lake and then OP fixed WC 7851.00 | 6 | C158-C170 | Santoy Lake | 0 | 44588 |  | 36 | 44588 |  |  | 7851.00 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1117120220115-7Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1117120220115-7Tractor Trailer - 60 Ton- After Jan 105611.95INV #164 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11171 | 20220115-7 | 53560601 | Water Crossings | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex was floated over to Santoy Lake and then OP fixed WC 7851.00 | 6 | C158-C170 | Santoy Lake | 0 | 44588 |  | 36 | 44588 |  |  | 7851.00 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1117120220115-7L.O.A.2420 | Corbiere and Sons Contracting1117120220115-7L.O.A.2420INV #164 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11171 | 20220115-7 | 53560601 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex was floated over to Santoy Lake and then OP fixed WC 7851.00 | 6 | C158-C170 | Santoy Lake | 0 | 44588 |  | 36 | 44588 |  |  | 7851.00 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1117120220115-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1117120220115-7Operator - Principle - After Jan 108600INV #164 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11171 | 20220115-7 | 53560601 | Water Crossings | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-01-15 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex was floated over to Santoy Lake and then OP fixed WC 7851.00 | 6 | C158-C170 | Santoy Lake | 0 | 44588 |  | 36 | 44588 |  |  | 7851.00 |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1117120220115-7Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1117120220115-7Driver - AZ - After Jan 105350INV #164 |  |  | W6-3rd Season Winter Crossings |  |  | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11216 | 20220116-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12 | Dynamic | 0 | 0 |  |  | 1523.76 | 198.0888 | 1721.8488 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44223 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121620220116-3Grader - Cat 12 to 14 or equal- After Jan 10121523.76 | Corbiere and Sons Contracting1121620220116-3Grader - Cat 12 to 14 or equal- After Jan 10121523.76INV #164 | [5 empty] | 1 | 1523.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11216 | 20220116-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44223 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121620220116-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1121620220116-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11216 | 20220116-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44223 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121620220116-3L.O.A.2420 | Corbiere and Sons Contracting1121620220116-3L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11216 | 20220116-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 0 | 0 | 975 | 126.75 | 1101.75 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44223 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121620220116-3Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1121620220116-3Operator - Principle - After Jan 1013975INV #164 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11216 | 20220116-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44223 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121620220116-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1121620220116-3Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11217 | 20220116-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12 | Dynamic | 0 | 0 |  |  | 1523.76 | 198.0888 | 1721.8488 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121720220116-4Grader - Cat 12 to 14 or equal- After Jan 10121523.76 | Corbiere and Sons Contracting1121720220116-4Grader - Cat 12 to 14 or equal- After Jan 10121523.76INV #164 | [5 empty] | 1 | 1523.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11217 | 20220116-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121720220116-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1121720220116-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11217 | 20220116-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121720220116-4L.O.A.1210 | Corbiere and Sons Contracting1121720220116-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11217 | 20220116-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 0 | 0 | 975 | 126.75 | 1101.75 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121720220116-4Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1121720220116-4Operator - Principle - After Jan 1013975INV #164 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11218 | 20220116-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121820220116-5Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1121820220116-5Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11218 | 20220116-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121820220116-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1121820220116-5Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11218 | 20220116-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121820220116-5L.O.A.1210 | Corbiere and Sons Contracting1121820220116-5L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11218 | 20220116-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1121820220116-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1121820220116-5Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11220 | 20220116-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 |  |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122020220116-7Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1122020220116-7Pickup w/ plow and sander4320INV #164 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11220 | 20220116-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 |  |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122020220116-7L.O.A.1210 | Corbiere and Sons Contracting1122020220116-7L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11220 | 20220116-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 |  |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122020220116-7Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1122020220116-7Operator - Intermdiate - After Jan 104280INV #164 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11222 | 20220116-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 |  |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122220220116-9Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1122220220116-9Pickup w/ plow and sander5400INV #164 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11222 | 20220116-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 0 | 0 | 350 | 45.5 | 395.5 | 2022-01-16 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 |  |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122220220116-9Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting1122220220116-9Operator - Intermdiate - After Jan 105350INV #164 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11224 | 20220117-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122420220117-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1122420220117-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11224 | 20220117-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122420220117-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1122420220117-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11224 | 20220117-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122420220117-3L.O.A.2420 | Corbiere and Sons Contracting1122420220117-3L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11224 | 20220117-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122420220117-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1122420220117-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11224 | 20220117-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122420220117-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1122420220117-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11225 | 20220117-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122520220117-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1122520220117-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11225 | 20220117-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122520220117-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1122520220117-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11225 | 20220117-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122520220117-4L.O.A.1210 | Corbiere and Sons Contracting1122520220117-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11225 | 20220117-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122520220117-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1122520220117-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11226 | 20220117-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122620220117-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1122620220117-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11226 | 20220117-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122620220117-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1122620220117-5Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11226 | 20220117-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122620220117-5L.O.A.1210 | Corbiere and Sons Contracting1122620220117-5L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11226 | 20220117-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-17 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1122620220117-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1122620220117-5Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11232 | 20220118-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123220220118-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1123220220118-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11232 | 20220118-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123220220118-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1123220220118-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11232 | 20220118-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123220220118-3Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1123220220118-3Pickup w/ plow and sander11880INV #164 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11232 | 20220118-3 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123220220118-3L.O.A.3630 | Corbiere and Sons Contracting1123220220118-3L.O.A.3630INV #164 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11232 | 20220118-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123220220118-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1123220220118-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11232 | 20220118-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123220220118-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1123220220118-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11232 | 20220118-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123220220118-3Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1123220220118-3Operator - Intermdiate - After Jan 1011770INV #164 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11233 | 20220118-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123320220118-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1123320220118-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11233 | 20220118-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123320220118-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1123320220118-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11233 | 20220118-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123320220118-4L.O.A.1210 | Corbiere and Sons Contracting1123320220118-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11233 | 20220118-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123320220118-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1123320220118-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11234 | 20220118-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123420220118-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1123420220118-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11234 | 20220118-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123420220118-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1123420220118-5Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11234 | 20220118-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123420220118-5L.O.A.1210 | Corbiere and Sons Contracting1123420220118-5L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11234 | 20220118-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-18 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123420220118-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1123420220118-5Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11235 | 20220119-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 16 | Dynamic | 0 | 0 |  |  | 2031.68 | 264.1184 | 2295.7984 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C070 - C075 | Antler Lake | 0 | 44589 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1123520220119-3Grader - Cat 12 to 14 or equal- After Jan 10162031.68 | Corbiere and Sons Contracting1123520220119-3Grader - Cat 12 to 14 or equal- After Jan 10162031.68INV #164 | [5 empty] | 1 | 2031.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11235 | 20220119-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C070 - C075 | Antler Lake | 0 | 44589 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1123520220119-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1123520220119-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11235 | 20220119-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C070 - C075 | Antler Lake | 0 | 44589 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1123520220119-3L.O.A.2420 | Corbiere and Sons Contracting1123520220119-3L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11235 | 20220119-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 0 | 0 | 1275 | 165.75 | 1440.75 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C070 - C075 | Antler Lake | 0 | 44589 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1123520220119-3Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting1123520220119-3Operator - Principle - After Jan 10171275INV #164 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11235 | 20220119-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C070 - C075 | Antler Lake | 0 | 44589 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1123520220119-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1123520220119-3Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11236 | 20220119-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123620220119-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1123620220119-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11236 | 20220119-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123620220119-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1123620220119-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11236 | 20220119-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123620220119-4L.O.A.1210 | Corbiere and Sons Contracting1123620220119-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11236 | 20220119-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123620220119-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1123620220119-4Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11237 | 20220119-5 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 0 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123720220119-5Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1123720220119-5Grader - Cat 12 to 14 or equal- After Jan 106761.88INV #164 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11237 | 20220119-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123720220119-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1123720220119-5Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11237 | 20220119-5 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123720220119-5Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting1123720220119-5Tractor Trailer - 60 Ton- After Jan 108979.12INV #164 | [5 empty] | 1 | 979.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11237 | 20220119-5 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123720220119-5L.O.A.2420 | Corbiere and Sons Contracting1123720220119-5L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11237 | 20220119-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123720220119-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1123720220119-5Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11237 | 20220119-5 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2022-01-19 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C031-C049 | Pays Plat River | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1123720220119-5Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting1123720220119-5Driver - AZ - After Jan 108560INV #164 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11243 | 20220120-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124320220120-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1124320220120-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11243 | 20220120-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124320220120-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1124320220120-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11243 | 20220120-3 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124320220120-3Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1124320220120-3Pickup w/ plow and sander3240INV #164 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11243 | 20220120-3 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124320220120-3L.O.A.3630 | Corbiere and Sons Contracting1124320220120-3L.O.A.3630INV #164 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11243 | 20220120-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124320220120-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1124320220120-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11243 | 20220120-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124320220120-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1124320220120-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11243 | 20220120-3 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124320220120-3Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1124320220120-3Operator - Intermdiate - After Jan 103210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11244 | 20220120-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124420220120-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1124420220120-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11244 | 20220120-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124420220120-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1124420220120-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11244 | 20220120-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124420220120-4L.O.A.1210 | Corbiere and Sons Contracting1124420220120-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11244 | 20220120-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124420220120-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1124420220120-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11246 | 20220120-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124620220120-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1124620220120-6Pickup w/ plow and sander3240INV #164 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11246 | 20220120-6 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-20 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C070-C075 | White Sand | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124620220120-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1124620220120-6Operator - Intermdiate - After Jan 103210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11249 | 20220121-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124920220121-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1124920220121-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11249 | 20220121-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124920220121-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1124920220121-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11249 | 20220121-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124920220121-3L.O.A.2420 | Corbiere and Sons Contracting1124920220121-3L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11249 | 20220121-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124920220121-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1124920220121-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11249 | 20220121-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1124920220121-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1124920220121-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11250 | 20220121-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125020220121-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1125020220121-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11250 | 20220121-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125020220121-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1125020220121-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11250 | 20220121-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125020220121-4Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1125020220121-4Pickup w/ plow and sander4320INV #164 | [5 empty] | 1 | 320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11250 | 20220121-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125020220121-4L.O.A.2420 | Corbiere and Sons Contracting1125020220121-4L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11250 | 20220121-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125020220121-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1125020220121-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11250 | 20220121-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125020220121-4Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1125020220121-4Operator - Intermdiate - After Jan 104280INV #164 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11253 | 20220121-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 0 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C | Del Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125320220121-7Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1125320220121-7Dozer D6 or equal- After Jan 1081051.84INV #164 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11253 | 20220121-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C | Del Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125320220121-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1125320220121-7Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11253 | 20220121-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 0 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C | Del Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125320220121-7Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1125320220121-7Tractor Trailer - 60 Ton- After Jan 106734.34INV #164 | [5 empty] | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11253 | 20220121-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C | Del Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125320220121-7L.O.A.2420 | Corbiere and Sons Contracting1125320220121-7L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11253 | 20220121-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C | Del Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125320220121-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1125320220121-7Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11253 | 20220121-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2021-01-21 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C | Del Lake | 0 | 44224 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125320220121-7Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1125320220121-7Driver - AZ - After Jan 106420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11262 | 20220122-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 0 |  |  | 0 |  |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126220220122-11Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1126220220122-11Pickup w/ plow and sander3240INV #164 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11262 | 20220122-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 0 |  |  | 0 |  |  | 36 | 44590 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126220220122-11Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1126220220122-11Operator - Intermdiate - After Jan 103210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11254 | 20220122-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125420220122-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1125420220122-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11254 | 20220122-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125420220122-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1125420220122-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11254 | 20220122-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125420220122-3L.O.A.2420 | Corbiere and Sons Contracting1125420220122-3L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11254 | 20220122-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125420220122-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1125420220122-3Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11254 | 20220122-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125420220122-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1125420220122-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11255 | 20220122-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125520220122-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1125520220122-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11255 | 20220122-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125520220122-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1125520220122-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11255 | 20220122-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125520220122-4L.O.A.1210 | Corbiere and Sons Contracting1125520220122-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11255 | 20220122-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-22 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1125520220122-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1125520220122-4Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11263 | 20220123-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 0 | Dynamic | 0 | 0 |  |  | 0 | 0 | 0 | 2022-01-23 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1126320220123-3Grader - Cat 12 to 14 or equal- After Jan 1000 | Corbiere and Sons Contracting1126320220123-3Grader - Cat 12 to 14 or equal- After Jan 1000INV #164 | [5 empty] | 1 | 0 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11263 | 20220123-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-23 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1126320220123-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1126320220123-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11263 | 20220123-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-23 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1126320220123-3L.O.A.1210 | Corbiere and Sons Contracting1126320220123-3L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11263 | 20220123-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-23 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1126320220123-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1126320220123-3Operator - Principle - After Jan 105375INV #164 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11264 | 20220123-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-01-23 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1126420220123-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1126420220123-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11264 | 20220123-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-23 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1126420220123-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1126420220123-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11264 | 20220123-4 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-23 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1126420220123-4L.O.A.2420 | Corbiere and Sons Contracting1126420220123-4L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11264 | 20220123-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-01-23 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1126420220123-4Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1126420220123-4Operator - Principle - After Jan 1010750INV #164 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11264 | 20220123-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-23 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44589 |  | 36 | 44590 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1126420220123-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1126420220123-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11868 | 20220124-10 | 53510711 | Access | 0 | 3rd Party Charges | 1 | 957 | unit |  |  |  |  | 957 | 124.41 | 1081.41 | 2022-01-24 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader into Three Finger Lake West | 6 | D006-D008 | Three Finger Lake West | 0 |  |  | 36 | 44615 | 405 | $2475.00/3 = $825.00*1.16 = $957.00 |  |  |  | Mike Lecocq | 07 | Corbiere and Sons Contracting1186820220124-103rd Party Charges957957 | Corbiere and Sons Contracting1186820220124-103rd Party Charges957957INV #165 | [5 empty] | 1 | 957 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11869 | 20220124-11 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 957 | unit |  |  |  |  | 957 | 124.41 | 1081.41 | 2022-01-24 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader into Prairie River | 6 | C171-C185 | Prairie River | 0 |  |  | 36 | 44615 | 405 | $2475.00/3 = $825.00*1.16 = $957.00 |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1186920220124-113rd Party Charges957957 | Corbiere and Sons Contracting1186920220124-113rd Party Charges957957INV #165 | [5 empty] | 1 | 957 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11269 | 20220124-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1126920220124-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1126920220124-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11269 | 20220124-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1126920220124-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1126920220124-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11269 | 20220124-3 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1126920220124-3L.O.A.1210 | Corbiere and Sons Contracting1126920220124-3L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11269 | 20220124-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Antler | 5 | C050-C069 | Antler Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1126920220124-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1126920220124-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11270 | 20220124-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127020220124-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1127020220124-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11270 | 20220124-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127020220124-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127020220124-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11270 | 20220124-4 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127020220124-4Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1127020220124-4Pickup w/ plow and sander5.5440INV #164 | [5 empty] | 1 | 440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11270 | 20220124-4 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127020220124-4L.O.A.3630 | Corbiere and Sons Contracting1127020220124-4L.O.A.3630INV #164 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11270 | 20220124-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127020220124-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127020220124-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11270 | 20220124-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127020220124-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127020220124-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11270 | 20220124-4 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127020220124-4Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1127020220124-4Operator - Intermdiate - After Jan 105.5385INV #164 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11273 | 20220124-7 | 53510711 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 0 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Three Fingers | 6 | D006-D008 | Three Fingers | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1127320220124-7Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting1127320220124-7Dozer D6 or equal- After Jan 105.5723.14INV #164 | [5 empty] | 1 | 723.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11273 | 20220124-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 0 | 0 | 412.5 | 53.625 | 466.125 | 2022-01-24 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Three Fingers | 6 | D006-D008 | Three Fingers | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127320220124-7Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1127320220124-7Operator - Principle - After Jan 105.5412.5INV #164 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11867 | 20220124-9 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 957 | unit |  |  |  |  | 957 | 124.41 | 1081.41 | 2022-01-24 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader into Peninsula | 6 | C268-D005 | Peninusla | 0 |  |  | 36 | 44615 | 405 | $2475.00/3 = $825.00*1.16 = $957.00 |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1186720220124-93rd Party Charges957957 | Corbiere and Sons Contracting1186720220124-93rd Party Charges957957INV #165 | [5 empty] | 1 | 957 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11276 | 20220125-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-25 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127620220125-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1127620220125-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11276 | 20220125-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-25 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127620220125-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127620220125-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11276 | 20220125-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-25 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127620220125-4L.O.A.1210 | Corbiere and Sons Contracting1127620220125-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11276 | 20220125-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-25 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127620220125-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127620220125-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11278 | 20220125-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-25 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127820220125-6Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1127820220125-6Pickup w/ plow and sander6480INV #164 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11278 | 20220125-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-01-25 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Pays Plat | 5 | C031-C049 | Pays Plat River | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1127820220125-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1127820220125-6Operator - Principle - After Jan 106450INV #164 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11280 | 20220126-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-26 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1128020220126-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1128020220126-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11280 | 20220126-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-26 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1128020220126-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1128020220126-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11280 | 20220126-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-26 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1128020220126-4L.O.A.1210 | Corbiere and Sons Contracting1128020220126-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11280 | 20220126-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-26 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44592 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1128020220126-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1128020220126-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11285 | 20220127-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-27 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C117 - C128 | Cook Lake | 0 |  |  | 37 | 44593 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1128520220127-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1128520220127-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11285 | 20220127-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-27 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C117 - C128 | Cook Lake | 0 |  |  | 37 | 44593 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1128520220127-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1128520220127-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11285 | 20220127-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-27 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C117 - C128 | Cook Lake | 0 |  |  | 37 | 44593 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1128520220127-4L.O.A.1210 | Corbiere and Sons Contracting1128520220127-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11285 | 20220127-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-27 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Cooks | 5 | C117 - C128 | Cook Lake | 0 |  |  | 37 | 44593 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1128520220127-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1128520220127-4Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11288 | 20220127-7 | 53510711 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-27 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Needs WF7 cost code |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1128820220127-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1128820220127-7Dozer D6 or equal- After Jan 104525.92INV #164 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11288 | 20220127-7 | 53510711 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 0 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2022-01-27 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Needs WF7 cost code |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1128820220127-7Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting1128820220127-7Tractor Trailer - 60 Ton- After Jan 10101223.9INV #164 | [5 empty] | 1 | 1223.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11288 | 20220127-7 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-27 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Needs WF7 cost code |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1128820220127-7L.O.A.1210 | Corbiere and Sons Contracting1128820220127-7L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11288 | 20220127-7 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-27 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Needs WF7 cost code |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1128820220127-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1128820220127-7Operator - Principle - After Jan 105375INV #164 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11288 | 20220127-7 | 53510711 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 0 | 0 | 700 | 91 | 791 | 2022-01-27 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Needs WF7 cost code |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1128820220127-7Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting1128820220127-7Driver - AZ - After Jan 1010700INV #164 | [5 empty] | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11293 | 20220128-4 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-28 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cook | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1129320220128-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1129320220128-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11293 | 20220128-4 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-28 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cook | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1129320220128-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1129320220128-4Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11293 | 20220128-4 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-28 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cook | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1129320220128-4L.O.A.1210 | Corbiere and Sons Contracting1129320220128-4L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11293 | 20220128-4 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-28 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Cook | 5 | C076-C116 | Cook Lake | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting1129320220128-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1129320220128-4Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11295 | 20220128-6 | 53510711 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 0 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2022-01-28 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 cost codes |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1129520220128-6Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1129520220128-6Dozer D6 or equal- After Jan 107920.36INV #164 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11295 | 20220128-6 | 53510711 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-28 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 cost codes |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1129520220128-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1129520220128-6Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11295 | 20220128-6 | 53510711 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 0 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-01-28 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 cost codes |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1129520220128-6Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1129520220128-6Tractor Trailer - 60 Ton- After Jan 10111346.29INV #164 | [5 empty] | 1 | 1346.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11295 | 20220128-6 | 53510711 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-01-28 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 cost codes |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1129520220128-6L.O.A.2420 | Corbiere and Sons Contracting1129520220128-6L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11295 | 20220128-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-28 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 cost codes |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1129520220128-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1129520220128-6Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11295 | 20220128-6 | 53510711 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-01-28 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 cost codes |  | Approved |  |  | WAM Activities on Black River | 6 | D032-D047 | Black River | 0 | 44591 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1129520220128-6Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1129520220128-6Driver - AZ - After Jan 1011770INV #164 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11417 | 20220129-6 | 53510711 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4.5 | Dynamic | 98.61 | 0 |  |  | 591.66 | 76.9158 | 668.5758 | 2022-01-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Black River | 6 |  | Black River | 0 | 44592 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1141720220129-6Dozer D6 or equal- After Jan 104.5591.66 | Corbiere and Sons Contracting1141720220129-6Dozer D6 or equal- After Jan 104.5591.66INV #164 | [5 empty] | 1 | 591.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11417 | 20220129-6 | 53510711 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Black River | 6 |  | Black River | 0 | 44592 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1141720220129-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1141720220129-6Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11417 | 20220129-6 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Black River | 6 |  | Black River | 0 | 44592 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1141720220129-6L.O.A.1210 | Corbiere and Sons Contracting1141720220129-6L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11417 | 20220129-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 0 | 0 | 412.5 | 53.625 | 466.125 | 2022-01-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Black River | 6 |  | Black River | 0 | 44592 |  | 37 | 44593 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1141720220129-6Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1141720220129-6Operator - Principle - After Jan 105.5412.5INV #164 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11435 | 20220129-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Jackfish River - WF3 | 3 | B133-B135 | Jackfish River | 0 | 44592 |  | 37 | 44596 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143520220129-9Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1143520220129-9Pickup w/ plow and sander6480INV #164 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11435 | 20220129-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-29 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Jackfish River - WF3 | 3 | B133-B135 | Jackfish River | 0 | 44592 |  | 37 | 44596 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143520220129-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1143520220129-9Operator - Principle - After Jan 106450INV #164 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11440 | 20220130-7 | 53510411 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-30 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Nishin | 4 | C014-C027 | Nishin | 0 | 44596 |  | 37 | 44597 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1144020220130-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1144020220130-7Dozer D6 or equal- After Jan 104525.92INV #164 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11440 | 20220130-7 | 53510411 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2022-01-30 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Nishin | 4 | C014-C027 | Nishin | 0 | 44596 |  | 37 | 44597 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1144020220130-7Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1144020220130-7Tractor Trailer - 60 Ton- After Jan 106734.34INV #164 | [5 empty] | 1 | 734.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11440 | 20220130-7 | 53510411 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-30 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Nishin | 4 | C014-C027 | Nishin | 0 | 44596 |  | 37 | 44597 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1144020220130-7L.O.A.2420 | Corbiere and Sons Contracting1144020220130-7L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11440 | 20220130-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-30 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Nishin | 4 | C014-C027 | Nishin | 0 | 44596 |  | 37 | 44597 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1144020220130-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1144020220130-7Operator - Principle - After Jan 106450INV #164 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11440 | 20220130-7 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2022-01-30 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Nishin | 4 | C014-C027 | Nishin | 0 | 44596 |  | 37 | 44597 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting1144020220130-7Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1144020220130-7Driver - AZ - After Jan 106420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11441 | 20220131-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-31 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 |  | Del Lake | 0 | 44605 |  | 37 | 44596 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1144120220131-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144120220131-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11441 | 20220131-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-31 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 |  | Del Lake | 0 | 44605 |  | 37 | 44596 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1144120220131-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144120220131-3Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11441 | 20220131-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-31 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 |  | Del Lake | 0 | 44605 |  | 37 | 44596 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1144120220131-3L.O.A.1210 | Corbiere and Sons Contracting1144120220131-3L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11441 | 20220131-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-31 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 |  | Del Lake | 0 | 44605 |  | 37 | 44596 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1144120220131-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144120220131-3Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11444 | 20220131-6 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2022-01-31 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn floated DZ from Nishin to Jackpine and then ran it for rest of day | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1144420220131-6Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1144420220131-6Dozer D6 or equal- After Jan 107920.36INV #164 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11444 | 20220131-6 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-01-31 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn floated DZ from Nishin to Jackpine and then ran it for rest of day | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1144420220131-6Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1144420220131-6Tractor Trailer - 60 Ton- After Jan 105611.95INV #164 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11444 | 20220131-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-31 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn floated DZ from Nishin to Jackpine and then ran it for rest of day | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1144420220131-6L.O.A.1210 | Corbiere and Sons Contracting1144420220131-6L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11444 | 20220131-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-31 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn floated DZ from Nishin to Jackpine and then ran it for rest of day | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1144420220131-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1144420220131-6Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11450 | 20220201-7 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 0 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2022-02-01 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn ran DZ in Jackpine for 7 hours | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1145020220201-7Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1145020220201-7Dozer D6 or equal- After Jan 107920.36INV #164 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11450 | 20220201-7 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-01 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn ran DZ in Jackpine for 7 hours | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1145020220201-7L.O.A.1210 | Corbiere and Sons Contracting1145020220201-7L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11450 | 20220201-7 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-02-01 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn ran DZ in Jackpine for 7 hours | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1145020220201-7Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1145020220201-7Operator - Principle - After Jan 107525INV #164 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11463 | 20220202-11 | 53510211 | Access | 0 | Loader JD 744 to 844 or equal | 162 | 7 | HR | 121.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2022-02-02 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities from B013-B016 for Fibre Ooptic box at tower | 2 | B004-B017 | Fish Hatchery | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1146320220202-11Loader JD 744 to 844 or equal71134 | Corbiere and Sons Contracting1146320220202-11Loader JD 744 to 844 or equal71134INV #164 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11463 | 20220202-11 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-02 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities from B013-B016 for Fibre Ooptic box at tower | 2 | B004-B017 | Fish Hatchery | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1146320220202-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146320220202-11Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11463 | 20220202-11 | 53510211 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 7 | Dynamic | 91.79 | 0 |  |  | 856.73 | 111.3749 | 968.1049 | 2022-02-02 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities from B013-B016 for Fibre Ooptic box at tower | 2 | B004-B017 | Fish Hatchery | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1146320220202-11Tractor Trailer - 60 Ton- After Jan 107856.73 | Corbiere and Sons Contracting1146320220202-11Tractor Trailer - 60 Ton- After Jan 107856.73INV #164 | [5 empty] | 1 | 856.73 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11463 | 20220202-11 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-02-02 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities from B013-B016 for Fibre Ooptic box at tower | 2 | B004-B017 | Fish Hatchery | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1146320220202-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1146320220202-11Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11463 | 20220202-11 | 53510211 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2022-02-02 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities from B013-B016 for Fibre Ooptic box at tower | 2 | B004-B017 | Fish Hatchery | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting1146320220202-11Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting1146320220202-11Driver - AZ - After Jan 107490INV #164 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11457 | 20220202-5 | 53510711 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-02 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Three fingers | 6 | D006-D008 | Three Fingers | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1145720220202-5Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1145720220202-5Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #164 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11457 | 20220202-5 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-02-02 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Three fingers | 6 | D006-D008 | Three Fingers | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1145720220202-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1145720220202-5Operator - Principle - After Jan 108600INV #164 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11473 | 20220204-7 | 53510711 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 0 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-02-04 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to 3 Fingers and worked rest of day there | 6 | D006-D017 | Three Fingers | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1147320220204-7Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1147320220204-7Dozer D6 or equal- After Jan 105657.4INV #164 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11473 | 20220204-7 | 53510711 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-02-04 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to 3 Fingers and worked rest of day there | 6 | D006-D017 | Three Fingers | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1147320220204-7Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1147320220204-7Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11473 | 20220204-7 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-02-04 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to 3 Fingers and worked rest of day there | 6 | D006-D017 | Three Fingers | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1147320220204-7Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1147320220204-7Operator - Principle - After Jan 107525INV #164 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11473 | 20220204-7 | 53510711 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-02-04 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to 3 Fingers and worked rest of day there | 6 | D006-D017 | Three Fingers | 0 | 44605 |  | 36 | 44608 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1147320220204-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1147320220204-7Driver - AZ - After Jan 104280INV #164 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11478 | 20220205-6 | 53510711 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-02-05 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 |  | Approved |  |  | Jesse and DZ spent day working in Pic River East | 6 | D018-D024 | Pic River | 0 | 44605 |  | 36 | 44609 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1147820220205-6Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1147820220205-6Dozer D6 or equal- After Jan 10101314.8INV #164 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11478 | 20220205-6 | 53510711 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-05 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 |  | Approved |  |  | Jesse and DZ spent day working in Pic River East | 6 | D018-D024 | Pic River | 0 | 44605 |  | 36 | 44609 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1147820220205-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1147820220205-6Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11478 | 20220205-6 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-05 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 |  | Approved |  |  | Jesse and DZ spent day working in Pic River East | 6 | D018-D024 | Pic River | 0 | 44605 |  | 36 | 44609 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1147820220205-6L.O.A.1210 | Corbiere and Sons Contracting1147820220205-6L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11478 | 20220205-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-05 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 |  | Approved |  |  | Jesse and DZ spent day working in Pic River East | 6 | D018-D024 | Pic River | 0 | 44605 |  | 36 | 44609 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1147820220205-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1147820220205-6Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11483 | 20220206-6 | 53510711 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 0 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-02-06 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 |  | Approved |  |  | Jesse and DZ spent day working in Pic River East | 6 | D018-D024 | Pic River | 0 | 44605 |  | 36 | 44609 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1148320220206-6Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1148320220206-6Dozer D6 or equal- After Jan 105657.4INV #164 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11483 | 20220206-6 | 53510711 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-06 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 |  | Approved |  |  | Jesse and DZ spent day working in Pic River East | 6 | D018-D024 | Pic River | 0 | 44605 |  | 36 | 44609 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1148320220206-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148320220206-6Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11483 | 20220206-6 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-06 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 |  | Approved |  |  | Jesse and DZ spent day working in Pic River East | 6 | D018-D024 | Pic River | 0 | 44605 |  | 36 | 44609 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1148320220206-6L.O.A.1210 | Corbiere and Sons Contracting1148320220206-6L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11483 | 20220206-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-06 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | WF7 |  | Approved |  |  | Jesse and DZ spent day working in Pic River East | 6 | D018-D024 | Pic River | 0 | 44605 |  | 36 | 44609 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1148320220206-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1148320220206-6Operator - Principle - After Jan 106450INV #164 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11501 | 20220209-8 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-02-09 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44609 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1150120220209-8Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1150120220209-8Pickup w/ plow and sander6480INV #164 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11501 | 20220209-8 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-09 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44609 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1150120220209-8Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1150120220209-8Operator - Principle - After Jan 106450INV #164 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11508 | 20220210-7 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2022-02-10 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44610 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1150820220210-7Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting1150820220210-7Dozer D6 or equal- After Jan 106788.88INV #164 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11508 | 20220210-7 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-10 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44610 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1150820220210-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1150820220210-7Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11508 | 20220210-7 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-02-10 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44610 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1150820220210-7Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1150820220210-7Tractor Trailer - 60 Ton- After Jan 10111346.29INV #164 | [5 empty] | 1 | 1346.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11508 | 20220210-7 | 53510311 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-10 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44610 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1150820220210-7L.O.A.2420 | Corbiere and Sons Contracting1150820220210-7L.O.A.2420INV #164 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11508 | 20220210-7 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-02-10 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44610 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1150820220210-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1150820220210-7Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11508 | 20220210-7 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-10 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44610 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1150820220210-7Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1150820220210-7Driver - AZ - After Jan 1011770INV #164 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11514 | 20220211-7 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 0 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2022-02-11 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44610 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1151420220211-7Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1151420220211-7Dozer D6 or equal- After Jan 107920.36INV #164 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11514 | 20220211-7 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-11 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44610 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1151420220211-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151420220211-7Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11514 | 20220211-7 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-11 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44610 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1151420220211-7L.O.A.1210 | Corbiere and Sons Contracting1151420220211-7L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11514 | 20220211-7 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-11 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44610 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1151420220211-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151420220211-7Operator - Principle - After Jan 1011825INV #164 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11520 | 20220212-7 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 0 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2022-02-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1152020220212-7Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1152020220212-7Dozer D6 or equal- After Jan 1081051.84INV #164 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11520 | 20220212-7 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1152020220212-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1152020220212-7Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11520 | 20220212-7 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1152020220212-7L.O.A.1210 | Corbiere and Sons Contracting1152020220212-7L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11520 | 20220212-7 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-02-12 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1152020220212-7Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1152020220212-7Operator - Principle - After Jan 1010750INV #164 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11525 | 20220213-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152520220213-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1152520220213-6Pickup w/ plow and sander12960INV #164 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11525 | 20220213-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152520220213-6L.O.A.1210 | Corbiere and Sons Contracting1152520220213-6L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11525 | 20220213-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152520220213-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1152520220213-6Operator - Principle - After Jan 1012900INV #164 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11526 | 20220213-7 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 1 | Dynamic | 0 | 0 |  |  | 131.48 | 17.0924 | 148.5724 | 2022-02-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1152620220213-7Dozer D6 or equal- After Jan 101131.48 | Corbiere and Sons Contracting1152620220213-7Dozer D6 or equal- After Jan 101131.48INV #164 | [5 empty] | 1 | 131.48 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11526 | 20220213-7 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1152620220213-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1152620220213-7Light Truck - Pick up- After Jan 101243.75INV #164 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11526 | 20220213-7 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1152620220213-7L.O.A.1210 | Corbiere and Sons Contracting1152620220213-7L.O.A.1210INV #164 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11526 | 20220213-7 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-13 | 0 | INV #164 | 44615 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B159-B160 | Jackfish | 0 | 44605 |  | 36 | 44611 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1152620220213-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1152620220213-7Operator - Principle - After Jan 105375INV #164 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11532 | 20220214-6 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 0 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2022-02-14 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp Road 81 | 0 | 44610 |  | 36 | 44615 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1153220220214-6Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1153220220214-6Dozer D6 or equal- After Jan 107920.36INV #165 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11532 | 20220214-6 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-14 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp Road 81 | 0 | 44610 |  | 36 | 44615 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1153220220214-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1153220220214-6Light Truck - Pick up- After Jan 101243.75INV #165 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11532 | 20220214-6 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-02-14 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp Road 81 | 0 | 44610 |  | 36 | 44615 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1153220220214-6Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1153220220214-6Tractor Trailer - 60 Ton- After Jan 105611.95INV #165 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11532 | 20220214-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp Road 81 | 0 | 44610 |  | 36 | 44615 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1153220220214-6L.O.A.1210 | Corbiere and Sons Contracting1153220220214-6L.O.A.1210INV #165 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11532 | 20220214-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-14 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp Road 81 | 0 | 44610 |  | 36 | 44615 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1153220220214-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1153220220214-6Operator - Principle - After Jan 1011825INV #165 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11532 | 20220214-6 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-02-14 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp Road 81 | 0 | 44610 |  | 36 | 44615 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1153220220214-6Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1153220220214-6Driver - AZ - After Jan 105350INV #165 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11870 | 20220215-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-15 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 36 | 44617 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1187020220215-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1187020220215-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #165 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11870 | 20220215-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-15 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 36 | 44617 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1187020220215-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1187020220215-4Light Truck - Pick up- After Jan 101243.75INV #165 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11870 | 20220215-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-15 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 36 | 44617 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1187020220215-4L.O.A.1210 | Corbiere and Sons Contracting1187020220215-4L.O.A.1210INV #165 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11870 | 20220215-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-02-15 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 36 | 44617 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1187020220215-4Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1187020220215-4Operator - Principle - After Jan 1010750INV #165 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11539 | 20220215-6 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-15 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp 81 | 0 | 44615 |  | 36 | 44617 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1153920220215-6Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1153920220215-6Dozer D6 or equal- After Jan 104525.92INV #165 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11539 | 20220215-6 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-15 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp 81 | 0 | 44615 |  | 36 | 44617 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1153920220215-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1153920220215-6Light Truck - Pick up- After Jan 101243.75INV #165 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11539 | 20220215-6 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-15 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp 81 | 0 | 44615 |  | 36 | 44617 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1153920220215-6L.O.A.1210 | Corbiere and Sons Contracting1153920220215-6L.O.A.1210INV #165 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11539 | 20220215-6 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-02-15 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp 81 | 0 | 44615 |  | 36 | 44617 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1153920220215-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1153920220215-6Operator - Principle - After Jan 104300INV #165 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11551 | 20220217-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-17 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 |  | Del Lake | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155120220217-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1155120220217-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11551 | 20220217-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-17 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 |  | Del Lake | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155120220217-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155120220217-4Light Truck - Pick up- After Jan 101243.75INV #165 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11551 | 20220217-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-17 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 |  | Del Lake | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155120220217-4L.O.A.1210 | Corbiere and Sons Contracting1155120220217-4L.O.A.1210INV #165 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11551 | 20220217-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-17 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 |  | Del Lake | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155120220217-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155120220217-4Operator - Principle - After Jan 1011825INV #165 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11559 | 20220218-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-18 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C050-C069 | Antler Lake | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1155920220218-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1155920220218-6Pickup w/ plow and sander11880INV #165 | [5 empty] | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11559 | 20220218-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-18 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C050-C069 | Antler Lake | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1155920220218-6L.O.A.1210 | Corbiere and Sons Contracting1155920220218-6L.O.A.1210INV #165 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11559 | 20220218-6 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-18 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 5 | C050-C069 | Antler Lake | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1155920220218-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1155920220218-6Operator - Intermdiate - After Jan 1011770INV #165 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11568 | 20220219-9 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-19 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp 81 | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1156820220219-9Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1156820220219-9Pickup w/ plow and sander12960INV #165 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11568 | 20220219-9 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-19 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp 81 | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1156820220219-9L.O.A.1210 | Corbiere and Sons Contracting1156820220219-9L.O.A.1210INV #165 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11568 | 20220219-9 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-19 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp 81 | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1156820220219-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1156820220219-9Operator - Principle - After Jan 1012900INV #165 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11573 | 20220220-6 | 53510711 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-20 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Three Fingers - WF7 | 6 | D006-D017 | Three Fingers - WF7 | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1157320220220-6Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1157320220220-6Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #165 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11573 | 20220220-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-20 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Three Fingers - WF7 | 6 | D006-D017 | Three Fingers - WF7 | 0 | 44615 |  | 36 | 44616 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1157320220220-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1157320220220-6Operator - Principle - After Jan 106450INV #165 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11575 | 20220220-8 | 53510311 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-20 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp 81 | 0 | 44615 |  | 36 | 44617 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1157520220220-8Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1157520220220-8Pickup w/ plow and sander12960INV #165 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11575 | 20220220-8 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-20 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp 81 | 0 | 44615 |  | 36 | 44617 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1157520220220-8L.O.A.1210 | Corbiere and Sons Contracting1157520220220-8L.O.A.1210INV #165 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11575 | 20220220-8 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-20 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 3 | B145-B147 | Camp 81 | 0 | 44615 |  | 36 | 44617 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting1157520220220-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1157520220220-8Operator - Principle - After Jan 1012900INV #165 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11580 | 20220221-6 | 53510711 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2022-02-21 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Three Fingers - WF7 | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44627 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1158020220221-6Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1158020220221-6Dozer D6 or equal- After Jan 1081051.84INV #165 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11580 | 20220221-6 | 53510711 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-21 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Three Fingers - WF7 | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44627 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1158020220221-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158020220221-6Light Truck - Pick up- After Jan 101243.75INV #165 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11580 | 20220221-6 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Three Fingers - WF7 | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44627 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1158020220221-6L.O.A.1210 | Corbiere and Sons Contracting1158020220221-6L.O.A.1210INV #165 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11580 | 20220221-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-21 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Three Fingers - WF7 | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44627 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1158020220221-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158020220221-6Operator - Principle - After Jan 1011825INV #165 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11594 | 20220223-8 | 53510711 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2022-02-23 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44628 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1159420220223-8Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting1159420220223-8Dozer D6 or equal- After Jan 106788.88INV #165 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11594 | 20220223-8 | 53510711 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2022-02-23 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44628 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1159420220223-8Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1159420220223-8Tractor Trailer - 60 Ton- After Jan 10121468.68INV #165 | [5 empty] | 1 | 1468.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11594 | 20220223-8 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44628 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1159420220223-8L.O.A.1210 | Corbiere and Sons Contracting1159420220223-8L.O.A.1210INV #165 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11594 | 20220223-8 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-02-23 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44628 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1159420220223-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1159420220223-8Operator - Principle - After Jan 108600INV #165 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11594 | 20220223-8 | 53510711 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2022-02-23 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44628 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1159420220223-8Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1159420220223-8Driver - AZ - After Jan 1012840INV #165 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11599 | 20220224-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-24 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 44623 |  | 37 | 44629 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159920220224-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1159920220224-6Operator - Intermdiate - After Jan 1011770INV #165 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11605 | 20220225-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-25 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 44623 |  | 37 | 44627 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160520220225-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1160520220225-6Operator - Intermdiate - After Jan 1011770INV #165 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11609 | 20220226-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-26 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 44623 |  | 37 | 44629 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160920220226-5Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1160920220226-5Operator - Intermdiate - After Jan 1011770INV #165 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11625 | 20220301-6 | 53510711 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-03-01 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44628 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1162520220301-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1162520220301-6Pickup w/ plow and sander12960INV #165 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11625 | 20220301-6 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-01 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44628 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1162520220301-6L.O.A.1210 | Corbiere and Sons Contracting1162520220301-6L.O.A.1210INV #165 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11625 | 20220301-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-03-01 | 0 | INV #165 | 44634 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | D006-D017 | Three Finger Lake | 0 | 44623 |  | 37 | 44628 | [5 empty] | Harold Furlong | 07 | Corbiere and Sons Contracting1162520220301-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1162520220301-6Operator - Principle - After Jan 1012900INV #165 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11725 | 20220302-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-03-02 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 0 |  |  | 0 | 44636 | [9 empty] | 06 | Corbiere and Sons Contracting1172520220302-5Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1172520220302-5Grader - Cat 12 to 14 or equal- After Jan 103380.94 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11725 | 20220302-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-03-02 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 0 |  |  | 0 | 44636 | [9 empty] | 06 | Corbiere and Sons Contracting1172520220302-5Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1172520220302-5Operator - Principle - After Jan 103225 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11726 | 20220302-7 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-03-02 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 1 | A002-A010 | MacGregor West | 0 | 44636 | [9 empty] | 01 | Corbiere and Sons Contracting1172620220302-7Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1172620220302-7Tractor Trailer - 60 Ton- After Jan 103367.17 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11726 | 20220302-7 | 53510111 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-03-02 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 1 | A002-A010 | MacGregor West | 0 | 44636 | [9 empty] | 01 | Corbiere and Sons Contracting1172620220302-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1172620220302-7Pickup w/ plow and sander12960 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11726 | 20220302-7 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-02 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 1 | A002-A010 | MacGregor West | 0 | 44636 | [9 empty] | 01 | Corbiere and Sons Contracting1172620220302-7L.O.A.1210 | Corbiere and Sons Contracting1172620220302-7L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11726 | 20220302-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-03-02 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 1 | A002-A010 | MacGregor West | 0 | 44636 | [9 empty] | 01 | Corbiere and Sons Contracting1172620220302-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1172620220302-7Operator - Principle - After Jan 1012900 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11726 | 20220302-7 | 53510111 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-03-02 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 1 | A002-A010 | MacGregor West | 0 | 44636 | [9 empty] | 01 | Corbiere and Sons Contracting1172620220302-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1172620220302-7Driver - AZ - After Jan 103210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11731 | 20220303-6 | 53510711 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-03-03 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1173120220303-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1173120220303-6Pickup w/ plow and sander12960 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11731 | 20220303-6 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-03 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1173120220303-6L.O.A.1210 | Corbiere and Sons Contracting1173120220303-6L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11731 | 20220303-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-03-03 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1173120220303-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1173120220303-6Operator - Principle - After Jan 1012900 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11733 | 20220303-8 | 53510111 | Access | 0 | Loader JD 744 to 844 or equal | 162 | 8 | HR | 121.5 | 0 |  |  | 1296 | 168.48 | 1464.48 | 2022-03-03 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 1 | A002-A010 | MacGregor | 0 | 44636 | [9 empty] | 01 | Corbiere and Sons Contracting1173320220303-8Loader JD 744 to 844 or equal81296 | Corbiere and Sons Contracting1173320220303-8Loader JD 744 to 844 or equal81296 | [5 empty] | 1 | 1296 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11733 | 20220303-8 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-03-03 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 1 | A002-A010 | MacGregor | 0 | 44636 | [9 empty] | 01 | Corbiere and Sons Contracting1173320220303-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1173320220303-8Tractor Trailer - 60 Ton- After Jan 104489.56 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11733 | 20220303-8 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-03-03 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 1 | A002-A010 | MacGregor | 0 | 44636 | [9 empty] | 01 | Corbiere and Sons Contracting1173320220303-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1173320220303-8Operator - Principle - After Jan 108600 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11733 | 20220303-8 | 53510111 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-03-03 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 1 | A002-A010 | MacGregor | 0 | 44636 | [9 empty] | 01 | Corbiere and Sons Contracting1173320220303-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1173320220303-8Driver - AZ - After Jan 104280 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11736 | 20220304-6 | 53510711 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-03-04 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1173620220304-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1173620220304-6Pickup w/ plow and sander12960 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11736 | 20220304-6 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1173620220304-6L.O.A.1210 | Corbiere and Sons Contracting1173620220304-6L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11736 | 20220304-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-03-04 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1173620220304-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1173620220304-6Operator - Principle - After Jan 1012900 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11738 | 20220304-8 | 53510311 | Access | 0 | Loader JD 744 to 844 or equal | 162 | 3 | HR | 0 | 0 |  |  | 486 | 63.18 | 549.18 | 2022-03-04 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 3 | B133-B135 | Jackfish River | 0 | 44636 | [9 empty] | 03 | Corbiere and Sons Contracting1173820220304-8Loader JD 744 to 844 or equal3486 | Corbiere and Sons Contracting1173820220304-8Loader JD 744 to 844 or equal3486 | [5 empty] | 1 | 486 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11738 | 20220304-8 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-04 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 3 | B133-B135 | Jackfish River | 0 | 44636 | [9 empty] | 03 | Corbiere and Sons Contracting1173820220304-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1173820220304-8Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11738 | 20220304-8 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 0 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2022-03-04 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 3 | B133-B135 | Jackfish River | 0 | 44636 | [9 empty] | 03 | Corbiere and Sons Contracting1173820220304-8Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting1173820220304-8Tractor Trailer - 60 Ton- After Jan 102244.78 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11738 | 20220304-8 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-03-04 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 3 | B133-B135 | Jackfish River | 0 | 44636 | [9 empty] | 03 | Corbiere and Sons Contracting1173820220304-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1173820220304-8Operator - Principle - After Jan 104300 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11738 | 20220304-8 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-03-04 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 3 | B133-B135 | Jackfish River | 0 | 44636 | [9 empty] | 03 | Corbiere and Sons Contracting1173820220304-8Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting1173820220304-8Driver - AZ - After Jan 102140 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11745 | 20220305-6 | 53510711 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-03-05 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1174520220305-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1174520220305-6Pickup w/ plow and sander12960 | [5 empty] | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11745 | 20220305-6 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-05 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1174520220305-6L.O.A.1210 | Corbiere and Sons Contracting1174520220305-6L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11745 | 20220305-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-03-05 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D018-D024 | Pic River | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1174520220305-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1174520220305-6Operator - Principle - After Jan 1012900 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11747 | 20220305-8 | 53510311 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 0 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-03-05 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 3 | B133-B135 | Jackfish River | 0 | 44636 | [9 empty] | 03 | Corbiere and Sons Contracting1174720220305-8Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1174720220305-8Tractor Trailer - 60 Ton- After Jan 10111346.29 | [5 empty] | 1 | 1346.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11747 | 20220305-8 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-05 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 3 | B133-B135 | Jackfish River | 0 | 44636 | [9 empty] | 03 | Corbiere and Sons Contracting1174720220305-8L.O.A.1210 | Corbiere and Sons Contracting1174720220305-8L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11747 | 20220305-8 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-03-05 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 3 | B133-B135 | Jackfish River | 0 | 44636 | [9 empty] | 03 | Corbiere and Sons Contracting1174720220305-8Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1174720220305-8Driver - AZ - After Jan 1011770 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11750 | 20220306-6 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 0 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2022-03-06 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175020220306-6Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting1175020220306-6Dozer D6 or equal- After Jan 105.5723.14 | [5 empty] | 1 | 723.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11750 | 20220306-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-06 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175020220306-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1175020220306-6Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11750 | 20220306-6 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-03-06 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175020220306-6Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1175020220306-6Tractor Trailer - 60 Ton- After Jan 104489.56 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11750 | 20220306-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-06 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175020220306-6L.O.A.1210 | Corbiere and Sons Contracting1175020220306-6L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11750 | 20220306-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-03-06 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175020220306-6Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1175020220306-6Operator - Principle - After Jan 107525 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11750 | 20220306-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 0.5 | HR |  |  | 75 | 0 | 37.5 | 4.875 | 42.375 | 2022-03-06 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175020220306-6Operator - Principle - After Jan 100.537.5 | Corbiere and Sons Contracting1175020220306-6Operator - Principle - After Jan 100.537.5 | [5 empty] | 1 | 37.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11750 | 20220306-6 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-03-06 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175020220306-6Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1175020220306-6Driver - AZ - After Jan 104280 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11756 | 20220307-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-03-07 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175620220307-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1175620220307-5Dozer D6 or equal- After Jan 10101314.8 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11756 | 20220307-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-07 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175620220307-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1175620220307-5Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11756 | 20220307-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-07 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175620220307-5L.O.A.1210 | Corbiere and Sons Contracting1175620220307-5L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11756 | 20220307-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-07 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1175620220307-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1175620220307-5Operator - Principle - After Jan 1011825 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11759 | 20220308-4 | 53510711 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-03-08 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1175920220308-4Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1175920220308-4Grader - Cat 12 to 14 or equal- After Jan 104507.92 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11759 | 20220308-4 | 53510711 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-08 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1175920220308-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1175920220308-4Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11759 | 20220308-4 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-08 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1175920220308-4L.O.A.1210 | Corbiere and Sons Contracting1175920220308-4L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11759 | 20220308-4 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-03-08 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1175920220308-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1175920220308-4Operator - Principle - After Jan 105375 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11759 | 20220308-4 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 0.5 | HR |  |  | 75 | 0 | 37.5 | 4.875 | 42.375 | 2022-03-08 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1175920220308-4Operator - Principle - After Jan 100.537.5 | Corbiere and Sons Contracting1175920220308-4Operator - Principle - After Jan 100.537.5 | [5 empty] | 1 | 37.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11760 | 20220308-5 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 0 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2022-03-08 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1176020220308-5Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1176020220308-5Dozer D6 or equal- After Jan 103394.44 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11760 | 20220308-5 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-08 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1176020220308-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1176020220308-5Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11760 | 20220308-5 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-08 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1176020220308-5L.O.A.1210 | Corbiere and Sons Contracting1176020220308-5L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11760 | 20220308-5 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-03-08 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C117-C128 | Terrace Bay | 0 | 44636 | [9 empty] | 05 | Corbiere and Sons Contracting1176020220308-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1176020220308-5Operator - Principle - After Jan 106450 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11764 | 20220309-4 | 53510711 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-03-09 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D006-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176420220309-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1176420220309-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11764 | 20220309-4 | 53510711 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-09 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D006-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176420220309-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1176420220309-4Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11764 | 20220309-4 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-09 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D006-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176420220309-4L.O.A.1210 | Corbiere and Sons Contracting1176420220309-4L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11764 | 20220309-4 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-09 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D006-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176420220309-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1176420220309-4Operator - Principle - After Jan 1011825 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11767 | 20220310-3 | 53510711 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-10 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176720220310-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1176720220310-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11767 | 20220310-3 | 53510711 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-10 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176720220310-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1176720220310-3Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11767 | 20220310-3 | 53510711 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2022-03-10 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176720220310-3Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1176720220310-3Pickup w/ plow and sander5400 | [5 empty] | 1 | 400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11767 | 20220310-3 | 53510711 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2022-03-10 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176720220310-3Foreman5475 | Corbiere and Sons Contracting1176720220310-3Foreman5475 | [5 empty] | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11767 | 20220310-3 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-10 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176720220310-3L.O.A.1210 | Corbiere and Sons Contracting1176720220310-3L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11767 | 20220310-3 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-10 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176720220310-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1176720220310-3Operator - Principle - After Jan 1011825 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11767 | 20220310-3 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 0.5 | HR |  |  | 0 | 0 | 37.5 | 4.875 | 42.375 | 2022-03-10 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44636 | [9 empty] | 07 | Corbiere and Sons Contracting1176720220310-3Operator - Principle - After Jan 100.537.5 | Corbiere and Sons Contracting1176720220310-3Operator - Principle - After Jan 100.537.5 | [5 empty] | 1 | 37.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11872 | 20220311-3 | 53510711 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 0 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44641 | [9 empty] | 07 | Corbiere and Sons Contracting1187220220311-3Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1187220220311-3Grader - Cat 12 to 14 or equal- After Jan 104507.92 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11872 | 20220311-3 | 53510711 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44641 | [9 empty] | 07 | Corbiere and Sons Contracting1187220220311-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1187220220311-3Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11872 | 20220311-3 | 53510711 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44641 | [9 empty] | 07 | Corbiere and Sons Contracting1187220220311-3L.O.A.1210 | Corbiere and Sons Contracting1187220220311-3L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11872 | 20220311-3 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44641 | [9 empty] | 07 | Corbiere and Sons Contracting1187220220311-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1187220220311-3Operator - Principle - After Jan 106450 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11872 | 20220311-3 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 0.5 | HR |  |  | 0 | 0 | 37.5 | 4.875 | 42.375 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | D009-D017 | Three Finger Lake | 0 | 44641 | [9 empty] | 07 | Corbiere and Sons Contracting1187220220311-3Operator - Principle - After Jan 100.537.5 | Corbiere and Sons Contracting1187220220311-3Operator - Principle - After Jan 100.537.5 | [5 empty] | 1 | 37.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11873 | 20220311-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187320220311-4Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1187320220311-4Grader - Cat 12 to 14 or equal- After Jan 103380.94 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11873 | 20220311-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187320220311-4Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1187320220311-4Tractor Trailer - 60 Ton- After Jan 105611.95 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11873 | 20220311-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187320220311-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1187320220311-4Operator - Principle - After Jan 106450 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11873 | 20220311-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187320220311-4Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1187320220311-4Driver - AZ - After Jan 105350 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11874 | 20220311-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C242 | Neys | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187420220311-5Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1187420220311-5Dozer D6 or equal- After Jan 105657.4 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11874 | 20220311-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-03-11 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C242 | Neys | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187420220311-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1187420220311-5Operator - Principle - After Jan 106450 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11876 | 20220312-3 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C050-C069 | Antler Lake | 0 | 44641 | [9 empty] | 05 | Corbiere and Sons Contracting1187620220312-3Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1187620220312-3Grader - Cat 12 to 14 or equal- After Jan 103380.94 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11876 | 20220312-3 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C050-C069 | Antler Lake | 0 | 44641 | [9 empty] | 05 | Corbiere and Sons Contracting1187620220312-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1187620220312-3Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11876 | 20220312-3 | 53510511 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C050-C069 | Antler Lake | 0 | 44641 | [9 empty] | 05 | Corbiere and Sons Contracting1187620220312-3Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1187620220312-3Tractor Trailer - 60 Ton- After Jan 104489.56 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11876 | 20220312-3 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C050-C069 | Antler Lake | 0 | 44641 | [9 empty] | 05 | Corbiere and Sons Contracting1187620220312-3L.O.A.2420 | Corbiere and Sons Contracting1187620220312-3L.O.A.2420 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11876 | 20220312-3 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C050-C069 | Antler Lake | 0 | 44641 | [9 empty] | 05 | Corbiere and Sons Contracting1187620220312-3Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1187620220312-3Operator - Principle - After Jan 104300 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11876 | 20220312-3 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 5 | C050-C069 | Antler Lake | 0 | 44641 | [9 empty] | 05 | Corbiere and Sons Contracting1187620220312-3Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1187620220312-3Driver - AZ - After Jan 104280 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11877 | 20220312-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187720220312-4Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1187720220312-4Grader - Cat 12 to 14 or equal- After Jan 103380.94 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11877 | 20220312-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187720220312-4Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1187720220312-4Tractor Trailer - 60 Ton- After Jan 104489.56 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11877 | 20220312-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187720220312-4Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1187720220312-4Operator - Principle - After Jan 104300 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11877 | 20220312-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187720220312-4Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1187720220312-4Driver - AZ - After Jan 104280 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11878 | 20220312-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187820220312-5Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting1187820220312-5Grader - Cat 12 to 14 or equal- After Jan 102253.96 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11878 | 20220312-5 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187820220312-5Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1187820220312-5Tractor Trailer - 60 Ton- After Jan 105611.95 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11878 | 20220312-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187820220312-5Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1187820220312-5Operator - Principle - After Jan 103225 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11878 | 20220312-5 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187820220312-5Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1187820220312-5Driver - AZ - After Jan 103210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11879 | 20220312-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 0 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Str range same as FDM as per H.Furlong |  | Pending |  |  | WAM Activities | 6 | C219-C242 | Neys | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187920220312-6Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1187920220312-6Dozer D6 or equal- After Jan 105657.4 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11879 | 20220312-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-03-12 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Str range same as FDM as per H.Furlong |  | Pending |  |  | WAM Activities | 6 | C219-C242 | Neys | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1187920220312-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1187920220312-6Operator - Principle - After Jan 106450 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11883 | 20220313-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-03-13 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188320220313-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1188320220313-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11883 | 20220313-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-13 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188320220313-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1188320220313-3Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11883 | 20220313-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 0 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2022-03-13 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188320220313-3Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting1188320220313-3Tractor Trailer - 60 Ton- After Jan 102244.78 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11883 | 20220313-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-13 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188320220313-3L.O.A.1210 | Corbiere and Sons Contracting1188320220313-3L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11883 | 20220313-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-13 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188320220313-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1188320220313-3Operator - Principle - After Jan 1011825 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11883 | 20220313-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-03-13 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188320220313-3Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting1188320220313-3Driver - AZ - After Jan 102140 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11885 | 20220314-3 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2022-03-14 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188520220314-3Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1188520220314-3Dozer D6 or equal- After Jan 107920.36 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11885 | 20220314-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-14 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188520220314-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1188520220314-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11885 | 20220314-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-14 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188520220314-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1188520220314-3Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11885 | 20220314-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-03-14 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188520220314-3L.O.A.2420 | Corbiere and Sons Contracting1188520220314-3L.O.A.2420 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11885 | 20220314-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-03-14 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188520220314-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1188520220314-3Operator - Principle - After Jan 1011825 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11885 | 20220314-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2022-03-14 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188520220314-3Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1188520220314-3Operator - Principle - After Jan 108600 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11887 | 20220315-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-03-15 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188720220315-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1188720220315-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11887 | 20220315-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-15 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188720220315-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1188720220315-3Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11887 | 20220315-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-15 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188720220315-3L.O.A.1210 | Corbiere and Sons Contracting1188720220315-3L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11887 | 20220315-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-03-15 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1188720220315-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1188720220315-3Operator - Principle - After Jan 106450 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11893 | 20220317-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-03-17 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1189320220317-3Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1189320220317-3Grader - Cat 12 to 14 or equal- After Jan 104507.92 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11893 | 20220317-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-17 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1189320220317-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1189320220317-3Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11893 | 20220317-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-03-17 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1189320220317-3Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1189320220317-3Tractor Trailer - 60 Ton- After Jan 103367.17 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11893 | 20220317-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-17 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1189320220317-3L.O.A.1210 | Corbiere and Sons Contracting1189320220317-3L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11893 | 20220317-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 |  | 600 | 78 | 678 | 2022-03-17 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1189320220317-3Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1189320220317-3Operator - Principle - After Jan 108600 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11893 | 20220317-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-03-17 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1189320220317-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1189320220317-3Driver - AZ - After Jan 103210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11897 | 20220318-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 0 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-03-18 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1189720220318-3Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1189720220318-3Grader - Cat 12 to 14 or equal- After Jan 104507.92 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11897 | 20220318-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-18 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1189720220318-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1189720220318-3Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11897 | 20220318-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-18 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1189720220318-3L.O.A.1210 | Corbiere and Sons Contracting1189720220318-3L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11897 | 20220318-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-03-18 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 44641 | [9 empty] | 06 | Corbiere and Sons Contracting1189720220318-3Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1189720220318-3Operator - Principle - After Jan 108600 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11920 | 20220319-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-19 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C152 - C154 | Lake A | 0 | 44649 | [6 empty] | ANWIN - Winter Only |  |  | 06 | Corbiere and Sons Contracting1192020220319-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1192020220319-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11920 | 20220319-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-19 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C152 - C154 | Lake A | 0 | 44649 | [6 empty] | ANWIN - Winter Only |  |  | 06 | Corbiere and Sons Contracting1192020220319-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1192020220319-3Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11920 | 20220319-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-19 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C152 - C154 | Lake A | 0 | 44649 | [6 empty] | ANWIN - Winter Only |  |  | 06 | Corbiere and Sons Contracting1192020220319-3L.O.A.1210 | Corbiere and Sons Contracting1192020220319-3L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11920 | 20220319-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-19 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C152 - C154 | Lake A | 0 | 44649 | [6 empty] | ANWIN - Winter Only |  |  | 06 | Corbiere and Sons Contracting1192020220319-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1192020220319-3Operator - Principle - After Jan 1011825 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11922 | 20220320-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-03-20 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 44649 | [9 empty] | 06 | Corbiere and Sons Contracting1192220220320-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1192220220320-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11922 | 20220320-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-20 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 44649 | [9 empty] | 06 | Corbiere and Sons Contracting1192220220320-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1192220220320-3Light Truck - Pick up- After Jan 101243.75 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11922 | 20220320-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 0 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2022-03-20 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 44649 | [9 empty] | 06 | Corbiere and Sons Contracting1192220220320-3Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting1192220220320-3Tractor Trailer - 60 Ton- After Jan 102244.78 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11922 | 20220320-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-20 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 44649 | [9 empty] | 06 | Corbiere and Sons Contracting1192220220320-3L.O.A.1210 | Corbiere and Sons Contracting1192220220320-3L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11922 | 20220320-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-20 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 44649 | [9 empty] | 06 | Corbiere and Sons Contracting1192220220320-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1192220220320-3Operator - Principle - After Jan 1011825 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11922 | 20220320-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-03-20 |  | Inv#169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 44649 | [9 empty] | 06 | Corbiere and Sons Contracting1192220220320-3Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting1192220220320-3Driver - AZ - After Jan 102140 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11913 | 20220324-3-RCL | 53540603 | Reclamation | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2022-03-24 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEL LAKE- Excavator mobilized from Jack fish to Del lake then removed the bridge tops from WC 8072, WC8071 and WC8090 CHANGE ORDER COST CODE 57010141 | 6 | C186-C195 | Del Lake | 0 | 44644 |  | 36 | 44644 |  |  | 8072, 8071, 8090 | ANWIN - Winter Only | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191320220324-3-RCLExcavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1191320220324-3-RCLExcavator - 30 ton- After Jan 105692.25 |  |  | WF6- Bridge Top Removals |  |  | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11913 | 20220324-3-RCL | 53540603 | Reclamation | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2022-03-24 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEL LAKE- Excavator mobilized from Jack fish to Del lake then removed the bridge tops from WC 8072, WC8071 and WC8090 CHANGE ORDER COST CODE 57010141 | 6 | C186-C195 | Del Lake | 0 | 44644 |  | 36 | 44644 |  |  | 8072, 8071, 8090 | ANWIN - Winter Only | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191320220324-3-RCLExcavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1191320220324-3-RCLExcavator Thumb - 30 - 50 ton- After Jan 10561.05 |  |  | WF6- Bridge Top Removals |  |  | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11913 | 20220324-3-RCL | 53540603 | Reclamation | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-24 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEL LAKE- Excavator mobilized from Jack fish to Del lake then removed the bridge tops from WC 8072, WC8071 and WC8090 CHANGE ORDER COST CODE 57010141 | 6 | C186-C195 | Del Lake | 0 | 44644 |  | 36 | 44644 |  |  | 8072, 8071, 8090 | ANWIN - Winter Only | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191320220324-3-RCLLight Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1191320220324-3-RCLLight Truck - Pick up- After Jan 101243.75 |  |  | WF6- Bridge Top Removals |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11913 | 20220324-3-RCL | 53540603 | Reclamation | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-24 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEL LAKE- Excavator mobilized from Jack fish to Del lake then removed the bridge tops from WC 8072, WC8071 and WC8090 CHANGE ORDER COST CODE 57010141 | 6 | C186-C195 | Del Lake | 0 | 44644 |  | 36 | 44644 |  |  | 8072, 8071, 8090 | ANWIN - Winter Only | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191320220324-3-RCLLight Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1191320220324-3-RCLLight Truck - Pick up- After Jan 101243.75 |  |  | WF6- Bridge Top Removals |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11913 | 20220324-3-RCL | 53540603 | Reclamation | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2022-03-24 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEL LAKE- Excavator mobilized from Jack fish to Del lake then removed the bridge tops from WC 8072, WC8071 and WC8090 CHANGE ORDER COST CODE 57010141 | 6 | C186-C195 | Del Lake | 0 | 44644 |  | 36 | 44644 |  |  | 8072, 8071, 8090 | ANWIN - Winter Only | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191320220324-3-RCLForeman10950 | Corbiere and Sons Contracting1191320220324-3-RCLForeman10950 |  |  | WF6- Bridge Top Removals |  |  | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11913 | 20220324-3-RCL | 53540603 | Reclamation | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-24 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEL LAKE- Excavator mobilized from Jack fish to Del lake then removed the bridge tops from WC 8072, WC8071 and WC8090 CHANGE ORDER COST CODE 57010141 | 6 | C186-C195 | Del Lake | 0 | 44644 |  | 36 | 44644 |  |  | 8072, 8071, 8090 | ANWIN - Winter Only | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191320220324-3-RCLL.O.A.1210 | Corbiere and Sons Contracting1191320220324-3-RCLL.O.A.1210 |  |  | WF6- Bridge Top Removals |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11913 | 20220324-3-RCL | 53540603 | Reclamation | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-24 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEL LAKE- Excavator mobilized from Jack fish to Del lake then removed the bridge tops from WC 8072, WC8071 and WC8090 CHANGE ORDER COST CODE 57010141 | 6 | C186-C195 | Del Lake | 0 | 44644 |  | 36 | 44644 |  |  | 8072, 8071, 8090 | ANWIN - Winter Only | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191320220324-3-RCLL.O.A.1210 | Corbiere and Sons Contracting1191320220324-3-RCLL.O.A.1210 |  |  | WF6- Bridge Top Removals |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11913 | 20220324-3-RCL | 53540607 | Reclamation | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-24 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Reclaim Mob/Demob | Reclaim Mob/Demob | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEL LAKE- Excavator mobilized from Jack fish to Del lake then removed the bridge tops from WC 8072, WC8071 and WC8090 CHANGE ORDER COST CODE 57010141 | 6 | C186-C195 | Del Lake | 0 | 44644 |  | 36 | 44644 |  |  | 8072, 8071, 8090 | ANWIN - Winter Only | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191320220324-3-RCLL.O.A.1210 | Corbiere and Sons Contracting1191320220324-3-RCLL.O.A.1210 |  |  | WF6- Bridge Top Removals |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11913 | 20220324-3-RCL | 53540603 | Reclamation | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2022-03-24 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEL LAKE- Excavator mobilized from Jack fish to Del lake then removed the bridge tops from WC 8072, WC8071 and WC8090 CHANGE ORDER COST CODE 57010141 | 6 | C186-C195 | Del Lake | 0 | 44644 |  | 36 | 44644 |  |  | 8072, 8071, 8090 | ANWIN - Winter Only | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191320220324-3-RCLOperator - Principle - After Jan 109675 | Corbiere and Sons Contracting1191320220324-3-RCLOperator - Principle - After Jan 109675 |  |  | WF6- Bridge Top Removals |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11913 | 20220324-3-RCL | 53540607 | Reclamation | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-03-24 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Reclaim Mob/Demob | Reclaim Mob/Demob | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEL LAKE- Excavator mobilized from Jack fish to Del lake then removed the bridge tops from WC 8072, WC8071 and WC8090 CHANGE ORDER COST CODE 57010141 | 6 | C186-C195 | Del Lake | 0 | 44644 |  | 36 | 44644 |  |  | 8072, 8071, 8090 | ANWIN - Winter Only | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191320220324-3-RCLDriver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1191320220324-3-RCLDriver - AZ - After Jan 1011770 |  |  | WF6- Bridge Top Removals |  |  | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11916 | 20220326-1-RCL | 53540603 | Reclamation | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2022-03-26 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEADHORSE CREEK- Excavator walked to the back of dead horse and removed the tops of the bridges at water crossings WC8140.00, WC8150.01, WC8161.00, WC8171.00 and WC8160 then mobilized to Middleton at the end of shift. CHANGE ORDER COST CODE 57010141 | 6 | C203-C209 | Dead Horse Creek | 0 | 44646 |  | 36 | 44646 |  |  |  | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191620220326-1-RCLExcavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting1191620220326-1-RCLExcavator - 30 ton- After Jan 1091246.05 |  |  | WF6- Bridge Top Removals |  |  | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11916 | 20220326-1-RCL | 53540603 | Reclamation | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2022-03-26 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEADHORSE CREEK- Excavator walked to the back of dead horse and removed the tops of the bridges at water crossings WC8140.00, WC8150.01, WC8161.00, WC8171.00 and WC8160 then mobilized to Middleton at the end of shift. CHANGE ORDER COST CODE 57010141 | 6 | C203-C209 | Dead Horse Creek | 0 | 44646 |  | 36 | 44646 |  |  |  | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191620220326-1-RCLExcavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1191620220326-1-RCLExcavator Thumb - 30 - 50 ton- After Jan 109109.89 |  |  | WF6- Bridge Top Removals |  |  | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11916 | 20220326-1-RCL | 53540603 | Reclamation | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2022-03-26 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEADHORSE CREEK- Excavator walked to the back of dead horse and removed the tops of the bridges at water crossings WC8140.00, WC8150.01, WC8161.00, WC8171.00 and WC8160 then mobilized to Middleton at the end of shift. CHANGE ORDER COST CODE 57010141 | 6 | C203-C209 | Dead Horse Creek | 0 | 44646 |  | 36 | 44646 |  |  |  | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191620220326-1-RCLForeman111045 | Corbiere and Sons Contracting1191620220326-1-RCLForeman111045 |  |  | WF6- Bridge Top Removals |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11916 | 20220326-1-RCL | 53540603 | Reclamation | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-26 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEADHORSE CREEK- Excavator walked to the back of dead horse and removed the tops of the bridges at water crossings WC8140.00, WC8150.01, WC8161.00, WC8171.00 and WC8160 then mobilized to Middleton at the end of shift. CHANGE ORDER COST CODE 57010141 | 6 | C203-C209 | Dead Horse Creek | 0 | 44646 |  | 36 | 44646 |  |  |  | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191620220326-1-RCLL.O.A.1210 | Corbiere and Sons Contracting1191620220326-1-RCLL.O.A.1210 |  |  | WF6- Bridge Top Removals |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11916 | 20220326-1-RCL | 53540603 | Reclamation | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-26 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEADHORSE CREEK- Excavator walked to the back of dead horse and removed the tops of the bridges at water crossings WC8140.00, WC8150.01, WC8161.00, WC8171.00 and WC8160 then mobilized to Middleton at the end of shift. CHANGE ORDER COST CODE 57010141 | 6 | C203-C209 | Dead Horse Creek | 0 | 44646 |  | 36 | 44646 |  |  |  | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191620220326-1-RCLL.O.A.1210 | Corbiere and Sons Contracting1191620220326-1-RCLL.O.A.1210 |  |  | WF6- Bridge Top Removals |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11916 | 20220326-1-RCL | 53540603 | Reclamation | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-26 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEADHORSE CREEK- Excavator walked to the back of dead horse and removed the tops of the bridges at water crossings WC8140.00, WC8150.01, WC8161.00, WC8171.00 and WC8160 then mobilized to Middleton at the end of shift. CHANGE ORDER COST CODE 57010141 | 6 | C203-C209 | Dead Horse Creek | 0 | 44646 |  | 36 | 44646 |  |  |  | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191620220326-1-RCLL.O.A.1210 | Corbiere and Sons Contracting1191620220326-1-RCLL.O.A.1210 |  |  | WF6- Bridge Top Removals |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11916 | 20220326-1-RCL | 53540603 | Reclamation | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-03-26 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEADHORSE CREEK- Excavator walked to the back of dead horse and removed the tops of the bridges at water crossings WC8140.00, WC8150.01, WC8161.00, WC8171.00 and WC8160 then mobilized to Middleton at the end of shift. CHANGE ORDER COST CODE 57010141 | 6 | C203-C209 | Dead Horse Creek | 0 | 44646 |  | 36 | 44646 |  |  |  | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191620220326-1-RCLOperator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1191620220326-1-RCLOperator - Principle - After Jan 1011825 |  |  | WF6- Bridge Top Removals |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11916 | 20220326-1-RCL | 53540603 | Reclamation | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-03-26 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | DEADHORSE CREEK- Excavator walked to the back of dead horse and removed the tops of the bridges at water crossings WC8140.00, WC8150.01, WC8161.00, WC8171.00 and WC8160 then mobilized to Middleton at the end of shift. CHANGE ORDER COST CODE 57010141 | 6 | C203-C209 | Dead Horse Creek | 0 | 44646 |  | 36 | 44646 |  |  |  | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191620220326-1-RCLDriver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1191620220326-1-RCLDriver - AZ - After Jan 1011770 |  |  | WF6- Bridge Top Removals |  |  | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2.5 | Dynamic | 103.84 | 0 |  |  | 346.125 | 89.9925 | 782.2425 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLExcavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1191820220327-1-RCLExcavator - 30 ton- After Jan 105692.25 |  |  | WF6- Bridge Top Removals |  |  | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2.5 | HR | 9.16 | 0 |  |  | 30.525 | 7.9365 | 68.9865 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLExcavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1191820220327-1-RCLExcavator Thumb - 30 - 50 ton- After Jan 10561.05 |  |  | WF6- Bridge Top Removals |  |  | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLLight Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1191820220327-1-RCLLight Truck - Pick up- After Jan 101243.75 |  |  | WF6- Bridge Top Removals |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 |  |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLLight Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1191820220327-1-RCLLight Truck - Pick up- After Jan 101243.75 |  |  | WF6- Bridge Top Removals |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3.5 | Dynamic | 91.79 | 0 |  |  | 428.365 | 111.3749 | 968.1049 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLTractor Trailer - 60 Ton- After Jan 107856.73 | Corbiere and Sons Contracting1191820220327-1-RCLTractor Trailer - 60 Ton- After Jan 107856.73 |  |  | WF6- Bridge Top Removals |  |  | 1 | 856.73 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | Foreman | 95 | 3.5 | HR |  |  | 95 | 0 | 332.5 | 86.45 | 751.45 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLForeman7665 | Corbiere and Sons Contracting1191820220327-1-RCLForeman7665 |  |  | WF6- Bridge Top Removals |  |  | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLL.O.A.1210 | Corbiere and Sons Contracting1191820220327-1-RCLL.O.A.1210 |  |  | WF6- Bridge Top Removals |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLL.O.A.1210 | Corbiere and Sons Contracting1191820220327-1-RCLL.O.A.1210 |  |  | WF6- Bridge Top Removals |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLL.O.A.1210 | Corbiere and Sons Contracting1191820220327-1-RCLL.O.A.1210 |  |  | WF6- Bridge Top Removals |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | Operator - Principle - After Jan 10 | 75 | 3.5 | HR |  |  | 75 | 0 | 262.5 | 68.25 | 593.25 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLOperator - Principle - After Jan 107525 | Corbiere and Sons Contracting1191820220327-1-RCLOperator - Principle - After Jan 107525 |  |  | WF6- Bridge Top Removals |  |  | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11918 | 20220327-1-RCL | 53540603 | Reclamation | 0 | Driver - AZ - After Jan 10 | 70 | 3.5 | HR |  |  | 70 | 0 | 245 | 63.7 | 553.7 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | MIDDLETON- Excavator completed removing the top of bridges off at WC8230.01 and unmarked crossing CHANGE ORDER COST CODE 57010141 | 6 | C210-C213 | Middleton | 0 | 44647 |  | 36 | 44647 |  |  | 8230.01 | AN - All season (no gravel cap) | Bridge | Mike Lecocq | 06 | Corbiere and Sons Contracting1191820220327-1-RCLDriver - AZ - After Jan 107490 | Corbiere and Sons Contracting1191820220327-1-RCLDriver - AZ - After Jan 107490 |  |  | WF6- Bridge Top Removals |  |  | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11919 | 20220327-3-RCL | 53540603 | Reclamation | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | LITTLE RED SUCKER- Excavator completed removing the top of bridges off at WC8370.00, WC609, WC8351.00, WC8352.00, WC8350.05, WC8350.04, WC8350.03 and WC8350.02 CHANGE ORDER COST CODE 57010141 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44647 |  | 36 | 44647 |  |  | 8370.00, 609, 8351.00, 8352.00, 8350.05, 8350.04, 8350.03, 8350.02 | AN - All season (no gravel cap) |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1191920220327-3-RCLExcavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1191920220327-3-RCLExcavator - 30 ton- After Jan 105692.25 |  |  | WF6- Bridge Top Removals |  |  | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11919 | 20220327-3-RCL | 53540603 | Reclamation | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | LITTLE RED SUCKER- Excavator completed removing the top of bridges off at WC8370.00, WC609, WC8351.00, WC8352.00, WC8350.05, WC8350.04, WC8350.03 and WC8350.02 CHANGE ORDER COST CODE 57010141 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44647 |  | 36 | 44647 |  |  | 8370.00, 609, 8351.00, 8352.00, 8350.05, 8350.04, 8350.03, 8350.02 | AN - All season (no gravel cap) |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1191920220327-3-RCLExcavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1191920220327-3-RCLExcavator Thumb - 30 - 50 ton- After Jan 10561.05 |  |  | WF6- Bridge Top Removals |  |  | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11919 | 20220327-3-RCL | 53540603 | Reclamation | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | LITTLE RED SUCKER- Excavator completed removing the top of bridges off at WC8370.00, WC609, WC8351.00, WC8352.00, WC8350.05, WC8350.04, WC8350.03 and WC8350.02 CHANGE ORDER COST CODE 57010141 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44647 |  | 36 | 44647 |  |  | 8370.00, 609, 8351.00, 8352.00, 8350.05, 8350.04, 8350.03, 8350.02 | AN - All season (no gravel cap) |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1191920220327-3-RCLLight Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1191920220327-3-RCLLight Truck - Pick up- After Jan 101243.75 |  |  | WF6- Bridge Top Removals |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11919 | 20220327-3-RCL | 53540603 | Reclamation | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | LITTLE RED SUCKER- Excavator completed removing the top of bridges off at WC8370.00, WC609, WC8351.00, WC8352.00, WC8350.05, WC8350.04, WC8350.03 and WC8350.02 CHANGE ORDER COST CODE 57010141 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44647 |  | 36 | 44647 |  |  | 8370.00, 609, 8351.00, 8352.00, 8350.05, 8350.04, 8350.03, 8350.02 | AN - All season (no gravel cap) |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1191920220327-3-RCLL.O.A.1210 | Corbiere and Sons Contracting1191920220327-3-RCLL.O.A.1210 |  |  | WF6- Bridge Top Removals |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 11919 | 20220327-3-RCL | 53540603 | Reclamation | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2022-03-27 |  | Inv#168 | 2021-04-07 |  | 0 | 0 | Nathan Kyme | Water Crossing Removal |  | VC7556-2019-017 | 929 OF |  | CHANGE ORDER COST CODE 57010141 |  | Approved |  |  | LITTLE RED SUCKER- Excavator completed removing the top of bridges off at WC8370.00, WC609, WC8351.00, WC8352.00, WC8350.05, WC8350.04, WC8350.03 and WC8350.02 CHANGE ORDER COST CODE 57010141 | 6 | C248-C256 | Little Red Sucker Creek | 0 | 44647 |  | 36 | 44647 |  |  | 8370.00, 609, 8351.00, 8352.00, 8350.05, 8350.04, 8350.03, 8350.02 | AN - All season (no gravel cap) |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1191920220327-3-RCLOperator - Principle - After Jan 107525 | Corbiere and Sons Contracting1191920220327-3-RCLOperator - Principle - After Jan 107525 |  |  | WF6- Bridge Top Removals |  |  | 1 | 525 |  | #N/A
Timothy Justin Case | 16 | 0 | 8971 | 233 | 53520104 | Clearing | 0 | Truck | 200 | 2 | Day | 0 | 0 |  |  | 400 | 52 | 452 | 2021-03-19 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Co-ordinate crews in A001. Cut and cleaned up A001-A002 around the highway and powerlines. | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8971233Truck2400 | Timothy Justin Case8971233Truck24001048R1 |  |  | WF1-Handfalling |  |  | 1 | 400 |  | #N/A
Timothy Justin Case | 16 | 0 | 8971 | 233 | 53520104 | Clearing | 0 | Faller Supervisor | 1200 | 2 | Day |  |  | 0 | 0 | 2400 | 312 | 2712 | 2021-03-19 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Co-ordinate crews in A001. Cut and cleaned up A001-A002 around the highway and powerlines. | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8971233Faller Supervisor22400 | Timothy Justin Case8971233Faller Supervisor224001048R1 |  |  | WF1-Handfalling |  |  | 1 | 2400 |  | #N/A
Timothy Justin Case | 16 | 0 | 8971 | 233 | 53520104 | Clearing | 0 | L.O.A (Meals only) | 50 | 2 | Day |  |  | 0 | 0 | 100 | 13 | 113 | 2021-03-19 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Co-ordinate crews in A001. Cut and cleaned up A001-A002 around the highway and powerlines. | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8971233L.O.A (Meals only)2100 | Timothy Justin Case8971233L.O.A (Meals only)21001048R1 |  |  | WF1-Handfalling |  |  | 1 | 100 |  | #N/A
Timothy Justin Case | 16 | 0 | 8972 | 234 | 53520104 | Clearing | 0 | Truck | 200 | 2 | Day | 0 | 0 |  |  | 400 | 52 | 452 | 2021-03-20 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Co-ordinate crews in A002. Cut and cleaned up A001-A002 around the highway and powerlines. | 1 | A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8972234Truck2400 | Timothy Justin Case8972234Truck24001048R1 |  |  | WF1-Handfalling |  |  | 1 | 400 |  | #N/A
Timothy Justin Case | 16 | 0 | 8972 | 234 | 53520104 | Clearing | 0 | Faller Supervisor | 1200 | 2 | Day |  |  | 0 | 0 | 2400 | 312 | 2712 | 2021-03-20 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Co-ordinate crews in A002. Cut and cleaned up A001-A002 around the highway and powerlines. | 1 | A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8972234Faller Supervisor22400 | Timothy Justin Case8972234Faller Supervisor224001048R1 |  |  | WF1-Handfalling |  |  | 1 | 2400 |  | #N/A
Timothy Justin Case | 16 | 0 | 8972 | 234 | 53520104 | Clearing | 0 | L.O.A (Meals only) | 50 | 2 | Day |  |  | 0 | 0 | 100 | 13 | 113 | 2021-03-20 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Co-ordinate crews in A002. Cut and cleaned up A001-A002 around the highway and powerlines. | 1 | A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8972234L.O.A (Meals only)2100 | Timothy Justin Case8972234L.O.A (Meals only)21001048R1 |  |  | WF1-Handfalling |  |  | 1 | 100 |  | #N/A
Timothy Justin Case | 16 | 0 | 8973 | 235 | 53520104 | Clearing | 0 | Truck | 200 | 2 | Day | 0 | 0 |  |  | 400 | 52 | 452 | 2021-03-21 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Demobe from job- Day 1 | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8973235Truck2400 | Timothy Justin Case8973235Truck24001048R1 |  |  | WF1-Handfalling |  |  | 1 | 400 |  | #N/A
Timothy Justin Case | 16 | 0 | 8973 | 235 | 53520104 | Clearing | 0 | Faller Supervisor | 1200 | 2 | Day |  |  | 0 | 0 | 2400 | 312 | 2712 | 2021-03-21 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Demobe from job- Day 1 | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8973235Faller Supervisor22400 | Timothy Justin Case8973235Faller Supervisor224001048R1 |  |  | WF1-Handfalling |  |  | 1 | 2400 |  | #N/A
Timothy Justin Case | 16 | 0 | 8973 | 235 | 53520104 | Clearing | 0 | L.O.A. | 200 | 2 | Day |  |  | 0 | 0 | 400 | 52 | 452 | 2021-03-21 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Demobe from job- Day 1 | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8973235L.O.A.2400 | Timothy Justin Case8973235L.O.A.24001048R1 |  |  | WF1-Handfalling |  |  | 1 | 400 |  | #N/A
Timothy Justin Case | 16 | 0 | 8974 | 236R1 | 53520104 | Clearing | 0 | Truck | 200 | 2 | Day | 0 | 0 |  |  | 400 | 52 | 452 | 2021-03-22 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Demobe from job- Day 2 | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8974236R1Truck2400 | Timothy Justin Case8974236R1Truck24001048R1 |  |  | WF1-Handfalling |  |  | 1 | 400 |  | #N/A
Timothy Justin Case | 16 | 0 | 8974 | 236R1 | 53520104 | Clearing | 0 | Faller Supervisor | 1200 | 2 | Day |  |  | 0 | 0 | 2400 | 312 | 2712 | 2021-03-22 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Demobe from job- Day 2 | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8974236R1Faller Supervisor22400 | Timothy Justin Case8974236R1Faller Supervisor224001048R1 |  |  | WF1-Handfalling |  |  | 1 | 2400 |  | #N/A
Timothy Justin Case | 16 | 0 | 8974 | 236R1 | 53520104 | Clearing | 0 | L.O.A. | 200 | 2 | Day |  |  | 0 | 0 | 400 | 52 | 452 | 2021-03-22 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Demobe from job- Day 2 | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8974236R1L.O.A.2400 | Timothy Justin Case8974236R1L.O.A.24001048R1 |  |  | WF1-Handfalling |  |  | 1 | 400 |  | #N/A
Timothy Justin Case | 16 | 0 | 8974 | 236R1 | 53520104 | Clearing | 0 | Unit Rate Fuel | 1 | 1249.37 | Unit |  |  |  |  | 1249.37 | 162.4181 | 1411.7881 | 2021-03-22 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Shane/Adam-Demobe from job- Day 2 | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8974236R1Unit Rate Fuel1249.371249.37 | Timothy Justin Case8974236R1Unit Rate Fuel1249.371249.371048R1 |  |  | WF1-Handfalling |  |  | 1 | 1249.37 |  | #N/A
Timothy Justin Case | 16 | 0 | 8975 | 237R1 | 53520104 | Clearing | 0 | Truck | 200 | 1 | Day | 0 | 0 |  |  | 200 | 26 | 226 | 2021-03-23 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Adam-Demobe from job- Day 3 (Montreal to Fredericton) | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8975237R1Truck1200 | Timothy Justin Case8975237R1Truck12001048R1 |  |  | WF1-Handfalling |  |  | 1 | 200 |  | #N/A
Timothy Justin Case | 16 | 0 | 8975 | 237R1 | 53520104 | Clearing | 0 | Faller Supervisor | 1200 | 1 | Day |  |  | 0 | 0 | 1200 | 156 | 1356 | 2021-03-23 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Adam-Demobe from job- Day 3 (Montreal to Fredericton) | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8975237R1Faller Supervisor11200 | Timothy Justin Case8975237R1Faller Supervisor112001048R1 |  |  | WF1-Handfalling |  |  | 1 | 1200 |  | #N/A
Timothy Justin Case | 16 | 0 | 8975 | 237R1 | 53520104 | Clearing | 0 | L.O.A (Meals only) | 50 | 1 | Day |  |  | 0 | 0 | 50 | 6.5 | 56.5 | 2021-03-23 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Adam-Demobe from job- Day 3 (Montreal to Fredericton) | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8975237R1L.O.A (Meals only)150 | Timothy Justin Case8975237R1L.O.A (Meals only)1501048R1 |  |  | WF1-Handfalling |  |  | 1 | 50 |  | #N/A
Timothy Justin Case | 16 | 0 | 8975 | 237R1 | 53520104 | Clearing | 0 | Unit Rate Fuel | 1 | 258.25 | Unit |  |  |  |  | 258.25 | 33.5725 | 291.8225 | 2021-03-23 | 0 | 1048R1 | 44292 | 150 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2020-033 | 932 OF |  |  |  | Approved |  |  | Adam-Demobe from job- Day 3 (Montreal to Fredericton) | 1 | A001-A002 |  | 0 |  |  | 51 | 44260 | [5 empty] | Betty Moghrabi | 01 | Timothy Justin Case8975237R1Unit Rate Fuel258.25258.25 | Timothy Justin Case8975237R1Unit Rate Fuel258.25258.251048R1 |  |  | WF1-Handfalling |  |  | 1 | 258.25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4787 | KL-20201203-7 | 53510811 | Access | 0 | Small Tools - per crew - Daily | 100 | 1 | Daily |  |  |  |  | 100 | 13 | 113 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Padda Roadlines hauling pit run from 5 km pit on 100 road to stockpile/labourers sanding access to stockpile with pickup and shovels. | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4787KL-20201203-7Small Tools - per crew - Daily1100 | KABI LAKE FOREST PRODUCTS LTD4787KL-20201203-7Small Tools - per crew - Daily1100OEWT-PA12-LEM-R1 | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4207 | KL-20201107-1 | 53510812 | Access | 0 | Small Tools - per crew - Daily | 100 | 1 | Daily |  | 0 |  |  | 100 | 13 | 113 | 2020-11-07 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scrape Mud from exiting vehicles to hwy 17 at entrance to silver sity. Pickup with beacon, flag paddle and radio contact watching traffic | 8 | E025-E036 | Silver City | 0 | 44162 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD4207KL-20201107-1Small Tools - per crew - Daily1100 | KABI LAKE FOREST PRODUCTS LTD4207KL-20201107-1Small Tools - per crew - Daily1100OEWT-PA11-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5931 | KL-20210216-12 | 53511111 | Access | 0 | Small Tools - per crew - Daily | 100 | 1 | Daily |  | 0 |  |  | 100 | 13 | 113 | 2021-02-16 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Lake and Cress float with Legos, access mats and bearing timbers for 12970.00 WC/ Excavator unloaded and storing/labourer cleaning snow off the Dam | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44249 |  | 15 | 44254 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5931KL-20210216-12Small Tools - per crew - Daily1100 | KABI LAKE FOREST PRODUCTS LTD5931KL-20210216-12Small Tools - per crew - Daily1100OEWT-PA14-Lem-R1 | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5616 | KL-20210125-13 | 53511111 | Access | 0 | Small Tools - per crew - Daily | 100 | 1 | Daily |  | 0 |  |  | 100 | 13 | 113 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Snow removal, drilling holes & pumping water for flooding of ice crossing @WC 12100.01 (2 floods). Cress prepping and doing lock block install WC 11333.00. Excavators prepping & doing lock block install, had to rent chipper due to blocks not matching up. CR-101260. | 11 | F119-F134 | Hensen Road | 0 | 44225 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5616KL-20210125-13Small Tools - per crew - Daily1100 | KABI LAKE FOREST PRODUCTS LTD5616KL-20210125-13Small Tools - per crew - Daily1100OEWT-PA14-Lem-R1 | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7428 | KL-20211005-2 | 53510712 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road & hauling concrete anchors on a rig mat for LEG. Excavator levelling ruts, shaping road, assisting pickups & rock truck. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7368 | KL-20210920-4 | 53510712 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Quad used to check on operators @ D024/ D025 and road progress | 7 | D018-D031 | Pic River West | 0 | 44466 |  | 36 | 44466 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7368KL-20210920-4ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7368KL-20210920-4ATV - side by side - Daily1250OEWT-PA21-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7425 | KL-20211004-2 | 53510712 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts, shaping road, pulling pickups & grout truck to D025 due to wet conditions. Excavator working after hours until all crews got out. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7432 | KL-20211006-2 | 53510712 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road and pushing rock trucks hauling gravel to D025 /excavator leveling ruts and shaping road. | 7 | D018-D031 | Pic river | 0 | 44484 |  | 63 | 44484 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 149.3278 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511003 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 128.1701 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511004 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-16 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.76183 | 190.4565 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1ATV - side by side - Daily1250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6610 | KL-20210402-2-R1 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-02 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track out to Km 1 on Hensen East for refueling and back to F132/ Continue reclamation @ F132/ ATV used due to no pickup access. Excavator time reduced from signed ticket for tracking as per Valard direction. Remaining excavator time will be submitted on KL-20210402-2-S1 | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R1ATV - side by side - Daily1250OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6611 | KL-20210402-3 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-02 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Reclamation @ F135 to F136 | 11 | F135-F149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6611KL-20210402-3ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6611KL-20210402-3ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6614 | KL-20210403-3 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F136 to F137/ side by side used due to no pickup access | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-3ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-3ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6615 | KL-20210403-4 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F133 to F132/ ATV used due to no pickup access | 11 | F-119 to F-134 | Hensen Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6615KL-20210403-4ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6615KL-20210403-4ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6619 | KL-20210404-4 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish reclamation from F133/ F131 and track out to Km 17 on Hensen Road/ ATV used due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 15 | 44303 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD6619KL-20210404-4ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6619KL-20210404-4ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6661 | KL-20210406-5-R1 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F138 to F141. Two hours of equipment/live out and pick up time removed from each excavator/operator from approved field ticket as per Valard direction. Those charges now listed on LEM KL-20210406-5-S1. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | 44328 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R1ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6704 | KL-20210412-6 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F151 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44308 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6704KL-20210412-6ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6704KL-20210412-6ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6757 | KL-20210414-6 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue reclamation @ F151 and F150. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44309 |  | 56 | 44312 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6757KL-20210414-6ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6757KL-20210414-6ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6786 | KL-20210407-8 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F139 to F143 (third revision.) Quad was used for operator travel to excavator, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6786KL-20210407-8ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6786KL-20210407-8ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6788 | KL-20210408-6 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on Reclamation @F139 to F140. Quad used for operator travel, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-6ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-6ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6790 | KL-20210409-8 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on reclamation @f139 to F140. (Third Revision). Quad used for operator travel, no tracking time for equipment. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6790KL-20210409-8ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6790KL-20210409-8ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6793 | KL-20210412-8 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on Reclamation @ F141/F142 (fourth revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6793KL-20210412-8ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6793KL-20210412-8ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6795 | KL-20210413-6 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 and Cat 330 Excavators workimg on Reclamation @F141 and F143 (4th Revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-6ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-6ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6797 | KL-20210414-9 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 and Cat 336 excavators working on Reclamation @ F142 and F143 (3rd revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-9ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-9ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6840 | KL-20210331-5 | 53541101 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track to F133 from Km 17 on Hensen and start reclaimation @ F133/F132. ATV used for crew due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44326 |  | 57 | 44327 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-5ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-5ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6607 | KL-20210401-6 | 53541104 | Reclamation | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-01 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Gravel Removal (Access) |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclaimation @ F133/ F132/ ATV used due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 57 | 44305 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6607KL-20210401-6ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD6607KL-20210401-6ATV - side by side - Daily1250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7428 | KL-20211005-2 | 53510712 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road & hauling concrete anchors on a rig mat for LEG. Excavator levelling ruts, shaping road, assisting pickups & rock truck. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7368 | KL-20210920-4 | 53510712 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Quad used to check on operators @ D024/ D025 and road progress | 7 | D018-D031 | Pic River West | 0 | 44466 |  | 36 | 44466 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7368KL-20210920-4Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7368KL-20210920-4Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7425 | KL-20211004-2 | 53510712 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts, shaping road, pulling pickups & grout truck to D025 due to wet conditions. Excavator working after hours until all crews got out. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7432 | KL-20211006-2 | 53510712 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road and pushing rock trucks hauling gravel to D025 /excavator leveling ruts and shaping road. | 7 | D018-D031 | Pic river | 0 | 44484 |  | 63 | 44484 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 17.9193 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 15 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511003 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 15.3804 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511004 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-16 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.76183 | 22.8548 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511004 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-15 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 0.5 | 0.5 | 15 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | [5 empty] | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6840 | KL-20210331-5 | 53541101 | Reclamation | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track to F133 from Km 17 on Hensen and start reclaimation @ F133/F132. ATV used for crew due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44326 |  | 57 | 44327 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-5Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-5Single Axle Trailer - without pickup - Daily130OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 30 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4018 | KL-20201028-4 | 53510812 | Access | 0 | Tandum Trailer - without pickup - Daily | 75 | 1 | Daily |  | 0 |  |  | 75 | 9.75 | 84.75 | 2020-10-28 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to the Paint Lake Road 1-B and drop off 4 rolls of geotextile | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 08 | KABI LAKE FOREST PRODUCTS LTD4018KL-20201028-4Tandum Trailer - without pickup - Daily175 | KABI LAKE FOREST PRODUCTS LTD4018KL-20201028-4Tandum Trailer - without pickup - Daily175OEWT-PA11-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | Tandum Trailer - without pickup - Daily | 75 | 1 | Daily |  | 0 |  |  | 75 | 9.75 | 84.75 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1Tandum Trailer - without pickup - Daily175 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1Tandum Trailer - without pickup - Daily175OEWT-PA22-Lem | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4143 | KL-20201103-13 | 53511103 | Access | 0 | Tandum Trailer - without pickup - Daily | 75 | 1 | Daily |  | 0 |  |  | 75 | 9.75 | 84.75 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to Hensen Road and pick up 8 rolls of Geo and take back to White River Yard | 11 | F119-F134 | Hensen Road | 0 | 44153 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD4143KL-20201103-13Tandum Trailer - without pickup - Daily175 | KABI LAKE FOREST PRODUCTS LTD4143KL-20201103-13Tandum Trailer - without pickup - Daily175OEWT-PA11-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5846 | KL-20210210-8 | 53511111 | Access | 0 | Culvert Steamer·without pickup or labour - Daily | 200 | 1 | Daily |  | 0 |  |  | 200 | 26 | 226 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go to Hensen Rd and steam a culvert @ km 3.5. Cover corduroy in shoefly past F73. Clear snow from road from 0 to 15Km on Hensen West and from Hwy17 to 17Km. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44250 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-8Culvert Steamer·without pickup or labour - Daily1200 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-8Culvert Steamer·without pickup or labour - Daily1200OEWT-PA14-Lem-R1 | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | Tri-Axle Gravel Dump Truck | 122 | 16 | HR | 92 | 0 |  |  | 1952 | 253.76 | 2205.76 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Tri-Axle Gravel Dump Truck161952 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Tri-Axle Gravel Dump Truck161952OEWT-PA3-LEM | [5 empty] | 1 | 1952 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3300 | KL-20200928-23 | 53511104 | Access | 0 | Tri-Axle Gravel Dump Truck | 122 | 5 | HR | 92 | 0 |  |  | 610 | 79.3 | 689.3 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23Tri-Axle Gravel Dump Truck5610 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23Tri-Axle Gravel Dump Truck5610OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 610 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3376 | KL-20201001-22 | 53511104 | Access | 0 | Tri-Axle Gravel Dump Truck | 122 | 21.5 | HR | 92 | 0 |  |  | 2623 | 340.99 | 2963.99 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Triaxles hauling Pit Run from Provost pit #5 , Dozer spreading and widening areas.Grade Hensen road for gravel Haul - SSF-14029.Haul Pit Run from Provost Pit #5 to AE1 on Hensen Road - JJR-70095. Hauled Gravel to Hensen Road from Provost Pit #5 - BMC-30121 | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22Tri-Axle Gravel Dump Truck21.52623 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22Tri-Axle Gravel Dump Truck21.52623OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 2623 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511104 | Access | 0 | Tri-Axle Gravel Dump Truck | 122 | 4.5 | HR | 92 | 0 |  |  | 549 | 71.37 | 620.37 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24Tri-Axle Gravel Dump Truck4.5549 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24Tri-Axle Gravel Dump Truck4.5549OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 549 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3831 | KL-20201018-15 | 53511104 | Access | 0 | Tri-Axle Gravel Dump Truck | 122 | 4.5 | HR | 92 | 0 |  |  | 549 | 71.37 | 620.37 | 2020-10-18 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauled 2 load pit run from Provost pit 5 to Km 3 on hensen road Culverts. Cress install cross drain culverts. 330 excavator installed 3 200mm culverts, Km 6.5, 4.5, 2 - A lot of travelling with Machine -travelled Km 10 to 2 - CR-10821 | 11 | F-119 to F-134 | Hensen Road | 0 | 44130 |  | 55 | 44132 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3831KL-20201018-15Tri-Axle Gravel Dump Truck4.5549 | KABI LAKE FOREST PRODUCTS LTD3831KL-20201018-15Tri-Axle Gravel Dump Truck4.5549OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 549 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3415 | KL-20200930-23 | 53511112 | Access | 0 | Tri-Axle Gravel Dump Truck | 122 | 12 | HR | 92 | 0 |  |  | 1464 | 190.32 | 1654.32 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pitrun from Provost pit #5 to F204 access | 11 | F-203 to F-211 | High Falls Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-23Tri-Axle Gravel Dump Truck121464 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-23Tri-Axle Gravel Dump Truck121464OEWT-PA10-LEM | [5 empty] | 1 | 1464 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4439 | KL-20201118-11 | 53510911 | Access | 0 | Tandem Gravel Dump Truck | 115 | 6 | HR | 87 | 0 |  |  | 690 | 89.7 | 779.7 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11Tandem Gravel Dump Truck6690 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11Tandem Gravel Dump Truck6690OEWT-PA11-LEM | [5 empty] | 1 | 690 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3273 | KL-20200927-17 | 53511104 | Access | 0 | Tandem Gravel Dump Truck | 115 | 12 | HR | 87 | 0 |  |  | 1380 | 179.4 | 1559.4 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit runfrom Provost pit #5/Dozer spreading | 11 | F-119 to F-134 | Hensen Road | 0 | 43900 |  | 48 | 43871 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17Tandem Gravel Dump Truck121380 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17Tandem Gravel Dump Truck121380OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1380 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3300 | KL-20200928-23 | 53511104 | Access | 0 | Tandem Gravel Dump Truck | 115 | 5 | HR | 87 | 0 |  |  | 575 | 74.75 | 649.75 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23Tandem Gravel Dump Truck5575 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23Tandem Gravel Dump Truck5575OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511104 | Access | 0 | Tandem Gravel Dump Truck | 115 | 7.5 | HR | 87 | 0 |  |  | 862.5 | 112.125 | 974.625 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24Tandem Gravel Dump Truck7.5862.5 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24Tandem Gravel Dump Truck7.5862.5OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 862.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3415 | KL-20200930-23 | 53511112 | Access | 0 | Tandem Gravel Dump Truck | 115 | 11.5 | HR | 87 | 0 |  |  | 1322.5 | 171.925 | 1494.425 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pitrun from Provost pit #5 to F204 access | 11 | F-203 to F-211 | High Falls Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-23Tandem Gravel Dump Truck11.51322.5 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-23Tandem Gravel Dump Truck11.51322.5OEWT-PA10-LEM | [5 empty] | 1 | 1322.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4654 | KL-20201126-8 | 53510811 | Access | 0 | Sander truck | 115 | 4 | HR | 87 | 0 |  |  | 460 | 59.8 | 519.8 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load sand from 6km pit on 600 road and sand Access from Hwy to E073 for concrete haul as per discussion with Valard | 8 | E068-E076 | North Crockers Lake | 0 | 44178 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-8Sander truck4460 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-8Sander truck4460OEWT-PA12-LEM-R1 | [5 empty] | 1 | 460 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4902 | KL-20201205-5 | 53510811 | Access | 0 | Sander truck | 115 | 4 | HR | 87 | 0 |  |  | 460 | 59.8 | 519.8 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Silver City AU1 Access to E025 as per Valard | 8 | E025-E036 | Silver City | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-5Sander truck4460 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-5Sander truck4460OEWT-PA12-LEM-R1 | [5 empty] | 1 | 460 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5000 | KL-20201214-3 | 53510811 | Access | 0 | Sander truck | 115 | 3 | HR | 87 | 0 |  |  | 345 | 44.85 | 389.85 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding and Grading Access to E073 for concrete haul as per Valard | 8 | E004-E016 | White Lake East | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3Sander truck3345 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3Sander truck3345OEWT-PA12-LEM-R1 | [5 empty] | 1 | 345 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | Sander truck | 115 | 2 | HR | 87 | 0 |  |  | 230 | 29.9 | 259.9 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Sander truck2230 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Sander truck2230OEWT-PA3-LEM | [5 empty] | 1 | 230 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3988 | KL-20201026-13 | 53510911 | Access | 0 | Sander truck | 115 | 12 | HR | 87 | 0 |  |  | 1380 | 179.4 | 1559.4 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sander truck and sorting material , sanding 600 road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44161 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3988KL-20201026-13Sander truck121380 | KABI LAKE FOREST PRODUCTS LTD3988KL-20201026-13Sander truck121380OEWT-PA11-LEM | [5 empty] | 1 | 1380 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4047 | KL-20201029-13 | 53510911 | Access | 0 | Sander truck | 115 | 6 | HR | 87 | 0 |  |  | 690 | 89.7 | 779.7 | 2020-10-29 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding the 600 rd km 1-km 20 and 700 Rd to km 13. Rock trucks hauling gravel from stockpile. AM-60161. Rock trucks hauling gravel from stockpile on 600 road to Kabi's excavator. AM-60161 | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4047KL-20201029-13Sander truck6690 | KABI LAKE FOREST PRODUCTS LTD4047KL-20201029-13Sander truck6690OEWT-PA11-LEM | [5 empty] | 1 | 690 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4081 | KL-20201031-7 | 53510911 | Access | 0 | Sander truck | 115 | 10.5 | HR | 87 | 0 |  |  | 1207.5 | 156.975 | 1364.475 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sand truck an sorting material, sanding 600 road. | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4081KL-20201031-7Sander truck10.51207.5 | KABI LAKE FOREST PRODUCTS LTD4081KL-20201031-7Sander truck10.51207.5OEWT-PA11-LEM | [5 empty] | 1 | 1207.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4113 | KL-20201102-9 | 53510911 | Access | 0 | Sander truck | 115 | 17 | HR | 87 | 0 |  |  | 1955 | 254.15 | 2209.15 | 2020-11-02 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sander truck and sorting materials at km 20 an km 6 pits on the 600 road and 100 road | 9 | E091-E102 | 600 Rd | 0 | 44153 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-9Sander truck171955 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-9Sander truck171955OEWT-PA11-LEM | [5 empty] | 1 | 1955 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4135 | KL-20201103-5 | 53510911 | Access | 0 | Sander truck | 115 | 15 | HR | 87 | 0 |  |  | 1725 | 224.25 | 1949.25 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Sand Truck and sorting material at 20km pit and 6km pit on 600 road, sanding 600, 700 and 100 roads | 9 | E-091 to E-102 | 600 Rd | 0 | 44153 |  | 50 | 44159 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5Sander truck151725 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5Sander truck151725OEWT-PA11-LEM | [5 empty] | 1 | 1725 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4417 | KL-20201116-16 | 53510911 | Access | 0 | Sander truck | 115 | 15 | HR | 87 | 0 |  |  | 1725 | 224.25 | 1949.25 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-16Sander truck151725 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-16Sander truck151725OEWT-PA11-LEM | [5 empty] | 1 | 1725 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4430 | KL-20201117-9 | 53510911 | Access | 0 | Sander truck | 115 | 16 | HR | 87 | 0 |  |  | 1840 | 239.2 | 2079.2 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 Rd and 100 Rd to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-9Sander truck161840 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-9Sander truck161840OEWT-PA11-LEM | [5 empty] | 1 | 1840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4439 | KL-20201118-11 | 53510911 | Access | 0 | Sander truck | 115 | 12 | HR | 87 | 0 |  |  | 1380 | 179.4 | 1559.4 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11Sander truck121380 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11Sander truck121380OEWT-PA11-LEM | [5 empty] | 1 | 1380 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4462 | KL-20201119-8 | 53510911 | Access | 0 | Sander truck | 115 | 21 | HR | 87 | 0 |  |  | 2415 | 313.95 | 2728.95 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-8Sander truck212415 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-8Sander truck212415OEWT-PA11-LEM | [5 empty] | 1 | 2415 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4513 | KL-20201121-14 | 53510911 | Access | 0 | Sander truck | 115 | 6 | HR | 87 | 0 |  |  | 690 | 89.7 | 779.7 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 rd and 100 rd to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4513KL-20201121-14Sander truck6690 | KABI LAKE FOREST PRODUCTS LTD4513KL-20201121-14Sander truck6690OEWT-PA11-LEM | [5 empty] | 1 | 690 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4574 | KL-20201123-12 | 53510911 | Access | 0 | Sander truck | 115 | 17 | HR | 87 | 0 |  |  | 1955 | 254.15 | 2209.15 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 roads and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4574KL-20201123-12Sander truck171955 | KABI LAKE FOREST PRODUCTS LTD4574KL-20201123-12Sander truck171955OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1955 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4609 | KL-20201124-12 | 53510911 | Access | 0 | Sander truck | 115 | 14 | HR | 87 | 0 |  |  | 1610 | 209.3 | 1819.3 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road, 700 road and 100 road to 5km pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4609KL-20201124-12Sander truck141610 | KABI LAKE FOREST PRODUCTS LTD4609KL-20201124-12Sander truck141610OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1610 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4636 | KL-20201125-13 | 53510911 | Access | 0 | Sander truck | 115 | 11 | HR | 87 | 0 |  |  | 1265 | 164.45 | 1429.45 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, and 100 rd to km5 pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4636KL-20201125-13Sander truck111265 | KABI LAKE FOREST PRODUCTS LTD4636KL-20201125-13Sander truck111265OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1265 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4661 | KL-20201126-14 | 53510911 | Access | 0 | Sander truck | 115 | 18 | HR | 87 | 0 |  |  | 2070 | 269.1 | 2339.1 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 road to km5 pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4661KL-20201126-14Sander truck182070 | KABI LAKE FOREST PRODUCTS LTD4661KL-20201126-14Sander truck182070OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2070 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4685 | KL-20201127-11 | 53510911 | Access | 0 | Sander truck | 115 | 22 | HR | 87 | 0 |  |  | 2530 | 328.9 | 2858.9 | 2020-11-27 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44180 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4685KL-20201127-11Sander truck222530 | KABI LAKE FOREST PRODUCTS LTD4685KL-20201127-11Sander truck222530OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2530 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4699 | KL-20201128-7 | 53510911 | Access | 0 | Sander truck | 115 | 12 | HR | 87 | 0 |  |  | 1380 | 179.4 | 1559.4 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4699KL-20201128-7Sander truck121380 | KABI LAKE FOREST PRODUCTS LTD4699KL-20201128-7Sander truck121380OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1380 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4709 | KL-20201129-10 | 53510911 | Access | 0 | Sander truck | 115 | 12 | HR | 87 | 0 |  |  | 1380 | 179.4 | 1559.4 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600Rd, 700, 100 roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4709KL-20201129-10Sander truck121380 | KABI LAKE FOREST PRODUCTS LTD4709KL-20201129-10Sander truck121380OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1380 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4724 | KL-20201130-7 | 53510911 | Access | 0 | Sander truck | 115 | 12 | HR | 87 | 0 |  |  | 1380 | 179.4 | 1559.4 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4724KL-20201130-7Sander truck121380 | KABI LAKE FOREST PRODUCTS LTD4724KL-20201130-7Sander truck121380OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1380 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4724 | KL-20201130-7 | 53510911 | Access | 0 | Sander truck | 115 | 4 | HR | 87 | 0 |  |  | 460 | 59.8 | 519.8 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4724KL-20201130-7Sander truck4460 | KABI LAKE FOREST PRODUCTS LTD4724KL-20201130-7Sander truck4460OEWT-PA12-LEM-R1 | [5 empty] | 1 | 460 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4742 | KL-20201201-11 | 53510911 | Access | 0 | Sander truck | 115 | 5 | HR | 87 | 0 |  |  | 575 | 74.75 | 649.75 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Rd | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4742KL-20201201-11Sander truck5575 | KABI LAKE FOREST PRODUCTS LTD4742KL-20201201-11Sander truck5575OEWT-PA12-LEM-R1 | [5 empty] | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4775 | KL-20201202-18 | 53510911 | Access | 0 | Sander truck | 115 | 9 | HR | 87 | 0 |  |  | 1035 | 134.55 | 1169.55 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Rds | 9 |  | 600 Road | 0 | 44193 |  | 53 | 44205 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-18Sander truck91035 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-18Sander truck91035OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4775 | KL-20201202-18 | 53510911 | Access | 0 | Sander truck | 115 | 5 | HR | 87 | 0 |  |  | 575 | 74.75 | 649.75 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Rds | 9 |  | 600 Road | 0 | 44193 |  | 53 | 44205 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-18Sander truck5575 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-18Sander truck5575OEWT-PA12-LEM-R1 | [5 empty] | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4810 | KL-20201209-12 | 53510911 | Access | 0 | Sander truck | 115 | 12 | HR | 87 | 0 |  |  | 1380 | 179.4 | 1559.4 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4810KL-20201209-12Sander truck121380 | KABI LAKE FOREST PRODUCTS LTD4810KL-20201209-12Sander truck121380OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1380 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4889 | KL-20201204-12 | 53510911 | Access | 0 | Sander truck | 115 | 4 | HR | 87 | 0 |  |  | 460 | 59.8 | 519.8 | 2020-12-04 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 100 Rd | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4889KL-20201204-12Sander truck4460 | KABI LAKE FOREST PRODUCTS LTD4889KL-20201204-12Sander truck4460OEWT-PA12-LEM-R1 | [5 empty] | 1 | 460 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4906 | KL-20201205-9 | 53510911 | Access | 0 | Sander truck | 115 | 8 | HR | 87 | 0 |  |  | 920 | 119.6 | 1039.6 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-9Sander truck8920 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-9Sander truck8920OEWT-PA12-LEM-R1 | [5 empty] | 1 | 920 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4906 | KL-20201205-9 | 53510911 | Access | 0 | Sander truck | 115 | 7 | HR | 87 | 0 |  |  | 805 | 104.65 | 909.65 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-9Sander truck7805 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-9Sander truck7805OEWT-PA12-LEM-R1 | [5 empty] | 1 | 805 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4920 | KL-20201206-7 | 53510911 | Access | 0 | Sander truck | 115 | 2 | HR | 87 | 0 |  |  | 230 | 29.9 | 259.9 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4920KL-20201206-7Sander truck2230 | KABI LAKE FOREST PRODUCTS LTD4920KL-20201206-7Sander truck2230OEWT-PA12-LEM-R1 | [5 empty] | 1 | 230 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4936 | KL-20201207-11 | 53510911 | Access | 0 | Sander truck | 115 | 11 | HR | 87 | 0 |  |  | 1265 | 164.45 | 1429.45 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4936KL-20201207-11Sander truck111265 | KABI LAKE FOREST PRODUCTS LTD4936KL-20201207-11Sander truck111265OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1265 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4950 | KL-20201208-8 | 53510911 | Access | 0 | Sander truck | 115 | 12 | HR | 87 | 0 |  |  | 1380 | 179.4 | 1559.4 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 road | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4950KL-20201208-8Sander truck121380 | KABI LAKE FOREST PRODUCTS LTD4950KL-20201208-8Sander truck121380OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1380 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4970 | KL-20201210-9 | 53510911 | Access | 0 | Sander truck | 115 | 4 | HR | 87 | 0 |  |  | 460 | 59.8 | 519.8 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600/700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4970KL-20201210-9Sander truck4460 | KABI LAKE FOREST PRODUCTS LTD4970KL-20201210-9Sander truck4460OEWT-PA12-LEM-R1 | [5 empty] | 1 | 460 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5004 | KL-20201214-7 | 53510911 | Access | 0 | Sander truck | 115 | 8 | HR | 87 | 0 |  |  | 920 | 119.6 | 1039.6 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5004KL-20201214-7Sander truck8920 | KABI LAKE FOREST PRODUCTS LTD5004KL-20201214-7Sander truck8920OEWT-PA12-LEM-R1 | [5 empty] | 1 | 920 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5021 | KL-20201215-9 | 53510911 | Access | 0 | Sander truck | 115 | 11 | HR | 87 | 0 |  |  | 1265 | 164.45 | 1429.45 | 2020-12-15 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44198 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5021KL-20201215-9Sander truck111265 | KABI LAKE FOREST PRODUCTS LTD5021KL-20201215-9Sander truck111265OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1265 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5044 | KL-20201218-5 | 53510911 | Access | 0 | Sander truck | 115 | 11 | HR | 87 | 0 |  |  | 1265 | 164.45 | 1429.45 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5044KL-20201218-5Sander truck111265 | KABI LAKE FOREST PRODUCTS LTD5044KL-20201218-5Sander truck111265OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1265 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5098 | KL-20201217-6 | 53510911 | Access | 0 | Sander truck | 115 | 6 | HR | 87 | 0 |  |  | 690 | 89.7 | 779.7 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5098KL-20201217-6Sander truck6690 | KABI LAKE FOREST PRODUCTS LTD5098KL-20201217-6Sander truck6690OEWT-PA12-LEM-R1 | [5 empty] | 1 | 690 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5413 | KL-20210117-1 | 53510911 | Access | 0 | Sander truck | 115 | 4 | HR | 87 |  |  |  | 460 | 59.8 | 519.8 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding hills on 600 Road between km 52 and Km 22, float truck was stuck on 47km hill | 9 | E091-E102 | 600 Road | 0 | 44216 |  | 53 | 44229 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1Sander truck4460 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1Sander truck4460OEWT-PA13-LEM | [5 empty] | 1 | 460 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4073 | KL-20201030-15 | 53510912 | Access | 0 | Sander truck | 115 | 11 | HR | 87 | 0 |  |  | 1265 | 164.45 | 1429.45 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding the 600 road and 700 road to Km 13 ( Revised Hours) | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD4073KL-20201030-15Sander truck111265 | KABI LAKE FOREST PRODUCTS LTD4073KL-20201030-15Sander truck111265OEWT-PA11-LEM | [5 empty] | 1 | 1265 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5746 | KL-20210203-3 | 53511011 | Access | 0 | Sander truck | 115 | 8 | HR | 87 | 0 |  |  | 920 | 119.6 | 1039.6 | 2021-02-03 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track excavator out and in, sand Paint Lake Road 2. Lay corduroy and cap road near WC 11159.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44243 |  | 50 | 44246 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5746KL-20210203-3Sander truck8920 | KABI LAKE FOREST PRODUCTS LTD5746KL-20210203-3Sander truck8920OEWT-PA14-Lem-R1 | [5 empty] | 1 | 920 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | Sander truck | 115 | 8 | HR | 87 | 0 |  |  | 920 | 119.6 | 1039.6 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1Sander truck8920 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1Sander truck8920OEWT-PA24-LEM | [5 empty] | 1 | 920 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4084 | KL-20201031-12 | 53511111 | Access | 0 | Sander truck | 115 | 11.5 | HR | 87 | 0 |  |  | 1322.5 | 171.925 | 1494.425 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sand Hills and corners on Hensen Road for float truck hauling in a buncher/Sanding hauled from provost pit in Wawa | 11 | F203-F211 | Hensen Rd | 0 | 44152 |  | 48 | 44154 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4084KL-20201031-12Sander truck11.51322.5 | KABI LAKE FOREST PRODUCTS LTD4084KL-20201031-12Sander truck11.51322.5OEWT-PA11-LEM | [5 empty] | 1 | 1322.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4992 | KL-20201211-12 | 53511111 | Access | 0 | Sander truck | 115 | 11.5 | HR | 87 | 0 |  |  | 1322.5 | 171.925 | 1494.425 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load partial load @6km pit on 600 road for sanding of hill laydown 1/ load sand from F119 and sand road for float access as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-12Sander truck11.51322.5 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-12Sander truck11.51322.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1322.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5160 | KL-20201228-11 | 53511111 | Access | 0 | Sander truck | 115 | 10 | HR | 87 | 0 |  |  | 1150 | 149.5 | 1299.5 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Hills & Corners on Hensen Rd from Hwy to Km 17 for 60' bridge delivery. Dozer and grader clearing different sections of Hensen Rd. | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44214 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-11Sander truck101150 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-11Sander truck101150OEWT-PA13-LEM | [5 empty] | 1 | 1150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5207 | KL-20210103-5 | 53511111 | Access | 0 | Sander truck | 115 | 10 | HR | 87 | 0 |  |  | 1150 | 149.5 | 1299.5 | 2021-01-03 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of sand from White River town pit/ sanding hills and corners on hensen road from hwy to 17km with existing material as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5Sander truck101150 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5Sander truck101150OEWT-PA13-LEM | [5 empty] | 1 | 1150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5283 | KL-20210109-6 | 53511111 | Access | 0 | Sander truck | 115 | 10 | HR | 87 | 0 |  |  | 1150 | 149.5 | 1299.5 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Take 1 load of screened sand from town pit, and finish sanding Hensen Rd to km 17. Floats with existing sand as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6Sander truck101150 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6Sander truck101150OEWT-PA13-LEM | [5 empty] | 1 | 1150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5363 | KL-20210114-9 | 53511111 | Access | 0 | Sander truck | 115 | 10 | HR | 87 | 0 |  |  | 1150 | 149.5 | 1299.5 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load screened sand from town pit and finished sanding Hensen Road to 17km with existing sand as per Valard/ Excavator cleaning up @ F119 for Sand | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9Sander truck101150 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9Sander truck101150OEWT-PA13-LEM | [5 empty] | 1 | 1150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5700 | KL-20210201-8 | 53511111 | Access | 0 | Sander truck | 115 | 10 | HR | 87 | 0 |  |  | 1150 | 149.5 | 1299.5 | 2021-02-01 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drive from White River/Load Screened sand from Provost Pit #5/Sand hills and corners to 17km on hensen road/drive back to White River | 11 | F119-F134 | Hensen Road | 0 | 44235 |  | 53 | 44241 | [5 empty] | Clint Maerz | 11 | KABI LAKE FOREST PRODUCTS LTD5700KL-20210201-8Sander truck101150 | KABI LAKE FOREST PRODUCTS LTD5700KL-20210201-8Sander truck101150OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5838 | KL-20210209-15 | 53511111 | Access | 0 | Sander truck | 115 | 11 | HR | 87 | 0 |  |  | 1265 | 164.45 | 1429.45 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drive from White River/load 5 loads of screened sand from Provost Pit 5/Sand hills & corners to km 17 then drive back to White River. | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44250 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5838KL-20210209-15Sander truck111265 | KABI LAKE FOREST PRODUCTS LTD5838KL-20210209-15Sander truck111265OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1265 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5874 | KL-20210212-5 | 53511111 | Access | 0 | Sander truck | 115 | 11 | HR | 87 | 0 |  |  | 1265 | 164.45 | 1429.45 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load 4 loads screen sand from Provost pit #5/ sand hills and corners to 17km on Hensen Road. Grader work form Hwy 17 to 17Km, loader open road to F110 to F112. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44254 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-5Sander truck111265 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-5Sander truck111265OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1265 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6048 | KL-20210225-16 | 53511111 | Access | 0 | Sander truck | 115 | 10 | HR | 87 | 0 |  |  | 1150 | 149.5 | 1299.5 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of screeded sand from Town Pit/Haul 2 loads of screened sand from MacIntyre Pit/Sand hills & corners to km 17 on Hensen, drive back to White River | 11 | F119-F134 | Hensen Road | 0 | 44256 |  | 56 | 44262 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6048KL-20210225-16Sander truck101150 | KABI LAKE FOREST PRODUCTS LTD6048KL-20210225-16Sander truck101150OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7661 | KL-20211209-4 | 53511111 | Access | 0 | Sander truck | 115 | 7 | HR | 87 | 0 |  |  | 805 | 104.65 | 909.65 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Road from hwy 17 to 17km. Sand truck sanding hills & corners with existing sand from 17km. Excavator used for loading sand. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4Sander truck7805 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4Sander truck7805OEWT-PA24-LEM | [5 empty] | 1 | 805 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1352 | KL-20200322-1 | 53510711 | Access | 0 | Float Truck - 50 ton | 177 | 3 | HR | 133 | 0 |  |  | 531 | 69.03 | 600.03 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW SNOW IN ACCESS ROADS | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43915 |  | 46 | 43919 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1352KL-20200322-1Float Truck - 50 ton3531 | KABI LAKE FOREST PRODUCTS LTD1352KL-20200322-1Float Truck - 50 ton3531OEWT-PA3-LEM | [5 empty] | 1 | 531 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1445 | KL-20200402-6 | 53510711 | Access | 0 | Float Truck - 50 ton | 177 | 4 | HR | 133 | 0 |  |  | 708 | 92.04 | 800.04 | 2020-04-02 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Remove and demob pusher for haul trucks on log haul | 7 | D-032 to D-055 | Black River | 0 | 43930 |  | 43 | 43933 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1445KL-20200402-6Float Truck - 50 ton4708 | KABI LAKE FOREST PRODUCTS LTD1445KL-20200402-6Float Truck - 50 ton4708OEWT PA4-LEM-R1 | [5 empty] | 1 | 708 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7918 | KL-20220223-3 | 53510711 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T Dozer from Denis Lake East to White Lake West | 7 | D142 - E002 | White Lake West | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7918KL-20220223-3Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7918KL-20220223-3Float Truck - 60 ton3564OEWT-PA26-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7903 | KL-20220219-4 | 53510811 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T Dozer from White Lake East to Denis Lake Road West | 8 | E042 - E058 | Denis Lake W | 0 | 44617 |  | 61 | 44617 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7903KL-20220219-4Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7903KL-20220219-4Float Truck - 60 ton3564OEWT-PA26-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7915 | KL-20220222-3 | 53510811 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T Dozer from Denis Lake West to Hwy entrance @ White Lake East | 8 | E004-E010 | White Lake East | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 08 | KABI LAKE FOREST PRODUCTS LTD7915KL-20220222-3Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7915KL-20220222-3Float Truck - 60 ton3564OEWT-PA26-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7942 | KL-20220227-5 | 53510811 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Cat D6T Dozer From Kabi Yard To Denis Lake Road West | 8 | E042 - E058 | Denis Lake W | 0 | 44628 | [9 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7942KL-20220227-5Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7942KL-20220227-5Float Truck - 60 ton3564 | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7947 | KL-20220228-4 | 53510811 | Access | 0 | Float Truck - 60 ton | 188 | 2.5 | HR | 141 | 0 |  |  | 470 | 61.1 | 531.1 | 2022-02-28 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Cat D6T Dozer From Denis Lake Road West to Kabi Yard. | 8 | E042 - E058 | Denis Lake W | 0 | 44628 | [9 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7947KL-20220228-4Float Truck - 60 ton2.5470 | KABI LAKE FOREST PRODUCTS LTD7947KL-20220228-4Float Truck - 60 ton2.5470 | [5 empty] | 1 | 470 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4447 | KL-20201118-8 | 53510812 | Access | 0 | Float Truck - 60 ton | 188 | 2 | HR | 141 | 0 |  |  | 376 | 48.88 | 424.88 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float had dozer loaded and Valard needed the dozer to stay/support for foundations as per email. | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 14 | 44177 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD4447KL-20201118-8Float Truck - 60 ton2376 | KABI LAKE FOREST PRODUCTS LTD4447KL-20201118-8Float Truck - 60 ton2376OEWT-PA11-LEM | [5 empty] | 1 | 376 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3904 | KL-20201025-8 | 53510911 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2020-10-25 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Mob Cat 320D Excavator to 20km pit for loading winter maintenance Sand | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 50 | 44134 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3904KL-20201025-8Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD3904KL-20201025-8Float Truck - 60 ton3564OEWT-PA10-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7937 | KL-20220226-3 | 53510911 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2022-02-26 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Dozer from Km 20 on 600 Road to Kabi Yard | 9 | E092-F009 | 600 Road | 0 | 44628 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7937KL-20220226-3Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7937KL-20220226-3Float Truck - 60 ton3564 | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7965 | KL-20220303-4 | 53510911 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2022-03-03 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Cat 962M Loader From 7 Km On Anjigami Road To Kabi Yard For Snow Removal To E193 On 600 Road | 9 | E092-F009 | 600 Road | 0 | 44630 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7965KL-20220303-4Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7965KL-20220303-4Float Truck - 60 ton4.5846 | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1623 | KL-20200531-4 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 10 | HR | 141 | 0 |  |  | 1880 | 244.4 | 2124.4 | 2020-05-31 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unclogg cross drain culverts @13.5, 30.5, 34.2, and 39.5 kms | 9 | E091-E102 | 600 Road | 0 | 43985 |  | 42 | 43986 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-4Float Truck - 60 ton101880 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-4Float Truck - 60 ton101880OEWT-PA6-LEM | [5 empty] | 1 | 1880 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1726 | KL-20200614-2 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 2 | HR | 141 | 0 |  |  | 376 | 48.88 | 424.88 | 2020-06-14 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Unclog cross drain culvert @ 13.5 Km on 600 Road. Ditching and shaping access to E-134. RV-40033 | 9 | E091-E102 | 600 Road | 0 | 44000 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-2Float Truck - 60 ton2376 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-2Float Truck - 60 ton2376OEWT-PA6-LEM | [5 empty] | 1 | 376 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3485 | KL-20201005-10 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 6 | HR | 141 | 0 |  |  | 1128 | 146.64 | 1274.64 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unplug Culverts at km 40 and 48 on 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3485KL-20201005-10Float Truck - 60 ton61128 | KABI LAKE FOREST PRODUCTS LTD3485KL-20201005-10Float Truck - 60 ton61128OEWT-PA10-LEM | [5 empty] | 1 | 1128 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3555 | KL-20201007-10 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 5 | HR | 141 | 0 |  |  | 940 | 122.2 | 1062.2 | 2020-10-07 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Buncher from E110 to 650 pit and back to E139 | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3555KL-20201007-10Float Truck - 60 ton5940 | KABI LAKE FOREST PRODUCTS LTD3555KL-20201007-10Float Truck - 60 ton5940OEWT-PA10-LEM | [5 empty] | 1 | 940 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3691 | KL-20201012-9 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 7 | HR | 141 | 0 |  |  | 1316 | 171.08 | 1487.08 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float and use log loader to unclog culverts @ 49km on 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-9Float Truck - 60 ton71316 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-9Float Truck - 60 ton71316OEWT-PA10-LEM | [5 empty] | 1 | 1316 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4101 | KL-20201101-10 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 2 | HR | 141 | 0 |  |  | 376 | 48.88 | 424.88 | 2020-11-01 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Move cat 335F Excavator to 6km on 600 Rd for loading of road maintenace sand | 9 | E091-E102 | 600 Rd | 0 | 44153 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4101KL-20201101-10Float Truck - 60 ton2376 | KABI LAKE FOREST PRODUCTS LTD4101KL-20201101-10Float Truck - 60 ton2376OEWT-PA11-LEM | [5 empty] | 1 | 376 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4174 | KL-20201105-8 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2020-11-05 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float buncher from E122, E124 to E165 | 9 | E091-E102 | 600 Road | 0 | 44160 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD4174KL-20201105-8Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD4174KL-20201105-8Float Truck - 60 ton3564OEWT-PA11-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4182 | KL-20201105-16 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 5 | HR | 141 | 0 |  |  | 940 | 122.2 | 1062.2 | 2020-11-05 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float D6 fro Km 32 600 road to Km57 and 336 from 650 pit to km52 F216 | 9 | E091-E102 | 600 Road | 0 | 44160 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4182KL-20201105-16Float Truck - 60 ton5940 | KABI LAKE FOREST PRODUCTS LTD4182KL-20201105-16Float Truck - 60 ton5940OEWT-PA11-LEM | [5 empty] | 1 | 940 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4359 | KL-20201114-12 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float D6 from F9 to E168 to shape roads | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4359KL-20201114-12Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD4359KL-20201114-12Float Truck - 60 ton4752OEWT-PA11-LEM | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6903 | KL-20210511-3 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2021-05-11 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 250 link belt log loader from mill yard to 13km on 600 road/unplug culvert and float log loader back to mill yard | 9 | E091-E102 | 600 Road | 0 | 44337 |  | 56 | 44341 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-3Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-3Float Truck - 60 ton3564OEWT-PA17-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7494 | KL-20211026-3 | 53510912 | Access | 0 | Float Truck - 60 ton | 188 | 3.5 | HR | 141 | 0 |  |  | 658 | 85.54 | 743.54 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Skagen Volvo Grader from Hensen Road for grading of the 600 Road. Grade from Km 1 on Paint Lake Road 2 to Km 52 on 600 road and grade towards Km 49 - SSF-14419 | 9 | E032-F009 | 600 Road | 0 | 44501 |  | 61 | 44502 | [6 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7494KL-20211026-3Float Truck - 60 ton3.5658 | KABI LAKE FOREST PRODUCTS LTD7494KL-20211026-3Float Truck - 60 ton3.5658OEWT-PA23-Lem | [5 empty] | 1 | 658 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7293 | KL-20210831-3 | 53511007 | Access | 0 | Float Truck - 60 ton | 188 | 6 | HR | 141 | 0 |  |  | 1128 | 146.64 | 1274.64 | 2021-08-31 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Mob Cat 730 Rock Truck from North of White River to 0.5Km on Hensen Road for Gravel haul | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44442 |  | 37 | 44445 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7293KL-20210831-3Float Truck - 60 ton61128 | KABI LAKE FOREST PRODUCTS LTD7293KL-20210831-3Float Truck - 60 ton61128OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1128 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7443 | KL-20211011-2 | 53511007 | Access | 0 | Float Truck - 60 ton | 188 | 5 | HR | 141 | 0 |  |  | 940 | 122.2 | 1062.2 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 725 Rock Truck from Three Finger Lake to Paint Lake Road 2 for gravel haul. Delivered to 0.5km on Hensen Road. | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7443KL-20211011-2Float Truck - 60 ton5940 | KABI LAKE FOREST PRODUCTS LTD7443KL-20211011-2Float Truck - 60 ton5940OEWT-PA22-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 940 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7477 | KL-20211019-3 | 53511007 | Access | 0 | Float Truck - 60 ton | 188 | 5 | HR | 141 | 0 |  |  | 940 | 122.2 | 1062.2 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330 Excavator from Kabi Yard to Km 49 Paint Lake Road 2 as per Valard | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7477KL-20211019-3Float Truck - 60 ton5940 | KABI LAKE FOREST PRODUCTS LTD7477KL-20211019-3Float Truck - 60 ton5940OEWT-PA22-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 940 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4792 | KL-20201203-12 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 9 | HR | 141 | 0 |  |  | 1692 | 219.96 | 1911.96 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up 40' bridge mats in Marathon, and deliver to Paint Lake RD 1-B | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4792KL-20201203-12Float Truck - 60 ton91692 | KABI LAKE FOREST PRODUCTS LTD4792KL-20201203-12Float Truck - 60 ton91692OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1692 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7621 | KL-20211202-3 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 950M Loader from Anjigami to 10.5 Km 0n Hensen Road as per Valard / Chain up required | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7621KL-20211202-3Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD7621KL-20211202-3Float Truck - 60 ton4752OEWT-PA24-LEM | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7658 | KL-20211209-2 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 14M grader from Kabi shop to 2Km on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7658KL-20211209-2Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7658KL-20211209-2Float Truck - 60 ton3564OEWT-PA24-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7659 | KL-20211209-3 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 9.5 | HR | 141 | 0 |  |  | 1786 | 232.18 | 2018.18 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Demobilized Skagen's Champion 740 grader form Paint Lake Road 2 to Sault Ste Marie, ON. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7659KL-20211209-3Float Truck - 60 ton9.51786 | KABI LAKE FOREST PRODUCTS LTD7659KL-20211209-3Float Truck - 60 ton9.51786OEWT-PA24-LEM | [5 empty] | 1 | 1786 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7703 | KL-20211217-3 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 3.5 | HR | 141 | 0 |  |  | 658 | 85.54 | 743.54 | 2021-12-17 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D6 Dozer from Km 9 on Paint Lake Road 2 to Kabi Yard | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7703KL-20211217-3Float Truck - 60 ton3.5658 | KABI LAKE FOREST PRODUCTS LTD7703KL-20211217-3Float Truck - 60 ton3.5658OEWT-PA24-LEM | [5 empty] | 1 | 658 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7707 | KL-20211219-3 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 3.5 | HR | 141 | 0 |  |  | 658 | 85.54 | 743.54 | 2021-12-19 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330F Excavator fro Km 2 on Paint Lake Road 2 to Kabi Yard | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7707KL-20211219-3Float Truck - 60 ton3.5658 | KABI LAKE FOREST PRODUCTS LTD7707KL-20211219-3Float Truck - 60 ton3.5658OEWT-PA24-LEM | [5 empty] | 1 | 658 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7709 | KL-20211220-2 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 9 | HR | 141 | 0 |  |  | 1692 | 219.96 | 1911.96 | 2021-12-20 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Demobilization of Morin 300 Excavator from Km 9 on Paint Lake Road 2 to Chapleau Ontario | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7709KL-20211220-2Float Truck - 60 ton91692 | KABI LAKE FOREST PRODUCTS LTD7709KL-20211220-2Float Truck - 60 ton91692OEWT-PA24-LEM | [5 empty] | 1 | 1692 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7731 | KL-20220105-1 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 962M Loader from Kabi yard to 9.2 Km on Paint Lake Road 2 | 10 | F0066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7731KL-20220105-1Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD7731KL-20220105-1Float Truck - 60 ton4752OEWT-PA25-Lem | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7736 | KL-20220106-1 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 10 | HR | 141 | 0 |  |  | 1880 | 244.4 | 2124.4 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Link Belt Log Loader from Km 49 to Km 9.2 on Paint Lake Road 2 and Cat 330 support excavator from Km 49 to Km 1 on Paint Lake Road and parked @ end of shift ( chain up required ) | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7736KL-20220106-1Float Truck - 60 ton101880 | KABI LAKE FOREST PRODUCTS LTD7736KL-20220106-1Float Truck - 60 ton101880OEWT-PA25-Lem | [5 empty] | 1 | 1880 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7739 | KL-20220107-1 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 7.5 | HR | 141 | 0 |  |  | 1410 | 183.3 | 1593.3 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330 support excavator from Km 1 on Paint Lake Road to Km 9.2 on Paint Lake Road 2 and Peterson Grinder from 17 on Hensen Road to Km 9.2 on Paint Lake Road 2 ( chain up required ) | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7739KL-20220107-1Float Truck - 60 ton7.51410 | KABI LAKE FOREST PRODUCTS LTD7739KL-20220107-1Float Truck - 60 ton7.51410OEWT-PA25-Lem | [5 empty] | 1 | 1410 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7774 | KL-20220115-3 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float ACI Cat 938M loader from .5 Km on Hensen road to Km 9.2 on Paint Lake Road 2 as per Valard | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7774KL-20220115-3Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7774KL-20220115-3Float Truck - 60 ton4.5846OEWT-PA25-Lem | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7963 | KL-20220303-2 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2022-03-03 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Kabi Cat 950M Loader Back To 9.2 Km On Paint Lake Road 2 From F170 After Completion Of Snow Removal. Access/Mob/Demob (Cost Code: 67776007556.591100.57010107) | 10 | F066-F118 | Paint Lake 2 | 1 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7963KL-20220303-2Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7963KL-20220303-2Float Truck - 60 ton4.5846 | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7967 | KL-20220304-2 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 3.5 | HR | 141 | 0 |  |  | 658 | 85.54 | 743.54 | 2022-03-04 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Cat 140M Grader From 2 Km On Paint Lake Road 2 Back To Kabi Yard | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7967KL-20220304-2Float Truck - 60 ton3.5658 | KABI LAKE FOREST PRODUCTS LTD7967KL-20220304-2Float Truck - 60 ton3.5658 | [5 empty] | 1 | 658 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7977 | KL-20220309-2 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2022-03-09 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Cat 12M Grader From 2 Km On Paint Lake Road 2 Back To Kabi Yard | 10 | F066-F118 | Paint Lake 2 | 0 | 44634 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7977KL-20220309-2Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD7977KL-20220309-2Float Truck - 60 ton4752 | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7833 | KL-20220204-2 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T dozer from 12Km on Paint Lake Road to F021 on Paint Lake Road. | 10 | F009-F065 | Paint Lake | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7833KL-20220204-2Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7833KL-20220204-2Float Truck - 60 ton4.5846OEWT-PA26-LEM | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7866 | KL-20220210-3 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D6 Dozer from Paint Lake Road 1-B to Km 9.2 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7866KL-20220210-3Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7866KL-20220210-3Float Truck - 60 ton3564OEWT-PA26-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7877 | KL-20220213-1 | 53511011 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 140M Grader from Kabi Yard to Km 2 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7877KL-20220213-1Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7877KL-20220213-1Float Truck - 60 ton3564OEWT-PA26-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5916 | KL-20210215-11 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D5K Dozer to F169 for snow removal. Dozer remove snow from F169 to F165. | 11 | F165-F169 | Magpie Hills Road | 0 | 44249 |  | 14 | 44250 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5916KL-20210215-11Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD5916KL-20210215-11Float Truck - 60 ton4752OEWT-PA14-Lem-R1 | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7598 | KL-20211126-2 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2021-11-26 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Skagen Volvo Grader from Anjigami to Km 13 on High Falls Road. Grader doing snow removal and widening road from Km 13 on High Falls Road to F207 and F199 - SSF- 14452 | 11 | F170 - F211 | High Falls | 0 | 44532 |  | 61 | 44534 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7598KL-20211126-2Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7598KL-20211126-2Float Truck - 60 ton4.5846OEWT-PA24-LEM | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7599 | KL-20211127-2 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 5 | HR | 141 | 0 |  |  | 940 | 122.2 | 1062.2 | 2021-11-27 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float D6 Dozer from Robert's Road to Km 13 on High Falls Road | 11 | F170 - F211 | High Falls | 0 | 44532 |  | 61 | 44534 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7599KL-20211127-2Float Truck - 60 ton5940 | KABI LAKE FOREST PRODUCTS LTD7599KL-20211127-2Float Truck - 60 ton5940OEWT-PA24-LEM | [5 empty] | 1 | 940 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7603 | KL-20211128-3 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2021-11-28 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 140M grader from Harte Gold Road to Hensen Road for snow removalas per Valard | 11 | F118-F127 | Hensen Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7603KL-20211128-3Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD7603KL-20211128-3Float Truck - 60 ton4752OEWT-PA24-LEM | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7613 | KL-20211201-3 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 2 | HR | 141 | 0 |  |  | 376 | 48.88 | 424.88 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6 Dozer from F185 to F196 Access | 11 | F170-F211 | High Falls | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7613KL-20211201-3Float Truck - 60 ton2376 | KABI LAKE FOREST PRODUCTS LTD7613KL-20211201-3Float Truck - 60 ton2376OEWT-PA24-LEM | [5 empty] | 1 | 376 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7617 | KL-20211201-7 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 5.5 | HR | 141 | 0 |  |  | 1034 | 134.42 | 1168.42 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6 Dozer from White River to 17 Km on Hensen Road as per Valard / Chain up required | 11 | F118-F127 | Henson | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7617KL-20211201-7Float Truck - 60 ton5.51034 | KABI LAKE FOREST PRODUCTS LTD7617KL-20211201-7Float Truck - 60 ton5.51034OEWT-PA24-LEM | [5 empty] | 1 | 1034 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7624 | KL-20211202-6 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330 Excavator from North Regan Road for Winter Access to F151 | 11 | F128-F158 | MFN | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7624KL-20211202-6Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD7624KL-20211202-6Float Truck - 60 ton4752OEWT-PA24-LEM | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7640 | KL-20211205-3 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 3.5 | HR | 141 | 0 |  |  | 658 | 85.54 | 743.54 | 2021-12-05 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 12M grader to 5.5 km on High Falls for snow removal | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7640KL-20211205-3Float Truck - 60 ton3.5658 | KABI LAKE FOREST PRODUCTS LTD7640KL-20211205-3Float Truck - 60 ton3.5658OEWT-PA24-LEM | [5 empty] | 1 | 658 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7662 | KL-20211209-5 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 5.5 | HR | 141 | 0 |  |  | 1034 | 134.42 | 1168.42 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330 excavator from MFN to 17km on Hensen Road. Chain up required. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7662KL-20211209-5Float Truck - 60 ton5.51034 | KABI LAKE FOREST PRODUCTS LTD7662KL-20211209-5Float Truck - 60 ton5.51034OEWT-PA24-LEM | [5 empty] | 1 | 1034 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7687 | KL-20211213-2 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 6 | HR | 141 | 0 |  |  | 1128 | 146.64 | 1274.64 | 2021-12-13 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D6 Dozer from Km 13 on High Falls Road to Km 17 on Hensen Road and float Cat 140M grader from Km .5 on Hensen Road to Kabi Yard/Chain Up required | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7687KL-20211213-2Float Truck - 60 ton61128 | KABI LAKE FOREST PRODUCTS LTD7687KL-20211213-2Float Truck - 60 ton61128OEWT-PA24-LEM | [5 empty] | 1 | 1128 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7692 | KL-20211214-4 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 14M Grader from Km .5 on Hensen Road to Kabi Yard | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7692KL-20211214-4Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7692KL-20211214-4Float Truck - 60 ton3564OEWT-PA24-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7770 | KL-20220114-3 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 3.5 | HR | 141 | 0 |  |  | 658 | 85.54 | 743.54 | 2022-01-14 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 12M Grader from 3.5 Km on High Falls Road to .5 Km on Hensen road | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7770KL-20220114-3Float Truck - 60 ton3.5658 | KABI LAKE FOREST PRODUCTS LTD7770KL-20220114-3Float Truck - 60 ton3.5658OEWT-PA25-Lem | [5 empty] | 1 | 658 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7783 | KL-20220118-2 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2022-01-18 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 962M Loader from 0.5Km on Hensen Road to 7Km on Anjigami Road. | 11 | F212-F235 | Anjigame | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7783KL-20220118-2Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7783KL-20220118-2Float Truck - 60 ton4.5846OEWT-PA25-Lem | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7879 | KL-20220213-3 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 12M grader from .5 Km on Hensen Road to Km 1 on Trembley Road | 11 | F161-F164 | Trembley Falls | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7879KL-20220213-3Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7879KL-20220213-3Float Truck - 60 ton3564OEWT-PA26-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7881 | KL-20220213-5 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 3 | HR | 141 | 0 |  |  | 564 | 73.32 | 637.32 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 12M grader frim Km 1 on Trembley road back to Km .5 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7881KL-20220213-5Float Truck - 60 ton3564 | KABI LAKE FOREST PRODUCTS LTD7881KL-20220213-5Float Truck - 60 ton3564OEWT-PA26-LEM | [5 empty] | 1 | 564 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7940 | KL-20220227-3 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Cat 950M Loader From 9.2 Km On Paint Lake Road 2 To Magpie Hills Road. (Cost Code: 67776007556.591100.57010107) | 11 | F165-F169 | Magpie Hills | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7940KL-20220227-3Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7940KL-20220227-3Float Truck - 60 ton4.5846 | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7949 | KL-20220228-6 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 5 | HR | 141 | 0 |  |  | 940 | 122.2 | 1062.2 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Cat 962M Loader From Kabi Shop To 3 Km On High Falls Road & Float Cat 950M Loader From Magpie Hills Road To 5 Km On High Falls Road (Cost Code: 67776007556.591100.57010107) | 11 | F170 - F211 | High Falls | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7949KL-20220228-6Float Truck - 60 ton5940 | KABI LAKE FOREST PRODUCTS LTD7949KL-20220228-6Float Truck - 60 ton5940 | [5 empty] | 1 | 940 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7959 | KL-20220302-4 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 2 | HR | 141 | 0 |  |  | 376 | 48.88 | 424.88 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Cat 950M loader from High Falls Road to F170/ Traffic control required ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170-F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4Float Truck - 60 ton2376 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4Float Truck - 60 ton2376 | [5 empty] | 1 | 376 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7961 | KL-20220302-6 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 3.5 | HR | 141 | 0 |  |  | 658 | 85.54 | 743.54 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Cat 962M loader from High Falls Road to Km 7 on Anjigami Road | 11 | F212-F235 | Anjigame | 0 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7961KL-20220302-6Float Truck - 60 ton3.5658 | KABI LAKE FOREST PRODUCTS LTD7961KL-20220302-6Float Truck - 60 ton3.5658 | [5 empty] | 1 | 658 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7971 | KL-20220306-2 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 5.5 | HR | 141 | 0 |  |  | 1034 | 134.42 | 1168.42 | 2022-03-06 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Kabi Cat 950M from 9.2Km on Paint Lake Road #2 to High Falls road. Delay due to bad weather. | 11 | F170-F211 | High Falls | 1 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7971KL-20220306-2Float Truck - 60 ton5.51034 | KABI LAKE FOREST PRODUCTS LTD7971KL-20220306-2Float Truck - 60 ton5.51034 | [5 empty] | 1 | 1034 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7973 | KL-20220307-3 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2022-03-07 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Cat 962M Loader From Kabi Yard To 7 Km On Anjigami Road | 11 | F212-F235 | Anjigame | 0 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7973KL-20220307-3Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7973KL-20220307-3Float Truck - 60 ton4.5846 | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7975 | KL-20220308-2 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2022-03-08 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Cat 962M Loader From 7 Km On Anjigami Road To Kabi Yard | 11 | F212-F235 | Anjigame | 0 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7975KL-20220308-2Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7975KL-20220308-2Float Truck - 60 ton4.5846 | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7976 | KL-20220309-1 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2022-03-09 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Kabi Cat 950M From High Falls Road Back To Kabi Yard. (Cost Code: 67776007556.591100.57010107) | 11 | F170-F211 | High Falls | 1 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7976KL-20220309-1Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD7976KL-20220309-1Float Truck - 60 ton4752 | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7790 | KL-20220120-3 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T Dozer from Kabi yard to 11Km on High Falls Road. | 11 | F170-F211 | High Falls | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7790KL-20220120-3Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD7790KL-20220120-3Float Truck - 60 ton4752OEWT-PA25-Lem | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7795 | KL-20220121-3 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 962 Loader from Km 7 on Anjigami Road to Km .5 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44589 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7795KL-20220121-3Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7795KL-20220121-3Float Truck - 60 ton4.5846OEWT-PA25-Lem | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7803 | KL-20220124-3 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 962M Loader from .5 on Hensen Road to Km 7 on Anjigami Road | 11 | F212-F235 | Anjigame | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7803KL-20220124-3Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD7803KL-20220124-3Float Truck - 60 ton4.5846OEWT-PA25-Lem | [5 empty] | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7823 | KL-20220201-2 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T dozer from 11Km on High Falls Road back to Kabi Yard. | 11 | F170 - F211 | High Falls | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7823KL-20220201-2Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD7823KL-20220201-2Float Truck - 60 ton4752OEWT-PA26-LEM | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7837 | KL-20220205-2 | 53511111 | Access | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi 950 Loader from 7km on Anjigami road to 0.5km on Hensen road. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7837KL-20220205-2Float Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD7837KL-20220205-2Float Truck - 60 ton4752OEWT-PA26-LEM | [5 empty] | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6620 | KL-20210404-5 | 53541101 | Reclamation | 0 | Float Truck - 60 ton | 188 | 4.5 | HR | 141 | 0 |  |  | 846 | 109.98 | 955.98 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 336 Excavator to Km 3 on Dore Lake road for Reclamation of Dore Lake Road West | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6620KL-20210404-5Float Truck - 60 ton4.5846 | KABI LAKE FOREST PRODUCTS LTD6620KL-20210404-5Float Truck - 60 ton4.5846OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 846 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6680 | KL-20210408-5-R1 | 53541101 | Reclamation | 0 | Float Truck - 60 ton | 188 | 5 | HR | 141 | 0 |  |  | 940 | 122.2 | 1062.2 | 2021-04-08 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Skagen 350 Excavator from Ajigami for Reclamation. Start Reclamation @F152. Supervisor and pickup hours from signed ticket removed per Valard direction, will be listed on KL-20210408-5-S1. | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44305 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6680KL-20210408-5-R1Float Truck - 60 ton5940 | KABI LAKE FOREST PRODUCTS LTD6680KL-20210408-5-R1Float Truck - 60 ton5940OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 940 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7928 | KL-20220301-1-RCL | 53541007 | Reclamation | 0 | Float Truck - 60 ton | 188 | 5 | HR | 141 | 0 |  |  | 940 | 122.2 | 1062.2 | 2022-03-01 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Reclamation Mob/Demob | Reclamation Mob/Demob | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float moved 330 excavator from White Lake West to 9.2km on Paint Lake 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44621 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7928KL-20220301-1-RCLFloat Truck - 60 ton5940 | KABI LAKE FOREST PRODUCTS LTD7928KL-20220301-1-RCLFloat Truck - 60 ton5940 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 940 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7929 | KL-20220302-1-RCL | 53541007 | Reclamation | 0 | Float Truck - 60 ton | 188 | 5.5 | HR | 141 | 0 |  |  | 1034 | 134.42 | 1168.42 | 2022-03-02 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Reclamation Mob/Demob | Reclamation Mob/Demob | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float moved 336 excavator from Dubreuilville Mine to 9.2km on Paint Lake 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44623 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7929KL-20220302-1-RCLFloat Truck - 60 ton5.51034 | KABI LAKE FOREST PRODUCTS LTD7929KL-20220302-1-RCLFloat Truck - 60 ton5.51034 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 1034 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7950 | KL-20220307-1-RCL | 53541007 | Reclamation | 0 | Float Truck - 60 ton | 188 | 5.5 | HR | 141 | 0 |  |  | 1034 | 134.42 | 1168.42 | 2022-03-07 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Reclamation Mob/Demob | Reclamation Mob/Demob | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 336 excavator from 9.2km Paint Lake 2 back to Dubreuilville | 10 | F066-F118 | Paint Lake 2 | 0 | 44627 |  | 37 | 44627 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7950KL-20220307-1-RCLFloat Truck - 60 ton5.51034 | KABI LAKE FOREST PRODUCTS LTD7950KL-20220307-1-RCLFloat Truck - 60 ton5.51034 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 1034 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7952 | KL-20220308-1-RCL | 53541007 | Reclamation | 0 | Float Truck - 60 ton | 188 | 4 | HR | 141 | 0 |  |  | 752 | 97.76 | 849.76 | 2022-03-08 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Reclamation Mob/Demob | Reclamation Mob/Demob | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 330 excavator from 9.2km Paint Lake 2 to Kabi yard | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 |  | 37 | 44628 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7952KL-20220308-1-RCLFloat Truck - 60 ton4752 | KABI LAKE FOREST PRODUCTS LTD7952KL-20220308-1-RCLFloat Truck - 60 ton4752 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 752 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 881 | KL-20200108-1-R1 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-01-10 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Buncher brushing road line on White Lake Rd., Float truck mobilizing mats from Thunder Bay. Supervisor on-site checking roads & ROW clearing. Buncher and skidder cleared estimated 0.8 Ha | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD881KL-20200108-1-R1Pickup Truck - Truck Only6150 | KABI LAKE FOREST PRODUCTS LTD881KL-20200108-1-R1Pickup Truck - Truck Only6150OEWT-PA1-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 902 | KL-20200121-2 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Brushed 15M road ROW to D146. Dozer shaped & pushed snow back D-147 & D146 | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-2Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-2Pickup Truck - Truck Only10250OEWT-PA1-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 934 | KL-20200126-3 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-01-26 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open Road from Hwy 17 to 3km on White Lake Road | 7 | D-142 to E-002 | White Lake | 0 | 43856 |  | 17 | 43861 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD934KL-20200126-3Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD934KL-20200126-3Pickup Truck - Truck Only250OEWT-PA2-LEM-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1121 | KL-20200222-1 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow for road access | 7 | D-119 to D-141 | Alder Creek | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1121KL-20200222-1Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD1121KL-20200222-1Pickup Truck - Truck Only125OEWT-PA2-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1122 | KL-20200222-2 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow- White Lake Road | 7 | D-142 to E-002 | White Lake | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1122KL-20200222-2Pickup Truck - Truck Only4100 | KABI LAKE FOREST PRODUCTS LTD1122KL-20200222-2Pickup Truck - Truck Only4100OEWT-PA2-LEM-R1 | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1124 | KL-20200222-4 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | low snow on Black River East road | 7 | D-032 to D-055 | Black River | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1124KL-20200222-4Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD1124KL-20200222-4Pickup Truck - Truck Only250OEWT-PA2-LEM-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1125 | KL-20200222-5 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow for access on Wabakoba Creek | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1125KL-20200222-5Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD1125KL-20200222-5Pickup Truck - Truck Only250OEWT-PA2-LEM-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1129 | KL-20200223-3 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-02-23 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow and maintain road | 7 | D-032 to D-055 | Black River | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1129KL-20200223-3Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD1129KL-20200223-3Pickup Truck - Truck Only250OEWT-PA2-LEM-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1159 | KL-20200224-4 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-02-24 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up buncher and drop off skidder | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1159KL-20200224-4Pickup Truck - Truck Only4100 | KABI LAKE FOREST PRODUCTS LTD1159KL-20200224-4Pickup Truck - Truck Only4100OEWT-PA2-LEM-R1 | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4932 | KL-20201207-6 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Snow removal from D018 to D025 and filling ruts for freezing | 7 | D-018 to D-031 | Pie River | 0 | 44193 |  | 47 | 44202 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4932KL-20201207-6Pickup Truck - Truck Only11275 | KABI LAKE FOREST PRODUCTS LTD4932KL-20201207-6Pickup Truck - Truck Only11275OEWT-PA12-LEM-R1 | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5094 | KL-20201217-2 | 53510711 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer starting road maintenance to D032 | 7 | D-032 to D-055 | Black River | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD5094KL-20201217-2Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD5094KL-20201217-2Pickup Truck - Truck Only250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 886 | KL-20200113-1-R1 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear and brush existing road for equpiment access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD886KL-20200113-1-R1Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD886KL-20200113-1-R1Pickup Truck - Truck Only375OEWT-PA1-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1551 | KL-20200521-3 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-05-21 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Ditching and Shaping Road | 7 | D032-D055 | Black River East | 0 | 43977 |  | 15 | 43977 | [5 empty] | Martin Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD1551KL-20200521-3Pickup Truck - Truck Only6150 | KABI LAKE FOREST PRODUCTS LTD1551KL-20200521-3Pickup Truck - Truck Only6150OEWT-PA5-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1886 | KL-20200626-7 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-06-26 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade section on 100 road to 5km pit for gravel haul to Alder Creek | 7 | D-119 to D-141 | Alder Creek | 0 | 44038 |  | 47 | 44014 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD1886KL-20200626-7Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD1886KL-20200626-7Pickup Truck - Truck Only125OEWT-PA7-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2018 | KL-20200712-9 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-07-12 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 Road from Hwy to 5KM pit for gravel haul | 7 | D-119 to D-141 | Alder Creek | 0 | 44027 |  | 48 | 44028 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2018KL-20200712-9Pickup Truck - Truck Only5125 | KABI LAKE FOREST PRODUCTS LTD2018KL-20200712-9Pickup Truck - Truck Only5125OEWT-PA7-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2018 | KL-20200712-9 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-07-12 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 Road from Hwy to 5KM pit for gravel haul | 7 | D-119 to D-141 | Alder Creek | 0 | 44027 |  | 48 | 44028 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2018KL-20200712-9Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD2018KL-20200712-9Pickup Truck - Truck Only125OEWT-PA7-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2019 | KL-20200712-10 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-07-12 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Grade 600 road from Km 4 to Km 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 | [9 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD2019KL-20200712-10Pickup Truck - Truck Only4100 | KABI LAKE FOREST PRODUCTS LTD2019KL-20200712-10Pickup Truck - Truck Only4100OEWT-PA7-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2019 | KL-20200712-10 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-07-12 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Grade 600 road from Km 4 to Km 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 | [9 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD2019KL-20200712-10Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD2019KL-20200712-10Pickup Truck - Truck Only125OEWT-PA7-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2092 | KL-20200717-4 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road to D055 to D053 | 7 | D-056 to D-073 | Umbatta Falls | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2092KL-20200717-4Pickup Truck - Truck Only5125 | KABI LAKE FOREST PRODUCTS LTD2092KL-20200717-4Pickup Truck - Truck Only5125OEWT-PA7-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2101 | KL-20200717-13 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road from Hwy to 5km pit for gravel Haul | 7 | D-100 to D-106 | 614 Road | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2101KL-20200717-13Pickup Truck - Truck Only6150 | KABI LAKE FOREST PRODUCTS LTD2101KL-20200717-13Pickup Truck - Truck Only6150OEWT-PA7-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2108 | KL-20200718-6 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2020-07-18 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road from D053 to D043 | 7 | D-032 to D-055 | Black River | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2108KL-20200718-6Pickup Truck - Truck Only9225 | KABI LAKE FOREST PRODUCTS LTD2108KL-20200718-6Pickup Truck - Truck Only9225OEWT-PA7-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2275 | KL-20200726-6 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-07-26 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance from D109 to D112 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44041 |  | 48 | 44041 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2275KL-20200726-6Pickup Truck - Truck Only5125 | KABI LAKE FOREST PRODUCTS LTD2275KL-20200726-6Pickup Truck - Truck Only5125OEWT-PA8-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2275 | KL-20200726-6 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-07-26 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance from D109 to D112 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44041 |  | 48 | 44041 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2275KL-20200726-6Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD2275KL-20200726-6Pickup Truck - Truck Only125OEWT-PA8-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4293 | KL-20201110-3 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and spread gravel and chips D071-D073 BMC-30143 | 7 | D065-D066 | Camp 36 Road | 0 | 44166 |  | 53 | 44168 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-3Pickup Truck - Truck Only14350 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-3Pickup Truck - Truck Only14350OEWT-PA11-LEM | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4352 | KL-20201114-5 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc working access from D125 to D129/1 hr excavator & grinder travel due to poor condition of access mats D121 to D132 | 7 | D-119 to D-141 | Alder Creek | 0 | 44166 |  | 53 | 44171 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4352KL-20201114-5Pickup Truck - Truck Only6150 | KABI LAKE FOREST PRODUCTS LTD4352KL-20201114-5Pickup Truck - Truck Only6150OEWT-PA11-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4456 | KL-20201119-2 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access to ROW and from D074 to D078, leveling ruts and track packing road | 7 | D-074 to D-079 | Brett’s Road | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4456KL-20201119-2Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4456KL-20201119-2Pickup Truck - Truck Only10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7432 | KL-20211006-2 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 23.5 | HR | 19 | 0 |  |  | 587.5 | 76.375 | 663.875 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road and pushing rock trucks hauling gravel to D025 /excavator leveling ruts and shaping road. | 7 | D018-D031 | Pic river | 0 | 44484 |  | 63 | 44484 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2Pickup Truck - Truck Only23.5587.5 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2Pickup Truck - Truck Only23.5587.5OEWT-PA22-Lem | [5 empty] | 1 | 587.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7437 | KL-20211008-2 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 6.5 | HR | 19 | 0 |  |  | 162.5 | 21.125 | 183.625 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator finishing levelling ruts & shaping road from D-019 to D-025 for pickup access. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-2Pickup Truck - Truck Only6.5162.5 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-2Pickup Truck - Truck Only6.5162.5OEWT-PA22-Lem | [5 empty] | 1 | 162.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7487 | KL-20211024-3 | 53510712 | Access | 0 | Pickup Truck - Truck Only | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer leveling ruts and shaping road from Hwy 17 to D018 and to D025 after completion of foundation work | 7 | D018-D031 | Pic River | 0 | 44493 |  | 61 | 44497 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7487KL-20211024-3Pickup Truck - Truck Only11275 | KABI LAKE FOREST PRODUCTS LTD7487KL-20211024-3Pickup Truck - Truck Only11275OEWT-PA23-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1150 | KL-20200224-6 | 53510811 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-02-24 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Flag to drop off Dozer D6 | 8 | E086 - E094 | Blue Cedar E | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 08 | KABI LAKE FOREST PRODUCTS LTD1150KL-20200224-6Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD1150KL-20200224-6Pickup Truck - Truck Only375OEWT-PA2-LEM-R1 | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4902 | KL-20201205-5 | 53510811 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Silver City AU1 Access to E025 as per Valard | 8 | E025-E036 | Silver City | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-5Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-5Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4919 | KL-20201206-6 | 53510811 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer blading AE1 Access from Hwy to ROW | 8 | E017-E024 | North Regan | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4919KL-20201206-6Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD4919KL-20201206-6Pickup Truck - Truck Only250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5151 | KL-20201228-2 | 53510811 | Access | 0 | Pickup Truck - Truck Only | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer working on snow removal from Hwy 17 to E014/E015 Access | 8 | E004-E016 | White Lake East | 0 | 43836 |  | 36 | 44213 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD5151KL-20201228-2Pickup Truck - Truck Only9225 | KABI LAKE FOREST PRODUCTS LTD5151KL-20201228-2Pickup Truck - Truck Only9225OEWT-PA13-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1542 | KL-20200520-13 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-05-20 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Ditching main access road | 8 | E068-E076 | North Crockers Lake | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD1542KL-20200520-13Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD1542KL-20200520-13Pickup Truck - Truck Only12300OEWT-PA5-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1640 | KL-20200602-10 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-06-02 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road to 5 KM Pit gor Blue Cedar Gravel Haul | 8 | E077-E091 | Blue Cedar Road | 0 | 43987 |  | 15 | 43988 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD1640KL-20200602-10Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD1640KL-20200602-10Pickup Truck - Truck Only250OEWT-PA6-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2941 | KL-20200915-12 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road to 5Km pit for gravel haul | 8 | E068 - E076 | Denis Lake W | 0 | 44096 |  | 15 | 44097 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD2941KL-20200915-12Pickup Truck - Truck Only5125 | KABI LAKE FOREST PRODUCTS LTD2941KL-20200915-12Pickup Truck - Truck Only5125OEWT-PA9-Lem-R1 | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3900 | KL-20201025-4 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-10-25 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator starting maintenance on access for concrete truck as per Valard | 8 | E-077 to E-091 | Blue Cedar Road | 0 | 44133 |  | 47 | 44133 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3900KL-20201025-4Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD3900KL-20201025-4Pickup Truck - Truck Only8200OEWT-PA10-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4207 | KL-20201107-1 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-11-07 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scrape Mud from exiting vehicles to hwy 17 at entrance to silver sity. Pickup with beacon, flag paddle and radio contact watching traffic | 8 | E025-E036 | Silver City | 0 | 44162 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD4207KL-20201107-1Pickup Truck - Truck Only5125 | KABI LAKE FOREST PRODUCTS LTD4207KL-20201107-1Pickup Truck - Truck Only5125OEWT-PA11-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4356 | KL-20201114-9 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade sections of Access to D142 as per Valard | 8 | E004-E016 | White Lake East | 0 | 44166 |  | 53 | 44171 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4356KL-20201114-9Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD4356KL-20201114-9Pickup Truck - Truck Only375OEWT-PA11-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6900 | KL-20210510-3 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 2.5 | HR | 19 | 0 |  |  | 62.5 | 8.125 | 70.625 | 2021-05-10 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 962M loader repairing washout @Blue Cedar entrance/Labourer escorting loader on Hwy 17 from Kabi Yard and back | 8 | E077-E091 | Blue Cedar | 0 | 44337 |  | 56 | 44341 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6900KL-20210510-3Pickup Truck - Truck Only2.562.5 | KABI LAKE FOREST PRODUCTS LTD6900KL-20210510-3Pickup Truck - Truck Only2.562.5OEWT-PA17-LEM | [5 empty] | 1 | 62.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6922 | KL-20210515-6 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-05-15 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading, hauling and spreading pit run from stock pile to E007/E006 access/loading and hauling trees for soft sections/dozer leveling ruts and excavator placing corduroy | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44342 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6Pickup Truck - Truck Only23575 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6Pickup Truck - Truck Only23575OEWT-PA17-LEM | [5 empty] | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6925 | KL-20210516-2 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-05-16 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator ditching along access @ E006 to E007 for capping material | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44343 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6925KL-20210516-2Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD6925KL-20210516-2Pickup Truck - Truck Only10250OEWT-PA17-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6945 | KL-20210518-2 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | loading , hauling and spreading existing material @ E014 for road repairs from E014.5 to E016 to maintain pickup access | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2Pickup Truck - Truck Only3.587.5 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2Pickup Truck - Truck Only3.587.5OEWT-PA17-LEM | [5 empty] | 1 | 87.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6977 | KL-20210523-4 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 13.5 | HR | 19 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material for road repairs near E011, 330 loading material and dozer spreading loads from rock truck and fixing punch outs | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4Pickup Truck - Truck Only13.5337.5 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4Pickup Truck - Truck Only13.5337.5OEWT-PA17-LEM | [5 empty] | 1 | 337.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6999 | KL-20210531-1 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling existing material for covering of soft sections on E005 access | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 36 | 44359 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1Pickup Truck - Truck Only5125 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1Pickup Truck - Truck Only5125OEWT-PA18-Lem | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7002 | KL-20210601-1 | 53510812 | Access | 0 | Pickup Truck - Truck Only | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road and leveling ruts from 8907.01 WC to Hwy 17/Cleaning up old access road from E007 to E006 as new route was built | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD7002KL-20210601-1Pickup Truck - Truck Only23575 | KABI LAKE FOREST PRODUCTS LTD7002KL-20210601-1Pickup Truck - Truck Only23575OEWT-PA18-Lem | [5 empty] | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1153 | KL-20200225-3 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-02-25 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open 600 Road KM 10-15 | 9 | E-091-E102 | 600 rd | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1153KL-20200225-3Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD1153KL-20200225-3Pickup Truck - Truck Only12300OEWT-PA2-LEM-R1 | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1173 | KL-20200226-10 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-03-26 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 RD - Continue to plow road to gain access to 20KM | 9 | E091-E121 | 600 Road | 0 | 43894 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1173KL-20200226-10Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD1173KL-20200226-10Pickup Truck - Truck Only12300OEWT-PA3-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1178 | KL-20200227-3 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-02-27 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd winter road maintenance - continue to open 600 rd @ 22km | 9 | E091-E121 | 600 Road | 0 | 43894 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1178KL-20200227-3Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD1178KL-20200227-3Pickup Truck - Truck Only12300OEWT-PA3-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1184 | KL-20200228-3 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-02-28 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd - plow 600 rd for access @30km. | 9 | E091-E102 | 600 road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1184KL-20200228-3Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD1184KL-20200228-3Pickup Truck - Truck Only12300OEWT-PA3-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1189 | KL-20200229-3 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2020-02-29 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd - open 600 road to 32KM | 9 | E091-E102 | 600 Road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1189KL-20200229-3Pickup Truck - Truck Only9225 | KABI LAKE FOREST PRODUCTS LTD1189KL-20200229-3Pickup Truck - Truck Only9225OEWT-PA3-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1197 | KL-20200301-5 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-03-01 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow down 600 road pushing back banks at 22km | 9 | E091-E102 | 600 Road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1197KL-20200301-5Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD1197KL-20200301-5Pickup Truck - Truck Only10250OEWT-PA3-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1209 | KL-20200302-7 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-03-02 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 Road for access km 4 with grader and open sub roads at 2km | 9 | E-091 to E-102 | 600 Road | 0 | 43896 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1209KL-20200302-7Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD1209KL-20200302-7Pickup Truck - Truck Only10250OEWT-PA3-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3903 | KL-20201025-7 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-10-25 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Prep KM20 pit on 600 road for Sander | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 50 | 44134 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3903KL-20201025-7Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD3903KL-20201025-7Pickup Truck - Truck Only250OEWT-PA10-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4662 | KL-20201126-15 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sander for 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4662KL-20201126-15Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4662KL-20201126-15Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4686 | KL-20201127-12 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-27 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44180 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4686KL-20201127-12Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4686KL-20201127-12Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4722 | KL-20201130-5 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervise grader on 600, 700, and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4722KL-20201130-5Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4722KL-20201130-5Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4739 | KL-20201201-8 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders for 600, 700, 100, and Paint Lake 2 RDs. | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44202 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4739KL-20201201-8Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4739KL-20201201-8Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4777 | KL-20201202-20 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders for 600, 700, 100, and Paint Lake 2 Road. | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4777KL-20201202-20Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4777KL-20201202-20Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4844 | KL-20201212-9 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 & 700 Roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44208 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4844KL-20201212-9Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4844KL-20201212-9Pickup Truck - Truck Only10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4845 | KL-20201212-10 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervise Grading 600 & 700 Roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44208 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4845KL-20201212-10Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4845KL-20201212-10Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4907 | KL-20201205-10 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4907KL-20201205-10Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4907KL-20201205-10Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4921 | KL-20201206-8 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4921KL-20201206-8Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4921KL-20201206-8Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4937 | KL-20201207-12 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4937KL-20201207-12Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4937KL-20201207-12Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4938 | KL-20201207-13 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 and 700 roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4938KL-20201207-13Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4938KL-20201207-13Pickup Truck - Truck Only10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4939 | KL-20201207-14 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grader 600, 700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4939KL-20201207-14Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4939KL-20201207-14Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4951 | KL-20201208-9 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision Sanding 600, 700 and 100 road | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4951KL-20201208-9Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4951KL-20201208-9Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4952 | KL-20201208-10 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4952KL-20201208-10Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4952KL-20201208-10Pickup Truck - Truck Only10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4971 | KL-20201210-10 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders for 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4971KL-20201210-10Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4971KL-20201210-10Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4972 | KL-20201210-11 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of graders 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4972KL-20201210-11Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4972KL-20201210-11Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4973 | KL-20201210-12 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4973KL-20201210-12Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4973KL-20201210-12Pickup Truck - Truck Only10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4983 | KL-20201213-8 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4983KL-20201213-8Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4983KL-20201213-8Pickup Truck - Truck Only10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4984 | KL-20201213-9 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision Grade 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4984KL-20201213-9Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4984KL-20201213-9Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5099 | KL-20201217-7 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5099KL-20201217-7Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD5099KL-20201217-7Pickup Truck - Truck Only10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5100 | KL-20201217-8 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5100KL-20201217-8Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD5100KL-20201217-8Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5101 | KL-20201217-9 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5101KL-20201217-9Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD5101KL-20201217-9Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5128 | KL-20201221-3 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-21 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of grader on 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5128KL-20201221-3Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD5128KL-20201221-3Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5129 | KL-20201221-4 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-21 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader on 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5129KL-20201221-4Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD5129KL-20201221-4Pickup Truck - Truck Only10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5130 | KL-20201221-5 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2020-12-21 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Stripping km 6 Pit | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5130KL-20201221-5Pickup Truck - Truck Only7175 | KABI LAKE FOREST PRODUCTS LTD5130KL-20201221-5Pickup Truck - Truck Only7175OEWT-PA12-LEM-R1 | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5152 | KL-20201228-3 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44202 |  | 36 | 44213 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD5152KL-20201228-3Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD5152KL-20201228-3Pickup Truck - Truck Only10250OEWT-PA13-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5153 | KL-20201228-4 | 53510911 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading | 9 | E091-E102 | 600 Road | 0 | 44202 |  | 36 | 44213 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD5153KL-20201228-4Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD5153KL-20201228-4Pickup Truck - Truck Only125OEWT-PA13-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1538 | KL-20200520-9 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-05-20 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road to KM 30 | 9 | E091-E102 | 600 Road | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1538KL-20200520-9Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD1538KL-20200520-9Pickup Truck - Truck Only10250OEWT-PA5-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1538 | KL-20200520-9 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-05-20 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road to KM 30 | 9 | E091-E102 | 600 Road | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1538KL-20200520-9Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD1538KL-20200520-9Pickup Truck - Truck Only250OEWT-PA5-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1552 | KL-20200521-4 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-05-21 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road to 40 km | 9 | E091-E102 | 600 Road | 0 | 43977 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1552KL-20200521-4Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD1552KL-20200521-4Pickup Truck - Truck Only12300OEWT-PA5-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1559 | KL-20200519-3 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-05-19 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start grading 600 Road at Km 9 | 9 | E091-E102 | 600 Road | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1559KL-20200519-3Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD1559KL-20200519-3Pickup Truck - Truck Only12300OEWT-PA5-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1623 | KL-20200531-4 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2020-05-31 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unclogg cross drain culverts @13.5, 30.5, 34.2, and 39.5 kms | 9 | E091-E102 | 600 Road | 0 | 43985 |  | 42 | 43986 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-4Pickup Truck - Truck Only14350 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-4Pickup Truck - Truck Only14350OEWT-PA6-LEM | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1726 | KL-20200614-2 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-06-14 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Unclog cross drain culvert @ 13.5 Km on 600 Road. Ditching and shaping access to E-134. RV-40033 | 9 | E091-E102 | 600 Road | 0 | 44000 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-2Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-2Pickup Truck - Truck Only125OEWT-PA6-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1778 | KL-20200618-4 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-06-18 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road to 9 KM | 9 | E-091 to E-102 | 600 Road | 0 | 44005 |  | 15 | 44004 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1778KL-20200618-4Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD1778KL-20200618-4Pickup Truck - Truck Only125OEWT-PA6-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1795 | KL-20200619-5 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-06-19 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade sections on 100 Road to 5KM pit for Gravel Haul (2 hours) & 600 Road to 15KM (5 Hours) | 9 | E-091 to E-102 | 600 Road | 0 | 44006 |  | 15 | 44005 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1795KL-20200619-5Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD1795KL-20200619-5Pickup Truck - Truck Only125OEWT-PA6-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1829 | KL-20200622-4 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-06-22 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from 12m to 20km | 9 |  | 600 Road | 0 | 44007 |  | 15 | 44008 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1829KL-20200622-4Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD1829KL-20200622-4Pickup Truck - Truck Only10250OEWT-PA6-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1829 | KL-20200622-4 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-06-22 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from 12m to 20km | 9 |  | 600 Road | 0 | 44007 |  | 15 | 44008 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1829KL-20200622-4Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD1829KL-20200622-4Pickup Truck - Truck Only375OEWT-PA6-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1850 | KL-20200623-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-06-23 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road from 20 km to 26km | 9 |  | 600 Road | 0 | 44007 |  | 14 | 44009 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD1850KL-20200623-13Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD1850KL-20200623-13Pickup Truck - Truck Only10250OEWT-PA6-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1850 | KL-20200623-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-06-23 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road from 20 km to 26km | 9 |  | 600 Road | 0 | 44007 |  | 14 | 44009 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD1850KL-20200623-13Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD1850KL-20200623-13Pickup Truck - Truck Only250OEWT-PA6-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1864 | KL-20200624-14 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-06-24 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approver- William Ouiet, not in data base as of June 27th |  | Approved |  |  | Continue grading 600 road from 25km to 32 km | 9 |  | 600 Road | 0 | 44008 |  | 14 | 44011 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD1864KL-20200624-14Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD1864KL-20200624-14Pickup Truck - Truck Only10250OEWT-PA6-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1864 | KL-20200624-14 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-06-24 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approver- William Ouiet, not in data base as of June 27th |  | Approved |  |  | Continue grading 600 road from 25km to 32 km | 9 |  | 600 Road | 0 | 44008 |  | 14 | 44011 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD1864KL-20200624-14Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD1864KL-20200624-14Pickup Truck - Truck Only250OEWT-PA6-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1919 | KL-20200630-8 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-06-30 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from 31 Km to 40 Km | 9 |  | 600 Road | 0 | 44012 |  | 50 | 44015 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1919KL-20200630-8Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD1919KL-20200630-8Pickup Truck - Truck Only10250OEWT-PA7-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1919 | KL-20200630-8 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-06-30 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from 31 Km to 40 Km | 9 |  | 600 Road | 0 | 44012 |  | 50 | 44015 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1919KL-20200630-8Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD1919KL-20200630-8Pickup Truck - Truck Only250OEWT-PA7-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1963 | KL-20200708-10 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-07-08 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Backup - pickup 12 hrs, only allowed 10 - charged for only 10 on LEM |  | Approved |  |  | Grade 600 Road from 9km to 17km | 9 | E-091 to E-102 | 600 Road | 0 | 44025 |  | 50 | 44026 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1963KL-20200708-10Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD1963KL-20200708-10Pickup Truck - Truck Only10250OEWT-PA7-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1963 | KL-20200708-10 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-07-08 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Backup - pickup 12 hrs, only allowed 10 - charged for only 10 on LEM |  | Approved |  |  | Grade 600 Road from 9km to 17km | 9 | E-091 to E-102 | 600 Road | 0 | 44025 |  | 50 | 44026 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1963KL-20200708-10Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD1963KL-20200708-10Pickup Truck - Truck Only250OEWT-PA7-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1973 | KL-20200702-9 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-07-02 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from 47km to 51km | 9 | E-091 to E-102 | 600 Road | 0 | 44021 |  | 50 | 44027 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1973KL-20200702-9Pickup Truck - Truck Only5125 | KABI LAKE FOREST PRODUCTS LTD1973KL-20200702-9Pickup Truck - Truck Only5125OEWT-PA7-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1973 | KL-20200702-9 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-07-02 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from 47km to 51km | 9 | E-091 to E-102 | 600 Road | 0 | 44021 |  | 50 | 44027 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1973KL-20200702-9Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD1973KL-20200702-9Pickup Truck - Truck Only125OEWT-PA7-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2004 | KL-20200711-10 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10Pickup Truck - Truck Only125OEWT-PA7-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2004 | KL-20200711-10 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10Pickup Truck - Truck Only10250OEWT-PA7-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2005 | KL-20200711-11 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road from Km17 to Km23 | 9 | E-091 to E-102 | 600 Road` | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2005KL-20200711-11Pickup Truck - Truck Only8.5212.5 | KABI LAKE FOREST PRODUCTS LTD2005KL-20200711-11Pickup Truck - Truck Only8.5212.5OEWT-PA7-LEM | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2005 | KL-20200711-11 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road from Km17 to Km23 | 9 | E-091 to E-102 | 600 Road` | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2005KL-20200711-11Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD2005KL-20200711-11Pickup Truck - Truck Only125OEWT-PA7-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2029 | KL-20200713-7 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-07-13 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44029 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7Pickup Truck - Truck Only125OEWT-PA7-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2029 | KL-20200713-7 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-07-13 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44029 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7Pickup Truck - Truck Only10250OEWT-PA7-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2099 | KL-20200717-11 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade E106 Access Road | 9 | E091-E106 | 600 Road | 0 | 44034 |  | 15 | 44034 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2099KL-20200717-11Pickup Truck - Truck Only4100 | KABI LAKE FOREST PRODUCTS LTD2099KL-20200717-11Pickup Truck - Truck Only4100OEWT-PA7-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2128 | KL-20200701-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-07-01 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road from 40km to 47km | 9 | E-091 to E-102 | 600 Road | 0 | 44019 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2128KL-20200701-12Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD2128KL-20200701-12Pickup Truck - Truck Only250OEWT-PA7-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2128 | KL-20200701-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-07-01 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road from 40km to 47km | 9 | E-091 to E-102 | 600 Road | 0 | 44019 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2128KL-20200701-12Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD2128KL-20200701-12Pickup Truck - Truck Only10250OEWT-PA7-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2176 | KL-20200703-1 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-07-03 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade AU1 Access to E-126/E-124 | 9 | E-091 to E-102 | 600 road | 0 | 44020 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2176KL-20200703-1Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD2176KL-20200703-1Pickup Truck - Truck Only375OEWT-PA7-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2176 | KL-20200703-1 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-07-03 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade AU1 Access to E-126/E-124 | 9 | E-091 to E-102 | 600 road | 0 | 44020 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2176KL-20200703-1Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD2176KL-20200703-1Pickup Truck - Truck Only125OEWT-PA7-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2180 | KL-20200703-5 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 5.5 | HR | 19 | 0 |  |  | 137.5 | 17.875 | 155.375 | 2020-07-03 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from 2 Km to 9 Km | 9 | E-091 to E-102 | 600 Road | 0 | 44020 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2180KL-20200703-5Pickup Truck - Truck Only5.5137.5 | KABI LAKE FOREST PRODUCTS LTD2180KL-20200703-5Pickup Truck - Truck Only5.5137.5OEWT-PA7-LEM | [5 empty] | 1 | 137.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2180 | KL-20200703-5 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-07-03 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from 2 Km to 9 Km | 9 | E-091 to E-102 | 600 Road | 0 | 44020 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2180KL-20200703-5Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD2180KL-20200703-5Pickup Truck - Truck Only125OEWT-PA7-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2237 | KL-20200723-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-07-23 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Road from Hwy to Km 10 | 9 | E-091 to E-102 | 600 Road | 0 | 44040 |  | 15 | 44040 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2237KL-20200723-13Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD2237KL-20200723-13Pickup Truck - Truck Only10250OEWT-PA7-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2237 | KL-20200723-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-07-23 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Road from Hwy to Km 10 | 9 | E-091 to E-102 | 600 Road | 0 | 44040 |  | 15 | 44040 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2237KL-20200723-13Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD2237KL-20200723-13Pickup Truck - Truck Only250OEWT-PA7-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2464 | KL-20200817-4 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-08-17 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44063 |  | 15 | 44064 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2464KL-20200817-4Pickup Truck - Truck Only11275 | KABI LAKE FOREST PRODUCTS LTD2464KL-20200817-4Pickup Truck - Truck Only11275OEWT-PA8-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2565 | KL-20200823-6 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-08-23 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance work from E-165 to E-167 | 9 | E-091 to E-102 | 600 Road | 0 | 44068 |  | 15 | 44071 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2565KL-20200823-6Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD2565KL-20200823-6Pickup Truck - Truck Only375OEWT-PA8-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2565 | KL-20200823-6 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-08-23 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance work from E-165 to E-167 | 9 | E-091 to E-102 | 600 Road | 0 | 44068 |  | 15 | 44071 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2565KL-20200823-6Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD2565KL-20200823-6Pickup Truck - Truck Only125OEWT-PA8-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2585 | KL-20200824-6 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-08-24 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road from 9 to 13 Km | 9 | E-091 to E-102 | 600 Road | 0 | 44069 |  | 15 | 44071 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2585KL-20200824-6Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD2585KL-20200824-6Pickup Truck - Truck Only125OEWT-PA8-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2585 | KL-20200824-6 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-08-24 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road from 9 to 13 Km | 9 | E-091 to E-102 | 600 Road | 0 | 44069 |  | 15 | 44071 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2585KL-20200824-6Pickup Truck - Truck Only5125 | KABI LAKE FOREST PRODUCTS LTD2585KL-20200824-6Pickup Truck - Truck Only5125OEWT-PA8-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2597 | KL-20200825-6 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-08-25 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44072 |  | 15 | 44074 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2597KL-20200825-6Pickup Truck - Truck Only11275 | KABI LAKE FOREST PRODUCTS LTD2597KL-20200825-6Pickup Truck - Truck Only11275OEWT-PA8-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2605 | KL-20200827-2 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-27 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to 9km | 9 | E091-E102 | 600 Road | 0 | 44074 |  | 15 | 44075 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2605KL-20200827-2Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD2605KL-20200827-2Pickup Truck - Truck Only13325OEWT-PA9-Lem-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2606 | KL-20200828-1 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-08-28 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to 14km | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 15 | 44077 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2606KL-20200828-1Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD2606KL-20200828-1Pickup Truck - Truck Only10250OEWT-PA9-Lem-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2612 | KL-20200829-3 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-29 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 15 | 44077 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2612KL-20200829-3Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD2612KL-20200829-3Pickup Truck - Truck Only13325OEWT-PA9-Lem-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2618 | KL-20200830-1 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-30 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 47 | 44077 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2618KL-20200830-1Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD2618KL-20200830-1Pickup Truck - Truck Only13325OEWT-PA9-Lem-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2736 | KL-20200907-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-09-07 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44089 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2736KL-20200907-13Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD2736KL-20200907-13Pickup Truck - Truck Only375OEWT-PA9-Lem-R1 | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2736 | KL-20200907-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-09-07 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44089 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2736KL-20200907-13Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD2736KL-20200907-13Pickup Truck - Truck Only8200OEWT-PA9-Lem-R1 | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2754 | KL-20200908-15 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2020-09-08 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44089 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2754KL-20200908-15Pickup Truck - Truck Only23575 | KABI LAKE FOREST PRODUCTS LTD2754KL-20200908-15Pickup Truck - Truck Only23575OEWT-PA9-Lem-R1 | [5 empty] | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2778 | KL-20200909-19 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2020-09-09 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44092 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2778KL-20200909-19Pickup Truck - Truck Only23575 | KABI LAKE FOREST PRODUCTS LTD2778KL-20200909-19Pickup Truck - Truck Only23575OEWT-PA9-Lem-R1 | [5 empty] | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2802 | KL-20200910-18 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2020-09-10 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44091 |  | 15 | 44094 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2802KL-20200910-18Pickup Truck - Truck Only23575 | KABI LAKE FOREST PRODUCTS LTD2802KL-20200910-18Pickup Truck - Truck Only23575OEWT-PA9-Lem-R1 | [5 empty] | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2853 | KL-20200911-20 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2020-09-11 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44094 |  | 15 | 44095 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20Pickup Truck - Truck Only18450 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20Pickup Truck - Truck Only18450OEWT-PA9-Lem-R1 | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2932 | KL-20200915-3 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of CDSL Logging Inc. for cross drain installs and fixing access roads. Cress floating equipment to 600 Rd | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44097 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2932KL-20200915-3Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD2932KL-20200915-3Pickup Truck - Truck Only375OEWT-PA9-Lem-R1 | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2937 | KL-20200915-8 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44097 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2937KL-20200915-8Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD2937KL-20200915-8Pickup Truck - Truck Only375OEWT-PA9-Lem-R1 | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2968 | KL-20200916-11 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 20 | HR | 19 | 0 |  |  | 500 | 65 | 565 | 2020-09-16 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2968KL-20200916-11Pickup Truck - Truck Only20500 | KABI LAKE FOREST PRODUCTS LTD2968KL-20200916-11Pickup Truck - Truck Only20500OEWT-PA9-Lem-R1 | [5 empty] | 1 | 500 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2996 | KL-20200917-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-09-17 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44097 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2996KL-20200917-13Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD2996KL-20200917-13Pickup Truck - Truck Only13325OEWT-PA9-Lem-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2997 | KL-20200917-14 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2020-09-17 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scale pit at 690 | 9 | E-091 to E-102 | 600 Road | 0 | 44097 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2997KL-20200917-14Pickup Truck - Truck Only14350 | KABI LAKE FOREST PRODUCTS LTD2997KL-20200917-14Pickup Truck - Truck Only14350OEWT-PA9-Lem-R1 | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3036 | KL-20200918-16 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-09-18 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | KL-20200918-16 | 600 Road | 0 | 44098 |  | 15 | 44099 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3036KL-20200918-16Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD3036KL-20200918-16Pickup Truck - Truck Only13325OEWT-PA9-Lem-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3059 | KL-20200920-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-09-20 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44099 |  | 15 | 44101 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3059KL-20200920-12Pickup Truck - Truck Only11275 | KABI LAKE FOREST PRODUCTS LTD3059KL-20200920-12Pickup Truck - Truck Only11275OEWT-PA9-Lem-R1 | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3131 | KL-20200922-16 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-09-22 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44103 |  | 15 | 44103 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3131KL-20200922-16Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD3131KL-20200922-16Pickup Truck - Truck Only13325OEWT-PA9-Lem-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3171 | KL-20200923-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-09-23 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44103 |  | 15 | 44104 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3171KL-20200923-12Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD3171KL-20200923-12Pickup Truck - Truck Only13325OEWT-PA9-Lem-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3268 | KL-20200927-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 43900 |  | 53 | 43900 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD3268KL-20200927-12Pickup Truck - Truck Only5125 | KABI LAKE FOREST PRODUCTS LTD3268KL-20200927-12Pickup Truck - Truck Only5125OEWT-PA10-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3487 | KL-20201005-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12Pickup Truck - Truck Only12300OEWT-PA10-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3517 | KL-20201006-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2020-10-06 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44124 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3517KL-20201006-13Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD3517KL-20201006-13Pickup Truck - Truck Only22550OEWT-PA10-LEM | [5 empty] | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3555 | KL-20201007-10 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-10-07 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Buncher from E110 to 650 pit and back to E139 | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3555KL-20201007-10Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD3555KL-20201007-10Pickup Truck - Truck Only125OEWT-PA10-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3598 | KL-20201008-18 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-10-08 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3598KL-20201008-18Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD3598KL-20201008-18Pickup Truck - Truck Only12300OEWT-PA10-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3599 | KL-20201008-19 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-10-08 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Stripping 650 pit | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3599KL-20201008-19Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD3599KL-20201008-19Pickup Truck - Truck Only12300OEWT-PA10-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3623 | KL-20201009-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix road and spread loads between E173 and E172, Haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12Pickup Truck - Truck Only18450 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12Pickup Truck - Truck Only18450OEWT-PA10-LEM | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3624 | KL-20201009-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13Pickup Truck - Truck Only18450 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13Pickup Truck - Truck Only18450OEWT-PA10-LEM | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3647 | KL-20201010-11 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3647KL-20201010-11Pickup Truck - Truck Only11275 | KABI LAKE FOREST PRODUCTS LTD3647KL-20201010-11Pickup Truck - Truck Only11275OEWT-PA10-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3648 | KL-20201010-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 24 | HR | 19 | 0 |  |  | 600 | 78 | 678 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix rds, spread loads between E-173, E-172 and haul gravel to E-168/E-171and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-12Pickup Truck - Truck Only24600 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-12Pickup Truck - Truck Only24600OEWT-PA10-LEM | [5 empty] | 1 | 600 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3671 | KL-20201011-11 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 44 | HR | 19 | 0 |  |  | 1100 | 143 | 1243 | 2020-10-11 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix road and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44157 |  | 15 | 44131 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-11Pickup Truck - Truck Only441100 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-11Pickup Truck - Truck Only441100OEWT-PA10-LEM | [5 empty] | 1 | 1100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3691 | KL-20201012-9 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float and use log loader to unclog culverts @ 49km on 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-9Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-9Pickup Truck - Truck Only250OEWT-PA10-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3698 | KL-20201012-16 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 40 | HR | 19 | 0 |  |  | 1000 | 130 | 1130 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3698KL-20201012-16Pickup Truck - Truck Only401000 | KABI LAKE FOREST PRODUCTS LTD3698KL-20201012-16Pickup Truck - Truck Only401000OEWT-PA10-LEM | [5 empty] | 1 | 1000 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3699 | KL-20201012-17 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 gravel haul and road maintenance | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3699KL-20201012-17Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD3699KL-20201012-17Pickup Truck - Truck Only10250OEWT-PA10-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3717 | KL-20201013-11 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 20 | HR | 19 | 0 |  |  | 500 | 65 | 565 | 2020-10-13 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3717KL-20201013-11Pickup Truck - Truck Only20500 | KABI LAKE FOREST PRODUCTS LTD3717KL-20201013-11Pickup Truck - Truck Only20500OEWT-PA10-LEM | [5 empty] | 1 | 500 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3741 | KL-20201014-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 32 | HR | 19 | 0 |  |  | 800 | 104 | 904 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy, install cross drain at F6. | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-12Pickup Truck - Truck Only32800 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-12Pickup Truck - Truck Only32800OEWT-PA10-LEM | [5 empty] | 1 | 800 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3743 | KL-20201014-14 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3743KL-20201014-14Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD3743KL-20201014-14Pickup Truck - Truck Only10250OEWT-PA10-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3765 | KL-20201015-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 40 | HR | 19 | 0 |  |  | 1000 | 130 | 1130 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit and 25km pit, fix roads and hauled gravel to E168-E171 and spread over Corduroy, pile up gravel at Km33 | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3765KL-20201015-13Pickup Truck - Truck Only401000 | KABI LAKE FOREST PRODUCTS LTD3765KL-20201015-13Pickup Truck - Truck Only401000OEWT-PA10-LEM | [5 empty] | 1 | 1000 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3767 | KL-20201015-15 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3767KL-20201015-15Pickup Truck - Truck Only5125 | KABI LAKE FOREST PRODUCTS LTD3767KL-20201015-15Pickup Truck - Truck Only5125OEWT-PA10-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3770 | KL-20201015-18 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3770KL-20201015-18Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD3770KL-20201015-18Pickup Truck - Truck Only10250OEWT-PA10-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3845 | KL-20201019-10 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-10-19 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44133 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3845KL-20201019-10Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD3845KL-20201019-10Pickup Truck - Truck Only13325OEWT-PA10-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3857 | KL-20201020-6 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-20 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44131 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3857KL-20201020-6Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD3857KL-20201020-6Pickup Truck - Truck Only10250OEWT-PA10-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3877 | KL-20201021-6 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-21 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44131 |  | 15 | 44133 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3877KL-20201021-6Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD3877KL-20201021-6Pickup Truck - Truck Only10250OEWT-PA10-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3886 | KL-20201023-5 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-23 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 50 | 44134 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3886KL-20201023-5Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD3886KL-20201023-5Pickup Truck - Truck Only10250OEWT-PA10-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3888 | KL-20201023-7 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2020-10-23 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 50 | 44134 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3888KL-20201023-7Pickup Truck - Truck Only7175 | KABI LAKE FOREST PRODUCTS LTD3888KL-20201023-7Pickup Truck - Truck Only7175OEWT-PA10-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3914 | KL-20201022-7 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-22 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 15 | 44134 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3914KL-20201022-7Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD3914KL-20201022-7Pickup Truck - Truck Only10250OEWT-PA10-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4048 | KL-20201029-14 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-29 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4048KL-20201029-14Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4048KL-20201029-14Pickup Truck - Truck Only10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4164 | KL-20201104-19 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-04 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Rd | 9 | E091-E102 | 600 Road | 0 | 44160 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4164KL-20201104-19Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4164KL-20201104-19Pickup Truck - Truck Only10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4183 | KL-20201105-17 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-05 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road , 700 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44160 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4183KL-20201105-17Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4183KL-20201105-17Pickup Truck - Truck Only10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4199 | KL-20201106-11 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-11-06 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44162 |  | 48 | 44162 | [5 empty] | Larse Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4199KL-20201106-11Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD4199KL-20201106-11Pickup Truck - Truck Only8200OEWT-PA11-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4237 | KL-20201108-16 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-08 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44162 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4237KL-20201108-16Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4237KL-20201108-16Pickup Truck - Truck Only10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4263 | KL-20201109-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-09 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44164 |  | 15 | 44171 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4263KL-20201109-12Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4263KL-20201109-12Pickup Truck - Truck Only10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4288 | KL-20201103-17 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 700 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 50 | 44167 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4288KL-20201103-17Pickup Truck - Truck Only18450 | KABI LAKE FOREST PRODUCTS LTD4288KL-20201103-17Pickup Truck - Truck Only18450OEWT-PA11-LEM | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4298 | KL-20201110-8 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-10 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Rd 2 graders | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44168 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4298KL-20201110-8Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4298KL-20201110-8Pickup Truck - Truck Only10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4299 | KL-20201110-9 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-11-10 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load 1 roll of Geo @ Kabi Laydown & Deliver @ E-139 | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 50 | 44168 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4299KL-20201110-9Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD4299KL-20201110-9Pickup Truck - Truck Only375OEWT-PA11-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4316 | KL-20201111-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-11 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44170 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4316KL-20201111-12Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4316KL-20201111-12Pickup Truck - Truck Only10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4329 | KL-20201112-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-11-12 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44168 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4329KL-20201112-12Pickup Truck - Truck Only11275 | KABI LAKE FOREST PRODUCTS LTD4329KL-20201112-12Pickup Truck - Truck Only11275OEWT-PA11-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4340 | KL-20201113-8 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-13 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd and 100rd | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44170 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4340KL-20201113-8Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4340KL-20201113-8Pickup Truck - Truck Only10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4359 | KL-20201114-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float D6 from F9 to E168 to shape roads | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4359KL-20201114-12Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4359KL-20201114-12Pickup Truck - Truck Only125OEWT-PA11-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4360 | KL-20201114-13 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4360KL-20201114-13Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD4360KL-20201114-13Pickup Truck - Truck Only10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4635 | KL-20201125-12 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders For 600 700 and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4635KL-20201125-12Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4635KL-20201125-12Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4638 | KL-20201125-15 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of grader 600, 700, and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4638KL-20201125-15Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4638KL-20201125-15Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6903 | KL-20210511-3 | 53510912 | Access | 0 | Pickup Truck - Truck Only | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2021-05-11 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 250 link belt log loader from mill yard to 13km on 600 road/unplug culvert and float log loader back to mill yard | 9 | E091-E102 | 600 Road | 0 | 44337 |  | 56 | 44341 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-3Pickup Truck - Truck Only3.587.5 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-3Pickup Truck - Truck Only3.587.5OEWT-PA17-LEM | [5 empty] | 1 | 87.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511003 | Access | 0 | Pickup Truck - Truck Only | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1Pickup Truck - Truck Only17425 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1Pickup Truck - Truck Only17425OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 217.8892 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7200 | KL-20210804-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-04 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load existing material from 17Km on Hensen Road & Gravel road sections @ 46/45Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7201 | KL-20210808-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-08 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. 1 Kabi Rock Truck & 2 Valard Rock Trucks Hauling | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7202 | KL-20210805-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-05 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 45/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7204 | KL-20210806-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-06 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7207 | KL-20210809-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-09 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7211 | KL-20210810-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-10 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7212 | KL-20210811-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-11 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 45/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/2 Valard Rock truck. Continue grading Paint Lake Road 2 from Km 7.5 to Km 11.5 - SSF-14324 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7213 | KL-20210812-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-08-12 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel access mat sections @ 45/44 km on Paint Lake Road 2/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on Valard 2nd rock truck. Finish grading Paint Lake Road 2 to Km 13 and touch up on way out to Paint Lake Road - SSF-14325 | 10 | F033-F118 | Paint ake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1Pickup Truck - Truck Only13325OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7214 | KL-20210813-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-13 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7215 | KL-20210814-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-14 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7218 | KL-20210815-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-15 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7221 | KL-20210816-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-08-16 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1Pickup Truck - Truck Only21525 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1Pickup Truck - Truck Only21525OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 525 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7224 | KL-20210817-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-17 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/46 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1Pickup Truck - Truck Only22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-09-11 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Pickup Truck - Truck Only9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Pickup Truck - Truck Only9.5237.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.71555 | 169.9431 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-09-11 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Pickup Truck - Truck Only8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Pickup Truck - Truck Only8.5212.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.71555 | 152.0543 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-09-11 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Pickup Truck - Truck Only9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Pickup Truck - Truck Only9.5237.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.71555 | 169.9431 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-09-11 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Pickup Truck - Truck Only14350 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Pickup Truck - Truck Only14350OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.71555 | 250.4424 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 18.5 | HR | 19 | 0 |  |  | 462.5 | 60.125 | 522.625 | 2021-09-16 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Pickup Truck - Truck Only18.5462.5 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Pickup Truck - Truck Only18.5462.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.76183 | 352.3444 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 17.5 | HR | 19 | 0 |  |  | 437.5 | 56.875 | 494.375 | 2021-09-16 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Pickup Truck - Truck Only17.5437.5 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Pickup Truck - Truck Only17.5437.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.76183 | 333.2988 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511004 | Access | 0 | Pickup Truck - Truck Only | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1Pickup Truck - Truck Only18450 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1Pickup Truck - Truck Only18450OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 230.7063 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4896 | KL-20201204-19 | 53511011 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-04 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervise float truck. Picked up 20 ' bridge mats in Marathon for Paint Lake 2 Rd | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4896KL-20201204-19Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4896KL-20201204-19Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5143 | KL-20201222-6 | 53511011 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-22 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake 2 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44200 |  | 56 | 44213 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5143KL-20201222-6Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD5143KL-20201222-6Pickup Truck - Truck Only10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5703 | KL-20210131-2 | 53511011 | Access | 0 | Pickup Truck - Truck Only | 25 | 2.5 | HR | 19 | 0 |  |  | 62.5 | 8.125 | 70.625 | 2021-01-31 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator making safety berm and sanding hill on F143 access | 11 | F135-F149 | Dore Lake Road | 0 | 44235 |  | 56 | 44236 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5703KL-20210131-2Pickup Truck - Truck Only2.562.5 | KABI LAKE FOREST PRODUCTS LTD5703KL-20210131-2Pickup Truck - Truck Only2.562.5OEWT-PA14-Lem-R1 | [5 empty] | 1 | 62.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6101 | KL-20210226-11 | 53511011 | Access | 0 | Pickup Truck - Truck Only | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, load and haul gravel, sand rd, unload and move legos, skid and place corduroy,Buncher was cutting wood and tracking wood to place on road | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44262 |  | 57 | 44277 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6101KL-20210226-11Pickup Truck - Truck Only18450 | KABI LAKE FOREST PRODUCTS LTD6101KL-20210226-11Pickup Truck - Truck Only18450OEWT PA15-LEM | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6109 | KL-20210227-7 | 53511011 | Access | 0 | Pickup Truck - Truck Only | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-02-27 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, sand road. Skid corduroy, move mats, place corduroy. | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44262 |  | 57 | 44266 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6109KL-20210227-7Pickup Truck - Truck Only9225 | KABI LAKE FOREST PRODUCTS LTD6109KL-20210227-7Pickup Truck - Truck Only9225OEWT-PA16-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6129 | KL-20210301-5 | 53511011 | Access | 0 | Pickup Truck - Truck Only | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, sand road, skid corduroy, placing corduroy, cut bundles in half | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44263 |  | 57 | 44266 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6129KL-20210301-5Pickup Truck - Truck Only6150 | KABI LAKE FOREST PRODUCTS LTD6129KL-20210301-5Pickup Truck - Truck Only6150OEWT PA15-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7897 | KL-20220217-2 | 53511011 | Access | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from Paint Lake Road 2, work on snow removal from F021 to F032 after hours and run grader back to Paint Lake Road 2 / Supervisor stayed after hours due to Operator working alone | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7897KL-20220217-2Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD7897KL-20220217-2Pickup Truck - Truck Only8200OEWT-PA26-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3130 | KL-20200922-15 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-09-22 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR Contracting for unloading Bridge and fixing wet areas on Paint Lake Road | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44103 |  | 15 | 44103 | [5 empty] | Martin Hunt | 10 | KABI LAKE FOREST PRODUCTS LTD3130KL-20200922-15Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD3130KL-20200922-15Pickup Truck - Truck Only250OEWT-PA9-Lem-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3780 | KL-20201015-27 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Take broken 3" pump to Marathon Valard Yard | 10 | F-021 to F-032 | Paint Lake Raod 1-B | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD3780KL-20201015-27Pickup Truck - Truck Only4100 | KABI LAKE FOREST PRODUCTS LTD3780KL-20201015-27Pickup Truck - Truck Only4100OEWT-PA10-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4050 | KL-20201029-16 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-10-29 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervisor of WF 10 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4050KL-20201029-16Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD4050KL-20201029-16Pickup Truck - Truck Only8200OEWT-PA11-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4177 | KL-20201105-11 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-11-05 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of CDSL logging and JJR | 10 | F033-F118 | Paint lake Road 2 | 0 | 44160 |  | 50 | 44163 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4177KL-20201105-11Pickup Truck - Truck Only4100 | KABI LAKE FOREST PRODUCTS LTD4177KL-20201105-11Pickup Truck - Truck Only4100OEWT-PA11-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7001 | KL-20210531-3 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on road maintenance and drainage from Km 16.5 to Km 19 /grader working on Paint Lake Road 2 from Km 12 to KM4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 36 | 44360 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-3Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-3Pickup Truck - Truck Only13325OEWT-PA18-Lem | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7004 | KL-20210601-3 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator continue working on road maintenance and drainage from km 17 to km 18/ Grader finishing on Paint Lake Road 2 to Km 0 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-3Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-3Pickup Truck - Truck Only13325OEWT-PA18-Lem | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 34.5 | HR | 19 | 0 |  |  | 862.5 | 112.125 | 974.625 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1Pickup Truck - Truck Only34.5862.5 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1Pickup Truck - Truck Only34.5862.5OEWT-PA22-Lem | [5 empty] | 1 | 862.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 15 | HR | 19 | 0 |  |  | 375 | 48.75 | 423.75 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1Pickup Truck - Truck Only15375 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1Pickup Truck - Truck Only15375OEWT-PA22-Lem | [5 empty] | 1 | 375 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7482 | KL-20211022-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 37 | HR | 19 | 0 |  |  | 925 | 120.25 | 1045.25 | 2021-10-22 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 working from Km 43 to Km 40 and F105 access Shaping road/ excavator 2 working from Km 43 to Km 45 and F111 shaping road. Excavator 3 Finishing @ F115 to F117 leveling ruts,shaping for freezing and track to F123/ Supervision of Morin, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-1Pickup Truck - Truck Only37925 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-1Pickup Truck - Truck Only37925OEWT-PA22-Lem | [5 empty] | 1 | 925 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1Pickup Truck - Truck Only9225 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1Pickup Truck - Truck Only9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1Pickup Truck - Truck Only9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1Pickup Truck - Truck Only9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1Pickup Truck - Truck Only9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1Pickup Truck - Truck Only9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1Pickup Truck - Truck Only8200OEWT-PA23-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3631 | KL-20201009-20 | 53511102 | Access | 0 | Pickup Truck - Truck Only | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Shaping Road and Widing Areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44125 |  | 55 | 44129 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3631KL-20201009-20Pickup Truck - Truck Only9225 | KABI LAKE FOREST PRODUCTS LTD3631KL-20201009-20Pickup Truck - Truck Only9225OEWT-PA10-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5516 | KL-20210121-15 | 53511102 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator Operator Extra Travel to F145 MFN Road Building/Based out of White River. | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5516KL-20210121-15Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD5516KL-20210121-15Pickup Truck - Truck Only125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3605 | KL-20201008-25 | 53511103 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-10-08 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Newbold gravel for Culvert instal. Install 2 cross drains culverts on AU1 Access | 11 | F-119 to F-134 | Hensen Road | 0 | 44125 |  | 55 | 44129 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3605KL-20201008-25Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD3605KL-20201008-25Pickup Truck - Truck Only125OEWT-PA10-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5339 | KL-20210113-5 | 53511103 | Access | 0 | Pickup Truck - Truck Only | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy at F132 access | 11 | F119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5339KL-20210113-5Pickup Truck - Truck Only4100 | KABI LAKE FOREST PRODUCTS LTD5339KL-20210113-5Pickup Truck - Truck Only4100OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3273 | KL-20200927-17 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit runfrom Provost pit #5/Dozer spreading | 11 | F-119 to F-134 | Hensen Road | 0 | 43900 |  | 48 | 43871 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17Pickup Truck - Truck Only13325OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3274 | KL-20200927-18 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Gord Enders Trucking gravel haul | 11 | F-119 to F-134 | Hensen Road | 0 | 43900 |  | 48 | 43871 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3274KL-20200927-18Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD3274KL-20200927-18Pickup Truck - Truck Only375OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3334 | KL-20200929-25 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-09-29 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR Contracting Gravel Haul | 11 | F119-F134 | Hensen Road | 0 | 44109 |  | 50 | 44115 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3334KL-20200929-25Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD3334KL-20200929-25Pickup Truck - Truck Only250OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3376 | KL-20201001-22 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Triaxles hauling Pit Run from Provost pit #5 , Dozer spreading and widening areas.Grade Hensen road for gravel Haul - SSF-14029.Haul Pit Run from Provost Pit #5 to AE1 on Hensen Road - JJR-70095. Hauled Gravel to Hensen Road from Provost Pit #5 - BMC-30121 | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22Pickup Truck - Truck Only13325OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3379 | KL-20201001-25 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR Contracting Gravel haul | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3379KL-20201001-25Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD3379KL-20201001-25Pickup Truck - Truck Only250OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24Pickup Truck - Truck Only13325OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3405 | KL-20201002-25 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR contracting Gravel haul | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3405KL-20201002-25Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD3405KL-20201002-25Pickup Truck - Truck Only250OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3406 | KL-20201002-26 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of CBT Excavating Gravel haul | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3406KL-20201002-26Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD3406KL-20201002-26Pickup Truck - Truck Only250OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3411 | KL-20200930-19 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer spreading Pit Run from Provost Pit #5 and widening areas. Trucks hauling gravel from Provost Pit | 11 | F-119 to F-134 | Hensen Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-19Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-19Pickup Truck - Truck Only375OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3413 | KL-20200930-21 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR Contracting Gravel Haul | 11 | F-119 to F-134 | Hensen Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3413KL-20200930-21Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD3413KL-20200930-21Pickup Truck - Truck Only250OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3831 | KL-20201018-15 | 53511104 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-10-18 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauled 2 load pit run from Provost pit 5 to Km 3 on hensen road Culverts. Cress install cross drain culverts. 330 excavator installed 3 200mm culverts, Km 6.5, 4.5, 2 - A lot of travelling with Machine -travelled Km 10 to 2 - CR-10821 | 11 | F-119 to F-134 | Hensen Road | 0 | 44130 |  | 55 | 44132 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3831KL-20201018-15Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD3831KL-20201018-15Pickup Truck - Truck Only125OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4713 | KL-20201129-14 | 53511111 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervisor of Grading on Paint Lake 2 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD4713KL-20201129-14Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD4713KL-20201129-14Pickup Truck - Truck Only125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5160 | KL-20201228-11 | 53511111 | Access | 0 | Pickup Truck - Truck Only | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Hills & Corners on Hensen Rd from Hwy to Km 17 for 60' bridge delivery. Dozer and grader clearing different sections of Hensen Rd. | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44214 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-11Pickup Truck - Truck Only125 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-11Pickup Truck - Truck Only125OEWT-PA13-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5700 | KL-20210201-8 | 53511111 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-02-01 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drive from White River/Load Screened sand from Provost Pit #5/Sand hills and corners to 17km on hensen road/drive back to White River | 11 | F119-F134 | Hensen Road | 0 | 44235 |  | 53 | 44241 | [5 empty] | Clint Maerz | 11 | KABI LAKE FOREST PRODUCTS LTD5700KL-20210201-8Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD5700KL-20210201-8Pickup Truck - Truck Only250OEWT-PA14-Lem-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6096 | KL-20210226-6 | 53511111 | Access | 0 | Pickup Truck - Truck Only | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to Hensen Road and steamed pipe at Km 3.6 and install heat trace top | 11 | F119-F134 | Hensen Road | 0 | 44262 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6096KL-20210226-6Pickup Truck - Truck Only14350 | KABI LAKE FOREST PRODUCTS LTD6096KL-20210226-6Pickup Truck - Truck Only14350OEWT PA15-LEM | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6100 | KL-20210226-10 | 53511111 | Access | 0 | Pickup Truck - Truck Only | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking to F212 access pushing snow back and clearing pull outs. Excavator brushing AE1 Access for F-228 and F-212 | 11 | F-212 to F-214 | Michipicoten Road- 1 | 0 | 44262 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-10Pickup Truck - Truck Only11275 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-10Pickup Truck - Truck Only11275OEWT PA15-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6124 | KL-20210228-10 | 53511111 | Access | 0 | Pickup Truck - Truck Only | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-02-28 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue snow removal on AE1 access to F212 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44263 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6124KL-20210228-10Pickup Truck - Truck Only7175 | KABI LAKE FOREST PRODUCTS LTD6124KL-20210228-10Pickup Truck - Truck Only7175OEWT PA15-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6140 | KL-20210222-14 | 53511111 | Access | 0 | Pickup Truck - Truck Only | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing roads km20 to km15, loader clearing km 0 to 5 Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44269 |  | 56 | 44270 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14Pickup Truck - Truck Only250 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14Pickup Truck - Truck Only250OEWT PA15-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7645 | KL-20211206-4 | 53511111 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F175 to F171 and from F185 to F193/ Grader working on High Falls Road and to F203 | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4Pickup Truck - Truck Only10250OEWT-PA24-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7645 | KL-20211206-4 | 53511111 | Access | 0 | Pickup Truck - Truck Only | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F175 to F171 and from F185 to F193/ Grader working on High Falls Road and to F203 | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4Pickup Truck - Truck Only4100 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4Pickup Truck - Truck Only4100OEWT-PA24-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7645 | KL-20211206-4 | 53511111 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F175 to F171 and from F185 to F193/ Grader working on High Falls Road and to F203 | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4Pickup Truck - Truck Only375OEWT-PA24-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3014 | KL-20200919-10-R1 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-09-19 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up 500mm cross drain in Marathon and deliver to Michipicoten Harbour Road-5 F159. Corduroy road @ F-160. | 11 | F-159 to F-160 | Michipicoten Harbour Road -5 | 0 | 44098 |  | 52 | 44098 | [5 empty] | Emma Derenowski | 11 | KABI LAKE FOREST PRODUCTS LTD3014KL-20200919-10-R1Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD3014KL-20200919-10-R1Pickup Truck - Truck Only8200OEWT-PA9-Lem-R1 | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3415 | KL-20200930-23 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pitrun from Provost pit #5 to F204 access | 11 | F-203 to F-211 | High Falls Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-23Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-23Pickup Truck - Truck Only375OEWT-PA10-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7012 | KL-20210611-1 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-06-11 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage from F190 to F191 for pickup access & grinder. | 11 | F185-C193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7012KL-20210611-1Pickup Truck - Truck Only375 | KABI LAKE FOREST PRODUCTS LTD7012KL-20210611-1Pickup Truck - Truck Only375OEWT-PA18-Lem | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7013 | KL-20210612-1 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2021-06-12 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator starting road maintenance from 11Km on Hensen to 0.5Km on Hensen East as per Valard. Supervisor doing pickup shuffle. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7013KL-20210612-1Pickup Truck - Truck Only7.5187.5 | KABI LAKE FOREST PRODUCTS LTD7013KL-20210612-1Pickup Truck - Truck Only7.5187.5OEWT-PA18-Lem | [5 empty] | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7015 | KL-20210612-3 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2021-06-16 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage from F191 to F192.5 for pickup access & grinder. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7015KL-20210612-3Pickup Truck - Truck Only3.587.5 | KABI LAKE FOREST PRODUCTS LTD7015KL-20210612-3Pickup Truck - Truck Only3.587.5OEWT-PA18-Lem | [5 empty] | 1 | 87.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7016 | KL-20210613-1 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-06-13 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to 1Km on Hensen East. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7016KL-20210613-1Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD7016KL-20210613-1Pickup Truck - Truck Only10250OEWT-PA18-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7018 | KL-20210614-1 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-06-14 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F122 on Hensen East. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7018KL-20210614-1Pickup Truck - Truck Only9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7018KL-20210614-1Pickup Truck - Truck Only9.5237.5OEWT-PA18-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7019 | KL-20210614-2 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-06-14 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road, working on drainage out from F193 to F189. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7019KL-20210614-2Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD7019KL-20210614-2Pickup Truck - Truck Only10250OEWT-PA18-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7023 | KL-20210607-1 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-06-07 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage & fixing hills from F188 to F190 for pickup access. | 11 | F185-F193 | High Falls Road | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7023KL-20210607-1Pickup Truck - Truck Only8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7023KL-20210607-1Pickup Truck - Truck Only8.5212.5OEWT-PA18-Lem | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7024 | KL-20210608-1 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 5.5 | HR | 19 | 0 |  |  | 137.5 | 17.875 | 155.375 | 2021-06-08 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators continuing shaping road, working on drainage & fixing hills from F188 to F190 for pickup access and grinder | 11 | F-185 to F-193 | High Falls Road - 5 | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7024KL-20210608-1Pickup Truck - Truck Only5.5137.5 | KABI LAKE FOREST PRODUCTS LTD7024KL-20210608-1Pickup Truck - Truck Only5.5137.5OEWT-PA18-Lem | [5 empty] | 1 | 137.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7026 | KL-20210615-1 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-06-15 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F127/stockpiling existing material for covering of corduroy sections | 11 | F119-F134 | Hensen Road | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7026KL-20210615-1Pickup Truck - Truck Only9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7026KL-20210615-1Pickup Truck - Truck Only9.5237.5OEWT-PA18-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7028 | KL-20210615-3 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-06-15 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing shaping road & levelling ruts from F189 to F185. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7028KL-20210615-3Pickup Truck - Truck Only6150 | KABI LAKE FOREST PRODUCTS LTD7028KL-20210615-3Pickup Truck - Truck Only6150OEWT-PA18-Lem | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7194 | KL-20210803-1 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-08-03 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operator moving rock truck from F-037 to F-119 & tracking Cat 330 excavator from 17Km on Hensen to 46Km on paint lake road 2 for gravel haul | 11 | F118-F127 | Hensen Road | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1Pickup Truck - Truck Only8200OEWT-PA20-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7493 | KL-20211026-2 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 19 | HR | 19 | 0 |  |  | 475 | 61.75 | 536.75 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2Pickup Truck - Truck Only19475 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2Pickup Truck - Truck Only19475OEWT-PA23-Lem | [5 empty] | 1 | 475 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7493 | KL-20211026-2 | 53511112 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2Pickup Truck - Truck Only22550OEWT-PA23-Lem | [5 empty] | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6611 | KL-20210402-3 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-02 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Reclamation @ F135 to F136 | 11 | F135-F149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6611KL-20210402-3Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD6611KL-20210402-3Pickup Truck - Truck Only10250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6614 | KL-20210403-3 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F136 to F137/ side by side used due to no pickup access | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-3Pickup Truck - Truck Only7175 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-3Pickup Truck - Truck Only7175OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6615 | KL-20210403-4 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F133 to F132/ ATV used due to no pickup access | 11 | F-119 to F-134 | Hensen Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6615KL-20210403-4Pickup Truck - Truck Only9.5237.5 | KABI LAKE FOREST PRODUCTS LTD6615KL-20210403-4Pickup Truck - Truck Only9.5237.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6619 | KL-20210404-4 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish reclamation from F133/ F131 and track out to Km 17 on Hensen Road/ ATV used due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 15 | 44303 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD6619KL-20210404-4Pickup Truck - Truck Only9.5237.5 | KABI LAKE FOREST PRODUCTS LTD6619KL-20210404-4Pickup Truck - Truck Only9.5237.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6620 | KL-20210404-5 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 0.5 | HR | 19 | 0 |  |  | 12.5 | 1.625 | 14.125 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 336 Excavator to Km 3 on Dore Lake road for Reclamation of Dore Lake Road West | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6620KL-20210404-5Pickup Truck - Truck Only0.512.5 | KABI LAKE FOREST PRODUCTS LTD6620KL-20210404-5Pickup Truck - Truck Only0.512.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 12.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6624 | KL-20210405-4-R1 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-05 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F137 to F138/ Cat 336 excavator tracking in from km 3 on Dore Road and starting @ F140. Chapman Reclamation of Dore lake Road East - CE-195. Excavator/pickup hours reduced for tracking time from signed ticket per Valard direction. Tracking time will be submitted on LEM KL-20210405-4-S1 | 11 | F-135 to F-149 | Dore lake Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1Pickup Truck - Truck Only10250OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6781 | KL-20210415-2 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-15 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F151 and F150 (Revised ). Removing wood, re-contouring road area. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44317 |  | 56 | 44319 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-2Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-2Pickup Truck - Truck Only10250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6784 | KL-20210415-5 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-04-15 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator Working on Reclamation@ F143/ F144 (Second Revision as per Valard ) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44319 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6784KL-20210415-5Pickup Truck - Truck Only8.5212.5 | KABI LAKE FOREST PRODUCTS LTD6784KL-20210415-5Pickup Truck - Truck Only8.5212.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6786 | KL-20210407-8 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F139 to F143 (third revision.) Quad was used for operator travel to excavator, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6786KL-20210407-8Pickup Truck - Truck Only9.5237.5 | KABI LAKE FOREST PRODUCTS LTD6786KL-20210407-8Pickup Truck - Truck Only9.5237.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6787 | KL-20210407-9 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation of structure pads @ F141 to F143 (fourth revision.) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6787KL-20210407-9Pickup Truck - Truck Only7.5187.5 | KABI LAKE FOREST PRODUCTS LTD6787KL-20210407-9Pickup Truck - Truck Only7.5187.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6788 | KL-20210408-6 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on Reclamation @F139 to F140. Quad used for operator travel, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-6Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-6Pickup Truck - Truck Only10250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6788 | KL-20210408-6 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 0.5 | HR | 19 | 0 |  |  | 12.5 | 1.625 | 14.125 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on Reclamation @F139 to F140. Quad used for operator travel, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-6Pickup Truck - Truck Only0.512.5 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-6Pickup Truck - Truck Only0.512.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 12.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6789 | KL-20210408-7 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamationof structure pads and access @ F145/F144 (fourth revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6789KL-20210408-7Pickup Truck - Truck Only9.5237.5 | KABI LAKE FOREST PRODUCTS LTD6789KL-20210408-7Pickup Truck - Truck Only9.5237.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6790 | KL-20210409-8 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 5.5 | HR | 19 | 0 |  |  | 137.5 | 17.875 | 155.375 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on reclamation @f139 to F140. (Third Revision). Quad used for operator travel, no tracking time for equipment. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6790KL-20210409-8Pickup Truck - Truck Only5.5137.5 | KABI LAKE FOREST PRODUCTS LTD6790KL-20210409-8Pickup Truck - Truck Only5.5137.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 137.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6791 | KL-20210409-9 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on reclamation @f139 to F140. (Third Revision). Quad used for operator travel, no tracking time for equipment. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6791KL-20210409-9Pickup Truck - Truck Only4100 | KABI LAKE FOREST PRODUCTS LTD6791KL-20210409-9Pickup Truck - Truck Only4100OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6793 | KL-20210412-8 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on Reclamation @ F141/F142 (fourth revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6793KL-20210412-8Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD6793KL-20210412-8Pickup Truck - Truck Only8200OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6795 | KL-20210413-6 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 and Cat 330 Excavators workimg on Reclamation @F141 and F143 (4th Revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-6Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-6Pickup Truck - Truck Only13325OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6797 | KL-20210414-9 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 and Cat 336 excavators working on Reclamation @ F142 and F143 (3rd revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-9Pickup Truck - Truck Only14350 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-9Pickup Truck - Truck Only14350OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6799 | KL-20210416-2 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-04-16 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamation @F142 and F143. Skidder removing WC-12150 | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6799KL-20210416-2Pickup Truck - Truck Only6150 | KABI LAKE FOREST PRODUCTS LTD6799KL-20210416-2Pickup Truck - Truck Only6150OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6800 | KL-20210416-3 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-04-16 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F150 and F151 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6800KL-20210416-3Pickup Truck - Truck Only11275 | KABI LAKE FOREST PRODUCTS LTD6800KL-20210416-3Pickup Truck - Truck Only11275OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6802 | KL-20210417-2 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-04-17 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamation @F143 and F144 | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6802KL-20210417-2Pickup Truck - Truck Only8.5212.5 | KABI LAKE FOREST PRODUCTS LTD6802KL-20210417-2Pickup Truck - Truck Only8.5212.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6808 | KL-20210418-1 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2021-04-18 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on reclamation @F144 and F145 ( Second revision). Chapman access reclamation at 7.5Km. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 56 | 44323 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-1Pickup Truck - Truck Only10.5262.5 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-1Pickup Truck - Truck Only10.5262.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6810 | KL-20210419-1 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2021-04-19 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 excavator working on reclamation on access to F145 (revised). Chapman removing access material from 7km to 4km Dore Lake Road. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 57 | 44323 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6810KL-20210419-1Pickup Truck - Truck Only7.5187.5 | KABI LAKE FOREST PRODUCTS LTD6810KL-20210419-1Pickup Truck - Truck Only7.5187.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6811 | KL-20210420-1 | 53541101 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-04-20 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator completing reclamation on access to F145 ( revised as per Valard ) | 11 | F135-F149 | Dore lake Road | 0 | 44322 |  | 57 | 44323 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6811KL-20210420-1Pickup Truck - Truck Only6150 | KABI LAKE FOREST PRODUCTS LTD6811KL-20210420-1Pickup Truck - Truck Only6150OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6607 | KL-20210401-6 | 53541104 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-01 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Gravel Removal (Access) |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclaimation @ F133/ F132/ ATV used due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 57 | 44305 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6607KL-20210401-6Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD6607KL-20210401-6Pickup Truck - Truck Only10250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6628 | KL-20210405-8 | 53541105 | Reclamation | 0 | Pickup Truck - Truck Only | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2021-04-05 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Erosion Cont Inst/Mon/Rem |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Reclamation @ F150 | 11 | F-150 to F-151 | Michipicoten Harbour Road -1 | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6628KL-20210405-8Pickup Truck - Truck Only4.5112.5 | KABI LAKE FOREST PRODUCTS LTD6628KL-20210405-8Pickup Truck - Truck Only4.5112.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4849 | KL-20201212-14 | 53551103 | Earthworks | 0 | Pickup Truck - Truck Only | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker & support excavator starting on F123 Access breaking outcrops on steep grades /straighten corners/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-14Pickup Truck - Truck Only7.5187.5 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-14Pickup Truck - Truck Only7.5187.5OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 93.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4988 | KL-20201213-13 | 53551103 | Earthworks | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support Excavator working on F123 access breaking outcrops on steep grade and straighten corners/ oper. travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-13Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-13Pickup Truck - Truck Only12300OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5110 | KL-20201217-18 | 53551103 | Earthworks | 0 | Pickup Truck - Truck Only | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support excavator working on F127 access Breaking outcrops on steep grades and straighten corners/ operators as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-18Pickup Truck - Truck Only12300 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-18Pickup Truck - Truck Only12300OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5122 | KL-20201220-9 | 53551103 | Earthworks | 0 | Pickup Truck - Truck Only | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-20 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades & straighten corners/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-9Pickup Truck - Truck Only10250 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-9Pickup Truck - Truck Only10250OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4849 | KL-20201212-14 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 4.5 | HR | 263 | 0 |  |  | 1575 | 204.75 | 1779.75 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker & support excavator starting on F123 Access breaking outcrops on steep grades /straighten corners/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-1436 Ton Excavator c/w Hydraulic Breaker4.51575 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-1436 Ton Excavator c/w Hydraulic Breaker4.51575OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 787.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5038 | KL-20201216-10 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 8.5 | HR | 263 | 0 |  |  | 2975 | 386.75 | 3361.75 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker and Support Excavator working on F127 access breaking outcrops on steep grades and straighten corners/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-1036 Ton Excavator c/w Hydraulic Breaker8.52975 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-1036 Ton Excavator c/w Hydraulic Breaker8.52975OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 1487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5062 | KL-20201219-9 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 7.5 | HR | 263 | 0 |  |  | 2625 | 341.25 | 2966.25 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades. Straighten corners. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-936 Ton Excavator c/w Hydraulic Breaker7.52625 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-936 Ton Excavator c/w Hydraulic Breaker7.52625OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 1312.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5110 | KL-20201217-18 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 8 | HR | 263 | 0 |  |  | 2800 | 364 | 3164 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support excavator working on F127 access Breaking outcrops on steep grades and straighten corners/ operators as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-1836 Ton Excavator c/w Hydraulic Breaker82800 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-1836 Ton Excavator c/w Hydraulic Breaker82800OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 1400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5122 | KL-20201220-9 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 3 | HR | 263 | 0 |  |  | 1050 | 136.5 | 1186.5 | 2020-12-20 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades & straighten corners/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-936 Ton Excavator c/w Hydraulic Breaker31050 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-936 Ton Excavator c/w Hydraulic Breaker31050OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 525 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5217 | KL-20210104-6 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 8.5 | HR | 263 | 0 |  |  | 2975 | 386.75 | 3361.75 | 2021-01-04 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops on steep grades and laying trees/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-636 Ton Excavator c/w Hydraulic Breaker8.52975 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-636 Ton Excavator c/w Hydraulic Breaker8.52975OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 1487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5230 | KL-20210105-9 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 8.5 | HR | 263 | 0 |  |  | 2975 | 386.75 | 3361.75 | 2021-01-05 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops an steep grades/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-936 Ton Excavator c/w Hydraulic Breaker8.52975 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-936 Ton Excavator c/w Hydraulic Breaker8.52975OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 1487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5243 | KL-20210106-7 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 8.5 | HR | 263 | 0 |  |  | 2975 | 386.75 | 3361.75 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 access breaking outcrops on steep grades/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-736 Ton Excavator c/w Hydraulic Breaker8.52975 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-736 Ton Excavator c/w Hydraulic Breaker8.52975OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 1487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5267 | KL-20210107-16 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 8.5 | HR | 263 | 0 |  |  | 2975 | 386.75 | 3361.75 | 2021-01-07 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 Access breaking outcrops on steep grades/operator travel as per Valard. Skagen excavator supporting breaker. | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-1636 Ton Excavator c/w Hydraulic Breaker8.52975 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-1636 Ton Excavator c/w Hydraulic Breaker8.52975OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 1487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5280 | KL-20210109-3 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 2 | HR | 263 | 0 |  |  | 700 | 91 | 791 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker breaking rock on Access @ 12070.01 WC | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5280KL-20210109-336 Ton Excavator c/w Hydraulic Breaker2700 | KABI LAKE FOREST PRODUCTS LTD5280KL-20210109-336 Ton Excavator c/w Hydraulic Breaker2700OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5628 | KL-20210126-12 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 8.5 | HR | 263 | 0 |  |  | 2975 | 386.75 | 3361.75 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | EXC with breaker & support excavator working on F111 Access breaking outcrops & laying trees. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-1236 Ton Excavator c/w Hydraulic Breaker8.52975 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-1236 Ton Excavator c/w Hydraulic Breaker8.52975OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5648 | KL-20210127-16 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 5 | HR | 263 | 0 |  |  | 1750 | 227.5 | 1977.5 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support excavator working on F111 Access breaking outcrops & laying trees/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-1636 Ton Excavator c/w Hydraulic Breaker51750 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-1636 Ton Excavator c/w Hydraulic Breaker51750OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 875 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5656 | KL-20210128-8 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Breaker | 350 | 8 | HR | 263 | 0 |  |  | 2800 | 364 | 3164 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc w breaker & support exc working on F111 Access breaking outcrops & laying trees/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-836 Ton Excavator c/w Hydraulic Breaker82800 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-836 Ton Excavator c/w Hydraulic Breaker82800OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 895 | KL-20200116-3-R1 | 53510711 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter road upgrade to site access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43889 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD895KL-20200116-3-R136 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD895KL-20200116-3-R136 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA1-LEM | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1195 | KL-20200301-3 | 53510711 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 4 | HR | 159 | 0 |  |  | 844 | 109.72 | 953.72 | 2020-03-01 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | At tower D-004 to rework road because of guide wire | 7 | D-001 to Highway 17 | Peninsula Road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1195KL-20200301-336 Ton Excavator c/w Hydraulic Thumb4844 | KABI LAKE FOREST PRODUCTS LTD1195KL-20200301-336 Ton Excavator c/w Hydraulic Thumb4844OEWT-PA3-LEM | [5 empty] | 1 | 844 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1551 | KL-20200521-3 | 53510712 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 5 | HR | 159 | 0 |  |  | 1055 | 137.15 | 1192.15 | 2020-05-21 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Ditching and Shaping Road | 7 | D032-D055 | Black River East | 0 | 43977 |  | 15 | 43977 | [5 empty] | Martin Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD1551KL-20200521-336 Ton Excavator c/w Hydraulic Thumb51055 | KABI LAKE FOREST PRODUCTS LTD1551KL-20200521-336 Ton Excavator c/w Hydraulic Thumb51055OEWT-PA5-LEM | [5 empty] | 1 | 1055 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4293 | KL-20201110-3 | 53510712 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 10 | HR | 159 | 0 |  |  | 2110 | 274.3 | 2384.3 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and spread gravel and chips D071-D073 BMC-30143 | 7 | D065-D066 | Camp 36 Road | 0 | 44166 |  | 53 | 44168 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-336 Ton Excavator c/w Hydraulic Thumb102110 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-336 Ton Excavator c/w Hydraulic Thumb102110OEWT-PA11-LEM | [5 empty] | 1 | 2110 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7428 | KL-20211005-2 | 53510712 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 10.5 | HR | 159 | 0 |  |  | 2215.5 | 288.015 | 2503.515 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road & hauling concrete anchors on a rig mat for LEG. Excavator levelling ruts, shaping road, assisting pickups & rock truck. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-236 Ton Excavator c/w Hydraulic Thumb10.52215.5 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-236 Ton Excavator c/w Hydraulic Thumb10.52215.5OEWT-PA22-Lem | [5 empty] | 1 | 2215.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7405 | KL-20210928-3 | 53510712 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 10.5 | HR | 159 | 0 |  |  | 2215.5 | 288.015 | 2503.515 | 2021-09-28 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue hauling pit run from Cress Pit & spreading on ROW access/excavator fixing soft areas & track packing for gravel trucks. Labourer sweeping dirt off Hwy 17 | 7 | D018-D031 | pic River West | 0 | 44475 |  | 62 | 44478 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7405KL-20210928-336 Ton Excavator c/w Hydraulic Thumb10.52215.5 | KABI LAKE FOREST PRODUCTS LTD7405KL-20210928-336 Ton Excavator c/w Hydraulic Thumb10.52215.5OEWT-PA22-Lem | [5 empty] | 1 | 2215.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7425 | KL-20211004-2 | 53510712 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 12 | HR | 159 | 0 |  |  | 2532 | 329.16 | 2861.16 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts, shaping road, pulling pickups & grout truck to D025 due to wet conditions. Excavator working after hours until all crews got out. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-236 Ton Excavator c/w Hydraulic Thumb122532 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-236 Ton Excavator c/w Hydraulic Thumb122532OEWT-PA22-Lem | [5 empty] | 1 | 2532 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7432 | KL-20211006-2 | 53510712 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 11 | HR | 159 | 0 |  |  | 2321 | 301.73 | 2622.73 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road and pushing rock trucks hauling gravel to D025 /excavator leveling ruts and shaping road. | 7 | D018-D031 | Pic river | 0 | 44484 |  | 63 | 44484 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-236 Ton Excavator c/w Hydraulic Thumb112321 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-236 Ton Excavator c/w Hydraulic Thumb112321OEWT-PA22-Lem | [5 empty] | 1 | 2321 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7435 | KL-20211007-2 | 53510712 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 8.5 | HR | 159 | 0 |  |  | 1793.5 | 233.155 | 2026.655 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts & shaping road from D-019 to D-025. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-236 Ton Excavator c/w Hydraulic Thumb8.51793.5 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-236 Ton Excavator c/w Hydraulic Thumb8.51793.5OEWT-PA22-Lem | [5 empty] | 1 | 1793.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7437 | KL-20211008-2 | 53510712 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 3 | HR | 159 | 0 |  |  | 633 | 82.29 | 715.29 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator finishing levelling ruts & shaping road from D-019 to D-025 for pickup access. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-236 Ton Excavator c/w Hydraulic Thumb3633 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-236 Ton Excavator c/w Hydraulic Thumb3633OEWT-PA22-Lem | [5 empty] | 1 | 633 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1496 | KL-20200401-7-R1 | 53510811 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 4 | HR | 159 | 0 |  |  | 844 | 109.72 | 953.72 | 2020-04-01 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair rutts on main access road | 8 | E042-E059 | Denis Lake Road West | 0 | 43933 |  | 45 | 43934 | [5 empty] | Howard Beaudet | 08 | KABI LAKE FOREST PRODUCTS LTD1496KL-20200401-7-R136 Ton Excavator c/w Hydraulic Thumb4844 | KABI LAKE FOREST PRODUCTS LTD1496KL-20200401-7-R136 Ton Excavator c/w Hydraulic Thumb4844OEWT PA4-LEM-R1 | [5 empty] | 1 | 844 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4654 | KL-20201126-8 | 53510811 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 2 | HR | 159 | 0 |  |  | 422 | 54.86 | 476.86 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load sand from 6km pit on 600 road and sand Access from Hwy to E073 for concrete haul as per discussion with Valard | 8 | E068-E076 | North Crockers Lake | 0 | 44178 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-836 Ton Excavator c/w Hydraulic Thumb2422 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-836 Ton Excavator c/w Hydraulic Thumb2422OEWT-PA12-LEM-R1 | [5 empty] | 1 | 422 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4902 | KL-20201205-5 | 53510811 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 2 | HR | 159 | 0 |  |  | 422 | 54.86 | 476.86 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Silver City AU1 Access to E025 as per Valard | 8 | E025-E036 | Silver City | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-536 Ton Excavator c/w Hydraulic Thumb2422 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-536 Ton Excavator c/w Hydraulic Thumb2422OEWT-PA12-LEM-R1 | [5 empty] | 1 | 422 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1542 | KL-20200520-13 | 53510812 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 11 | HR | 159 | 0 |  |  | 2321 | 301.73 | 2622.73 | 2020-05-20 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Ditching main access road | 8 | E068-E076 | North Crockers Lake | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD1542KL-20200520-1336 Ton Excavator c/w Hydraulic Thumb112321 | KABI LAKE FOREST PRODUCTS LTD1542KL-20200520-1336 Ton Excavator c/w Hydraulic Thumb112321OEWT-PA5-LEM | [5 empty] | 1 | 2321 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4135 | KL-20201103-5 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 3 | HR | 159 | 0 |  |  | 633 | 82.29 | 715.29 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Sand Truck and sorting material at 20km pit and 6km pit on 600 road, sanding 600, 700 and 100 roads | 9 | E-091 to E-102 | 600 Rd | 0 | 44153 |  | 50 | 44159 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-536 Ton Excavator c/w Hydraulic Thumb3633 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-536 Ton Excavator c/w Hydraulic Thumb3633OEWT-PA11-LEM | [5 empty] | 1 | 633 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4417 | KL-20201116-16 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-1636 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-1636 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA11-LEM | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4430 | KL-20201117-9 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 Rd and 100 Rd to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-936 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-936 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA11-LEM | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4439 | KL-20201118-11 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-1136 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-1136 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA11-LEM | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4462 | KL-20201119-8 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-836 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-836 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA11-LEM | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4513 | KL-20201121-14 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 3 | HR | 159 | 0 |  |  | 633 | 82.29 | 715.29 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 rd and 100 rd to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4513KL-20201121-1436 Ton Excavator c/w Hydraulic Thumb3633 | KABI LAKE FOREST PRODUCTS LTD4513KL-20201121-1436 Ton Excavator c/w Hydraulic Thumb3633OEWT-PA11-LEM | [5 empty] | 1 | 633 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4574 | KL-20201123-12 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 8 | HR | 159 | 0 |  |  | 1688 | 219.44 | 1907.44 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 roads and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4574KL-20201123-1236 Ton Excavator c/w Hydraulic Thumb81688 | KABI LAKE FOREST PRODUCTS LTD4574KL-20201123-1236 Ton Excavator c/w Hydraulic Thumb81688OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1688 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4636 | KL-20201125-13 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, and 100 rd to km5 pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4636KL-20201125-1336 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD4636KL-20201125-1336 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4661 | KL-20201126-14 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 road to km5 pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4661KL-20201126-1436 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD4661KL-20201126-1436 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4685 | KL-20201127-11 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-11-27 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44180 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4685KL-20201127-1136 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD4685KL-20201127-1136 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4699 | KL-20201128-7 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4699KL-20201128-736 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD4699KL-20201128-736 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4709 | KL-20201129-10 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600Rd, 700, 100 roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4709KL-20201129-1036 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD4709KL-20201129-1036 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4724 | KL-20201130-7 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4724KL-20201130-736 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD4724KL-20201130-736 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4742 | KL-20201201-11 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 2 | HR | 159 | 0 |  |  | 422 | 54.86 | 476.86 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Rd | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4742KL-20201201-1136 Ton Excavator c/w Hydraulic Thumb2422 | KABI LAKE FOREST PRODUCTS LTD4742KL-20201201-1136 Ton Excavator c/w Hydraulic Thumb2422OEWT-PA12-LEM-R1 | [5 empty] | 1 | 422 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4775 | KL-20201202-18 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 4 | HR | 159 | 0 |  |  | 844 | 109.72 | 953.72 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Rds | 9 |  | 600 Road | 0 | 44193 |  | 53 | 44205 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-1836 Ton Excavator c/w Hydraulic Thumb4844 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-1836 Ton Excavator c/w Hydraulic Thumb4844OEWT-PA12-LEM-R1 | [5 empty] | 1 | 844 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4810 | KL-20201209-12 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 5 | HR | 159 | 0 |  |  | 1055 | 137.15 | 1192.15 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4810KL-20201209-1236 Ton Excavator c/w Hydraulic Thumb51055 | KABI LAKE FOREST PRODUCTS LTD4810KL-20201209-1236 Ton Excavator c/w Hydraulic Thumb51055OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1055 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4889 | KL-20201204-12 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 1 | HR | 159 | 0 |  |  | 211 | 27.43 | 238.43 | 2020-12-04 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 100 Rd | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4889KL-20201204-1236 Ton Excavator c/w Hydraulic Thumb1211 | KABI LAKE FOREST PRODUCTS LTD4889KL-20201204-1236 Ton Excavator c/w Hydraulic Thumb1211OEWT-PA12-LEM-R1 | [5 empty] | 1 | 211 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4906 | KL-20201205-9 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 4 | HR | 159 | 0 |  |  | 844 | 109.72 | 953.72 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-936 Ton Excavator c/w Hydraulic Thumb4844 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-936 Ton Excavator c/w Hydraulic Thumb4844OEWT-PA12-LEM-R1 | [5 empty] | 1 | 844 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4920 | KL-20201206-7 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 1 | HR | 159 | 0 |  |  | 211 | 27.43 | 238.43 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4920KL-20201206-736 Ton Excavator c/w Hydraulic Thumb1211 | KABI LAKE FOREST PRODUCTS LTD4920KL-20201206-736 Ton Excavator c/w Hydraulic Thumb1211OEWT-PA12-LEM-R1 | [5 empty] | 1 | 211 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4936 | KL-20201207-11 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 5 | HR | 159 | 0 |  |  | 1055 | 137.15 | 1192.15 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4936KL-20201207-1136 Ton Excavator c/w Hydraulic Thumb51055 | KABI LAKE FOREST PRODUCTS LTD4936KL-20201207-1136 Ton Excavator c/w Hydraulic Thumb51055OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1055 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4950 | KL-20201208-8 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 5 | HR | 159 | 0 |  |  | 1055 | 137.15 | 1192.15 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 road | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4950KL-20201208-836 Ton Excavator c/w Hydraulic Thumb51055 | KABI LAKE FOREST PRODUCTS LTD4950KL-20201208-836 Ton Excavator c/w Hydraulic Thumb51055OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1055 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4970 | KL-20201210-9 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 2 | HR | 159 | 0 |  |  | 422 | 54.86 | 476.86 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600/700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4970KL-20201210-936 Ton Excavator c/w Hydraulic Thumb2422 | KABI LAKE FOREST PRODUCTS LTD4970KL-20201210-936 Ton Excavator c/w Hydraulic Thumb2422OEWT-PA12-LEM-R1 | [5 empty] | 1 | 422 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5011 | KL-20201214-14 | 53510911 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | -71 | HR | 159 | 0 |  |  | -14981 | -1947.53 | -16928.53 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CREDIT: 336 Cat excavator in 6km pit on 600 road was swapped out on nov 24 for 320 Cat Excavator, excavator should have been billed out for 320 cat not 336 Cat | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5011KL-20201214-1436 Ton Excavator c/w Hydraulic Thumb-71-14981 | KABI LAKE FOREST PRODUCTS LTD5011KL-20201214-1436 Ton Excavator c/w Hydraulic Thumb-71-14981OEWT-PA12-LEM-R1 | [5 empty] | 1 | -14981 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2004 | KL-20200711-10 | 53510912 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 11 | HR | 159 | 0 |  |  | 2321 | 301.73 | 2622.73 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-1036 Ton Excavator c/w Hydraulic Thumb112321 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-1036 Ton Excavator c/w Hydraulic Thumb112321OEWT-PA7-LEM | [5 empty] | 1 | 2321 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2029 | KL-20200713-7 | 53510912 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 11 | HR | 159 | 0 |  |  | 2321 | 301.73 | 2622.73 | 2020-07-13 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44029 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-736 Ton Excavator c/w Hydraulic Thumb112321 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-736 Ton Excavator c/w Hydraulic Thumb112321OEWT-PA7-LEM | [5 empty] | 1 | 2321 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2565 | KL-20200823-6 | 53510912 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 3 | HR | 159 | 0 |  |  | 633 | 82.29 | 715.29 | 2020-08-23 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance work from E-165 to E-167 | 9 | E-091 to E-102 | 600 Road | 0 | 44068 |  | 15 | 44071 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2565KL-20200823-636 Ton Excavator c/w Hydraulic Thumb3633 | KABI LAKE FOREST PRODUCTS LTD2565KL-20200823-636 Ton Excavator c/w Hydraulic Thumb3633OEWT-PA8-LEM | [5 empty] | 1 | 633 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3599 | KL-20201008-19 | 53510912 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 11 | HR | 159 | 0 |  |  | 2321 | 301.73 | 2622.73 | 2020-10-08 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Stripping 650 pit | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3599KL-20201008-1936 Ton Excavator c/w Hydraulic Thumb112321 | KABI LAKE FOREST PRODUCTS LTD3599KL-20201008-1936 Ton Excavator c/w Hydraulic Thumb112321OEWT-PA10-LEM | [5 empty] | 1 | 2321 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3648 | KL-20201010-12 | 53510912 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 11 | HR | 159 | 0 |  |  | 2321 | 301.73 | 2622.73 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix rds, spread loads between E-173, E-172 and haul gravel to E-168/E-171and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-1236 Ton Excavator c/w Hydraulic Thumb112321 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-1236 Ton Excavator c/w Hydraulic Thumb112321OEWT-PA10-LEM | [5 empty] | 1 | 2321 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3671 | KL-20201011-11 | 53510912 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 11 | HR | 159 | 0 |  |  | 2321 | 301.73 | 2622.73 | 2020-10-11 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix road and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44157 |  | 15 | 44131 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-1136 Ton Excavator c/w Hydraulic Thumb112321 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-1136 Ton Excavator c/w Hydraulic Thumb112321OEWT-PA10-LEM | [5 empty] | 1 | 2321 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3698 | KL-20201012-16 | 53510912 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 11 | HR | 159 | 0 |  |  | 2321 | 301.73 | 2622.73 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3698KL-20201012-1636 Ton Excavator c/w Hydraulic Thumb112321 | KABI LAKE FOREST PRODUCTS LTD3698KL-20201012-1636 Ton Excavator c/w Hydraulic Thumb112321OEWT-PA10-LEM | [5 empty] | 1 | 2321 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3741 | KL-20201014-12 | 53510912 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 11 | HR | 159 | 0 |  |  | 2321 | 301.73 | 2622.73 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy, install cross drain at F6. | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-1236 Ton Excavator c/w Hydraulic Thumb112321 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-1236 Ton Excavator c/w Hydraulic Thumb112321OEWT-PA10-LEM | [5 empty] | 1 | 2321 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3765 | KL-20201015-13 | 53510912 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 22 | HR | 159 | 0 |  |  | 4642 | 603.46 | 5245.46 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit and 25km pit, fix roads and hauled gravel to E168-E171 and spread over Corduroy, pile up gravel at Km33 | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3765KL-20201015-1336 Ton Excavator c/w Hydraulic Thumb224642 | KABI LAKE FOREST PRODUCTS LTD3765KL-20201015-1336 Ton Excavator c/w Hydraulic Thumb224642OEWT-PA10-LEM | [5 empty] | 1 | 4642 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7932 | KL-20220305-1-RCL | 53541001 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 9 | HR | 159 | 0 |  |  | 1899 | 246.87 | 2145.87 | 2022-03-05 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 excavator clearing snow from ditches, and spreading ripped material. 336 excavator ripping frozen roadway F033-F034 | 10 | F066-F118 | Paint Lake 2 | 0 | 44625 |  | 37 | 44625 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCL36 Ton Excavator c/w Hydraulic Thumb91899 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCL36 Ton Excavator c/w Hydraulic Thumb91899 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 1899 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5330 | KL-20210112-17 | 53511102 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 2.5 | HR | 159 | 0 |  |  | 527.5 | 68.575 | 596.075 | 2021-01-12 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track from 17km to F127.5 due to no float access. | 11 | f119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5330KL-20210112-1736 Ton Excavator c/w Hydraulic Thumb2.5527.5 | KABI LAKE FOREST PRODUCTS LTD5330KL-20210112-1736 Ton Excavator c/w Hydraulic Thumb2.5527.5OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 527.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5497 | KL-20210120-19 | 53511102 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 8 | HR | 159 | 0 |  |  | 1688 | 219.44 | 1907.44 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336F excavator building new road around F128 structure as per Valard/Operator extra travel/based out of White River | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5497KL-20210120-1936 Ton Excavator c/w Hydraulic Thumb81688 | KABI LAKE FOREST PRODUCTS LTD5497KL-20210120-1936 Ton Excavator c/w Hydraulic Thumb81688OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1688 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5339 | KL-20210113-5 | 53511103 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 4 | HR | 159 | 0 |  |  | 844 | 109.72 | 953.72 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy at F132 access | 11 | F119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5339KL-20210113-536 Ton Excavator c/w Hydraulic Thumb4844 | KABI LAKE FOREST PRODUCTS LTD5339KL-20210113-536 Ton Excavator c/w Hydraulic Thumb4844OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 844 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4992 | KL-20201211-12 | 53511111 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 1 | HR | 159 | 0 |  |  | 211 | 27.43 | 238.43 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load partial load @6km pit on 600 road for sanding of hill laydown 1/ load sand from F119 and sand road for float access as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-1236 Ton Excavator c/w Hydraulic Thumb1211 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-1236 Ton Excavator c/w Hydraulic Thumb1211OEWT-PA12-LEM-R1 | [5 empty] | 1 | 211 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5363 | KL-20210114-9 | 53511111 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 1 | HR | 159 | 0 |  |  | 211 | 27.43 | 238.43 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load screened sand from town pit and finished sanding Hensen Road to 17km with existing sand as per Valard/ Excavator cleaning up @ F119 for Sand | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-936 Ton Excavator c/w Hydraulic Thumb1211 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-936 Ton Excavator c/w Hydraulic Thumb1211OEWT-PA13-LEM | [5 empty] | 1 | 211 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5555 | KL-20210123-14 | 53511111 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 2 | HR | 159 | 0 |  |  | 422 | 54.86 | 476.86 | 2021-01-23 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336F tracking out from F127 to 17km on Hensen due to no float access. Plowed out all pullouts and F117 Access | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5555KL-20210123-1436 Ton Excavator c/w Hydraulic Thumb2422 | KABI LAKE FOREST PRODUCTS LTD5555KL-20210123-1436 Ton Excavator c/w Hydraulic Thumb2422OEWT-PA13-LEM | [5 empty] | 1 | 422 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6039 | KL-20210225-7 | 53511111 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 3 | HR | 159 | 0 |  |  | 633 | 82.29 | 715.29 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator moving trees & levelling snow banks for snowmobile trail @ F232 | 11 | F232 | F-232 Road | 0 | 44256 |  | 56 | 44259 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6039KL-20210225-736 Ton Excavator c/w Hydraulic Thumb3633 | KABI LAKE FOREST PRODUCTS LTD6039KL-20210225-736 Ton Excavator c/w Hydraulic Thumb3633OEWT-PA14-Lem-R1 | [5 empty] | 1 | 633 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6100 | KL-20210226-10 | 53511111 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 5 | HR | 159 | 0 |  |  | 1055 | 137.15 | 1192.15 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking to F212 access pushing snow back and clearing pull outs. Excavator brushing AE1 Access for F-228 and F-212 | 11 | F-212 to F-214 | Michipicoten Road- 1 | 0 | 44262 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-1036 Ton Excavator c/w Hydraulic Thumb51055 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-1036 Ton Excavator c/w Hydraulic Thumb51055OEWT PA15-LEM | [5 empty] | 1 | 1055 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6346 | KL-20210316-5 | 53511111 | Access | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 4 | HR | 159 | 0 |  |  | 844 | 109.72 | 953.72 | 2021-03-16 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish tracking 2 excavators out from F215 to 9km on Ajigami road/pushing snow back for drainage (revised | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6346KL-20210316-536 Ton Excavator c/w Hydraulic Thumb4844 | KABI LAKE FOREST PRODUCTS LTD6346KL-20210316-536 Ton Excavator c/w Hydraulic Thumb4844OEWT PA15-LEM | [5 empty] | 1 | 844 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6624 | KL-20210405-4-R1 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 10 | HR | 159 | 0 |  |  | 2110 | 274.3 | 2384.3 | 2021-04-05 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F137 to F138/ Cat 336 excavator tracking in from km 3 on Dore Road and starting @ F140. Chapman Reclamation of Dore lake Road East - CE-195. Excavator/pickup hours reduced for tracking time from signed ticket per Valard direction. Tracking time will be submitted on LEM KL-20210405-4-S1 | 11 | F-135 to F-149 | Dore lake Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R136 Ton Excavator c/w Hydraulic Thumb102110 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R136 Ton Excavator c/w Hydraulic Thumb102110OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2110 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6661 | KL-20210406-5-R1 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 9 | HR | 159 | 0 |  |  | 1899 | 246.87 | 2145.87 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F138 to F141. Two hours of equipment/live out and pick up time removed from each excavator/operator from approved field ticket as per Valard direction. Those charges now listed on LEM KL-20210406-5-S1. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | 44328 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R136 Ton Excavator c/w Hydraulic Thumb91899 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R136 Ton Excavator c/w Hydraulic Thumb91899OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1899 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6784 | KL-20210415-5 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 8.5 | HR | 159 | 0 |  |  | 1793.5 | 233.155 | 2026.655 | 2021-04-15 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator Working on Reclamation@ F143/ F144 (Second Revision as per Valard ) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44319 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6784KL-20210415-536 Ton Excavator c/w Hydraulic Thumb8.51793.5 | KABI LAKE FOREST PRODUCTS LTD6784KL-20210415-536 Ton Excavator c/w Hydraulic Thumb8.51793.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1793.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6787 | KL-20210407-9 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 7 | HR | 159 | 0 |  |  | 1477 | 192.01 | 1669.01 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation of structure pads @ F141 to F143 (fourth revision.) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6787KL-20210407-936 Ton Excavator c/w Hydraulic Thumb71477 | KABI LAKE FOREST PRODUCTS LTD6787KL-20210407-936 Ton Excavator c/w Hydraulic Thumb71477OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1477 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6789 | KL-20210408-7 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 9 | HR | 159 | 0 |  |  | 1899 | 246.87 | 2145.87 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamationof structure pads and access @ F145/F144 (fourth revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6789KL-20210408-736 Ton Excavator c/w Hydraulic Thumb91899 | KABI LAKE FOREST PRODUCTS LTD6789KL-20210408-736 Ton Excavator c/w Hydraulic Thumb91899OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1899 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6791 | KL-20210409-9 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 3.5 | HR | 159 | 0 |  |  | 738.5 | 96.005 | 834.505 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on reclamation @f139 to F140. (Third Revision). Quad used for operator travel, no tracking time for equipment. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6791KL-20210409-936 Ton Excavator c/w Hydraulic Thumb3.5738.5 | KABI LAKE FOREST PRODUCTS LTD6791KL-20210409-936 Ton Excavator c/w Hydraulic Thumb3.5738.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 738.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6795 | KL-20210413-6 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 8 | HR | 159 | 0 |  |  | 1688 | 219.44 | 1907.44 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 and Cat 330 Excavators workimg on Reclamation @F141 and F143 (4th Revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-636 Ton Excavator c/w Hydraulic Thumb81688 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-636 Ton Excavator c/w Hydraulic Thumb81688OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1688 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6797 | KL-20210414-9 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 9 | HR | 159 | 0 |  |  | 1899 | 246.87 | 2145.87 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 and Cat 336 excavators working on Reclamation @ F142 and F143 (3rd revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-936 Ton Excavator c/w Hydraulic Thumb91899 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-936 Ton Excavator c/w Hydraulic Thumb91899OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1899 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6799 | KL-20210416-2 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2021-04-16 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamation @F142 and F143. Skidder removing WC-12150 | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6799KL-20210416-236 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD6799KL-20210416-236 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6802 | KL-20210417-2 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 7.5 | HR | 159 | 0 |  |  | 1582.5 | 205.725 | 1788.225 | 2021-04-17 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamation @F143 and F144 | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6802KL-20210417-236 Ton Excavator c/w Hydraulic Thumb7.51582.5 | KABI LAKE FOREST PRODUCTS LTD6802KL-20210417-236 Ton Excavator c/w Hydraulic Thumb7.51582.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1582.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6808 | KL-20210418-1 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 8.5 | HR | 159 | 0 |  |  | 1793.5 | 233.155 | 2026.655 | 2021-04-18 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on reclamation @F144 and F145 ( Second revision). Chapman access reclamation at 7.5Km. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 56 | 44323 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-136 Ton Excavator c/w Hydraulic Thumb8.51793.5 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-136 Ton Excavator c/w Hydraulic Thumb8.51793.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1793.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6810 | KL-20210419-1 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 7.5 | HR | 159 | 0 |  |  | 1582.5 | 205.725 | 1788.225 | 2021-04-19 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 excavator working on reclamation on access to F145 (revised). Chapman removing access material from 7km to 4km Dore Lake Road. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 57 | 44323 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6810KL-20210419-136 Ton Excavator c/w Hydraulic Thumb7.51582.5 | KABI LAKE FOREST PRODUCTS LTD6810KL-20210419-136 Ton Excavator c/w Hydraulic Thumb7.51582.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1582.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6811 | KL-20210420-1 | 53541101 | Reclamation | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 6 | HR | 159 | 0 |  |  | 1266 | 164.58 | 1430.58 | 2021-04-20 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator completing reclamation on access to F145 ( revised as per Valard ) | 11 | F135-F149 | Dore lake Road | 0 | 44322 |  | 57 | 44323 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6811KL-20210420-136 Ton Excavator c/w Hydraulic Thumb61266 | KABI LAKE FOREST PRODUCTS LTD6811KL-20210420-136 Ton Excavator c/w Hydraulic Thumb61266OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4988 | KL-20201213-13 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 8.5 | HR | 159 | 0 |  |  | 1793.5 | 233.155 | 2026.655 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support Excavator working on F123 access breaking outcrops on steep grade and straighten corners/ oper. travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-1336 Ton Excavator c/w Hydraulic Thumb8.51793.5 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-1336 Ton Excavator c/w Hydraulic Thumb8.51793.5OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 896.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5010 | KL-20201214-13 | 53551103 | Earthworks | 0 | 36 Ton Excavator c/w Hydraulic Thumb | 211 | 8.5 | HR | 159 | 0 |  |  | 1793.5 | 233.155 | 2026.655 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator hydaulic breaker and support excavator working onF123 access breaking outcrops on steep grades and straighten corners / operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44196 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-1336 Ton Excavator c/w Hydraulic Thumb8.51793.5 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-1336 Ton Excavator c/w Hydraulic Thumb8.51793.5OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 896.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7891 | KL-20220215-4 | 53510711 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3.5 | HR | 147 | 0 |  |  | 682.5 | 88.725 | 771.225 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on snow removal from Lay Down to D148 for wood grinding access and start snow removal to E002 for stringers | 7 | D142-E002 | White Lake West | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7891KL-20220215-430 Ton Excavator c/w Hydraulic Thumb3.5682.5 | KABI LAKE FOREST PRODUCTS LTD7891KL-20220215-430 Ton Excavator c/w Hydraulic Thumb3.5682.5OEWT-PA26-LEM | [5 empty] | 1 | 682.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7895 | KL-20220216-3 | 53510711 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing snow removal from Lay Down to D148 and to E002 for stringers | 7 | D142 - E002 | White Lake West | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7895KL-20220216-330 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7895KL-20220216-330 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA26-LEM | [5 empty] | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1404 | KL-20200328-2 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2020-03-28 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push snow banks back on access road , scrape road and grade | 7 | D-119 to D-141 | Alder Creek | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-230 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-230 Ton Excavator c/w Hydraulic Thumb2390OEWT PA4-LEM-R1 | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2426 | KL-20200812-2 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 2 Rock Trucks hauling from stock pile to D132/ Excavator loading | 7 | D-119 to D-141 | Alder Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-230 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-230 Ton Excavator c/w Hydraulic Thumb4780OEWT-PA8-LEM | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3820 | KL-20201018-4 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3 | HR | 147 | 0 |  |  | 585 | 76.05 | 661.05 | 2020-10-18 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Level ruts in Access to D096 to D097 for Drainage | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44130 |  | 47 | 44131 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3820KL-20201018-430 Ton Excavator c/w Hydraulic Thumb3585 | KABI LAKE FOREST PRODUCTS LTD3820KL-20201018-430 Ton Excavator c/w Hydraulic Thumb3585OEWT-PA10-LEM | [5 empty] | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4352 | KL-20201114-5 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc working access from D125 to D129/1 hr excavator & grinder travel due to poor condition of access mats D121 to D132 | 7 | D-119 to D-141 | Alder Creek | 0 | 44166 |  | 53 | 44171 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4352KL-20201114-530 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD4352KL-20201114-530 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA11-LEM | [5 empty] | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4456 | KL-20201119-2 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access to ROW and from D074 to D078, leveling ruts and track packing road | 7 | D-074 to D-079 | Brett’s Road | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4456KL-20201119-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD4456KL-20201119-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA11-LEM | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4480 | KL-20201120-6 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3 | HR | 147 | 0 |  |  | 585 | 76.05 | 661.05 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access to ROW & to D74 levelling ruts & track packing road for Pickup Access | 7 | D-074 to D-079 | Brett’s Road | 0 | 44167 |  | 47 | 44173 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4480KL-20201120-630 Ton Excavator c/w Hydraulic Thumb3585 | KABI LAKE FOREST PRODUCTS LTD4480KL-20201120-630 Ton Excavator c/w Hydraulic Thumb3585OEWT-PA11-LEM | [5 empty] | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7872 | KL-20220211-4 | 53510811 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on snow removal from E034 to E035/E036 for wood grinding access | 8 | E025-E036 | SIlver City | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7872KL-20220211-430 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD7872KL-20220211-430 Ton Excavator c/w Hydraulic Thumb4780OEWT-PA26-LEM | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3900 | KL-20201025-4 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 6 | HR | 147 | 0 |  |  | 1170 | 152.1 | 1322.1 | 2020-10-25 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator starting maintenance on access for concrete truck as per Valard | 8 | E-077 to E-091 | Blue Cedar Road | 0 | 44133 |  | 47 | 44133 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3900KL-20201025-430 Ton Excavator c/w Hydraulic Thumb61170 | KABI LAKE FOREST PRODUCTS LTD3900KL-20201025-430 Ton Excavator c/w Hydraulic Thumb61170OEWT-PA10-LEM | [5 empty] | 1 | 1170 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3982 | KL-20201026-7 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 11 | HR | 147 | 0 |  |  | 2145 | 278.85 | 2423.85 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator doing maintenance on access for concrete trucks as per Valard | 8 | E077-E091 | Blue Cedar | 0 | 44147 |  | 47 | 44151 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3982KL-20201026-730 Ton Excavator c/w Hydraulic Thumb112145 | KABI LAKE FOREST PRODUCTS LTD3982KL-20201026-730 Ton Excavator c/w Hydraulic Thumb112145OEWT-PA11-LEM | [5 empty] | 1 | 2145 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3999 | KL-20201027-4 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 11 | HR | 147 | 0 |  |  | 2145 | 278.85 | 2423.85 | 2020-10-27 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator doing road maintenance on access for Concrete trucks as per Valard | 8 | E-077 to E-091 | Blue Cedar W | 0 | 44147 |  | 47 | 44151 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3999KL-20201027-430 Ton Excavator c/w Hydraulic Thumb112145 | KABI LAKE FOREST PRODUCTS LTD3999KL-20201027-430 Ton Excavator c/w Hydraulic Thumb112145OEWT-PA11-LEM | [5 empty] | 1 | 2145 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4096 | KL-20201101-5 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5.5 | HR | 147 | 0 |  |  | 1072.5 | 139.425 | 1211.925 | 2020-11-01 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator doing Road Maintenance on Access per Valard | 8 | E077-E091 | Blue Cedar W | 0 | 44152 |  | 47 | 44163 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4096KL-20201101-530 Ton Excavator c/w Hydraulic Thumb5.51072.5 | KABI LAKE FOREST PRODUCTS LTD4096KL-20201101-530 Ton Excavator c/w Hydraulic Thumb5.51072.5OEWT-PA11-LEM | [5 empty] | 1 | 1072.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4507 | KL-20201121-8 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E077 to E086, levelling ruts & track packing road | 8 | E077-E091 | Blue Cedar Road | 0 | 44167 |  | 47 | 44174 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4507KL-20201121-830 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD4507KL-20201121-830 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA11-LEM | [5 empty] | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4550 | KL-20201122-8 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3 | HR | 147 | 0 |  |  | 585 | 76.05 | 661.05 | 2020-11-22 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E086 to E091, leveling ruts and track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44172 |  | 47 | 44184 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4550KL-20201122-830 Ton Excavator c/w Hydraulic Thumb3585 | KABI LAKE FOREST PRODUCTS LTD4550KL-20201122-830 Ton Excavator c/w Hydraulic Thumb3585OEWT-PA11-LEM | [5 empty] | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4568 | KL-20201123-6 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 1 | HR | 147 | 0 |  |  | 195 | 25.35 | 220.35 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E086 to E091, leveling ruts and track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44172 |  | 47 | 44175 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4568KL-20201123-630 Ton Excavator c/w Hydraulic Thumb1195 | KABI LAKE FOREST PRODUCTS LTD4568KL-20201123-630 Ton Excavator c/w Hydraulic Thumb1195OEWT-PA12-LEM-R1 | [5 empty] | 1 | 195 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4604 | KL-20201124-7 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3 | HR | 147 | 0 |  |  | 585 | 76.05 | 661.05 | 2020-11-24 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working Access from E086 to E091, leveling ruts and track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44172 |  | 47 | 44179 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4604KL-20201124-730 Ton Excavator c/w Hydraulic Thumb3585 | KABI LAKE FOREST PRODUCTS LTD4604KL-20201124-730 Ton Excavator c/w Hydraulic Thumb3585OEWT-PA11-LEM | [5 empty] | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4627 | KL-20201125-4 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E086 to E077, leveling ruts & track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44173 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4627KL-20201125-430 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD4627KL-20201125-430 Ton Excavator c/w Hydraulic Thumb4780OEWT-PA12-LEM-R1 | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6922 | KL-20210515-6 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 11 | HR | 147 | 0 |  |  | 2145 | 278.85 | 2423.85 | 2021-05-15 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading, hauling and spreading pit run from stock pile to E007/E006 access/loading and hauling trees for soft sections/dozer leveling ruts and excavator placing corduroy | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44342 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-630 Ton Excavator c/w Hydraulic Thumb112145 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-630 Ton Excavator c/w Hydraulic Thumb112145OEWT-PA17-LEM | [5 empty] | 1 | 2145 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6925 | KL-20210516-2 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8 | HR | 147 | 0 |  |  | 1560 | 202.8 | 1762.8 | 2021-05-16 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator ditching along access @ E006 to E007 for capping material | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44343 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6925KL-20210516-230 Ton Excavator c/w Hydraulic Thumb81560 | KABI LAKE FOREST PRODUCTS LTD6925KL-20210516-230 Ton Excavator c/w Hydraulic Thumb81560OEWT-PA17-LEM | [5 empty] | 1 | 1560 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6945 | KL-20210518-2 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2.5 | HR | 147 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | loading , hauling and spreading existing material @ E014 for road repairs from E014.5 to E016 to maintain pickup access | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-230 Ton Excavator c/w Hydraulic Thumb2.5487.5 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-230 Ton Excavator c/w Hydraulic Thumb2.5487.5OEWT-PA17-LEM | [5 empty] | 1 | 487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6947 | KL-20210518-4 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 1.5 | HR | 147 | 0 |  |  | 292.5 | 38.025 | 330.525 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Original route was reclaimed, total supervision 7 hours. |  | Approved |  |  | Excavator leveling ruts and shapes access to E007 for drainage | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6947KL-20210518-430 Ton Excavator c/w Hydraulic Thumb1.5292.5 | KABI LAKE FOREST PRODUCTS LTD6947KL-20210518-430 Ton Excavator c/w Hydraulic Thumb1.5292.5OEWT-PA17-LEM | [5 empty] | 1 | 292.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6951 | KL-20210519-2 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3.5 | HR | 147 | 0 |  |  | 682.5 | 88.725 | 771.225 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading, hauling and spreading exsiting material @ E014 for road repairs from E016 to E013.5 (revised) | 8 | E034 - E036 | White Lake East | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-230 Ton Excavator c/w Hydraulic Thumb3.5682.5 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-230 Ton Excavator c/w Hydraulic Thumb3.5682.5OEWT-PA17-LEM | [5 empty] | 1 | 682.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6959 | KL-20210520-1 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread existing material @ 1.5 km and pit run from stock pile for road repair on E007/E006 main access road/ Laboures laying Geo ( revised) | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-130 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-130 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA17-LEM | [5 empty] | 1 | 2047.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6960 | KL-20210520-2 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat excavator Leveling ruts and shaping road from E016 to E010 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6960KL-20210520-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD6960KL-20210520-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA17-LEM | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6967 | KL-20210521-2 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 |  |  |  | 2047.5 | 266.175 | 2313.675 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stockpile for road repairs to the access going into E005. Dozer spreading loads from from rock truck and fixing ruts. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-230 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-230 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA17-LEM | [5 empty] | 1 | 2047.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6970 | KL-20210522-1 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-05-22 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stock pile and bundles of wood from the main road to E006 for road repairs, dozer spreading loads and pushing up bundle of wood | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44348 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-130 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-130 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA17-LEM | [5 empty] | 1 | 2047.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6977 | KL-20210523-4 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material for road repairs near E011, 330 loading material and dozer spreading loads from rock truck and fixing punch outs | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-430 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-430 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA17-LEM | [5 empty] | 1 | 2047.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6980 | KL-20210524-1 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2021-05-24 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on drainage out of E016/Dozer leveling ruts and back blading out from E016 to E006 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-130 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-130 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA17-LEM | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6983 | KL-20210525-2 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Haul and spread existing material @ E014 for Road repairs from E015 to E016/Excavator and Dozer working on Road maintenance E013 to E006 | 8 | E004-E016 | White Lake East | 0 | 44343 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-230 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-230 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA17-LEM | [5 empty] | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6988 | KL-20210526-1 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E011 to E016 | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-130 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-130 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA18-Lem | [5 empty] | 1 | 2047.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6991 | KL-20210527-1 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Supervisor site visit with Valard ROW and directing Operators | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-130 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-130 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA18-Lem | [5 empty] | 1 | 2047.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6993 | KL-20210528-1 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Start shaping hill @E017 Access | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-130 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-130 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA18-Lem | [5 empty] | 1 | 2047.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6999 | KL-20210531-1 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling existing material for covering of soft sections on E005 access | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 36 | 44359 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-130 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-130 Ton Excavator c/w Hydraulic Thumb4780OEWT-PA18-Lem | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7002 | KL-20210601-1 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road and leveling ruts from 8907.01 WC to Hwy 17/Cleaning up old access road from E007 to E006 as new route was built | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD7002KL-20210601-130 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7002KL-20210601-130 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA18-Lem | [5 empty] | 1 | 3900 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7068 | KL-20210529-2 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3 | HR | 147 | 0 |  |  | 585 | 76.05 | 661.05 | 2021-05-29 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer shaping hill and filling ruts on E017 access from E016 | 8 | E004-E016 | White Lake East | 0 | 44372 |  | 36 | 44373 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-230 Ton Excavator c/w Hydraulic Thumb3585 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-230 Ton Excavator c/w Hydraulic Thumb3585OEWT-PA18-Lem | [5 empty] | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7268 | KL-20210823-2 | 53510812 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 7 | HR | 147 | 0 |  |  | 1365 | 177.45 | 1542.45 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair & shape road from 9049.00 WC to E-017. Loader loading rig mats on float for return to Valard Marathon yard | 8 | E017-E024 | North Regan | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 08 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-230 Ton Excavator c/w Hydraulic Thumb71365 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-230 Ton Excavator c/w Hydraulic Thumb71365OEWT-PA20-Lem | [5 empty] | 1 | 1365 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4609 | KL-20201124-12 | 53510911 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 6 | HR | 147 | 0 |  |  | 1170 | 152.1 | 1322.1 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road, 700 road and 100 road to 5km pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4609KL-20201124-1230 Ton Excavator c/w Hydraulic Thumb61170 | KABI LAKE FOREST PRODUCTS LTD4609KL-20201124-1230 Ton Excavator c/w Hydraulic Thumb61170OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1170 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1623 | KL-20200531-4 | 53510912 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2020-05-31 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unclogg cross drain culverts @13.5, 30.5, 34.2, and 39.5 kms | 9 | E091-E102 | 600 Road | 0 | 43985 |  | 42 | 43986 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-430 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-430 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA6-LEM | [5 empty] | 1 | 1950 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1726 | KL-20200614-2 | 53510912 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2020-06-14 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Unclog cross drain culvert @ 13.5 Km on 600 Road. Ditching and shaping access to E-134. RV-40033 | 9 | E091-E102 | 600 Road | 0 | 44000 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-230 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-230 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA6-LEM | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3741 | KL-20201014-12 | 53510912 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy, install cross drain at F6. | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-1230 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-1230 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA10-LEM | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 877.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 877.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511003 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 899.7544 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7200 | KL-20210804-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-08-04 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load existing material from 17Km on Hensen Road & Gravel road sections @ 46/45Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7201 | KL-20210808-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-08-08 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. 1 Kabi Rock Truck & 2 Valard Rock Trucks Hauling | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7202 | KL-20210805-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-08-05 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 45/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7204 | KL-20210806-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-08-06 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7207 | KL-20210809-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 |  |  |  | 3510 | 456.3 | 3966.3 | 2021-08-09 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7211 | KL-20210810-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-08-10 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7212 | KL-20210811-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-08-11 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 45/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/2 Valard Rock truck. Continue grading Paint Lake Road 2 from Km 7.5 to Km 11.5 - SSF-14324 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7213 | KL-20210812-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 16.5 | HR | 147 | 0 |  |  | 3217.5 | 418.275 | 3635.775 | 2021-08-12 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel access mat sections @ 45/44 km on Paint Lake Road 2/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on Valard 2nd rock truck. Finish grading Paint Lake Road 2 to Km 13 and touch up on way out to Paint Lake Road - SSF-14325 | 10 | F033-F118 | Paint ake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-130 Ton Excavator c/w Hydraulic Thumb16.53217.5 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-130 Ton Excavator c/w Hydraulic Thumb16.53217.5OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 3217.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7214 | KL-20210813-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-08-13 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7215 | KL-20210814-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-08-14 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7218 | KL-20210815-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-08-15 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7221 | KL-20210816-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 17 | HR | 147 | 0 |  |  | 3315 | 430.95 | 3745.95 | 2021-08-16 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-130 Ton Excavator c/w Hydraulic Thumb173315 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-130 Ton Excavator c/w Hydraulic Thumb173315OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 3315 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7224 | KL-20210817-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-08-17 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/46 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-19 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-430 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-430 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-19 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-430 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-430 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-20 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-530 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-530 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8 | HR | 147 | 0 |  |  | 1560 | 202.8 | 1762.8 | 2021-08-20 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-530 Ton Excavator c/w Hydraulic Thumb81560 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-530 Ton Excavator c/w Hydraulic Thumb81560OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1560 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-21 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44434 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-530 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-530 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-21 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44434 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-530 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-530 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-22 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-430 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-430 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-22 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-430 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-430 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 44439 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-530 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-530 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 44439 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-530 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-530 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-24 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-08-24 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-330 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-330 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7285 | KL-20210828-3 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-28 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from km49 to Skagen excavator @ 46/45 km - 1 Kabi , 1 Chapman and 2 Cobiere rock trucks | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-30 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44439 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-Access |  | 0 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-08-31 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44442 |  | 37 | 44445 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-230 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-230 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-08-31 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44442 |  | 37 | 44445 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-230 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-230 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-01 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8 | HR | 147 | 0 |  |  | 1560 | 202.8 | 1762.8 | 2021-09-01 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-230 Ton Excavator c/w Hydraulic Thumb81560 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-230 Ton Excavator c/w Hydraulic Thumb81560OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1560 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-02 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-03 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 50 | 44450 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-14 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-230 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-230 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-25 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-25 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-15 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 0.5 | 0.5 | 877.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511004 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 899.7544 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5703 | KL-20210131-2 | 53511011 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2021-01-31 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator making safety berm and sanding hill on F143 access | 11 | F135-F149 | Dore Lake Road | 0 | 44235 |  | 56 | 44236 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5703KL-20210131-230 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD5703KL-20210131-230 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA14-Lem-R1 | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7593 | KL-20211125-2 | 53511011 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road @ F118, scraping and sanding hill @ Km 48. Excavator filling ruts and shaping road from km 24 to 21 for freezing - JJR-70306 | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-230 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-230 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA23-Lem | [5 empty] | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7646 | KL-20211206-5 | 53511011 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4.5 | HR | 147 | 0 |  |  | 877.5 | 114.075 | 991.575 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking out from Km 13 to Km 2 for loading of sand truck with existing material in support of Valard fuel tank demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7646KL-20211206-530 Ton Excavator c/w Hydraulic Thumb4.5877.5 | KABI LAKE FOREST PRODUCTS LTD7646KL-20211206-530 Ton Excavator c/w Hydraulic Thumb4.5877.5OEWT-PA24-LEM | [5 empty] | 1 | 877.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-130 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-130 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA24-LEM | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7772 | KL-20220115-1 | 53511011 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening roads from Km 32 to Km 36 /Clearing spur roads on way out. Excavator setting up @ 12Km for loader access to sand. | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-130 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-130 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA25-Lem | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6987 | KL-20210525-5 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator Starting road maintenance to F038 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44348 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6987KL-20210525-530 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD6987KL-20210525-530 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA17-LEM | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6990 | KL-20210526-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F40/ Grader starting on Paint Lake Road 2 to Km 4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-330 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-330 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA18-Lem | [5 empty] | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6992 | KL-20210527-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4.5 | HR | 147 | 0 |  |  | 877.5 | 114.075 | 991.575 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F040 / Grader working on Paint Lake Road 2 at km4 to km 10 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-230 Ton Excavator c/w Hydraulic Thumb4.5877.5 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-230 Ton Excavator c/w Hydraulic Thumb4.5877.5OEWT-PA18-Lem | [5 empty] | 1 | 877.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6994 | KL-20210528-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 7.5 | HR | 147 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance from Km 15.5 to Km 19/ Grader working on Paint Lake Road 2 at Km 7 to 12 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-230 Ton Excavator c/w Hydraulic Thumb7.51462.5 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-230 Ton Excavator c/w Hydraulic Thumb7.51462.5OEWT-PA18-Lem | [5 empty] | 1 | 1462.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7001 | KL-20210531-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on road maintenance and drainage from Km 16.5 to Km 19 /grader working on Paint Lake Road 2 from Km 12 to KM4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 36 | 44360 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA18-Lem | [5 empty] | 1 | 1950 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7004 | KL-20210601-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator continue working on road maintenance and drainage from km 17 to km 18/ Grader finishing on Paint Lake Road 2 to Km 0 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA18-Lem | [5 empty] | 1 | 1950 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7066 | KL-20210530-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-05-30 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working road maintenance and drainage to F044/045 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44372 |  | 36 | 44373 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7066KL-20210530-230 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD7066KL-20210530-230 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA18-Lem | [5 empty] | 1 | 2047.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-130 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-130 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA22-Lem | [5 empty] | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-130 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-130 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA22-Lem | [5 empty] | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 17 | HR | 147 | 0 |  |  | 3315 | 430.95 | 3745.95 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-130 Ton Excavator c/w Hydraulic Thumb173315 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-130 Ton Excavator c/w Hydraulic Thumb173315OEWT-PA22-Lem | [5 empty] | 1 | 3315 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 16.5 | HR | 147 | 0 |  |  | 3217.5 | 418.275 | 3635.775 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R130 Ton Excavator c/w Hydraulic Thumb16.53217.5 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R130 Ton Excavator c/w Hydraulic Thumb16.53217.5OEWT-PA22-Lem | [5 empty] | 1 | 3217.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 19.5 | HR | 147 | 0 |  |  | 3802.5 | 494.325 | 4296.825 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-130 Ton Excavator c/w Hydraulic Thumb19.53802.5 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-130 Ton Excavator c/w Hydraulic Thumb19.53802.5OEWT-PA22-Lem | [5 empty] | 1 | 3802.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 27.5 | HR | 147 | 0 |  |  | 5362.5 | 697.125 | 6059.625 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-130 Ton Excavator c/w Hydraulic Thumb27.55362.5 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-130 Ton Excavator c/w Hydraulic Thumb27.55362.5OEWT-PA22-Lem | [5 empty] | 1 | 5362.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 27 | HR | 147 | 0 |  |  | 5265 | 684.45 | 5949.45 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-130 Ton Excavator c/w Hydraulic Thumb275265 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-130 Ton Excavator c/w Hydraulic Thumb275265OEWT-PA22-Lem | [5 empty] | 1 | 5265 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7482 | KL-20211022-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 27 | HR | 147 | 0 |  |  | 5265 | 684.45 | 5949.45 | 2021-10-22 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 working from Km 43 to Km 40 and F105 access Shaping road/ excavator 2 working from Km 43 to Km 45 and F111 shaping road. Excavator 3 Finishing @ F115 to F117 leveling ruts,shaping for freezing and track to F123/ Supervision of Morin, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-130 Ton Excavator c/w Hydraulic Thumb275265 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-130 Ton Excavator c/w Hydraulic Thumb275265OEWT-PA22-Lem | [5 empty] | 1 | 5265 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7483 | KL-20211023-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 19 | HR | 147 | 0 |  |  | 3705 | 481.65 | 4186.65 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 shaping road from Km 43 to Km 40 anf F098/ Excavator 2 shaping road from 45 to 49 km and starting in F123 access/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44496 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-130 Ton Excavator c/w Hydraulic Thumb193705 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-130 Ton Excavator c/w Hydraulic Thumb193705OEWT-PA22-Lem | [5 empty] | 1 | 3705 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7485 | KL-20211024-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 46 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7488 | KL-20211025-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 44 to Km 40 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7492 | KL-20211026-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from F110 to Km 41 /supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 14.5 | HR | 147 | 0 |  |  | 2827.5 | 367.575 | 3195.075 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-130 Ton Excavator c/w Hydraulic Thumb14.52827.5 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-130 Ton Excavator c/w Hydraulic Thumb14.52827.5OEWT-PA23-Lem | [5 empty] | 1 | 2827.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 14 | HR | 147 | 0 |  |  | 2730 | 354.9 | 3084.9 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-130 Ton Excavator c/w Hydraulic Thumb142730 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-130 Ton Excavator c/w Hydraulic Thumb142730OEWT-PA23-Lem | [5 empty] | 1 | 2730 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7506 | KL-20211029-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8 | HR | 147 | 0 |  |  | 1560 | 202.8 | 1762.8 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing clean up of excavation @ Km 17 on Hensen road and start shaping road to Km 45.5. Rock truck hauling existing material from F088 to Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-130 Ton Excavator c/w Hydraulic Thumb81560 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-130 Ton Excavator c/w Hydraulic Thumb81560OEWT-PA23-Lem | [5 empty] | 1 | 1560 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7510 | KL-20211030-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road to Km 45 to Km 43 and spreading spotted rock trucks loads. Rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas. | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 16.5 | HR | 147 | 0 |  |  | 3217.5 | 418.275 | 3635.775 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-130 Ton Excavator c/w Hydraulic Thumb16.53217.5 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-130 Ton Excavator c/w Hydraulic Thumb16.53217.5OEWT-PA23-Lem | [5 empty] | 1 | 3217.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7519 | KL-20211101-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-01 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads. Rock truck hauling existing material from F-088 to Morin @ 33.5Km as per Valard. Supervision of Morin, Skagen, JJR & Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44501 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-230 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-230 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA23-Lem | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA23-Lem | [5 empty] | 1 | 1852.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-430 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-430 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5.5 | HR | 147 | 0 |  |  | 1072.5 | 139.425 | 1211.925 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-230 Ton Excavator c/w Hydraulic Thumb5.51072.5 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-230 Ton Excavator c/w Hydraulic Thumb5.51072.5OEWT-PA23-Lem | [5 empty] | 1 | 1072.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7572 | KL-20211114-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-14 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from 44Km to 41Km levelling ruts and shaping road. Rock truck on site for hauling of existing material @ 27Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-430 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-430 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7576 | KL-20211117-4 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-17 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road & snow removal @ 44km to 43km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-430 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-430 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7577 | KL-20211118-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-18 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 46 due to icy conditions /Supervision of Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44525 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA23-Lem | [5 empty] | 1 | 1852.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-330 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-330 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA23-Lem | [5 empty] | 1 | 1852.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7583 | KL-20211119-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-19 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 40 due to icy conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7584 | KL-20211120-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-20 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7585 | KL-20211121-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-21 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and sanding road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7587 | KL-20211123-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 42 to Km 46 /Excavator 2 scraping and sanding Km 13.5 to 17 for stringing crews/Supervision of Skagen and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7587 | KL-20211123-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 42 to Km 46 /Excavator 2 scraping and sanding Km 13.5 to 17 for stringing crews/Supervision of Skagen and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7590 | KL-20211124-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 45 to Km 48 /Excavator 2 scraping and sanding Km 16 to 18 for stringing crews demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7590 | KL-20211124-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 45 to Km 48 /Excavator 2 scraping and sanding Km 16 to 18 for stringing crews demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7932 | KL-20220305-1-RCL | 53541001 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2022-03-05 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 excavator clearing snow from ditches, and spreading ripped material. 336 excavator ripping frozen roadway F033-F034 | 10 | F066-F118 | Paint Lake 2 | 0 | 44625 |  | 37 | 44625 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCL30 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCL30 Ton Excavator c/w Hydraulic Thumb91755 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5248 | KL-20210106-12 | 53511102 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track Excavator from F117 to F127 due to no float Access/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5248KL-20210106-1230 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD5248KL-20210106-1230 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5442 | KL-20210118-16 | 53511102 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8 | HR | 147 | 0 |  |  | 1560 | 202.8 | 1762.8 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator filling gorge with trees for fill @ F144/F143 Access (Revised | 11 | F135-F149 | Dore Lake Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5442KL-20210118-1630 Ton Excavator c/w Hydraulic Thumb81560 | KABI LAKE FOREST PRODUCTS LTD5442KL-20210118-1630 Ton Excavator c/w Hydraulic Thumb81560OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1560 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5475 | KL-20210119-26 | 53511102 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3 | HR | 147 | 0 |  |  | 585 | 76.05 | 661.05 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator starting to make ramp with trees for F133 Hub | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44238 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5475KL-20210119-2630 Ton Excavator c/w Hydraulic Thumb3585 | KABI LAKE FOREST PRODUCTS LTD5475KL-20210119-2630 Ton Excavator c/w Hydraulic Thumb3585OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5496 | KL-20210120-18 | 53511102 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8 | HR | 147 | 0 |  |  | 1560 | 202.8 | 1762.8 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Exc finishing making ramp with trees and capping for F133 Hub Access & track to F114/Operator Extra travel/Based out of White River. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5496KL-20210120-1830 Ton Excavator c/w Hydraulic Thumb81560 | KABI LAKE FOREST PRODUCTS LTD5496KL-20210120-1830 Ton Excavator c/w Hydraulic Thumb81560OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1560 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5539 | KL-20210122-17 | 53511102 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator using existing material to minimize steep grade at F117/F116 Access, as per Valard (Revised) | 11 | F119--F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5539KL-20210122-1730 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD5539KL-20210122-1730 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5648 | KL-20210127-16 | 53511102 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support excavator working on F111 Access breaking outcrops & laying trees/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-1630 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-1630 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5283 | KL-20210109-6 | 53511111 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Take 1 load of screened sand from town pit, and finish sanding Hensen Rd to km 17. Floats with existing sand as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-630 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-630 Ton Excavator c/w Hydraulic Thumb4780OEWT-PA13-LEM | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6100 | KL-20210226-10 | 53511111 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking to F212 access pushing snow back and clearing pull outs. Excavator brushing AE1 Access for F-228 and F-212 | 11 | F-212 to F-214 | Michipicoten Road- 1 | 0 | 44262 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-1030 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-1030 Ton Excavator c/w Hydraulic Thumb5975OEWT PA15-LEM | [5 empty] | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6346 | KL-20210316-5 | 53511111 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2021-03-16 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish tracking 2 excavators out from F215 to 9km on Ajigami road/pushing snow back for drainage (revised | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6346KL-20210316-530 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD6346KL-20210316-530 Ton Excavator c/w Hydraulic Thumb4780OEWT PA15-LEM | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6352 | KL-20210317-5 | 53511111 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2021-03-17 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track to F123/F124 from Km 17 on Hensen Road and repair hills for pick up use | 11 | F119-F134 | Hensen Road | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6352KL-20210317-530 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD6352KL-20210317-530 Ton Excavator c/w Hydraulic Thumb4780OEWT PA15-LEM | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6357 | KL-20210318-3 | 53511111 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2021-03-18 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair hills from F123 to F127 for pick up access | 11 | F119-F134 | Hensen Road | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6357KL-20210318-330 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD6357KL-20210318-330 Ton Excavator c/w Hydraulic Thumb4780OEWT PA15-LEM | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7661 | KL-20211209-4 | 53511111 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Road from hwy 17 to 17km. Sand truck sanding hills & corners with existing sand from 17km. Excavator used for loading sand. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-430 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-430 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA24-LEM | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7729 | KL-20220104-2 | 53511111 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3 | HR | 147 | 0 |  |  | 585 | 76.05 | 661.05 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working out from F131 to F125 fixing rough areas and shaping road | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7729KL-20220104-230 Ton Excavator c/w Hydraulic Thumb3585 | KABI LAKE FOREST PRODUCTS LTD7729KL-20220104-230 Ton Excavator c/w Hydraulic Thumb3585OEWT-PA25-Lem | [5 empty] | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7732 | KL-20220105-2 | 53511111 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 and assisting stringing crews/Excavatorcleaning up and setting up a face @Km 17 for sand access | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-230 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-230 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA25-Lem | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7012 | KL-20210611-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3 | HR | 147 | 0 |  |  | 585 | 76.05 | 661.05 | 2021-06-11 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage from F190 to F191 for pickup access & grinder. | 11 | F185-C193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7012KL-20210611-130 Ton Excavator c/w Hydraulic Thumb3585 | KABI LAKE FOREST PRODUCTS LTD7012KL-20210611-130 Ton Excavator c/w Hydraulic Thumb3585OEWT-PA18-Lem | [5 empty] | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7013 | KL-20210612-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5.5 | HR | 147 | 0 |  |  | 1072.5 | 139.425 | 1211.925 | 2021-06-12 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator starting road maintenance from 11Km on Hensen to 0.5Km on Hensen East as per Valard. Supervisor doing pickup shuffle. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7013KL-20210612-130 Ton Excavator c/w Hydraulic Thumb5.51072.5 | KABI LAKE FOREST PRODUCTS LTD7013KL-20210612-130 Ton Excavator c/w Hydraulic Thumb5.51072.5OEWT-PA18-Lem | [5 empty] | 1 | 1072.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7015 | KL-20210612-3 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 3 | HR | 147 | 0 |  |  | 585 | 76.05 | 661.05 | 2021-06-16 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage from F191 to F192.5 for pickup access & grinder. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7015KL-20210612-330 Ton Excavator c/w Hydraulic Thumb3585 | KABI LAKE FOREST PRODUCTS LTD7015KL-20210612-330 Ton Excavator c/w Hydraulic Thumb3585OEWT-PA18-Lem | [5 empty] | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7016 | KL-20210613-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-06-13 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to 1Km on Hensen East. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7016KL-20210613-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7016KL-20210613-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA18-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7018 | KL-20210614-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-06-14 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F122 on Hensen East. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7018KL-20210614-130 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7018KL-20210614-130 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA18-Lem | [5 empty] | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7019 | KL-20210614-2 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8 | HR | 147 | 0 |  |  | 1560 | 202.8 | 1762.8 | 2021-06-14 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road, working on drainage out from F193 to F189. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7019KL-20210614-230 Ton Excavator c/w Hydraulic Thumb81560 | KABI LAKE FOREST PRODUCTS LTD7019KL-20210614-230 Ton Excavator c/w Hydraulic Thumb81560OEWT-PA18-Lem | [5 empty] | 1 | 1560 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7023 | KL-20210607-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 7.5 | HR | 147 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2021-06-07 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage & fixing hills from F188 to F190 for pickup access. | 11 | F185-F193 | High Falls Road | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7023KL-20210607-130 Ton Excavator c/w Hydraulic Thumb7.51462.5 | KABI LAKE FOREST PRODUCTS LTD7023KL-20210607-130 Ton Excavator c/w Hydraulic Thumb7.51462.5OEWT-PA18-Lem | [5 empty] | 1 | 1462.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7024 | KL-20210608-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-06-08 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators continuing shaping road, working on drainage & fixing hills from F188 to F190 for pickup access and grinder | 11 | F-185 to F-193 | High Falls Road - 5 | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7024KL-20210608-130 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD7024KL-20210608-130 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA18-Lem | [5 empty] | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7026 | KL-20210615-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-06-15 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F127/stockpiling existing material for covering of corduroy sections | 11 | F119-F134 | Hensen Road | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7026KL-20210615-130 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7026KL-20210615-130 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA18-Lem | [5 empty] | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7028 | KL-20210615-3 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-06-15 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing shaping road & levelling ruts from F189 to F185. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7028KL-20210615-330 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD7028KL-20210615-330 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA18-Lem | [5 empty] | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7034 | KL-20210616-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5.5 | HR | 147 | 0 |  |  | 1072.5 | 139.425 | 1211.925 | 2021-06-16 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F-127 / Stockpiling existing material fro covering of corduroy sections. | 11 | F119-F134 | Hensen Road | 0 | 44368 |  | 50 | 44369 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7034KL-20210616-130 Ton Excavator c/w Hydraulic Thumb5.51072.5 | KABI LAKE FOREST PRODUCTS LTD7034KL-20210616-130 Ton Excavator c/w Hydraulic Thumb5.51072.5OEWT-PA18-Lem | [5 empty] | 1 | 1072.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7044 | KL-20210620-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2021-06-20 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator repairing washout on hill at WC 12570.00 and access to F171 for pickup access. | 11 | F171-F176 | High Falls Road 1 | 0 | 44369 |  | 50 | 44369 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7044KL-20210620-130 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD7044KL-20210620-130 Ton Excavator c/w Hydraulic Thumb4780OEWT-PA18-Lem | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7058 | KL-20210621-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 6 | HR | 147 | 0 |  |  | 1170 | 152.1 | 1322.1 | 2021-06-21 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Levelling ruts and shaping access from F-171 to F-177 | 11 | F171-F176 | High Falls Road - 1 | 0 | 44370 |  | 50 | 44371 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7058KL-20210621-130 Ton Excavator c/w Hydraulic Thumb61170 | KABI LAKE FOREST PRODUCTS LTD7058KL-20210621-130 Ton Excavator c/w Hydraulic Thumb61170OEWT-PA18-Lem | [5 empty] | 1 | 1170 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7194 | KL-20210803-1 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 1.5 | HR | 147 | 0 |  |  | 292.5 | 38.025 | 330.525 | 2021-08-03 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operator moving rock truck from F-037 to F-119 & tracking Cat 330 excavator from 17Km on Hensen to 46Km on paint lake road 2 for gravel haul | 11 | F118-F127 | Hensen Road | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-130 Ton Excavator c/w Hydraulic Thumb1.5292.5 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-130 Ton Excavator c/w Hydraulic Thumb1.5292.5OEWT-PA20-Lem | [5 empty] | 1 | 292.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7601 | KL-20211029-2 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continue working on drainage, tracking material and shaping road @ F126 / F125 | 11 | F118 - F134 | Henson | 0 | 44501 |  | 61 | 44503 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7601KL-20211029-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7601KL-20211029-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7484 | KL-20211023-2 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul trees for fill and start capping with existing material @ F123 to F124 access realignment | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44496 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA22-Lem | [5 empty] | 1 | 1852.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7486 | KL-20211024-2 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from F123 access to F124 access realignment capping and start raising road and 1.5 km for crane access | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-230 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-230 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA23-Lem | [5 empty] | 1 | 3510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7489 | KL-20211025-2 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 19 | HR | 147 | 0 |  |  | 3705 | 481.65 | 4186.65 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to 1.5 km for raising of road | 11 | F119-F134 | Hensen Road | 0 | 44496 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-230 Ton Excavator c/w Hydraulic Thumb193705 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-230 Ton Excavator c/w Hydraulic Thumb193705OEWT-PA23-Lem | [5 empty] | 1 | 3705 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7493 | KL-20211026-2 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18.5 | HR | 147 | 0 |  |  | 3607.5 | 468.975 | 4076.475 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-230 Ton Excavator c/w Hydraulic Thumb18.53607.5 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-230 Ton Excavator c/w Hydraulic Thumb18.53607.5OEWT-PA23-Lem | [5 empty] | 1 | 3607.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7497 | KL-20211027-2 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 12 | HR | 147 | 0 |  |  | 2340 | 304.2 | 2644.2 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping/excavator speading existing material and shaping road from Hensen Road to F123 | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-230 Ton Excavator c/w Hydraulic Thumb122340 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-230 Ton Excavator c/w Hydraulic Thumb122340OEWT-PA23-Lem | [5 empty] | 1 | 2340 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7503 | KL-20211028-2 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from F123 to F127 working on drainage and shaping road to F126 | 11 | F118-F127 | Hensen Road | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7503KL-20211028-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7503KL-20211028-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7511 | KL-20211030-2 | 53511112 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing working on drainage, shaping road and sloping excavation @ Km .5 on Hensen Road East | 11 | F119-F127 | Hensen Road | 0 | 44502 |  | 61 | 44503 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7511KL-20211030-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7511KL-20211030-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA23-Lem | [5 empty] | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6610 | KL-20210402-2-R1 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 7.5 | HR | 147 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2021-04-02 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track out to Km 1 on Hensen East for refueling and back to F132/ Continue reclamation @ F132/ ATV used due to no pickup access. Excavator time reduced from signed ticket for tracking as per Valard direction. Remaining excavator time will be submitted on KL-20210402-2-S1 | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R130 Ton Excavator c/w Hydraulic Thumb7.51462.5 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R130 Ton Excavator c/w Hydraulic Thumb7.51462.5OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1462.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6611 | KL-20210402-3 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-04-02 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Reclamation @ F135 to F136 | 11 | F135-F149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6611KL-20210402-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD6611KL-20210402-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6614 | KL-20210403-3 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 6 | HR | 147 | 0 |  |  | 1170 | 152.1 | 1322.1 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F136 to F137/ side by side used due to no pickup access | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-330 Ton Excavator c/w Hydraulic Thumb61170 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-330 Ton Excavator c/w Hydraulic Thumb61170OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1170 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6615 | KL-20210403-4 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F133 to F132/ ATV used due to no pickup access | 11 | F-119 to F-134 | Hensen Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6615KL-20210403-430 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD6615KL-20210403-430 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6619 | KL-20210404-4 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish reclamation from F133/ F131 and track out to Km 17 on Hensen Road/ ATV used due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 15 | 44303 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD6619KL-20210404-430 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD6619KL-20210404-430 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6624 | KL-20210405-4-R1 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4.5 | HR | 147 | 0 |  |  | 877.5 | 114.075 | 991.575 | 2021-04-05 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F137 to F138/ Cat 336 excavator tracking in from km 3 on Dore Road and starting @ F140. Chapman Reclamation of Dore lake Road East - CE-195. Excavator/pickup hours reduced for tracking time from signed ticket per Valard direction. Tracking time will be submitted on LEM KL-20210405-4-S1 | 11 | F-135 to F-149 | Dore lake Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R130 Ton Excavator c/w Hydraulic Thumb4.5877.5 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R130 Ton Excavator c/w Hydraulic Thumb4.5877.5OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 877.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6661 | KL-20210406-5-R1 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8 | HR | 147 | 0 |  |  | 1560 | 202.8 | 1762.8 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F138 to F141. Two hours of equipment/live out and pick up time removed from each excavator/operator from approved field ticket as per Valard direction. Those charges now listed on LEM KL-20210406-5-S1. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | 44328 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R130 Ton Excavator c/w Hydraulic Thumb81560 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R130 Ton Excavator c/w Hydraulic Thumb81560OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1560 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6662 | KL-20210406-6 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F150 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44292 |  | 56 | 44305 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6662KL-20210406-630 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD6662KL-20210406-630 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1950 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6674 | KL-20210407-6 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Start Reclamation @ F151/Sloping crane pad amd assembley pad (Revised) | 11 | F150-F151 | Michipicoten Harbour Road -1 | 1 | 44305 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6674KL-20210407-630 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD6674KL-20210407-630 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6677 | KL-20210408-2 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Continue Reclamation @ F151/ sloping crane pads and assembly pad | 11 | F150-F151 | Michipicoten Harbour Road -1 | 1 | 44305 |  | 56 | 44307 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6677KL-20210408-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD6677KL-20210408-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1852.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6687 | KL-20210409-7 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Continue Reclamation @F151/ Sloping crane pad and assembley pad | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44306 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6687KL-20210409-730 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD6687KL-20210409-730 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6704 | KL-20210412-6 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F151 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44308 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6704KL-20210412-630 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD6704KL-20210412-630 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1950 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6757 | KL-20210414-6 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue reclamation @ F151 and F150. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44309 |  | 56 | 44312 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6757KL-20210414-630 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD6757KL-20210414-630 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2047.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6781 | KL-20210415-2 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-04-15 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F151 and F150 (Revised ). Removing wood, re-contouring road area. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44317 |  | 56 | 44319 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6786 | KL-20210407-8 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F139 to F143 (third revision.) Quad was used for operator travel to excavator, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6786KL-20210407-830 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD6786KL-20210407-830 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6788 | KL-20210408-6 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on Reclamation @F139 to F140. Quad used for operator travel, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-630 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-630 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1950 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6790 | KL-20210409-8 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on reclamation @f139 to F140. (Third Revision). Quad used for operator travel, no tracking time for equipment. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6790KL-20210409-830 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD6790KL-20210409-830 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6793 | KL-20210412-8 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8 | HR | 147 | 0 |  |  | 1560 | 202.8 | 1762.8 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on Reclamation @ F141/F142 (fourth revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6793KL-20210412-830 Ton Excavator c/w Hydraulic Thumb81560 | KABI LAKE FOREST PRODUCTS LTD6793KL-20210412-830 Ton Excavator c/w Hydraulic Thumb81560OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1560 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6795 | KL-20210413-6 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 and Cat 330 Excavators workimg on Reclamation @F141 and F143 (4th Revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-630 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-630 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6797 | KL-20210414-9 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 and Cat 336 excavators working on Reclamation @ F142 and F143 (3rd revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-930 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-930 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6800 | KL-20210416-3 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-04-16 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F150 and F151 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6800KL-20210416-330 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD6800KL-20210416-330 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2047.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6840 | KL-20210331-5 | 53541101 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track to F133 from Km 17 on Hensen and start reclaimation @ F133/F132. ATV used for crew due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44326 |  | 57 | 44327 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-530 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-530 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1657.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6607 | KL-20210401-6 | 53541104 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-04-01 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Gravel Removal (Access) |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclaimation @ F133/ F132/ ATV used due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 57 | 44305 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6607KL-20210401-630 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD6607KL-20210401-630 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1755 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6628 | KL-20210405-8 | 53541105 | Reclamation | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2021-04-05 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Erosion Cont Inst/Mon/Rem |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Reclamation @ F150 | 11 | F-150 to F-151 | Michipicoten Harbour Road -1 | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6628KL-20210405-830 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD6628KL-20210405-830 Ton Excavator c/w Hydraulic Thumb4780OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4849 | KL-20201212-14 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5 | HR | 147 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker & support excavator starting on F123 Access breaking outcrops on steep grades /straighten corners/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-1430 Ton Excavator c/w Hydraulic Thumb5975 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-1430 Ton Excavator c/w Hydraulic Thumb5975OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4988 | KL-20201213-13 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support Excavator working on F123 access breaking outcrops on steep grade and straighten corners/ oper. travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-1330 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-1330 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 828.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5010 | KL-20201214-13 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator hydaulic breaker and support excavator working onF123 access breaking outcrops on steep grades and straighten corners / operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44196 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-1330 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-1330 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 828.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5038 | KL-20201216-10 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker and Support Excavator working on F127 access breaking outcrops on steep grades and straighten corners/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-1030 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-1030 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 828.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5062 | KL-20201219-9 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 7.5 | HR | 147 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades. Straighten corners. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-930 Ton Excavator c/w Hydraulic Thumb7.51462.5 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-930 Ton Excavator c/w Hydraulic Thumb7.51462.5OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 731.25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5110 | KL-20201217-18 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8 | HR | 147 | 0 |  |  | 1560 | 202.8 | 1762.8 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support excavator working on F127 access Breaking outcrops on steep grades and straighten corners/ operators as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-1830 Ton Excavator c/w Hydraulic Thumb81560 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-1830 Ton Excavator c/w Hydraulic Thumb81560OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5122 | KL-20201220-9 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2020-12-20 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades & straighten corners/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-930 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-930 Ton Excavator c/w Hydraulic Thumb4780OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5217 | KL-20210104-6 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-01-04 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops on steep grades and laying trees/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-630 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-630 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 828.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5230 | KL-20210105-9 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-01-05 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops an steep grades/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-930 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-930 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 828.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5628 | KL-20210126-12 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 5.5 | HR | 147 | 0 |  |  | 1072.5 | 139.425 | 1211.925 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | EXC with breaker & support excavator working on F111 Access breaking outcrops & laying trees. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-1230 Ton Excavator c/w Hydraulic Thumb5.51072.5 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-1230 Ton Excavator c/w Hydraulic Thumb5.51072.5OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 536.25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5656 | KL-20210128-8 | 53551103 | Earthworks | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc w breaker & support exc working on F111 Access breaking outcrops & laying trees/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-830 Ton Excavator c/w Hydraulic Thumb4780 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-830 Ton Excavator c/w Hydraulic Thumb4780OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 902 | KL-20200121-2 | 53510711 | Access | 0 | 30 Ton Excavator c/w Brushing Head | 206 | 11 | HR | 155 | 0 |  |  | 2266 | 294.58 | 2560.58 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Brushed 15M road ROW to D146. Dozer shaped & pushed snow back D-147 & D146 | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-230 Ton Excavator c/w Brushing Head112266 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-230 Ton Excavator c/w Brushing Head112266OEWT-PA1-LEM | [5 empty] | 1 | 2266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 885 | KL-20200112-1-R2 | 53510712 | Access | 0 | 30 Ton Excavator c/w Brushing Head | 206 | 11 | HR | 155 | 0 |  |  | 2266 | 294.58 | 2560.58 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Brush out White Lake Rd. for All season access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD885KL-20200112-1-R230 Ton Excavator c/w Brushing Head112266 | KABI LAKE FOREST PRODUCTS LTD885KL-20200112-1-R230 Ton Excavator c/w Brushing Head112266OEWT-PA1-LEM | [5 empty] | 1 | 2266 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 886 | KL-20200113-1-R1 | 53510712 | Access | 0 | 30 Ton Excavator c/w Brushing Head | 206 | 12 | HR | 155 | 0 |  |  | 2472 | 321.36 | 2793.36 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear and brush existing road for equpiment access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD886KL-20200113-1-R130 Ton Excavator c/w Brushing Head122472 | KABI LAKE FOREST PRODUCTS LTD886KL-20200113-1-R130 Ton Excavator c/w Brushing Head122472OEWT-PA1-LEM | [5 empty] | 1 | 2472 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 897 | KL-20200120-1 | 53510712 | Access | 0 | 30 Ton Excavator c/w Brushing Head | 206 | 3 | HR | 155 | 0 |  |  | 618 | 80.34 | 698.34 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Mob Brusher to site, initiate all seanson access maintenance | 7 | D-109 to D-118 | Wabakoba Creek | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD897KL-20200120-130 Ton Excavator c/w Brushing Head3618 | KABI LAKE FOREST PRODUCTS LTD897KL-20200120-130 Ton Excavator c/w Brushing Head3618OEWT-PA1-LEM | [5 empty] | 1 | 618 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5474 | KL-20210119-25 | 53511103 | Access | 0 | 30 Ton Excavator c/w Brushing Head | 206 | 4 | HR | 155 | 0 |  |  | 824 | 107.12 | 931.12 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 335F Boom Brusher tracking from F124 to F133 & start to grind & freeze corduroy for pick up access. | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44237 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5474KL-20210119-2530 Ton Excavator c/w Brushing Head4824 | KABI LAKE FOREST PRODUCTS LTD5474KL-20210119-2530 Ton Excavator c/w Brushing Head4824OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 824 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5499 | KL-20210120-21 | 53511103 | Access | 0 | 30 Ton Excavator c/w Brushing Head | 206 | 4 | HR | 155 | 0 |  |  | 824 | 107.12 | 931.12 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 335F boom brusher finishing to grind & freeze corduroy for Pick up access & tracking back to F124 | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5499KL-20210120-2130 Ton Excavator c/w Brushing Head4824 | KABI LAKE FOREST PRODUCTS LTD5499KL-20210120-2130 Ton Excavator c/w Brushing Head4824OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 824 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5000 | KL-20201214-3 | 53510811 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 1.5 | HR | 121 | 0 |  |  | 241.5 | 31.395 | 272.895 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding and Grading Access to E073 for concrete haul as per Valard | 8 | E004-E016 | White Lake East | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-320 Ton Excavator c/w Hydraulic Thumb1.5241.5 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-320 Ton Excavator c/w Hydraulic Thumb1.5241.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 241.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3903 | KL-20201025-7 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 2 | HR | 121 | 0 |  |  | 322 | 41.86 | 363.86 | 2020-10-25 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Prep KM20 pit on 600 road for Sander | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 50 | 44134 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3903KL-20201025-720 Ton Excavator c/w Hydraulic Thumb2322 | KABI LAKE FOREST PRODUCTS LTD3903KL-20201025-720 Ton Excavator c/w Hydraulic Thumb2322OEWT-PA10-LEM | [5 empty] | 1 | 322 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3988 | KL-20201026-13 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 11 | HR | 121 | 0 |  |  | 1771 | 230.23 | 2001.23 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sander truck and sorting material , sanding 600 road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44161 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3988KL-20201026-1320 Ton Excavator c/w Hydraulic Thumb111771 | KABI LAKE FOREST PRODUCTS LTD3988KL-20201026-1320 Ton Excavator c/w Hydraulic Thumb111771OEWT-PA11-LEM | [5 empty] | 1 | 1771 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4047 | KL-20201029-13 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 6 | HR | 121 | 0 |  |  | 966 | 125.58 | 1091.58 | 2020-10-29 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding the 600 rd km 1-km 20 and 700 Rd to km 13. Rock trucks hauling gravel from stockpile. AM-60161. Rock trucks hauling gravel from stockpile on 600 road to Kabi's excavator. AM-60161 | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4047KL-20201029-1320 Ton Excavator c/w Hydraulic Thumb6966 | KABI LAKE FOREST PRODUCTS LTD4047KL-20201029-1320 Ton Excavator c/w Hydraulic Thumb6966OEWT-PA11-LEM | [5 empty] | 1 | 966 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4081 | KL-20201031-7 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 10.5 | HR | 121 | 0 |  |  | 1690.5 | 219.765 | 1910.265 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sand truck an sorting material, sanding 600 road. | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4081KL-20201031-720 Ton Excavator c/w Hydraulic Thumb10.51690.5 | KABI LAKE FOREST PRODUCTS LTD4081KL-20201031-720 Ton Excavator c/w Hydraulic Thumb10.51690.5OEWT-PA11-LEM | [5 empty] | 1 | 1690.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4113 | KL-20201102-9 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 6 | HR | 121 | 0 |  |  | 966 | 125.58 | 1091.58 | 2020-11-02 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sander truck and sorting materials at km 20 an km 6 pits on the 600 road and 100 road | 9 | E091-E102 | 600 Rd | 0 | 44153 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-920 Ton Excavator c/w Hydraulic Thumb6966 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-920 Ton Excavator c/w Hydraulic Thumb6966OEWT-PA11-LEM | [5 empty] | 1 | 966 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4135 | KL-20201103-5 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 4 | HR | 121 | 0 |  |  | 644 | 83.72 | 727.72 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Sand Truck and sorting material at 20km pit and 6km pit on 600 road, sanding 600, 700 and 100 roads | 9 | E-091 to E-102 | 600 Rd | 0 | 44153 |  | 50 | 44159 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-520 Ton Excavator c/w Hydraulic Thumb4644 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-520 Ton Excavator c/w Hydraulic Thumb4644OEWT-PA11-LEM | [5 empty] | 1 | 644 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5004 | KL-20201214-7 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 4 | HR | 121 | 0 |  |  | 644 | 83.72 | 727.72 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5004KL-20201214-720 Ton Excavator c/w Hydraulic Thumb4644 | KABI LAKE FOREST PRODUCTS LTD5004KL-20201214-720 Ton Excavator c/w Hydraulic Thumb4644OEWT-PA12-LEM-R1 | [5 empty] | 1 | 644 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5011 | KL-20201214-14 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 71 | HR | 121 | 0 |  |  | 11431 | 1486.03 | 12917.03 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CREDIT: 336 Cat excavator in 6km pit on 600 road was swapped out on nov 24 for 320 Cat Excavator, excavator should have been billed out for 320 cat not 336 Cat | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5011KL-20201214-1420 Ton Excavator c/w Hydraulic Thumb7111431 | KABI LAKE FOREST PRODUCTS LTD5011KL-20201214-1420 Ton Excavator c/w Hydraulic Thumb7111431OEWT-PA12-LEM-R1 | [5 empty] | 1 | 11431 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5021 | KL-20201215-9 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 5 | HR | 121 | 0 |  |  | 805 | 104.65 | 909.65 | 2020-12-15 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44198 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5021KL-20201215-920 Ton Excavator c/w Hydraulic Thumb5805 | KABI LAKE FOREST PRODUCTS LTD5021KL-20201215-920 Ton Excavator c/w Hydraulic Thumb5805OEWT-PA12-LEM-R1 | [5 empty] | 1 | 805 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5044 | KL-20201218-5 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 5 | HR | 121 | 0 |  |  | 805 | 104.65 | 909.65 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5044KL-20201218-520 Ton Excavator c/w Hydraulic Thumb5805 | KABI LAKE FOREST PRODUCTS LTD5044KL-20201218-520 Ton Excavator c/w Hydraulic Thumb5805OEWT-PA12-LEM-R1 | [5 empty] | 1 | 805 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5098 | KL-20201217-6 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 2 | HR | 121 | 0 |  |  | 322 | 41.86 | 363.86 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5098KL-20201217-620 Ton Excavator c/w Hydraulic Thumb2322 | KABI LAKE FOREST PRODUCTS LTD5098KL-20201217-620 Ton Excavator c/w Hydraulic Thumb2322OEWT-PA12-LEM-R1 | [5 empty] | 1 | 322 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5130 | KL-20201221-5 | 53510911 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 6 | HR | 121 | 0 |  |  | 966 | 125.58 | 1091.58 | 2020-12-21 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Stripping km 6 Pit | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5130KL-20201221-520 Ton Excavator c/w Hydraulic Thumb6966 | KABI LAKE FOREST PRODUCTS LTD5130KL-20201221-520 Ton Excavator c/w Hydraulic Thumb6966OEWT-PA12-LEM-R1 | [5 empty] | 1 | 966 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4073 | KL-20201030-15 | 53510912 | Access | 0 | 20 Ton Excavator c/w Hydraulic Thumb | 161 | 6 | HR | 121 | 0 |  |  | 966 | 125.58 | 1091.58 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding the 600 road and 700 road to Km 13 ( Revised Hours) | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD4073KL-20201030-1520 Ton Excavator c/w Hydraulic Thumb6966 | KABI LAKE FOREST PRODUCTS LTD4073KL-20201030-1520 Ton Excavator c/w Hydraulic Thumb6966OEWT-PA11-LEM | [5 empty] | 1 | 966 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 879 | KL-20200106-1-R1 | 53510711 | Access | 0 | CAT D7 Semi U·Blade | 202 | 9 | HR | 152 | 0 |  |  | 1818 | 236.34 | 2054.34 | 2020-01-10 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Beginning of work in WF7 towers D-142 to E-002. Opening up White Lake Rd., installing signage, and beginning clearing | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD879KL-20200106-1-R1CAT D7 Semi U·Blade91818 | KABI LAKE FOREST PRODUCTS LTD879KL-20200106-1-R1CAT D7 Semi U·Blade91818OEWT-PA1-LEM | [5 empty] | 1 | 1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 880 | KL-20200107-1-R2 | 53510711 | Access | 0 | CAT D7 Semi U·Blade | 202 | 10 | HR | 152 | 0 |  |  | 2020 | 262.6 | 2282.6 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D7 Opened existing White Lake Road to the end. Kabi supervisor led internal meeting after the 1st day of work updating on the site conditions, planned processes and documentation needs. Buncher and skidder cleared estimated 0.8 Ha | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD880KL-20200107-1-R2CAT D7 Semi U·Blade102020 | KABI LAKE FOREST PRODUCTS LTD880KL-20200107-1-R2CAT D7 Semi U·Blade102020OEWT-PA1-LEM | [5 empty] | 1 | 2020 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 888 | KL-20200114-2 | 53510711 | Access | 0 | CAT D7 Semi U·Blade | 202 | 11 | HR | 152 | 0 |  |  | 2222 | 288.86 | 2510.86 | 2020-01-17 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter Access Maintenance, dozer opening roads | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD888KL-20200114-2CAT D7 Semi U·Blade112222 | KABI LAKE FOREST PRODUCTS LTD888KL-20200114-2CAT D7 Semi U·Blade112222OEWT-PA1-LEM | [5 empty] | 1 | 2222 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 890 | KL-20200115-2-R1 | 53510711 | Access | 0 | CAT D7 Semi U·Blade | 202 | 2 | HR | 152 | 0 |  |  | 404 | 52.52 | 456.52 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear snow from road and parking area | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD890KL-20200115-2-R1CAT D7 Semi U·Blade2404 | KABI LAKE FOREST PRODUCTS LTD890KL-20200115-2-R1CAT D7 Semi U·Blade2404OEWT-PA1-LEM | [5 empty] | 1 | 404 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 895 | KL-20200116-3-R1 | 53510711 | Access | 0 | CAT D7 Semi U·Blade | 202 | 4 | HR | 152 | 0 |  |  | 808 | 105.04 | 913.04 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter road upgrade to site access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43889 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD895KL-20200116-3-R1CAT D7 Semi U·Blade4808 | KABI LAKE FOREST PRODUCTS LTD895KL-20200116-3-R1CAT D7 Semi U·Blade4808OEWT-PA1-LEM | [5 empty] | 1 | 808 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 902 | KL-20200121-2 | 53510711 | Access | 0 | CAT D7 Semi U·Blade | 202 | 3 | HR | 152 | 0 |  |  | 606 | 78.78 | 684.78 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Brushed 15M road ROW to D146. Dozer shaped & pushed snow back D-147 & D146 | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-2CAT D7 Semi U·Blade3606 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-2CAT D7 Semi U·Blade3606OEWT-PA1-LEM | [5 empty] | 1 | 606 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 934 | KL-20200126-3 | 53510711 | Access | 0 | CAT D7 Semi U·Blade | 202 | 5 | HR | 152 | 0 |  |  | 1010 | 131.3 | 1141.3 | 2020-01-26 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open Road from Hwy 17 to 3km on White Lake Road | 7 | D-142 to E-002 | White Lake | 0 | 43856 |  | 17 | 43861 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD934KL-20200126-3CAT D7 Semi U·Blade51010 | KABI LAKE FOREST PRODUCTS LTD934KL-20200126-3CAT D7 Semi U·Blade51010OEWT-PA2-LEM-R1 | [5 empty] | 1 | 1010 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 886 | KL-20200113-1-R1 | 53510712 | Access | 0 | CAT D7 Semi U·Blade | 202 | 11 | HR | 152 | 0 |  |  | 2222 | 288.86 | 2510.86 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear and brush existing road for equpiment access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD886KL-20200113-1-R1CAT D7 Semi U·Blade112222 | KABI LAKE FOREST PRODUCTS LTD886KL-20200113-1-R1CAT D7 Semi U·Blade112222OEWT-PA1-LEM | [5 empty] | 1 | 2222 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 898 | KL-20200120-2 | 53510811 | Access | 0 | CAT D7 Semi U·Blade | 202 | 10 | HR | 152 | 0 |  |  | 2020 | 262.6 | 2282.6 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road to E002 | 8 |  |  | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 08 | KABI LAKE FOREST PRODUCTS LTD898KL-20200120-2CAT D7 Semi U·Blade102020 | KABI LAKE FOREST PRODUCTS LTD898KL-20200120-2CAT D7 Semi U·Blade102020OEWT-PA1-LEM | [5 empty] | 1 | 2020 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2997 | KL-20200917-14 | 53510912 | Access | 0 | CAT D7 Semi U·Blade | 202 | 12 | HR | 152 | 0 |  |  | 2424 | 315.12 | 2739.12 | 2020-09-17 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scale pit at 690 | 9 | E-091 to E-102 | 600 Road | 0 | 44097 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2997KL-20200917-14CAT D7 Semi U·Blade122424 | KABI LAKE FOREST PRODUCTS LTD2997KL-20200917-14CAT D7 Semi U·Blade122424OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2424 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1058 | KL-20200212-3 | 53510711 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2020-02-12 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter access - snow removal from D-142 to D-148 | 7 | D-142 to E-002 | White Lake | 0 | 43878 |  | 42 | 43882 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1058KL-20200212-3CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD1058KL-20200212-3CAT D6 - LPG5895OEWT-PA2-LEM-R1 | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1369 | KL-20200323-5 | 53510711 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-23 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing Road and prep for log haul | 7 | D-032 to D-055 | Black River | 0 | 43917 |  | 46 | 43921 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1369KL-20200323-5CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1369KL-20200323-5CAT D6 - LPG111969OEWT PA4-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1378 | KL-20200324-8 | 53510711 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-24 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Prep and fix roads for log haul | 7 | D-032 to D-055 | Black River East | 0 | 43917 |  | 46 | 43921 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1378KL-20200324-8CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1378KL-20200324-8CAT D6 - LPG111969OEWT PA4-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1444 | KL-20200402-5 | 53510711 | Access | 0 | CAT D6 - LPG | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-04-02 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair and maintain road from D054 to HWY 17 | 7 | D-032 to D-055 | Black River | 0 | 43930 |  | 43 | 43933 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1444KL-20200402-5CAT D6 - LPG81432 | KABI LAKE FOREST PRODUCTS LTD1444KL-20200402-5CAT D6 - LPG81432OEWT PA4-LEM-R1 | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4932 | KL-20201207-6 | 53510711 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Snow removal from D018 to D025 and filling ruts for freezing | 7 | D-018 to D-031 | Pie River | 0 | 44193 |  | 47 | 44202 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4932KL-20201207-6CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD4932KL-20201207-6CAT D6 - LPG101790OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5040 | KL-20201218-1 | 53510711 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer continuing road maintenance from D032 to D061 | 7 | D-032 to D-055 | Black River | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD5040KL-20201218-1CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD5040KL-20201218-1CAT D6 - LPG111969OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5094 | KL-20201217-2 | 53510711 | Access | 0 | CAT D6 - LPG | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer starting road maintenance to D032 | 7 | D-032 to D-055 | Black River | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD5094KL-20201217-2CAT D6 - LPG2358 | KABI LAKE FOREST PRODUCTS LTD5094KL-20201217-2CAT D6 - LPG2358OEWT-PA12-LEM-R1 | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7922 | KL-20220224-3 | 53510711 | Access | 0 | CAT D6 - LPG | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from E-001 to D148. | 7 | D142 - E002 | White Lake West | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7922KL-20220224-3CAT D6 - LPG4716 | KABI LAKE FOREST PRODUCTS LTD7922KL-20220224-3CAT D6 - LPG4716OEWT-PA26-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1404 | KL-20200328-2 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2020-03-28 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push snow banks back on access road , scrape road and grade | 7 | D-119 to D-141 | Alder Creek | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2CAT D6 - LPG5895OEWT PA4-LEM-R1 | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2092 | KL-20200717-4 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road to D055 to D053 | 7 | D-056 to D-073 | Umbatta Falls | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2092KL-20200717-4CAT D6 - LPG4716 | KABI LAKE FOREST PRODUCTS LTD2092KL-20200717-4CAT D6 - LPG4716OEWT-PA7-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2108 | KL-20200718-6 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2020-07-18 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road from D053 to D043 | 7 | D-032 to D-055 | Black River | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2108KL-20200718-6CAT D6 - LPG71253 | KABI LAKE FOREST PRODUCTS LTD2108KL-20200718-6CAT D6 - LPG71253OEWT-PA7-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2275 | KL-20200726-6 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2020-07-26 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance from D109 to D112 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44041 |  | 48 | 44041 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2275KL-20200726-6CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD2275KL-20200726-6CAT D6 - LPG5895OEWT-PA8-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2300 | KL-20200729-3 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2020-07-29 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Maintenance from D118 to D116 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44047 |  | 50 | 44048 | [5 empty] | Jim Budgell | 07 | KABI LAKE FOREST PRODUCTS LTD2300KL-20200729-3CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD2300KL-20200729-3CAT D6 - LPG61074OEWT-PA8-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2430 | KL-20200812-6 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Maintenance from D114 to D119 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2430KL-20200812-6CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD2430KL-20200812-6CAT D6 - LPG61074OEWT-PA8-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4293 | KL-20201110-3 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and spread gravel and chips D071-D073 BMC-30143 | 7 | D065-D066 | Camp 36 Road | 0 | 44166 |  | 53 | 44168 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-3CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-3CAT D6 - LPG101790OEWT-PA11-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7428 | KL-20211005-2 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road & hauling concrete anchors on a rig mat for LEG. Excavator levelling ruts, shaping road, assisting pickups & rock truck. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2CAT D6 - LPG101790OEWT-PA22-Lem | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7399 | KL-20210927-3 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2021-09-27 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue hauling pit run from Cress Pit & spreading on ROW access. Dozer levelling ruts after hours. | 7 | D018-D031 | Pic River | 0 | 44475 |  | 62 | 44478 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7399KL-20210927-3CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD7399KL-20210927-3CAT D6 - LPG111969OEWT-PA22-Lem | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7425 | KL-20211004-2 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts, shaping road, pulling pickups & grout truck to D025 due to wet conditions. Excavator working after hours until all crews got out. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2CAT D6 - LPG10.51879.5OEWT-PA22-Lem | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7432 | KL-20211006-2 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road and pushing rock trucks hauling gravel to D025 /excavator leveling ruts and shaping road. | 7 | D018-D031 | Pic river | 0 | 44484 |  | 63 | 44484 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2CAT D6 - LPG10.51879.5OEWT-PA22-Lem | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7435 | KL-20211007-2 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts & shaping road from D-019 to D-025. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-2CAT D6 - LPG8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-2CAT D6 - LPG8.51521.5OEWT-PA22-Lem | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7437 | KL-20211008-2 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator finishing levelling ruts & shaping road from D-019 to D-025 for pickup access. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-2CAT D6 - LPG3537 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-2CAT D6 - LPG3537OEWT-PA22-Lem | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7470 | KL-20211017-6 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Double Star Drilling support hauling steel in and light plant out/back blade and shape road | 7 | D018-D031 | Pic River West | 0 | 44494 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7470KL-20211017-6CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD7470KL-20211017-6CAT D6 - LPG5895OEWT-PA22-Lem | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7487 | KL-20211024-3 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer leveling ruts and shaping road from Hwy 17 to D018 and to D025 after completion of foundation work | 7 | D018-D031 | Pic River | 0 | 44493 |  | 61 | 44497 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7487KL-20211024-3CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7487KL-20211024-3CAT D6 - LPG101790OEWT-PA23-Lem | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1244 | KL-20200308-1 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2020-03-08 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | E-042 to E-053 Open access road to ROW | 8 | E068 - E076 | Denis Lake W | 0 | 43903 |  | 42 | 43910 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1244KL-20200308-1CAT D6 - LPG71253 | KABI LAKE FOREST PRODUCTS LTD1244KL-20200308-1CAT D6 - LPG71253OEWT-PA3-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1299 | KL-20200313-6 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road from HWY to E-049 | 8 | E-042 to E-053 | Denis Lake W | 0 | 43907 |  | 42 | 43914 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1299KL-20200313-6CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD1299KL-20200313-6CAT D6 - LPG61074OEWT-PA3-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1319 | KL-20200317-4 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 1 | HR | 135 | 0 |  |  | 179 | 23.27 | 202.27 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CONTINUE TO OPEN ROAD TO ACCESS ROW | 8 | E-062 to E-067 | Buck Lake | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1319KL-20200317-4CAT D6 - LPG1179 | KABI LAKE FOREST PRODUCTS LTD1319KL-20200317-4CAT D6 - LPG1179OEWT-PA3-LEM | [5 empty] | 1 | 179 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1325 | KL-20200318-3 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2020-03-18 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue to widen access road | 8 | E-062 to E-067 | Buck Lake | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1325KL-20200318-3CAT D6 - LPG4716 | KABI LAKE FOREST PRODUCTS LTD1325KL-20200318-3CAT D6 - LPG4716OEWT-PA3-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1333 | KL-20200319-7 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-03-19 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW OPEN (WIDEN) ACCESS RD | 8 | E-062 to E-067 | Buck Lake | 0 | 43913 |  | 42 | 43917 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1333KL-20200319-7CAT D6 - LPG81432 | KABI LAKE FOREST PRODUCTS LTD1333KL-20200319-7CAT D6 - LPG81432OEWT-PA3-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1339 | KL-20200320-2 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2020-03-20 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix road access to ROW | 8 | E-062 to E-067 | Buck Lake | 0 | 43914 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1339KL-20200320-2CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD1339KL-20200320-2CAT D6 - LPG61074OEWT-PA3-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4919 | KL-20201206-6 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer blading AE1 Access from Hwy to ROW | 8 | E017-E024 | North Regan | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4919KL-20201206-6CAT D6 - LPG2358 | KABI LAKE FOREST PRODUCTS LTD4919KL-20201206-6CAT D6 - LPG2358OEWT-PA12-LEM-R1 | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5151 | KL-20201228-2 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer working on snow removal from Hwy 17 to E014/E015 Access | 8 | E004-E016 | White Lake East | 0 | 43836 |  | 36 | 44213 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD5151KL-20201228-2CAT D6 - LPG81432 | KABI LAKE FOREST PRODUCTS LTD5151KL-20201228-2CAT D6 - LPG81432OEWT-PA13-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5858 | KL-20210211-2 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from 9020.00 WC to Hwy 17 | 8 | E004-E016 | White Lake East | 0 | 44244 |  | 36 | 44250 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD5858KL-20210211-2CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD5858KL-20210211-2CAT D6 - LPG5895OEWT-PA14-Lem-R1 | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7882 | KL-20220213-6 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening from Hwy 17 to E004 and clearing pad @ E005 | 8 | E004 - E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7882KL-20220213-6CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD7882KL-20220213-6CAT D6 - LPG10.51879.5OEWT-PA26-LEM | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7886 | KL-20220214-4 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening from Hwy 17 to E013 and clearing pad @ E013 | 8 | E004-E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7886KL-20220214-4CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD7886KL-20220214-4CAT D6 - LPG10.51879.5OEWT-PA26-LEM | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7890 | KL-20220215-3 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal and widening from Hwy 17 to E013 | 8 | E004 - E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7890KL-20220215-3CAT D6 - LPG71253 | KABI LAKE FOREST PRODUCTS LTD7890KL-20220215-3CAT D6 - LPG71253OEWT-PA26-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7907 | KL-20220219-3 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal & clearing pull offs from Hwy 17 to E051. | 8 | E042 - E058 | Denis Lake W | 0 | 44617 |  | 61 | 44617 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7907KL-20220219-3CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7907KL-20220219-3CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7916 | KL-20220223-1 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 7.5 | HR | 135 | 0 |  |  | 1342.5 | 174.525 | 1517.025 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hwy 17 to E013 & to E005. | 8 | E004 - E010 | White Lake East | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 08 | KABI LAKE FOREST PRODUCTS LTD7916KL-20220223-1CAT D6 - LPG7.51342.5 | KABI LAKE FOREST PRODUCTS LTD7916KL-20220223-1CAT D6 - LPG7.51342.5OEWT-PA26-LEM | [5 empty] | 1 | 1342.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7943 | KL-20220227-6 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Dozer working on snow removal & clearing pull offs from Hwy 17 to E-051 | 8 | E042 - E058 | Denis Lake W | 0 | 44628 | [9 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7943KL-20220227-6CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD7943KL-20220227-6CAT D6 - LPG61074 | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7863 | KL-20220209-6 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hwy 17 to E002 | 10 |  | White Lake east | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7863KL-20220209-6CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD7863KL-20220209-6CAT D6 - LPG10.51879.5OEWT-PA26-LEM | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7868 | KL-20220210-5 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hwy 17 to E002 and to E008 | 8 | E004 - E010 | White Lake East | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7868KL-20220210-5CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD7868KL-20220210-5CAT D6 - LPG10.51879.5OEWT-PA26-LEM | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7871 | KL-20220211-3 | 53510811 | Access | 0 | CAT D6 - LPG | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hwy 17 to E004 | 8 | E004 - E010 | White Lake East | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7871KL-20220211-3CAT D6 - LPG3537 | KABI LAKE FOREST PRODUCTS LTD7871KL-20220211-3CAT D6 - LPG3537OEWT-PA26-LEM | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4409 | KL-20201116-8 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard. (Cost Code as per Frank 53510812) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44171 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4409KL-20201116-8CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD4409KL-20201116-8CAT D6 - LPG61074OEWT-PA11-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4410 | KL-20201116-9 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Charged to move Cat D6T dozer to E069/due to Adam from foundations (Cost Code 53510812 as per Frank) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44171 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4410KL-20201116-9CAT D6 - LPG2358 | KABI LAKE FOREST PRODUCTS LTD4410KL-20201116-9CAT D6 - LPG2358OEWT-PA11-LEM | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4425 | KL-20201117-5 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard/Support for Foundations (CC as per Frank 53510812) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4425KL-20201117-5CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD4425KL-20201117-5CAT D6 - LPG111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4447 | KL-20201118-8 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float had dozer loaded and Valard needed the dozer to stay/support for foundations as per email. | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 14 | 44177 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD4447KL-20201118-8CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD4447KL-20201118-8CAT D6 - LPG111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4460 | KL-20201119-6 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road leveling ruts from E069 to E073 as per valard/ Support for foundations | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4460KL-20201119-6CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD4460KL-20201119-6CAT D6 - LPG111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4485 | KL-20201120-11 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | (CC 53510812 as per Frank) needs cost code changed. |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard/support for Foundations (CC 53510812 as per Frank) | 8 | E068-E076 | North Regan | 0 | 44167 |  | 47 | 44173 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4485KL-20201120-11CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD4485KL-20201120-11CAT D6 - LPG111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4551 | KL-20201122-9 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2020-11-22 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on AU1 Access shaping and leveling ruts/cleaning up the turn around | 8 | E062-E067 | Buck Lake Road | 0 | 44172 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4551KL-20201122-9CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD4551KL-20201122-9CAT D6 - LPG5895OEWT-PA11-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6922 | KL-20210515-6 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2021-05-15 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading, hauling and spreading pit run from stock pile to E007/E006 access/loading and hauling trees for soft sections/dozer leveling ruts and excavator placing corduroy | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44342 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6CAT D6 - LPG111969OEWT-PA17-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6945 | KL-20210518-2 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 2.5 | HR | 135 | 0 |  |  | 447.5 | 58.175 | 505.675 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | loading , hauling and spreading existing material @ E014 for road repairs from E014.5 to E016 to maintain pickup access | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2CAT D6 - LPG2.5447.5 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2CAT D6 - LPG2.5447.5OEWT-PA17-LEM | [5 empty] | 1 | 447.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6951 | KL-20210519-2 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 3.5 | HR | 135 | 0 |  |  | 626.5 | 81.445 | 707.945 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading, hauling and spreading exsiting material @ E014 for road repairs from E016 to E013.5 (revised) | 8 | E034 - E036 | White Lake East | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2CAT D6 - LPG3.5626.5 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2CAT D6 - LPG3.5626.5OEWT-PA17-LEM | [5 empty] | 1 | 626.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6959 | KL-20210520-1 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread existing material @ 1.5 km and pit run from stock pile for road repair on E007/E006 main access road/ Laboures laying Geo ( revised) | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1CAT D6 - LPG10.51879.5OEWT-PA17-LEM | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6967 | KL-20210521-2 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 6.5 | HR | 135 | 0 |  |  | 1163.5 | 151.255 | 1314.755 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stockpile for road repairs to the access going into E005. Dozer spreading loads from from rock truck and fixing ruts. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2CAT D6 - LPG6.51163.5 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2CAT D6 - LPG6.51163.5OEWT-PA17-LEM | [5 empty] | 1 | 1163.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6970 | KL-20210522-1 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2021-05-22 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stock pile and bundles of wood from the main road to E006 for road repairs, dozer spreading loads and pushing up bundle of wood | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44348 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1CAT D6 - LPG10.51879.5OEWT-PA17-LEM | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6976 | KL-20210523-3 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator fixing road going to E016 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6976KL-20210523-3CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD6976KL-20210523-3CAT D6 - LPG61074OEWT-PA17-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6977 | KL-20210523-4 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 4.5 | HR | 135 | 0 |  |  | 805.5 | 104.715 | 910.215 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material for road repairs near E011, 330 loading material and dozer spreading loads from rock truck and fixing punch outs | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4CAT D6 - LPG4.5805.5 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4CAT D6 - LPG4.5805.5OEWT-PA17-LEM | [5 empty] | 1 | 805.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6980 | KL-20210524-1 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2021-05-24 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on drainage out of E016/Dozer leveling ruts and back blading out from E016 to E006 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-1CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-1CAT D6 - LPG10.51879.5OEWT-PA17-LEM | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6983 | KL-20210525-2 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Haul and spread existing material @ E014 for Road repairs from E015 to E016/Excavator and Dozer working on Road maintenance E013 to E006 | 8 | E004-E016 | White Lake East | 0 | 44343 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2CAT D6 - LPG8.51521.5 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2CAT D6 - LPG8.51521.5OEWT-PA17-LEM | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6988 | KL-20210526-1 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E011 to E016 | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-1CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-1CAT D6 - LPG10.51879.5OEWT-PA18-Lem | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6991 | KL-20210527-1 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Supervisor site visit with Valard ROW and directing Operators | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-1CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-1CAT D6 - LPG10.51879.5OEWT-PA18-Lem | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6993 | KL-20210528-1 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Start shaping hill @E017 Access | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-1CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-1CAT D6 - LPG10.51879.5OEWT-PA18-Lem | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7068 | KL-20210529-2 | 53510812 | Access | 0 | CAT D6 - LPG | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2021-05-29 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer shaping hill and filling ruts on E017 access from E016 | 8 | E004-E016 | White Lake East | 0 | 44372 |  | 36 | 44373 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-2CAT D6 - LPG3537 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-2CAT D6 - LPG3537OEWT-PA18-Lem | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1057 | KL-20200212-2 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-02-12 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter Maintenance - Plow open road to get access to WF9 | 9 | E-091 to E-121 | 600 Rd | 0 | 43878 |  | 42 | 43882 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1057KL-20200212-2CAT D6 - LPG122148 | KABI LAKE FOREST PRODUCTS LTD1057KL-20200212-2CAT D6 - LPG122148OEWT-PA2-LEM-R1 | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1153 | KL-20200225-3 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-02-25 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open 600 Road KM 10-15 | 9 | E-091-E102 | 600 rd | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1153KL-20200225-3CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1153KL-20200225-3CAT D6 - LPG111969OEWT-PA2-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1173 | KL-20200226-10 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-26 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 RD - Continue to plow road to gain access to 20KM | 9 | E091-E121 | 600 Road | 0 | 43894 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1173KL-20200226-10CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1173KL-20200226-10CAT D6 - LPG111969OEWT-PA3-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1178 | KL-20200227-3 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-02-27 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd winter road maintenance - continue to open 600 rd @ 22km | 9 | E091-E121 | 600 Road | 0 | 43894 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1178KL-20200227-3CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1178KL-20200227-3CAT D6 - LPG111969OEWT-PA3-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1184 | KL-20200228-3 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-02-28 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd - plow 600 rd for access @30km. | 9 | E091-E102 | 600 road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1184KL-20200228-3CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD1184KL-20200228-3CAT D6 - LPG101790OEWT-PA3-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1209 | KL-20200302-7 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-02 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 Road for access km 4 with grader and open sub roads at 2km | 9 | E-091 to E-102 | 600 Road | 0 | 43896 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1209KL-20200302-7CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1209KL-20200302-7CAT D6 - LPG111969OEWT-PA3-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1222 | KL-20200304-4 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-03-04 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open access roads for WF9 | 7 | E-091 to E-102 | 600 Road | 0 | 43900 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1222KL-20200304-4CAT D6 - LPG122148 | KABI LAKE FOREST PRODUCTS LTD1222KL-20200304-4CAT D6 - LPG122148OEWT-PA3-LEM | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1225 | KL-20200305-1 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2020-03-05 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road and make turn arounds on 600 Road | 9 | E-091 to E-102 | 600 road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1CAT D6 - LPG3537 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1CAT D6 - LPG3537OEWT-PA3-LEM | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1225 | KL-20200305-1 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2020-03-05 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road and make turn arounds on 600 Road | 9 | E-091 to E-102 | 600 road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1CAT D6 - LPG4716 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1CAT D6 - LPG4716OEWT-PA3-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1254 | KL-20200309-5 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-03-09 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Missing LOA |  | Approved |  |  | Continue to open existing roads on 600 Road. Towers E-104 to E-106 | 9 | E-104 to E-106 | 600 Road | 0 | 43903 |  | 42 | 43911 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1254KL-20200309-5CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD1254KL-20200309-5CAT D6 - LPG101790OEWT-PA3-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1310 | KL-20200316-4 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-16 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road by KM 30 and plow after snowfall | 9 | E-091 to E-102 | 600 Road | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4CAT D6 - LPG111969OEWT-PA3-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1315 | KL-20200317-1 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road on 600 around km 36 | 9 | E-091 to E-102 | 600 Road. | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1315KL-20200317-1CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1315KL-20200317-1CAT D6 - LPG111969OEWT-PA3-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1324 | KL-20200318-2 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-18 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW OPEN ROAD AT 40KM AND WING BACK BANKS | 9 | E-091 to E-102 | 600 Road | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1324KL-20200318-2CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1324KL-20200318-2CAT D6 - LPG111969OEWT-PA3-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1382 | KL-20200325-4 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-25 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open 600 road to gain access | 9 | E-091 to E-102 | 600 Road | 0 | 43922 |  | 45 | 43923 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1382KL-20200325-4CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1382KL-20200325-4CAT D6 - LPG111969OEWT PA4-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1387 | KL-20200326-5 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-26 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open more access on 600 road aprox 50km | 9 | E-091 to E-102 | 600 Road | 0 | 43922 |  | 45 | 43923 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1387KL-20200326-5CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1387KL-20200326-5CAT D6 - LPG111969OEWT PA4-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1400 | KL-20200327-5 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 7.5 | HR | 135 | 0 |  |  | 1342.5 | 174.525 | 1517.025 | 2020-03-27 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 for WF-9 access and grade road | 9 | E-091 to E-102 | 600 Road | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1400KL-20200327-5CAT D6 - LPG7.51342.5 | KABI LAKE FOREST PRODUCTS LTD1400KL-20200327-5CAT D6 - LPG7.51342.5OEWT PA4-LEM-R1 | [5 empty] | 1 | 1342.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1411 | KL-20200329-5 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-29 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open up 600 raod (plow snow) | 9 | E-091 to E-102 | 600 Road | 0 | 43927 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1411KL-20200329-5CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1411KL-20200329-5CAT D6 - LPG111969OEWT PA4-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1418 | KL-20200330-6 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-30 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Open up 600 Road (plow snow) | 9 |  | 600 Road | 0 | 43928 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1418KL-20200330-6CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD1418KL-20200330-6CAT D6 - LPG111969OEWT PA4-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1427 | KL-20200331-7 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2020-03-31 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow off road | 9 | E091-E102 | 600 Road | 0 | 43928 |  | 45 | 43929 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1427KL-20200331-7CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD1427KL-20200331-7CAT D6 - LPG5895OEWT PA4-LEM-R1 | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7927 | KL-20220225-3 | 53510911 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader and dozer finishing snow removal fro 9km to E-182 on 600 Road | 9 | E092-F009 | 600 Raod | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 09 | KABI LAKE FOREST PRODUCTS LTD7927KL-20220225-3CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7927KL-20220225-3CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2004 | KL-20200711-10 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10CAT D6 - LPG111969OEWT-PA7-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2029 | KL-20200713-7 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-07-13 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44029 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7CAT D6 - LPG111969OEWT-PA7-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3623 | KL-20201009-12 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix road and spread loads between E173 and E172, Haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12CAT D6 - LPG111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3648 | KL-20201010-12 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix rds, spread loads between E-173, E-172 and haul gravel to E-168/E-171and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-12CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-12CAT D6 - LPG111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3671 | KL-20201011-11 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-11 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix road and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44157 |  | 15 | 44131 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-11CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-11CAT D6 - LPG111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3698 | KL-20201012-16 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3698KL-20201012-16CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD3698KL-20201012-16CAT D6 - LPG111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3741 | KL-20201014-12 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy, install cross drain at F6. | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-12CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-12CAT D6 - LPG111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3765 | KL-20201015-13 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit and 25km pit, fix roads and hauled gravel to E168-E171 and spread over Corduroy, pile up gravel at Km33 | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3765KL-20201015-13CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD3765KL-20201015-13CAT D6 - LPG101790OEWT-PA10-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4064 | KL-20201030-6 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix Roads between E95 to E102 | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4064KL-20201030-6CAT D6 - LPG122148 | KABI LAKE FOREST PRODUCTS LTD4064KL-20201030-6CAT D6 - LPG122148OEWT-PA11-LEM | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4415 | KL-20201116-14 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix roads E168 to E171 and E212 to E210 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4415KL-20201116-14CAT D6 - LPG122148 | KABI LAKE FOREST PRODUCTS LTD4415KL-20201116-14CAT D6 - LPG122148OEWT-PA11-LEM | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4463 | KL-20201119-9 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads E217 to E194 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4463KL-20201119-9CAT D6 - LPG122148 | KABI LAKE FOREST PRODUCTS LTD4463KL-20201119-9CAT D6 - LPG122148OEWT-PA11-LEM | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4573 | KL-20201123-11 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads and pulling a drag F3 and F9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44175 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4573KL-20201123-11CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD4573KL-20201123-11CAT D6 - LPG111969OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4605 | KL-20201124-8 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access road and pulling a drag F3, F9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4605KL-20201124-8CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD4605KL-20201124-8CAT D6 - LPG91611OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4637 | KL-20201125-14 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads and pulling a drag F3-F9 | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4637KL-20201125-14CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD4637KL-20201125-14CAT D6 - LPG111969OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6949 | KL-20210518-6 | 53510912 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer leveling ruts and shaping road E200 to E216/ Supervisor while checking on Operator and process did pickup shuffle (Revised) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6949KL-20210518-6CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD6949KL-20210518-6CAT D6 - LPG111969OEWT-PA17-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4663 | KL-20201126-16 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping and back blading access road and pulling a drag F09, F24 | 10 | F009-F020 | Paint Lake Road 1-A | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4663KL-20201126-16CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD4663KL-20201126-16CAT D6 - LPG111969OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5841 | KL-20210210-3 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer plow snow & open road between F21 to F32 | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44244 |  | 50 | 44249 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5841KL-20210210-3CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD5841KL-20210210-3CAT D6 - LPG61074OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7620 | KL-20211202-2 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 to Km 40/ loader sanding road from Km 48 to Km 46.5 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2CAT D6 - LPG5895OEWT-PA24-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7637 | KL-20211204-5 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46 to Km 38 with existing material /dozer working from Km 49 to Km 13/ supervisior picking up dozer operator @ Km 13 at end of shift | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5CAT D6 - LPG10.51879.5OEWT-PA24-LEM | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7639 | KL-20211205-2 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-05 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader piling existing material from Km 46 to Km 38 for upcoming snow fall/ dozer working on snow removal from km 13 to km 21 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2CAT D6 - LPG91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1CAT D6 - LPG91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7657 | KL-20211209-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from 48km to 34km sanding & clearing pull offs. Dozer working to F057, F058 & F058 access. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1CAT D6 - LPG91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7686 | KL-20211213-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2021-12-13 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer starting snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44560 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7686KL-20211213-1CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD7686KL-20211213-1CAT D6 - LPG5895OEWT-PA24-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7689 | KL-20211214-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 2.5 | HR | 135 | 0 |  |  | 447.5 | 58.175 | 505.675 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finishing snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44560 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7689KL-20211214-1CAT D6 - LPG2.5447.5 | KABI LAKE FOREST PRODUCTS LTD7689KL-20211214-1CAT D6 - LPG2.5447.5OEWT-PA24-LEM | [5 empty] | 1 | 447.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7705 | KL-20211218-3 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-18 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on shaping road and leveling ruts from F112 to F117 for freezing | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7705KL-20211218-3CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7705KL-20211218-3CAT D6 - LPG91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7718 | KL-20220101-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-01 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 on Paint Lake Road 2 to F111 | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7718KL-20220101-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7718KL-20220101-1CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7723 | KL-20220103-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 7.5 | HR | 135 | 0 |  |  | 1342.5 | 174.525 | 1517.025 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7723KL-20220103-1CAT D6 - LPG7.51342.5 | KABI LAKE FOREST PRODUCTS LTD7723KL-20220103-1CAT D6 - LPG7.51342.5OEWT-PA25-Lem | [5 empty] | 1 | 1342.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7728 | KL-20220104-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening road from Km 47 to Km 43.5, F109 to F111, F105 and F104 Access | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7728KL-20220104-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7728KL-20220104-1CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7737 | KL-20220106-2 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 4.5 | HR | 135 | 0 |  |  | 805.5 | 104.715 | 910.215 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Working on Snow Removal and Widening road from Km 46 to F111/ Loader working on snow removal from F037 to F033 and sanding km 10.5 Hill | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2CAT D6 - LPG4.5805.5 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2CAT D6 - LPG4.5805.5OEWT-PA25-Lem | [5 empty] | 1 | 805.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7744 | KL-20220108-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working from Km 48 to Km 41 pushing back snow banks, clearing pull offs and F105/F104 access | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7744KL-20220108-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7744KL-20220108-1CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7755 | KL-20220111-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 48 to Km 38 | 10 | F066-F118 | Paint Lake 2 | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7755KL-20220111-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7755KL-20220111-1CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7758 | KL-20220112-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 42 to Km 34/ Supervisor doing pick up shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7758KL-20220112-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7758KL-20220112-1CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7763 | KL-20220113-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 38 to Km 32 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7763KL-20220113-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7763KL-20220113-1CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7768 | KL-20220114-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2022-01-14 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening roads from Km 32 to Km 36 /Clearing spur roads on way out | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7768KL-20220114-1CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD7768KL-20220114-1CAT D6 - LPG5895OEWT-PA25-Lem | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7772 | KL-20220115-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening roads from Km 32 to Km 36 /Clearing spur roads on way out. Excavator setting up @ 12Km for loader access to sand. | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-1CAT D6 - LPG3537 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-1CAT D6 - LPG3537OEWT-PA25-Lem | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7776 | KL-20220116-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 7.5 | HR | 135 | 0 |  |  | 1342.5 | 174.525 | 1517.025 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue working on widening roads from Km 33 to Km 42 /Loader Clearing pull offs / Grader Scarifying from Km 49 to Km 42 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1CAT D6 - LPG7.51342.5 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1CAT D6 - LPG7.51342.5OEWT-PA25-Lem | [5 empty] | 1 | 1342.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7779 | KL-20220117-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finish working on widening roads and clearing pull offs from Km 42 to Km 49 /Grader Scarifying from Km 49 to Km 39 and F117 to F112/ supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1CAT D6 - LPG71253 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1CAT D6 - LPG71253OEWT-PA25-Lem | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7878 | KL-20220213-2 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F032 and clearing pad @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7878KL-20220213-2CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7878KL-20220213-2CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7884 | KL-20220214-2 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal and widening from F021 to F032 and clearing pad @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7884KL-20220214-2CAT D6 - LPG81432 | KABI LAKE FOREST PRODUCTS LTD7884KL-20220214-2CAT D6 - LPG81432OEWT-PA26-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7793 | KL-20220121-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 4.5 | HR | 135 | 0 |  |  | 805.5 | 104.715 | 910.215 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer starting from Km 49 Km 45 clearing pull offs and widening where required/Delay Due to Stringers having road closed @ F118/ supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7793KL-20220121-1CAT D6 - LPG4.5805.5 | KABI LAKE FOREST PRODUCTS LTD7793KL-20220121-1CAT D6 - LPG4.5805.5OEWT-PA25-Lem | [5 empty] | 1 | 805.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7801 | KL-20220124-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening F112 to F117, clearing snow @ F109 to F111, F105 access, widening and cleaning pulloffs from Km 48 to 41.5/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7801KL-20220124-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7801KL-20220124-1CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7805 | KL-20220125-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and cleaning pulloffs from Km 41 to 38.5/Snow removal on spur roads from F104 to F095 /Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7805KL-20220125-1CAT D6 - LPG81432 | KABI LAKE FOREST PRODUCTS LTD7805KL-20220125-1CAT D6 - LPG81432OEWT-PA25-Lem | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7809 | KL-20220126-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and cleaning pulloffs from Km 38 to 35/Snow removal on spur roads /Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7809KL-20220126-1CAT D6 - LPG8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7809KL-20220126-1CAT D6 - LPG8.51521.5OEWT-PA26-LEM | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7814 | KL-20220129-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-01-29 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road , clearing pull offs and spur roads from Km 38 to Km 35/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7814KL-20220129-1CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD7814KL-20220129-1CAT D6 - LPG61074OEWT-PA26-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7818 | KL-20220131-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working from Km 35 to Km 32 widening road , clearing pull offs and spur roads from Km 35 to Km 29 / Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7818KL-20220131-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7818KL-20220131-1CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7822 | KL-20220201-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs, spur roads from 29km to 25km & access road to F057. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7822KL-20220201-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7822KL-20220201-1CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7826 | KL-20220202-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs, spur roads from 25km to 21km. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7826KL-20220202-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7826KL-20220202-1CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7828 | KL-20220203-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-03 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snow banks & scarifying road from 49 to 40km. Dozer widening road, clearing pull offs & spur roads from 21km to 12.5km. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7832 | KL-20220204-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F077 to F073 and clearing laydown at 12km. Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7832KL-20220204-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7832KL-20220204-1CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7836 | KL-20220205-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F020 to F009 and clearing pull offs. | 10 | F009-F065 | Paint Lake | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7836KL-20220205-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7836KL-20220205-1CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7841 | KL-20220206-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 6.5 | HR | 135 | 0 |  |  | 1163.5 | 151.255 | 1314.755 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F020 to F009 for removal of repeater tower trailer. | 10 | F009-F065 | Paint Lake | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7841KL-20220206-1CAT D6 - LPG6.51163.5 | KABI LAKE FOREST PRODUCTS LTD7841KL-20220206-1CAT D6 - LPG6.51163.5OEWT-PA26-LEM | [5 empty] | 1 | 1163.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7844 | KL-20220207-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F028 | 10 | F009 - F0665 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7844KL-20220207-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7844KL-20220207-1CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7852 | KL-20220208-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F030 | 10 | F009-F065 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7852KL-20220208-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7852KL-20220208-1CAT D6 - LPG91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7864 | KL-20220210-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Km 49 to Km 32 on Paint Lake Road 2 /Dozer pushing snowbanks and widening road from Km 9.2 to Km 11/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1CAT D6 - LPG81432 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1CAT D6 - LPG81432OEWT-PA26-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7869 | KL-20220211-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 35 /Dozer pushing snowbanks and widening road from Km 11 to Km 15/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1CAT D6 - LPG71253 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1CAT D6 - LPG71253OEWT-PA26-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7873 | KL-20220212-1 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 29 /Dozer tracking from Km 15 to Km 9.2 for float access/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1CAT D6 - LPG2358 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1CAT D6 - LPG2358OEWT-PA26-LEM | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7875 | KL-20220212-3 | 53511011 | Access | 0 | CAT D6 - LPG | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F027 | 10 | F009-F065 | Paint Lake | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7875KL-20220212-3CAT D6 - LPG71253 | KABI LAKE FOREST PRODUCTS LTD7875KL-20220212-3CAT D6 - LPG71253OEWT-PA26-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6963 | KL-20210520-5 | 53511012 | Access | 0 | CAT D6 - LPG | 179 | 7.5 | HR | 135 | 0 |  |  | 1342.5 | 174.525 | 1517.025 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T Dozer starting leveling ruts and shaping road from Km 2 to Km 9.5 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD6963KL-20210520-5CAT D6 - LPG7.51342.5 | KABI LAKE FOREST PRODUCTS LTD6963KL-20210520-5CAT D6 - LPG7.51342.5OEWT-PA17-LEM | [5 empty] | 1 | 1342.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3631 | KL-20201009-20 | 53511102 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Shaping Road and Widing Areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44125 |  | 55 | 44129 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3631KL-20201009-20CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD3631KL-20201009-20CAT D6 - LPG61074OEWT-PA10-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3273 | KL-20200927-17 | 53511104 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit runfrom Provost pit #5/Dozer spreading | 11 | F-119 to F-134 | Hensen Road | 0 | 43900 |  | 48 | 43871 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17CAT D6 - LPG111969OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3300 | KL-20200928-23 | 53511104 | Access | 0 | CAT D6 - LPG | 179 | 11.5 | HR | 135 | 0 |  |  | 2058.5 | 267.605 | 2326.105 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23CAT D6 - LPG11.52058.5 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23CAT D6 - LPG11.52058.5OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 2058.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3376 | KL-20201001-22 | 53511104 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Triaxles hauling Pit Run from Provost pit #5 , Dozer spreading and widening areas.Grade Hensen road for gravel Haul - SSF-14029.Haul Pit Run from Provost Pit #5 to AE1 on Hensen Road - JJR-70095. Hauled Gravel to Hensen Road from Provost Pit #5 - BMC-30121 | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22CAT D6 - LPG111969OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511104 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24CAT D6 - LPG111969OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3411 | KL-20200930-19 | 53511104 | Access | 0 | CAT D6 - LPG | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer spreading Pit Run from Provost Pit #5 and widening areas. Trucks hauling gravel from Provost Pit | 11 | F-119 to F-134 | Hensen Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-19CAT D6 - LPG111969 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-19CAT D6 - LPG111969OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5439 | KL-20210118-13 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer Clearing snow from Anjigami Rd to Anjigami River for Bridge delivery as per Valard. | 11 | F228 | F-228 Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5439KL-20210118-13CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD5439KL-20210118-13CAT D6 - LPG101790OEWT-PA13-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5510 | KL-20210121-9 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from km 17 on Hensen Rd to F133/Operator extra travel/Based out of White River. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5510KL-20210121-9CAT D6 - LPG8.51521.5 | KABI LAKE FOREST PRODUCTS LTD5510KL-20210121-9CAT D6 - LPG8.51521.5OEWT-PA13-LEM | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5614 | KL-20210125-11 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6K dozer starting snow removal from km 17 on Hensen Rd to F133. | 11 | F119-F134 | Hensen Road | 0 | 44225 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5614KL-20210125-11CAT D6 - LPG10.51879.5 | KABI LAKE FOREST PRODUCTS LTD5614KL-20210125-11CAT D6 - LPG10.51879.5OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5632 | KL-20210126-16 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6K Dozer finishing snow removal from km 17 on Hensen to F133. | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5632KL-20210126-16CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD5632KL-20210126-16CAT D6 - LPG101790OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6124 | KL-20210228-10 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2021-02-28 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue snow removal on AE1 access to F212 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44263 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6124KL-20210228-10CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD6124KL-20210228-10CAT D6 - LPG61074OEWT PA15-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6347 | KL-20210316-6 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-03-16 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6T Dozer pushing snow banks back and clearing debris off the road fro F121/F215 access on Anjigami road | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6347KL-20210316-6CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD6347KL-20210316-6CAT D6 - LPG101790OEWT PA15-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7602 | KL-20211128-2 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9.5 | HR | 135 | 0 |  |  | 1700.5 | 221.065 | 1921.565 | 2021-11-28 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road from F204 to F211 and to F200 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-2CAT D6 - LPG9.51700.5 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-2CAT D6 - LPG9.51700.5OEWT-PA24-LEM | [5 empty] | 1 | 1700.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7605 | KL-20211129-2 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F203 to F185 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7605KL-20211129-2CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7605KL-20211129-2CAT D6 - LPG101790OEWT-PA24-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7611 | KL-20211130-4 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F184 to F181 and F177 to F171 / supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7611KL-20211130-4CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7611KL-20211130-4CAT D6 - LPG101790OEWT-PA24-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7612 | KL-20211201-2 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F179 to F180 and F193 to F181 / supervision of Skagen | 11 | F170-F212 | High Falls | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-2CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-2CAT D6 - LPG101790OEWT-PA24-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7622 | KL-20211202-4 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17.5 on Hensen road/ Dozer working on snow removal and shaping road from F122 to F132 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4CAT D6 - LPG5895 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4CAT D6 - LPG5895OEWT-PA24-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7626 | KL-20211202-8 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road @ F203 to F211 | 11 | F170-F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7626KL-20211202-8CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7626KL-20211202-8CAT D6 - LPG101790OEWT-PA24-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7629 | KL-20211203-3 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road @ F198 to F202 and track to Km 11 on High Falls Raod/ Supervision of Skagen | 11 | F170 - F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-3CAT D6 - LPG71253 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-3CAT D6 - LPG71253OEWT-PA24-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7634 | KL-20211204-2 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from Km 11 to 1.5, scraping road from F177 to F171 and assist stringing crews/ Supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-2CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-2CAT D6 - LPG91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A